## Erosion & Sediment Control
|  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  | Contract Name: G1302A Culvert 33 – SH38 RS179 RP5.805 |  |  | CPS Approver | Quality Approver | CPS Eng.
|  |  | Procedure: | Compliance and Environmental |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [7 empty] | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  | Compliance with Work Instructions and Specifications
Detailed Location: SH38 at RP179/5.805
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Conformance Criteria | Records | Initials | Others Initials (Grey if not required) | Date(s)
1 | Approved Consents | M | Is a copy of approved consent(s) available on site | Check latest consents and SSESCP's are at each site office | This ITP | Site Engineer
2 | Internal ESC Pre-Construction | H | Internal pre-construction meeting held with E Team | Environmental Advisor to organise | This ITP | Site Engineer | MTT
3 | Type and Location of Erosion & Sedimentation Control | M | Confirm type and location of erosion and sedimentation control, based on relevant drawing/s | Relevant ESCP drawing | This ITP | Site Engineer | MTT
4 | Channel Bund (if required) | M | Bund is constructed in correct location; to agreed / specified dimensions and levels; and is firmly compacted. | Work Instruction, Drawings and Checklist |  | Site Engineer | ES Supervisor
5 | Silt Fence (SF) (if required) | M | Silt Fence or Super Silt Fence is constructed in correct location; to correct dimensions, and geotextile secured and waratahs located as shown on the WI and drawings | Work Instruction, Drawings and Checklist |  | Site Engineer | ES Supervisor
6 | As-Builts | H | Confirm as-built details of completed works | Submit to Document Control/Environmental Advisor to issue to HRC within 24 Hours | This ITP | Site Engineer | Environmental Advisor
7 | Maintenance Inspections | W | Undertake weekly inspections of all erosion and sedimentation controls and after > 5mm rain to identify required maintenance | Approved ESC Plan. Complete weekly and upload to ConQA / Procore |  | ES Supervisor | Environmental Advisor
8 | Decommissioning of Erosion Sediment Controls | H | Decommissioning Plan submitted to HRC for Approval |  |  | Site Engineer | Environmental Advisor
9 | Decommissioning of Erosion Sediment Controls | H | HRC to issue an approval document so that Decommissioning works can commence | Approval for Decommissioning |  | Site Engineer | Environmental Advisor
10 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  | Signature: |  |  | Date: