## Construction ITP
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: |  |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | D1603B - ID587B - Otoko Flats Underslip |  | Name / Signature | Name / Signature | Site Engineer
|  |  |  | Inspection & Test Plan / Checklist |  |  | 11.12.2023 |  | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-??-???? |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage: SH2 / RS390 / RP14.5
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Specification/Drawings Reference | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
Section 1 : RECEIVING INSPECTIONS
1.1 | Rock Armour (D50=600) | H | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | Prior to commencement | Supplier material test certificate | Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 600 with a minimum specific Gravity SG of 2350kg/m3. | Material source test results, Delivery Dockets | Site Engineer | CPS Engineer
1.2 | Bulk Fill (GAP65/GAP100) or similar | H | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | Prior to commencement | Supplier material test certificate | Should comprise clean granular aggregate and have broken faces. Material source testing | Material source test results, Delivery Dockets | Site Engineer | CPS Engineer
1.3 | Class D A39 Geotextile | W | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001, NZTA F/7 | Prior to commencement | Manufacturers certificate | NZTA F/7 compliant before placing foundation material and engineered hardfill | Material certificate(s) | Site Engineer
1.4 | Class E A49 Geotextile | W | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001, NZTA F/7 | Prior to commencement | Manufacturers certificate | NZTA F/7 compliant before placing foundation material and engineered hardfill | Material certificate(s) | Site Engineer
1.5 | Megaflow strip drain or drainage blanket for seepage if encountered | W | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | Prior to commencement | Manufacturers certificate | Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved. | Material certificate(s) | Site Engineer
1.6 | Top Buttress and surface water drain rock D50=150mm | W | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | Prior to commencement | Source test reports | D50=150mm rock with minimum specific gravity (SG) of2350kg/m3 | Material source test results, Delivery Dockets | Site Engineer
Section 2 : IN PROGRESS INSPECTIONS (Buttress)
2.1 | Survey Setout | H | Consistency with Construction Drawing | Prior to commencement | Survey | Set out extents of fill and check against design drawings | Survey receipt | Site Engineer | CPS Engineer
2.2 | Vegetation Clearance and removal of loose debris | W | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | Prior to commencement | Visual inspection | Remove and clear the vegetation | Photo's | Site Engineer
2.3 | Subgrade Excavation | H | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | During Construction | Visual inspection | Engineer to assess foundation material suitability | CPS COR report | Site Engineer | CPS Engineer
2.4 | Subgrade Inspection | H | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | Per area as required | Visual inspection | Inspect fill foundation. Fill foundation must be approved, in writing, before filling commences | CPS COR report | Site Engineer | CPS Engineer
2.5 | Ground Improvements | H | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | Prior to commencement | Document Review | Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence | CPS COR report | Site Engineer | CPS Engineer
2.6 | Class D (A39) Geotextile installation on the excavated face | W | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | During Construction | Visual Inspection | Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill | Photo's | Site Engineer
2.7 | Megaflow strip or drainage blanket installation or 110mm Novaflow in 300x300mm trench for seepage if Encountered | H | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | During Construction | Visual Inspection | Engineer to assess suitable drainage location. Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required. | Photo's, Drainage Line record check sheet (CS-4025) | Site Engineer | CPS Engineer
2.8 | Bulk Fill placement | M | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001, NZS4431:2022 | During Construction | Visual Inspection | Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill should be placed on dry subgrade. | Photo's | Site Engineer
2.9 | Bulk Fill Compaction | W | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | During Construction | NDM Testing | A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3 Nuclear densometer testing (NDM), by an IANZ accredited laboratory, will be required to confirm the engineered fill has achieved the required level of compaction | Compaction test reports, Photo's | Site Engineer
2.1 | Form and cut fill batter as per design 2.5H:1V | H | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | During Construction | Survey | Engineer to assess the completed slopes suitability to the design guidance. Slope angle of buttress is to not exceed 2.5H:1V | Survey as builts | Site Engineer | CPS Engineer
2.11 | Class E (A49) Geotextile placement along the face of fill batter | W | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | During Construction | Visual Inspection | Class E (A49) geotextile to be placed between the rock armour and bulk fill | Photo's | Site Engineer
2.12 | Rock Armour placement along the face of fill embankment | W | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | During Construction | Visual Inspection, survey | 2 x Layers of Rock riprap D50=600mm diameter) | Photo's, Survey As builts | Site Engineer
2.13 | Rock Armour key into ground | H | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | During Construction | Visual Inspection, survey | Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 3m wide as per notes on drawing. | CPS COR report and survey as built | Site Engineer | CPS Engineer
2.14 | Buttress Crest | H | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | During Construction | Visual Inspection, survey | The crest of the buttress slope shall extend to a width of 2m beyond the current fence line alignment. The drain and top of the buttress and secondary flow path shall be lined with rock (approx. d50 = 150mm diameter) | CPS COR report | Site Engineer | CPS Engineer
2.15 | As-built Survey | H |  | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
2.16 | Fence installation | W | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | During Construction | Visual Inspection | Fence line to be reinstated shall be "like for like" and positioned along similar alignment to the existing fence line | Photos | Site Engineer
Section 3 : Final Inspection and Handover
3.1 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
3.2 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date: