## Sheet1
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | F2501A-ID460 - D9 Gully Underslip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: |  |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: F2501A |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here) |  | Compliance with Work Instructions and Specifications
Detailed Location: SH35 RS172-RP4.140 to 4.180 North of Tikitiki
Chainage: SH35 RS172 RP4.14-4.18
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Specification/Drawings Reference | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
Section 1 : RECEIVING INSPECTIONS
1.1 | Bulk Fill (GAP65/GAP100) or similar | H | Buttress typical details and F2501A-DS-RP-GT-0003 | Prior to commencement | Supplier material test certificate | Should comprise clean granular aggregate and have broken faces. Material source testing | Material source test results | Site Engineer | CPS Engineer
1.2 | Class C A29 Geotextile | W | Buttress typical details and F2501A-DS-RP-GT-0003 | Prior to commencement | Manufacturers certificate | before placing foundation material and engineered hardfill | Material certificate(s) | Site Engineer
1.3 | Drainage blanket (AP65 or approved material) | W | F2501A-DS-RP-GT-0003, F2501A-DS-SK-GT-0048-A | Prior to commencement | Supplier material test certificate | Material source testing | Material source test results | Site Engineer
1.4 | AP40 (Basecourse) | W | TNZ M/4 | Prior to commencement | Submission | Source property testing Traceability of all materials delivered to site | Lab test reports, Delivery dockets | Site Engineer
1.5 | Geogrid/Geotextile | W | F2501A-DS-RP-GT-0003, F2501A-DS-SK-GT-0048-A | Prior to commencement | Visual Inspection | Delivery dockets with roll details. Check information on the delivery docket against the requirements indicated on the Drawings. | Delivery docket | Site Engineer
1.6 | AP65 (Sub-base) | W |  | Prior to commencement | Submission | Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak) | Lab test reports | Site Engineer
1.7 | Grade 3/5 Chip | W | NZTA M/6 | Prior to commencement | Submission | Source property testing Traceability of all materials delivered to site | Lab test reports, Delivery dockets | Site Engineer
1.8 | Cement Material cert | W |  | Prior to commencement | Submission |  | Material certificate(s) | Site Engineer
1.9 | Enkamat 7018 (or similar approved) | W | Buttress typical details and F2501A-DS-RP-GT-0003 | Prior to commencement | Submission | NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders | Material certificate(s) | Site Engineer
1.1 | Bitumen | W | TNZ M/1 | Prior to commencement | Submission | Binder to meet TNZ M/1 standard. E2 Certificate | E2 Certificate | Site Engineer
Section 2 : IN PROGRESS INSPECTIONS
2.1 | Survey Setout | H | Consistency with Construction Drawing | Prior to commencement | Survey | Set out extents of fill and check against design drawings. Subcontractor to arrange survey | Survey receipt | Site Engineer | CPS Engineer
2.2 | Vegetation Clearance and removal of fence & loose debris | W | Buttress typical details and F2501A-DS-RP-GT-0003 | Prior to commencement | Visual inspection | Remove and clear the vegetation & fence | Photo's | Site Engineer
2.3 | Subgrade Inspection | H | Buttress typical details and F2501A-DS-RP-GT-0003 | Per area as required | Visual inspection | Inspect fill foundation. Fill foundation must be approved, in writing, before filling commences | CPS COR report | Site Engineer | CPS Engineer
2.4 | Ground Improvements | H | Buttress typical details and F2501A-DS-RP-GT-0003 | Prior to commencement | Document Review | Any area that requires Ground Improvements (i.e undercut) must be completed as per CPS Engineer requirements and be signed off and closed before bulk earthwork operations commence | CPS COR report | Site Engineer | CPS Engineer
2.5 | Class C (A29) Geotextile installation on the excavated face | H | Buttress typical details and F2501A-DS-RP-GT-0003 | During Construction | Visual Inspection | Excavation undercut to be underlain with Bidim A29 or similar approved before placing drainage gravel material & and engineered fill. | Photo's, CPS COR Report | Site Engineer | CPS Engineer
2.6 | Drainage blanket/material installation (AP65 or approved material) | H | Buttress typical details and F2501A-DS-RP-GT-0003 | During Construction | Visual Inspection | CPS Engineer to assess suitable drainage location & extent. | Photo's, CPS COR Report | Site Engineer | CPS Engineer
2.7 | Bulk Fill placement | M | Buttress typical details and F2501A-DS-RP-GT-0003, NZS4431:2022, NZS 4402:1986 | During Construction | Visual Inspection | Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022. Fill should be placed on dry subgrade. | Bulk Fill Earthworks checksheet (CS-4100), Photo's | Site Engineer
2.8 | Placement of Geogrid/Geofabric | H | F2501A-DS-RP-GT-0003, F2501A-DS-SK-GT-0048-A | Prior to backfill | Visual inspection | Placement to be sighted & approved by CPS Engineer | CPS COR report | Site Engineer | CPS Engineer
2.9 | Cutting of Geogrid/Geotextile | W | Cuts shall be limited to 0.5m and only made along the weak axis. | Prior to backfill | Visual inspection | Geotextile/Geogrid cuts shall be undertaken if pre-approved and inspected by Engineer as per photographic evidence | Photo's | Site Engineer
2.1 | Bulk Fill Compaction | H | Buttress typical details and F2501A-DS-RP-GT-0003 | During Construction | Testing | A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3. Completed and signed COR per 1000m2 with a minimum of 3 checksheets for area covered. Scala results to determine CBR and required lap widths. | Compaction test reports, 1M Scala check sheet (CS-4000) | Site Engineer | CPS Engineer
2.11 | Form and cut fill batter as per design 2H:1V | H | Buttress typical details and F2501A-DS-RP-GT-0003 | During Construction | Survey | Engineer to assess the completed slopes suitability to the design guidance. Slope angle of buttress is to not exceed 2H:1V | Survey as builts | Site Engineer | CPS Engineer
Section 3 : IN PROGRESS INSPECTIONS (Pavement)
3.1 | Saw cut existing pavement | W |  | Prior to pavement construction | Visual inspection | Smooth and straight saw cut | Photo's | Site Engineer
3.2 | Subgrade construction | W | TNZ B2 | Every 20m | NDM testing | 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92% | Test reports | Site Engineer
3.3 | Subgrade Cement Application rate | W |  |  | Bag test | 2% cement stabilisation at 250mm deep subgrade | Bag test records | Site Engineer
3.4 | Sub-base construction | W | TNZ B2 | Every 20m | NDM testing | 200mm thick AP65 sub-base compacted to a minimum dry density of 95% Average 95% of MDD with nothing less than 92% | Test reports | Site Engineer
3.5 | Sub-base construction | W | TNZ B2 | Every 20m | Clegg Hammer testing | CIV>=25 | Test reports | Site Engineer
3.6 | Sub-base construction | W | TNZ B2 |  | Survey | Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction | Survey as builts | Site Engineer
3.7 | Basecourse construction | W | TNZ B2 | Every 20m | NDM testing | 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98% Average 98% of MDD with nothing less than 95% | Test reports, Photo's | Site Engineer
3.8 | Basecourse Cement application rate | W | TNZ B/5 |  | Visual inspection | 2% cement stabilisation at 150mm deep basecourse | Material specs, Photo's | Site Engineer
3.9 | Basecourse construction | W | TNZ B2 | Every 20m | Survey | Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction | Survey as builts | Site Engineer
3.1 | Basecourse construction | W | TNZ B2 | Every 20m | Clegg Hammer testing | CIV>=25 | Test reports, Photo's | Site Engineer
3.11 | Basecourse construction | H | TNZ B2 | Before sealing | Pre-seal checksheet | Mosaic surface | Photo's, Pre-seal checksheet (CS-4060) | Site Engineer | CPS Engineer
3.12 | Applying Bitumen | W | NZTA M/6 |  | Visual inspection | Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours | Photo's, Pre-seal checksheet (CS-4060) | Site Engineer
3.13 | Degree of saturation | W |  | Before sealing | Pre-seal checksheet | Degree of saturation should not exceed 80% | Pre-seal checksheet (CS-4060) | Site Engineer
3.14 | Chip seal laying | W | NZTA M/6 | During Construction | Submission | grade 3 and 5 chip seal | Material certificate(s), Photo's | Site Engineer
3.15 | Sweep & Line mark new chip seal road | W | TNZ P/12:2000 | During Construction | Visual inspection | As per TNZ P/12:2000 | Photo's
3.16 | As-built Survey | H |  | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
Section 4 : Final Inspection and Handover
4.1 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
4.2 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date: