## Sheet1
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: |  |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | F3202B - Earthworks Mangatuna River Buttress |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | 30.11.2023 |  | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-??-???? |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage: SH35 / RS250 / RP7.8-9.6
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Specification/Drawings Reference | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
Section 1 : RECEIVING INSPECTIONS
1.1 | Rock Armour (D50=450) | H | Buttress typical details and F3202B-DS-GT-RP-0001 | Prior to commencement | Supplier material test certificate | Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3. | Material source test results | Site Engineer | CPS Engineer
1.2 | Bulk Fill (GAP65/GAP100) or similar | H | Buttress typical details and F3202B-DS-GT-RP-0001 | Prior to commencement | Supplier material test certificate | Should comprise clean granular aggregate and have broken faces. Material source testing | Material source test results | Site Engineer | CPS Engineer
1.3 | Class D A39 Geotextile | W | Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7 compliant | Prior to commencement | Manufacturers certificate | NZTA F/7 compliant before placing foundation material and engineered hardfill | Material certificate(s) | Site Engineer
1.4 | Class E A49 Geotextile | W | Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7 compliant | Prior to commencement | Manufacturers certificate | NZTA F/7 compliant before placing foundation material and engineered hardfill | Material certificate(s) | Site Engineer
1.5 | Megaflow strip drain or drainage blanket for seepage if encountered | W | Buttress typical details and F3202B-DS-GT-RP-0001 | Prior to commencement | Manufacturers certificate | Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved. | Material certificate(s) | Site Engineer
1.6 | AP40 (Basecourse) | W | TNZ M/4 | Prior to commencement | Submission, Testing | Comply with TNZ M/4 specification Source property testing Traceability of all materials delivered to site | Lab test reports, Delivery Dockets | Site Engineer
1.7 | AP65 (Sub-base) | W |  | Prior to commencement | Submission | Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak) | Lab test reports | Site Engineer
1.8 | Grade 3/5 Chip | W | NZTA M/6 | Prior to commencement | Submission, Testing | Comply with NZTA M/6 specification Source property testing Traceability of all materials delivered to site | Lab test reports, Delivery Dockets | Site Engineer
1.9 | Cement Material cert | W |  | Prior to commencement | Submission |  | Material certificate(s) | Site Engineer
1.1 | Bitumen | W | TNZ M/1 | Prior to commencement | Submission | Binder to meet TNZ M/1 standard. E2 Certificate | E2 Certificate | Site Engineer
Section 2 : IN PROGRESS INSPECTIONS
2.1 | Survey Setout | H | Consistency with Construction Drawing | Prior to commencement | Survey | Set out extents of fill and check against design drawings | Survey receipt | Site Engineer | CPS Engineer
2.2 | Vegetation Clearance and removal of loose debris | W | Buttress typical details C and F3202B-DS-GT-RP-0001 | Prior to commencement | Visual inspection | Remove and clear the vegetation | Photo's | Site Engineer
2.3 | Subgrade Excavation | H | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual inspection During Construction | Engineer to assess foundation material suitability | CPS COR report | Site Engineer | CPS Engineer
2.4 | Subgrade Inspection | H | Buttress typical details C and F3202B-DS-GT-RP-0001 | Per area as required | Inspection by the Geotechnical Design Manager | Inspect fill foundation. Fill foundation must be approved, in writing, before filling commences | CPS COR report | Site Engineer | CPS Engineer
2.5 | Ground Improvements | H | Buttress typical details C and F3202B-DS-GT-RP-0001 | Prior to commencement | Document Review | Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence | CPS COR report | Site Engineer | CPS Engineer
2.6 | Class D (A39) Geotextile installation on the excavated face | W | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual Inspection | Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill. | Photo's | Site Engineer
2.7 | Megaflow strip or drainage blanket installation for seepage if Encountered | H | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual Inspection | Engineer to assess suitable drainage location. Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required. | Photo's, Drainage Line record check sheet (CS-4025) | Site Engineer | CPS Engineer
2.8 | Bulk Fill placement | M | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual Inspection | Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill should be placed on dry subgrade. | Photo's | Site Engineer
2.9 | Bulk Fill Compaction | M | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Testing | A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3 | Compaction test reports | Site Engineer
2.1 | Form and cut fill batter as per design 2H:1V | H | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Survey | Engineer to assess the completed slopes suitability to the design guidance. Slope angle of buttress is to not exceed 2H:1V | Survey as builts | Site Engineer | CPS Engineer
2.11 | ClassE (A49) Geotextile placement along the face of fill batter | W | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual Inspection | Class E geotextile to be placed between the rock armour and bulk fill | Photo's | Site Engineer
2.12 | Rock Armour placement along the face of fill embankment | W | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual Inspection, survey | 2 x Layers of Rock riprap (D50=450mm diameter) | Photo's, Survey as builts | Site Engineer
2.13 | Rock Armour key into ground | H | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual Inspection, survey | Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 1m to 2m wide. | CPS COR report and survey as built | Site Engineer | CPS Engineer
Section 3 : IN PROGRESS INSPECTIONS (Pavement)
3.1 | Saw cut existing pavement | W |  | Prior to pavement construction | Visual inspection | Smooth and straight saw cut | Photo's | Site Engineer
3.2 | Subgrade construction | W | TNZ B2 | Every 20m | NDM testing | 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92% | Test reports | Site Engineer
3.3 | Subgrade Cement Application rate | W |  |  | Bag test | 2% cement stabilisation at 250mm deep subgrade | Bag test records | Site Engineer
3.4 | Sub-base construction | W | TNZ B2 | Every 20m | NDM testing | 200mm thick AP65 sub-base compacted to a minimum dry density of 95% Average 95% of MDD with nothing less than 92% | Test reports | Site Engineer
3.5 | Sub-base construction | W | TNZ B2 | Every 20m | Clegg Hammer testing | CIV>=25 | Test reports | Site Engineer
3.6 | Sub-base construction | H | TNZ B2 |  | Survey as-builts | Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction | Survey as builts | Site Engineer | CPS Engineer
3.7 | Basecourse construction | W | TNZ B2 | Every 20m | NDM testing | 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98% Average 98% of MDD with nothing less than 95% | Test reports, Photo's | Site Engineer
3.8 | Basecourse Cement application rate | W | TNZ B/5 |  | Visual inspection | 2% cement stabilisation at 150mm deep basecourse | Material specs, Photo's | Site Engineer
3.9 | Basecourse construction | W | TNZ B2 | Every 20m | Survey | Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction | Survey as builts | Site Engineer
3.1 | Basecourse construction | W | TNZ B2 | Every 20m | Clegg Hammer testing | CIV>=25 | Test reports, Photo's | Site Engineer
3.11 | Basecourse construction | H | TNZ B2 | Before sealing | Pre-seal checksheet | Mosaic surface | Photo's, Pre-seal checksheet (CS-4060) | Site Engineer | CPS Engineer
3.12 | Applying Bitumen | W | NZTA M/6 |  | Visual inspection | Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours | Photo's, Pre-seal checksheet (CS-4060) | Site Engineer
3.13 | Degree of saturation | W |  | Before sealing | Pre-seal checksheet | Degree of saturation should not exceed 80% | Pre-seal checksheet (CS-4060) | Site Engineer
3.14 | Chip seal laying | W | NZTA M/6 | During Construction | Submission | Grade 3 and 5 chip seal | Material certificate(s), Photo's | Site Engineer
3.15 | As-built Survey | H |  | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
Section 4 : Final Inspection and Handover
4.1 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
4.2 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date:
Note on M22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Gurdeep Singh will survey set out be required for this specific site? May be on others but not sure this one. Reply: @Nick Reid Agree, i don't think the survey set out required but we should be able to cover this during the site visit with CPS team to finalise the extent.
Note on M25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Gurdeep Singh will scala or other subgrade testing be required or only inspection? Reply: @Nick Reid I couldn't find anything regarding the subgrade testing on the design report and drawings. Talking to Adam, he advised we may not be able to do the scalas one because of Safety reasons and second because of expected soft ground conditions. we will just find a good subgrade surface to place fill.