## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Maraetaha Bridge 5 - D2102A-ID1507 | itp |  |  |  |  | ITP - Maraetaha Bridge 5 - D2102A-ID1507
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - 2t Ecogreen/Kyowa bags
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3436.BM(14) S02-S03
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Purchased from Bluemont or similar approved
label | Records - Material cert, delivery dockets
checkpoint | 1.2 - Class D A39 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3436.BM(14) S02-S03, TNZ F/7
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - TNZ F/7 filtration class 1 strength Class D
label | Records - Material cert, delivery dockets
checkpoint | 1.3 - Granular Backfill AP65
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - SH2 R5 461/7.78 - Maraetaha Bridge No. 5 (BSN4688) Pier Protection works 2-U3436.BM(14)-S2-2
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Material source property reports
label | Conformance Criteria - AP65 shall be hard, durable, well graded, free draining material with maximum particle size of 65mm and not more than 5% by mass passing a 75-micron sieve
label | Records - Material cert, delivery dockets
checkpoint | 1.4 - Rock Infill for Eco-Green Rock Bags
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - SH2 R5 461/7.78 - Maraetaha Bridge No. 5 (BSN4688) Pier Protection works 2-U3436.BM(14)-S2-2
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Material source property reports
label | Conformance Criteria - Sound, hard, durable rock resistant to weathering shall be used as rock bag infill material.
label | ○ Sized from 50mm up to 175mm but not exceeding 200mm. Should be round in shape and not flat.
label | Records - Material cert, delivery dockets
holdpoint | AUTHORITY HOLDPOINT
section | Section 2: IN PROGRESS INSPECTIONS (Buttress)
checkpoint | 2.1 - Survey Setout and joint site visit
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with 2-U3436.BM(14) S01-S03
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - CPS Engineer to confirm and agree the extent of works including rock bag placement and survey set-out
label | Records - Survey receipt, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Remove and clear the vegetation
label | Records - Photo's
checkpoint | 2.3 - Subgrade Excavation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - CPS Engineer to inspect foundation level when required depth has been met.
label | ○ Scala check sheet (to 1.5 metres)
label | Records - Scala Check sheet (CS-4000), CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Any area that requires Ground Improvements (i.e. additional undercuts) must be completed as per CPS Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Granular Backfill AP65
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03, TNZ F/1
label | Frequency - At 5m intervals max taken at mid point between the rock bags on each 600mm thick layer prior to placing next layer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg hammer or NDM testing
label | Conformance Criteria - Comply with TNZ F/1.
label | ○ Well graded AP65 compacted to Minimum of 95% MDD. Compaction test results submitted to the CPS Engineer for approval prior to placing the next layer
label | Records - Test Reports, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Class D (A39) Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Installation between the AP65 fill and rock filled bags.
label | ○ The fabric shall be laid and overlapped as per manufacturers recommendations
label | Records - Photo's
checkpoint | 2.7 - Rock Bag installation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Rock bags to be filled and placed in accordance with the manufacturers specification and are to be stacked so that the average angle is no steeper than 2H to 1V.
label | ○ The final layer will be determined by the CPS Engineer on site
label | Records - Photo's, CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Bulk Fill Placement access roads
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Consistency with Construction Drawing 2-U3436.BM(14) S01-S03, NZS4431:2022, TNZ F/1
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
label | Records - Bulk Fill Earthworks check sheet (CS-4020), Photo's
checkpoint | 2.9 - Topsoiling
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - 2-U3436.BM(14)-S03
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Topsoil shall be spread out on the disturbed area at a nominal thickness of 100mm but not less than 50mm nor more than 120mm.
label | ○ Batter steeper than 2:1 are not to be topsoiled.
label | Records - Photos
checkpoint | 2.10 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Grassing
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - 2-U3436.BM(14)-S03
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Grassing should be superphosphate at a rate 50grams per square meter, Grass seed shall be sown at the rate of 25 grams per square metre bare seed weight
label | Records - Photos
section | Section 3: Final Inspection and Handover
checkpoint | 3.1 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 3.2 - Completion Sign Off From Fields Below
label | Records - Signatures