## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - B1004C White Pine Bush - Subsoil Drainage | itp |  |  |  |  | ITP - B1004C White Pine Bush - Subsoil Drainage
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out Edge of Seal to 1m offset. Setout and mark all known services along the line of the Sub-soil Drain.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
checkpoint | 2 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 100mm diameter
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - 100mm diameter Drain flow TNZ F/2 Grade pipe
label | Records - Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure Material for Bedding, Side support and backfill is 3 to 7 Clean Drainage Chip (Reject Chip)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure clean drainage chip
label | Records - Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the bidim material is A14. A similar material maybe used but it must be approved
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - Ensure geotextile is approved for use
label | Records - Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Trenching
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect trench profile and ensure it is 0.300m wide and 1.000m below Edge of Seal level.
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | Conformance Criteria - Record levels of base of trench on dip sheet
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | Conformance Criteria - Ensure trench line and levels match the design drawings
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Design Engineer to instruct action and record on dip sheet and as built drawing
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Bedding, pipe installation and Backfill.
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Upon completion of trenching Bidim 14 or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure material covers the trench and is pinned in place
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure 100mm thick 3 to 7 Clean Drainage chip (Reject Chip) bedding is placed in base of trench.
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Record levels of top of bedding on dip sheet
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Consistency with Subsoil Details
label | Records - Photos
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - As built Survey the Pipe before backfill
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Consistency with Subsoil Details
label | Records - As-built receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill by tipping 3 to 7 Clean Drainage chip (Reject chip) into the trench
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure good coverage
label | Records - Photos
checkpoint | 13 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
checkpoint | 14 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT