## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Compliance and Environmental | itp |  |  |  |  | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Compliance and Environmental
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Approved Consents
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Is a copy of approved consent(s) available on site
label | Conformance Criteria - Check latest consents and SSESCP's are at each site office
label | Records - This ITP
checkpoint | 2 - Internal ESC Pre-Construction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Internal pre-construction meeting held with E Team
label | Conformance Criteria - Environmental Advisor to organise
label | Records - This ITP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Type and Location of Erosion & Sedimentation Control
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Confirm type and location of erosion and sedimentation control, based on relevant drawing/s
label | Conformance Criteria - Relevant ESCP drawing
label | Records - This ITP
checkpoint | 4 - Channel Bund (if required)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Bund is constructed in correct location; to agreed / specified dimensions and levels; and is firmly compacted.
label | Conformance Criteria - Work Instruction, Drawings and Checklist
checkpoint | 5 - Silt Fence (SF) (if required)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Silt Fence or Super Silt Fence is constructed in correct location; to correct dimensions, and geotextile secured and waratahs located as shown on the WI and drawings
label | Conformance Criteria - Work Instruction, Drawings and Checklist
checkpoint | 6 - As-Builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm as-built details of completed works
label | Conformance Criteria - Submit to Document Control/Environmental Advisor to issue to HRC within 24 Hours
label | Records - This ITP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Maintenance Inspections
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Undertake weekly inspections of all erosion and sedimentation controls and after > 5mm rain to identify required maintenance
label | Conformance Criteria - Approved ESC Plan. Complete weekly and upload to ConQA / Procore
checkpoint | 8 - Decommissioning of Erosion Sediment Controls
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Decommissioning Plan submitted to HRC for Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Decommissioning of Erosion Sediment Controls
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - HRC to issue an approval document so that Decommissioning works can commence
label | Conformance Criteria - Approval for Decommissioning
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register