## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Maraetaha Bridge 5 - D2102A-ID1507 | itp |  |  |  |  | ITP - Maraetaha Bridge 5 - D2102A-ID1507 | 576460f8-072f-412f-bf4a-eb21bfd70cac
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - 2t Ecogreen/Kyowa bags
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3436.BM(14) S02-S03
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Purchased from Bluemont or similar approved
label | Records - Material cert, delivery dockets
checkpoint | 1.2 - Class D A39 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3436.BM(14) S02-S03, TNZ F/7
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - TNZ F/7 filtration class 1 strength Class D
label | Records - Material cert, delivery dockets
checkpoint | 1.3 - Granular Backfill AP65
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - SH2 R5 461/7.78 - Maraetaha Bridge No. 5 (BSN4688) Pier Protection works 2-U3436.BM(14)-S2-2
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Material source property reports
label | Conformance Criteria - AP65 shall be hard, durable, well graded, free draining material with maximum particle size of 65mm and not more than 5% by mass passing a 75-micron sieve
label | Records - Material cert, delivery dockets
checkpoint | 1.4 - Rock Infill for Eco-Green Rock Bags
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - SH2 R5 461/7.78 - Maraetaha Bridge No. 5 (BSN4688) Pier Protection works 2-U3436.BM(14)-S2-2
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Material source property reports
label | Conformance Criteria - Sound, hard, durable rock resistant to weathering shall be used as rock bag infill material.
label | ○ Sized from 50mm up to 175mm but not exceeding 200mm. Should be round in shape and not flat.
label | Records - Material cert, delivery dockets
holdpoint | AUTHORITY HOLDPOINT
section | Section 2: IN PROGRESS INSPECTIONS (Buttress)
checkpoint | 2.1 - Survey Setout and joint site visit
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with 2-U3436.BM(14) S01-S03
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - CPS Engineer to confirm and agree the extent of works including rock bag placement and survey set-out
label | Records - Survey receipt, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Remove and clear the vegetation
label | Records - Photo's
checkpoint | 2.3 - Subgrade Excavation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - CPS Engineer to inspect foundation level when required depth has been met.
label | ○ Scala check sheet (to 1.5 metres)
label | Records - Scala Check sheet (CS-4000), CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Any area that requires Ground Improvements (i.e. additional undercuts) must be completed as per CPS Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Granular Backfill AP65
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03, TNZ F/1
label | Frequency - At 5m intervals max taken at mid point between the rock bags on each 600mm thick layer prior to placing next layer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg hammer or NDM testing
label | Conformance Criteria - Comply with TNZ F/1.
label | ○ Well graded AP65 compacted to Minimum of 95% MDD. Compaction test results submitted to the CPS Engineer for approval prior to placing the next layer
label | Records - Test Reports, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Class D (A39) Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Installation between the AP65 fill and rock filled bags.
label | ○ The fabric shall be laid and overlapped as per manufacturers recommendations
label | Records - Photo's
checkpoint | 2.7 - Rock Bag installation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Rock bags to be filled and placed in accordance with the manufacturers specification and are to be stacked so that the average angle is no steeper than 2H to 1V.
label | ○ The final layer will be determined by the CPS Engineer on site
label | Records - Photo's, CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Bulk Fill Placement access roads
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Consistency with Construction Drawing 2-U3436.BM(14) S01-S03, NZS4431:2022, TNZ F/1
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
label | Records - Bulk Fill Earthworks check sheet (CS-4020), Photo's
checkpoint | 2.9 - Topsoiling
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - 2-U3436.BM(14)-S03
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Topsoil shall be spread out on the disturbed area at a nominal thickness of 100mm but not less than 50mm nor more than 120mm.
label | ○ Batter steeper than 2:1 are not to be topsoiled.
label | Records - Photos
checkpoint | 2.10 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Grassing
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - 2-U3436.BM(14)-S03
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Grassing should be superphosphate at a rate 50grams per square meter, Grass seed shall be sown at the rate of 25 grams per square metre bare seed weight
label | Records - Photos
section | Section 3: Final Inspection and Handover
checkpoint | 3.1 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 3.2 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist-flat | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Network Drainage | itp |  |  |  |  | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Network Drainage | 55b5d343-05dd-44a2-94d9-bc79056fcc1c
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Setout inlet & outlet points with inverts as required by Contractor to construct to design
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey (As agreed with Engineer)
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Locate existing services by hand digging
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging/hudro excavation
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
label | Records - As-built Drawings Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Trenching and Excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Inspect trench profile and ensure it is correct to lines and levels to design
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Line and level is correct
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - D/6 or 150mm whichever is greater on either side of the pipe
checkpoint | 5 - Foundation Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test formation level on completion of excavation to check if undercut required
label | Frequency - As stated
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection by Designer
label | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
label | Records - CS-4025 Drainage Line Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Pipe Bedding Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Compliance with requirements from Specifications
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfill Construction Material
label | Frequency - 1 test per 50m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Solid wall pipe – Pea Metal < 7mm
label | Records - CS-4025 Drainage Line Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Bedding
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Bedding - Ensure correct thickness of bedding is placed
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Type 3 support as per drawing
label | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint | 9 - Pipes and Precast Units
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Frequency - Each delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | Conformance Criteria - Comply with Section 3 AS/NZS2566.2
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Pipe Laying
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall be less than 3mm
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Line and level to follow existing pipe
label | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
label | Records - Photos
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - As-built survey of pipes installed
label | Frequency - Once line is completed between 2 structures
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Invert level <= 5mm and grade <= 3mm from design levels
label | Records - Survey Receipt
checkpoint | 13 - Design Engineer Pre backfill Inspection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps.
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Compliance with the Specification
label | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint | 14 - Pipe Backfill Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Comply with grading specification 100% pass 50mm at least 45% pass the 19mm sieve, and not more than 10% pass 425 micron sieve, CBR not less than 40 and SE of not less than 40
label | Records - CS-4025 Drainage Line Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfill Construction Material
label | Frequency - 1 test per 100m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Comply with grading specification 100% pass 50mm at least 45% pass the 19mm sieve, and not more than 10% pass 425 micron sieve, CBR not less than 40 and SE of not less than 40
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Backfilling
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
label | Frequency - 1 test per 20 m length of trench per 300mm lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent
label | Records - Lab test results
checkpoint | 17 - Structure installation (Manhole, Catchpit, Wingwall)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Structures to be installed to the design survey location and level
label | Frequency - During structure construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - As Built Survey
label | Records - CS-4006 Manhole Catchpit Board Check Sheet and Survey receipt
checkpoint | 18 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Arrange as-built survey of the structure and all invert levels
label | Frequency - Once installed
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - As Built Survey
label | Records - Survey Receipt
checkpoint | 20 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 21 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - B1004C White Pine Bush - Subsoil Drainage | itp |  |  |  |  | ITP - B1004C White Pine Bush - Subsoil Drainage | 72731249-5c49-48b8-845d-b0c8f1394a97
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out Edge of Seal to 1m offset. Setout and mark all known services along the line of the Sub-soil Drain.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
checkpoint | 2 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 100mm diameter
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - 100mm diameter Drain flow TNZ F/2 Grade pipe
label | Records - Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure Material for Bedding, Side support and backfill is 3 to 7 Clean Drainage Chip (Reject Chip)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure clean drainage chip
label | Records - Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the bidim material is A14. A similar material maybe used but it must be approved
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - Ensure geotextile is approved for use
label | Records - Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Trenching
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect trench profile and ensure it is 0.300m wide and 1.000m below Edge of Seal level.
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | Conformance Criteria - Record levels of base of trench on dip sheet
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | Conformance Criteria - Ensure trench line and levels match the design drawings
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Design Engineer to instruct action and record on dip sheet and as built drawing
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Bedding, pipe installation and Backfill.
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Upon completion of trenching Bidim 14 or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure material covers the trench and is pinned in place
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure 100mm thick 3 to 7 Clean Drainage chip (Reject Chip) bedding is placed in base of trench.
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Record levels of top of bedding on dip sheet
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Consistency with Subsoil Details
label | Records - Photos
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - As built Survey the Pipe before backfill
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Consistency with Subsoil Details
label | Records - As-built receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill by tipping 3 to 7 Clean Drainage chip (Reject chip) into the trench
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure good coverage
label | Records - Photos
checkpoint | 13 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
checkpoint | 14 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Compliance and Environmental | itp |  |  |  |  | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Compliance and Environmental | 12e678d8-bc59-49b5-bf5f-7447a11f0a2f
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Approved Consents
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Is a copy of approved consent(s) available on site
label | Conformance Criteria - Check latest consents and SSESCP's are at each site office
label | Records - This ITP
checkpoint | 2 - Internal ESC Pre-Construction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Internal pre-construction meeting held with E Team
label | Conformance Criteria - Environmental Advisor to organise
label | Records - This ITP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Type and Location of Erosion & Sedimentation Control
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Confirm type and location of erosion and sedimentation control, based on relevant drawing/s
label | Conformance Criteria - Relevant ESCP drawing
label | Records - This ITP
checkpoint | 4 - Channel Bund (if required)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Bund is constructed in correct location; to agreed / specified dimensions and levels; and is firmly compacted.
label | Conformance Criteria - Work Instruction, Drawings and Checklist
checkpoint | 5 - Silt Fence (SF) (if required)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Silt Fence or Super Silt Fence is constructed in correct location; to correct dimensions, and geotextile secured and waratahs located as shown on the WI and drawings
label | Conformance Criteria - Work Instruction, Drawings and Checklist
checkpoint | 6 - As-Builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm as-built details of completed works
label | Conformance Criteria - Submit to Document Control/Environmental Advisor to issue to HRC within 24 Hours
label | Records - This ITP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Maintenance Inspections
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Undertake weekly inspections of all erosion and sedimentation controls and after > 5mm rain to identify required maintenance
label | Conformance Criteria - Approved ESC Plan. Complete weekly and upload to ConQA / Procore
checkpoint | 8 - Decommissioning of Erosion Sediment Controls
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Decommissioning Plan submitted to HRC for Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Decommissioning of Erosion Sediment Controls
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - HRC to issue an approval document so that Decommissioning works can commence
label | Conformance Criteria - Approval for Decommissioning
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checklist | ITP - D1603B - ID587B - Otoko Flats Underslip | itp |  |  |  |  | ITP - D1603B - ID587B - Otoko Flats Underslip | f08233bc-12f7-4efc-8321-92d9e17a472f
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Rock Armour (D50=600)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 600 with a minimum specific Gravity SG of 2350kg/m3.
label | Records - Material source test results, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Bulk Fill (GAP65/GAP100) or similar
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | ○ Material source testing
label | Records - Material source test results, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Class D A39 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001, NZTA F/7
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
label | Records - Material certificate(s)
checkpoint | 1.4 - Class E A49 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001, NZTA F/7
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
label | Records - Material certificate(s)
checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | Records - Material certificate(s)
checkpoint | 1.6 - Top Buttress and surface water drain rock D50=150mm
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Source test reports
label | Conformance Criteria - D50=150mm rock with minimum specific gravity (SG) of2350kg/m3
label | Records - Material source test results, Delivery Dockets
section | Section 2: IN PROGRESS INSPECTIONS (Buttress)
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Set out extents of fill and check against design drawings
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Remove and clear the vegetation
label | Records - Photo's
checkpoint | 2.3 - Subgrade Excavation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer to assess foundation material suitability
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Subgrade Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Inspect fill foundation.
label | ○ Fill foundation must be approved, in writing, before filling commences
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Class D (A39) Geotextile installation on the excavated face
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill
label | Records - Photo's
checkpoint | 2.7 - Megaflow strip or drainage blanket installation or 110mm Novaflow in 300x300mm trench for seepage if Encountered
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineer to assess suitable drainage location.
label | ○ Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
label | Records - Photo's, Drainage Line record check sheet (CS-4025)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Bulk Fill placement
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001, NZS4431:2022
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control.
label | ○ Fill should be placed on dry subgrade.
label | Records - Photo's
checkpoint | 2.9 - Bulk Fill Compaction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | ○ Nuclear densometer testing (NDM), by an IANZ accredited laboratory, will be required to confirm the engineered fill has achieved the required level of compaction
label | Records - Compaction test reports, Photo's
checkpoint | 2.10 - Form and cut fill batter as per design 2.5H:1V
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | ○ Slope angle of buttress is to not exceed 2.5H:1V
label | Records - Survey as builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Class E (A49) Geotextile placement along the face of fill batter
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Class E (A49) geotextile to be placed between the rock armour and bulk fill
label | Records - Photo's
checkpoint | 2.12 - Rock Armour placement along the face of fill embankment
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - 2 x Layers of Rock riprap D50=600mm diameter)
label | Records - Photo's, Survey As builts
checkpoint | 2.13 - Rock Armour key into ground
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 3m wide as per notes on drawing.
label | Records - CPS COR report and survey as built
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.14 - Buttress Crest
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - The crest of the buttress slope shall extend to a width of 2m beyond the current fence line alignment. The drain and top of the buttress and secondary flow path shall be lined with rock (approx. d50 = 150mm diameter)
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.15 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.16 - Fence installation
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Fence line to be reinstated shall be "like for like" and positioned along similar alignment to the existing fence line
label | Records - Photos
section | Section 3: Final Inspection and Handover
checkpoint | 3.1 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 3.2 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist | ITP - F2501A-ID460 - D9 Gully Underslip | itp |  |  |  |  | ITP - F2501A-ID460 - D9 Gully Underslip | ea7851d6-da70-4bfc-9305-881dc286549d
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Bulk Fill (GAP65/GAP100) or similar
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | ○ Material source testing
label | Records - Material source test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Class C A29 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - before placing foundation material and engineered hardfill
label | Records - Material certificate(s)
checkpoint | 1.3 - Drainage blanket (AP65 or approved material)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F2501A-DS-RP-GT-0003, F2501A-DS-SK-GT-0048-A
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Material source testing
label | Records - Material source test results
checkpoint | 1.4 - AP40 (Basecourse)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ M/4
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Source property testing
label | ○ Traceability of all materials delivered to site
label | Records - Lab test reports, Delivery dockets
checkpoint | 1.5 - Geogrid/Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F2501A-DS-RP-GT-0003, F2501A-DS-SK-GT-0048-A
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Delivery dockets with roll details. Check information on the delivery docket against the requirements indicated on the Drawings.
label | Records - Delivery docket
checkpoint | 1.6 - AP65 (Sub-base)
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
label | Records - Lab test reports
checkpoint | 1.7 - Grade 3/5 Chip
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Source property testing
label | ○ Traceability of all materials delivered to site
label | Records - Lab test reports, Delivery dockets
checkpoint | 1.8 - Cement Material cert
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Material certificate(s)
checkpoint | 1.9 - Enkamat 7018 (or similar approved)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
label | Records - Material certificate(s)
checkpoint | 1.10 - Bitumen
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ M/1
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | Records - E2 Certificate
section | Section 2: IN PROGRESS INSPECTIONS
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Set out extents of fill and check against design drawings. Subcontractor to arrange survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Vegetation Clearance and removal of fence & loose debris
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Remove and clear the vegetation & fence
label | Records - Photo's
checkpoint | 2.3 - Subgrade Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Inspect fill foundation.
label | ○ Fill foundation must be approved, in writing, before filling commences
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Any area that requires Ground Improvements (i.e undercut) must be completed as per CPS Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Class C (A29) Geotextile installation on the excavated face
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Excavation undercut to be underlain with Bidim A29 or similar approved before placing drainage gravel material & and engineered fill.
label | Records - Photo's, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Drainage blanket/material installation (AP65 or approved material)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS Engineer to assess suitable drainage location & extent.
label | Records - Photo's, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Bulk Fill placement
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003, NZS4431:2022, NZS 4402:1986
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022.
label | ○ Fill should be placed on dry subgrade.
label | Records - Bulk Fill Earthworks checksheet (CS-4100), Photo's
checkpoint | 2.8 - Placement of Geogrid/Geofabric
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F2501A-DS-RP-GT-0003, F2501A-DS-SK-GT-0048-A
label | Frequency - Prior to backfill
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Placement to be sighted & approved by CPS Engineer
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Cutting of Geogrid/Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Cuts shall be limited to 0.5m and only made along the weak axis.
label | Frequency - Prior to backfill
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Geotextile/Geogrid cuts shall be undertaken if pre-approved and inspected by Engineer as per photographic evidence
label | Records - Photo's
checkpoint | 2.10 - Bulk Fill Compaction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3.
label | ○ Completed and signed COR per 1000m2 with a minimum of 3 checksheets for area covered. Scala results to determine CBR and required lap widths.
label | Records - Compaction test reports, 1M Scala check sheet (CS-4000)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Form and cut fill batter as per design 2H:1V
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | ○ Slope angle of buttress is to not exceed 2H:1V
label | Records - Survey as builts
holdpoint | AUTHORITY HOLDPOINT
section | Section 3: IN PROGRESS INSPECTIONS (Pavement)
checkpoint | 3.1 - Saw cut existing pavement
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Prior to pavement construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Smooth and straight saw cut
label | Records - Photo's
checkpoint | 3.2 - Subgrade construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
label | Records - Test reports
checkpoint | 3.3 - Subgrade Cement Application rate
label | ACTION (Hold, Monitor, Witness) - W
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
label | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
label | Records - Bag test records
checkpoint | 3.4 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%
label | ○ Average 95% of MDD with nothing less than 92%
label | Records - Test reports
checkpoint | 3.5 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | Conformance Criteria - CIV>=25
label | Records - Test reports
checkpoint | 3.6 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | Records - Survey as builts
checkpoint | 3.7 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
label | ○ Average 98% of MDD with nothing less than 95%
label | Records - Test reports, Photo's
checkpoint | 3.8 - Basecourse Cement application rate
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B/5
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | Records - Material specs, Photo's
checkpoint | 3.9 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | Records - Survey as builts
checkpoint | 3.10 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | Conformance Criteria - CIV>=25
label | Records - Test reports, Photo's
checkpoint | 3.11 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Before sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | Conformance Criteria - Mosaic surface
label | Records - Photo's, Pre-seal checksheet (CS-4060)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Applying Bitumen
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint | 3.13 - Degree of saturation
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Before sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | Conformance Criteria - Degree of saturation should not exceed 80%
label | Records - Pre-seal checksheet (CS-4060)
checkpoint | 3.14 - Chip seal laying
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - grade 3 and 5 chip seal
label | Records - Material certificate(s), Photo's
checkpoint | 3.15 - Sweep & Line mark new chip seal road
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ P/12:2000
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - As per TNZ P/12:2000
label | Records - Photo's
checkpoint | 3.16 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
section | Section 4: Final Inspection and Handover
checkpoint | 4.1 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.2 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist | ITP - F3202B - Earthworks Mangatuna River Buttress | itp |  |  |  |  | ITP - F3202B - Earthworks Mangatuna River Buttress | a186a86a-03fd-426f-90c4-e10ceef55c74
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Rock Armour (D50=450)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
label | Records - Material source test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Bulk Fill (GAP65/GAP100) or similar
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | ○ Material source testing
label | Records - Material source test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Class D A39 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7 compliant
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
label | Records - Material certificate(s)
checkpoint | 1.4 - Class E A49 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7 compliant
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
label | Records - Material certificate(s)
checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | Records - Material certificate(s)
checkpoint | 1.6 - AP40 (Basecourse)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ M/4
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
label | Conformance Criteria - Comply with TNZ M/4 specification
label | ○ Source property testing
label | ○ Traceability of all materials delivered to site
label | Records - Lab test reports, Delivery Dockets
checkpoint | 1.7 - AP65 (Sub-base)
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
label | Records - Lab test reports
checkpoint | 1.8 - Grade 3/5 Chip
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
label | Conformance Criteria - Comply with NZTA M/6 specification
label | ○ Source property testing
label | ○ Traceability of all materials delivered to site
label | Records - Lab test reports, Delivery Dockets
checkpoint | 1.9 - Cement Material cert
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Material certificate(s)
checkpoint | 1.10 - Bitumen
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ M/1
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | Records - E2 Certificate
section | Section 2: IN PROGRESS INSPECTIONS
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Set out extents of fill and check against design drawings
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Remove and clear the vegetation
label | Records - Photo's
checkpoint | 2.3 - Subgrade Excavation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection During Construction
label | Conformance Criteria - Engineer to assess foundation material suitability
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Subgrade Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | Conformance Criteria - Inspect fill foundation.
label | ○ Fill foundation must be approved, in writing, before filling commences
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Class D (A39) Geotextile installation on the excavated face
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
label | Records - Photo's
checkpoint | 2.7 - Megaflow strip or drainage blanket installation for seepage if Encountered
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineer to assess suitable drainage location.
label | ○ Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
label | Records - Photo's, Drainage Line record check sheet (CS-4025)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Bulk Fill placement
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control.
label | ○ Fill should be placed on dry subgrade.
label | Records - Photo's
checkpoint | 2.9 - Bulk Fill Compaction
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | Records - Compaction test reports
checkpoint | 2.10 - Form and cut fill batter as per design 2H:1V
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | ○ Slope angle of buttress is to not exceed 2H:1V
label | Records - Survey as builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - ClassE (A49) Geotextile placement along the face of fill batter
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Class E geotextile to be placed between the rock armour and bulk fill
label | Records - Photo's
checkpoint | 2.12 - Rock Armour placement along the face of fill embankment
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - 2 x Layers of Rock riprap (D50=450mm diameter)
label | Records - Photo's, Survey as builts
checkpoint | 2.13 - Rock Armour key into ground
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 1m to 2m wide.
label | Records - CPS COR report and survey as built
holdpoint | AUTHORITY HOLDPOINT
section | Section 3: IN PROGRESS INSPECTIONS (Pavement)
checkpoint | 3.1 - Saw cut existing pavement
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Prior to pavement construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Smooth and straight saw cut
label | Records - Photo's
checkpoint | 3.2 - Subgrade construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
label | Records - Test reports
checkpoint | 3.3 - Subgrade Cement Application rate
label | ACTION (Hold, Monitor, Witness) - W
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
label | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
label | Records - Bag test records
checkpoint | 3.4 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%
label | ○ Average 95% of MDD with nothing less than 92%
label | Records - Test reports
checkpoint | 3.5 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | Conformance Criteria - CIV>=25
label | Records - Test reports
checkpoint | 3.6 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ B2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey as-builts
label | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | Records - Survey as builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
label | ○ Average 98% of MDD with nothing less than 95%
label | Records - Test reports, Photo's
checkpoint | 3.8 - Basecourse Cement application rate
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B/5
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | Records - Material specs, Photo's
checkpoint | 3.9 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | Records - Survey as builts
checkpoint | 3.10 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | Conformance Criteria - CIV>=25
label | Records - Test reports, Photo's
checkpoint | 3.11 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Before sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | Conformance Criteria - Mosaic surface
label | Records - Photo's, Pre-seal checksheet (CS-4060)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Applying Bitumen
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint | 3.13 - Degree of saturation
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Before sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | Conformance Criteria - Degree of saturation should not exceed 80%
label | Records - Pre-seal checksheet (CS-4060)
checkpoint | 3.14 - Chip seal laying
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Grade 3 and 5 chip seal
label | Records - Material certificate(s), Photo's
checkpoint | 3.15 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
section | Section 4: Final Inspection and Handover
checkpoint | 4.1 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.2 - Completion Sign Off From Fields Below
label | Records - Signatures