## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Generic - ITP - Enabling Works - Footpath, Kerb and Channel, Pram Crossing | itp | ITP - Enabling Works - Footpath, Kerb and Channel, Pram Crossing | 26b1df68-75ca-4d60-968f-f4eb8ad7bbf5
| section | Site Set Out
| checkpoint | 1 - Site Set out
37348add-c5a3-51c6-bdda-2b198cbd3eb9 | note | VERIFICATION ACTIVITY: Surveyor
741fa328-4969-5a30-aaa8-eafa4a9d807c | note | METHODS OR REFERENCE: Surveyor
1e18f068-af91-5705-b7b2-aa6affab2644 | note | FREQUENCY: Every site
3bc3215d-6800-5f1b-b82d-b20e5e4ebf39 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
d5e8afb3-14c4-584b-8479-0fe8a0a23ffd | note | HOLD POINT: Mandatory HOLD POINT -
cc2a8aff-38c4-52d4-8d4a-a783365a81bd | note | RECORDS: Onsite records/photos
6bc8d6b5-717d-5b93-bba8-ea524d6281d5 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Kerb and Channel
| checkpoint | 2A - Kerb & Channel
f2e3c2d7-8160-525a-a12c-36eddf756fb8 | note | VERIFICATION ACTIVITY: QA FORM
b311c14b-dcae-5e86-b94d-92419b5e196c | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
00b083d9-532c-56b1-8773-87375f88a9de | note | FREQUENCY: Every 10m for Scalar
49718849-30c3-56db-91f0-5a7876240eea | note | ACCEPTANCE CRITERIA: Subgrade CBR > 5
77a48ebf-13c1-5f8c-adf1-2f34627b89d8 | note | HOLD POINT: In process Inspection
5b3306c6-15de-5f2a-a31f-b4d01894c939 | note | RECORDS: Scalar Sheet
dbfa145b-7928-50ab-bcc0-bff00fa87f34 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2B - Kerb & Channel
9a48ee6d-91b0-5da3-909c-a4e02593c26b | note | VERIFICATION ACTIVITY: QA FORM
1ac037d2-de20-5774-b0be-fa4d84944dcc | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
15461fe5-bc4d-5ac9-a8d9-107b138f0dd5 | note | FREQUENCY: Every 10m for Clegg
356ab40b-3494-50c0-868a-d1310d8f03bf | note | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid on compacted GAP40.
978bd73a-88be-537d-9cc3-2f0c5afd4cff | note | ○ Thickness - 100mm on Footpath / 300mm on roads
095a8c5f-9573-532d-8744-57fb03170f93 | note | ○ CVI > 12
294f028d-3c5b-5b9d-aad7-379919f4c864 | note | HOLD POINT: In process Inspection
91c0420c-870e-5801-82dc-485eae46c192 | note | RECORDS: Clegg Sheet, Photos
427d9e3d-ef43-5618-aff8-43dac9ce9440 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2C - Kerb Setout
4624b3bf-a496-53d8-b381-6993575445e6 | note | VERIFICATION ACTIVITY: QA FORM
9d1031d6-7ce9-5cf7-b9be-d3a5abea9fd0 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
1ba52203-6b83-5386-800f-0c5e9417d9e6 | note | FREQUENCY: Every site
f9743e3f-b67e-59b8-aeee-b82ee9345079 | note | ACCEPTANCE CRITERIA: Site Setout as per construction drawings and heights and falls verified
04cebf37-522e-5f7a-a8e3-a923221cf68b | note | HOLD POINT: Mandatory HOLD POINT -
ee063951-e692-5784-a995-c55e4e3c650d | note | RECORDS: K&C Pre-pour Checklist
b4f249d5-26ba-575d-81ac-a70131af5126 | note | ONSITE RESPONSIBILITY: Site Engineer / MSQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2D - Channel Material
6e765a50-3dad-59b4-ad83-b597707f3b61 | note | VERIFICATION ACTIVITY: QA FORM
939fa9d4-f90c-52bc-91a5-3f1e06374e5f | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
b4d09b5a-16b1-5ef3-baed-a93b26e5eb06 | note | FREQUENCY: Every site
05eb1f79-5d88-5e24-8d1f-6090a182fc26 | note | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days
0db649a3-2fb0-5622-8ad4-33fe40c79e79 | note | HOLD POINT: In process Inspection
ce6c6184-6a6c-5fe2-afb0-d272436b0468 | note | RECORDS: Concrete Docket
2e6c777c-2d3c-5912-b083-adc1a3146857 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2E - Channel Level
53075479-3df6-5710-a88f-d642b0ea86ac | note | VERIFICATION ACTIVITY: QA FORM
90d7abc6-57df-58b3-a715-2b934eef7f4b | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
68be5fec-1cd0-5072-9cae-3bac6f57f1c1 | note | FREQUENCY: Every site
f3b94cf5-27de-5f55-94b0-376cc0e9ba74 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
67d23cdb-9c14-547b-9f5d-2936f661d41d | note | HOLD POINT: In process Inspection
cbce98d4-0d21-5d05-9f45-c99edbe7c90b | note | RECORDS: Photos
a7fcb097-cccc-5e49-9a71-b627a86ea386 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Footpath
| checkpoint | 3A - Concrete Footpaths
1f0c6cca-e8df-50ca-82ce-d5ae20bb18da | note | VERIFICATION ACTIVITY: QA FORM
aa03a965-a063-5f34-98ac-e8e2baa956ab | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
431fc44c-ed9f-50fc-9487-117650677329 | note | FREQUENCY: 10m intervals
ff615669-f94b-5b6f-9e09-7e9b0bd43c3b | note | ACCEPTANCE CRITERIA: Subgrade CBR > 3
f510cbbd-2256-56e0-b40a-da2654a82f78 | note | HOLD POINT: In process Inspection
200ead51-9b9d-5a8f-b216-716dafd2314d | note | RECORDS: Scalar Sheet
9259d270-1e6a-5713-b0cf-dda4979f7f41 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3B - Concrete Footpaths
8281f1ad-e748-5afc-9949-ce6475a695ed | note | VERIFICATION ACTIVITY: QA FORM
6488d403-02b9-53cc-8d94-59be7b2e7de5 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
cacca5e3-40e7-5282-bd4a-a02ce99dd4c2 | note | FREQUENCY: 10m intervals
3eb73cf1-1914-5e17-8790-0fc1c3a47b7c | note | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness
361f7126-f3b8-5906-9f25-ffdeb630c9a0 | note | ○ Clegg CIV > 12
2c96ee10-73e2-5acc-8f17-8a3b3d1997a9 | note | HOLD POINT: In process Inspection
fe743841-c62e-54bf-b93c-92cb9efd60bc | note | RECORDS: Clegg Sheet, Photos
3cd39fbd-dbcf-5070-90d8-805025993f30 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3C - Footpath Setout
794a7d94-e21b-5d18-abbb-e314fbe01e02 | note | VERIFICATION ACTIVITY: QA FORM
8a9eadad-f3ea-5d4f-802d-b0790c95c319 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
bfcac348-655c-5b4b-80a4-f763ae2d083f | note | FREQUENCY: 10m intervals
a7ceef4f-8d49-5069-802b-6ce1d41fb148 | note | ACCEPTANCE CRITERIA: Site set out as per construction drawings and heights and falls verified
04d04f9b-a03b-5e28-babf-330b7a7353de | note | HOLD POINT: Mandatory HOLD POINT -
6ece6da1-8d4a-5e9f-8ca2-ea0640f91fab | note | RECORDS: Pre-pour Concrete Sheet, Photos
1eaaf716-31f5-5a25-989a-9b7000cb316c | note | ONSITE RESPONSIBILITY: Site Engineer / MSQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3D - Footpath finishing
9bf1b369-000f-5de3-aecb-c4dcd4fd53d8 | note | VERIFICATION ACTIVITY: QA FORM
94c588da-837d-556f-8e6c-2882d98f0a63 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
a3b008c6-3408-59c5-aa29-4fcc60669334 | note | FREQUENCY: Every site
4a85379f-2c8f-5195-b2ac-50094bf90ed6 | note | ACCEPTANCE CRITERIA: Concrete Strength 20 MPa @ 28 days.
43613606-bfad-518e-8e6a-7fbf1740355a | note | ○ 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing)
77b8414b-5cc7-559c-a79c-23f56ca5db9f | note | ○ Standard Footpath - 100mm thick
f8cdd8e2-166b-5822-940e-8104cc3588d7 | note | ○ Heavy Duty - 150mm thick
dd4ce1b2-7dea-5241-87c1-52121b25956c | note | HOLD POINT: In process Inspection
5349694a-9639-5115-8897-733f8eb5aea3 | note | RECORDS: Concrete Docket, Photos
1385ca46-ab54-5a11-8945-636ac120a82b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Grass Berms
4b467a0b-0a35-5b05-a16d-376bbbe0b4cb | note | VERIFICATION ACTIVITY: Visual
e75a70c2-8adc-5e96-a22d-c3f0462812cc | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
c166e7b8-d418-556f-9881-e042d914042c | note | FREQUENCY: 10m Intervals
3a380300-f83f-5d24-951e-3fb9ca3ef34f | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
ad1f50c9-90d0-5af1-bbda-e66289f07811 | note | HOLD POINT: In process Inspection
af1ebbae-0f0c-5bf0-bb66-8f633fa00d7b | note | RECORDS: Photos
deb3f735-57fc-5484-ab62-061184420471 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Service Covers and Street Furniture
88287524-c2a7-51b6-8d40-1e08df0a2efc | note | VERIFICATION ACTIVITY: Visual
861d10a6-269c-55d3-b045-502d48452f49 | note | METHODS OR REFERENCE: AT Contract Specification 14000
877d3f87-d07d-5dd5-9819-06252bd47480 | note | FREQUENCY: Every site
b95016c2-ca36-567a-9a53-ea5f72775462 | note | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
942594f8-828e-5379-b048-19b02e73f05e | note | HOLD POINT: In process Inspection
3f8e2ee7-7bf8-579a-be1c-d0612513e436 | note | RECORDS: Nil
ddfabd5e-90f2-5d4d-9439-db805286f9d0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6A - Tactiles /Pram crossing
25cbbb58-c435-5f82-8384-d4907840dba7 | note | VERIFICATION ACTIVITY: Visual
3ec6ef76-a5ea-5684-868b-b9d3f08425a6 | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
9ccb8f92-122a-5381-a161-d2c49184979d | note | ○ TDM Technical Standards - FP0010
a7289436-a690-5e07-8912-b2bdb04478b2 | note | FREQUENCY: Every site
b293a988-6c92-5952-80af-9e607ef99ecf | note | ACCEPTANCE CRITERIA: Tactiles set out must be agreed with MSQA
12e42f24-a925-53f6-b342-21b730f29138 | note | ○ Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
d58073cf-e4b5-5637-a650-22f70bc972dc | note | ○ Warning TGSI tiles should have 100mm concrete slab underneath
32848c5c-75fc-5aa9-80ec-72370637bf3f | note | HOLD POINT: Mandatory HOLD POINT -
6b11d507-66e4-5f53-a91d-9740120173b2 | note | RECORDS: Photos
3f46f9bf-2ea9-5603-9343-6ca88fea8008 | note | ONSITE RESPONSIBILITY: Site Engineer / MSQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6B - Tactile Material
82e7f228-009b-5a79-9388-f1c1deeeafa5 | note | VERIFICATION ACTIVITY: Visual
83b2fdf9-82f3-5645-b909-68eed9879ae4 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
66f8bc46-93d8-5cfe-a169-0698385792fc | note | FREQUENCY: Every site
7af24fb0-aee6-546f-8aad-537360e180b7 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type - 300x300mmx60mm
ffd4fd1e-04da-512c-9768-04a2e8833cb6 | note | HOLD POINT: In process Inspection
c0dfbed5-e14b-5ca0-8532-ac5266c90eff | note | RECORDS: Photos
5c7e22d6-d671-5051-af3f-b52b1658d4f4 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6C - Tactile
06a93128-f936-5aaf-af49-868046347e49 | note | VERIFICATION ACTIVITY: Visual
6275b83f-e061-50dd-8c96-43558d63b7f4 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
69888d02-4ea5-56d4-8f19-8f5364985d1c | note | FREQUENCY: Every site
8208dc74-eb23-583f-bb80-648692bbcd06 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
492d1d45-38d0-58ae-bb47-795f1b55b4e1 | note | HOLD POINT: In process Inspection
c8af76b7-11d4-526e-b94e-3686514c504c | note | RECORDS: Photos
d1b58b30-0f49-5e51-866e-f09a3de1cda7 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | As-builts
| checkpoint | 7 - As built information
1aa74bc8-36b8-5205-aed5-54f5a0b353fb | note | VERIFICATION ACTIVITY: Drawings
7e9a9d1d-7ce9-5338-b72d-37af444666d4 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
ace26f81-f860-524e-af23-bcfc9068d2ee | note | FREQUENCY: Every Site
d689586a-bb74-5dc2-91c9-7b0a5700a9be | note | ACCEPTANCE CRITERIA: As-Built drawings
93ed5fa2-7d36-586e-965d-e24645044cf6 | note | HOLD POINT: In Process Inspection
046b2374-6c2f-5537-90c6-f8d8825b5f35 | note | RECORDS: As-built records
ec84a75e-c3da-5d07-bc1a-dc220b8405b9 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 8 - RAMM DATA
df32f3a6-1f2f-5fa2-98f7-2bf43db0ad0d | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
0b257ce2-23cd-53e9-ad82-a348028d4e93 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
dab57434-41fa-5e3f-8a08-e56937718bf9 | note | FREQUENCY: Every Site
8c7a4884-e585-5d88-b94c-d537c6dad5e0 | note | ACCEPTANCE CRITERIA: RAMM SHEET
f094e2a8-94db-5a13-ac87-41b803da9a6f | note | HOLD POINT: In Process Inspection
d0a67be1-081f-53ad-8aa9-97706b0e4c9c | note | RECORDS: As-built records
948d75ca-ebf3-53bd-a1ab-bfa90bb07d6e | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
0560b2a0-be32-5915-9716-db9a1702be3b | note | Prepared by: Daniel Tat
099508fc-8a77-5ec0-80b9-1a8c133094c3 | note | Approving Delegate: Daeyoung Jeong
| checklist | Generic - ITP - Enabling Works - Vehicle Crossing | itp | ITP - Enabling Works - Vehicle Crossing | e5312353-c81f-4ea3-b091-049573bc67b2
| section | Site Set Out
| checkpoint | 1 - Site Set out
bed02b40-dd4a-5f7a-8ce6-105a3b9d875d | note | VERIFICATION ACTIVITY: Surveyor
896ac3fd-84e3-5352-9d47-12cdb01aeba3 | note | METHODS OR REFERENCE: Surveyor
03381a6f-b18e-5c3c-9446-dd55026d541d | note | FREQUENCY: Every site
6e516294-c5a2-5564-b187-17f9bf372ce7 | note | ACCEPTANCE CRITERIA: Site set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
66054417-5178-58bb-9606-28df12d42ca8 | note | HOLD POINT: Mandatory HOLD POINT -
4260c472-7d0f-561d-9853-ecddbdfe3e19 | note | RECORDS: Onsite records/photos
17af8160-3767-552e-9a79-07d72f725adb | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Standard VX
| checkpoint | 2A - Residential VX
54ef2463-fcf6-59a3-beb7-d712b297b54a | note | VERIFICATION ACTIVITY: QA FORM
20896e55-e538-5d98-99c9-37c5f1913f54 | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
1fae260a-701c-5d61-86de-75b59cf1a4fd | note | FREQUENCY: Each VX
9dfca79b-51de-5438-b51c-8432d6727ac4 | note | ACCEPTANCE CRITERIA: Subgrade CBR > 3
e091bbe9-66a5-5375-82ae-b337c9f53aed | note | HOLD POINT: In process Inspection
d11e5d75-3f61-527d-95d4-3ba546dfa446 | note | RECORDS: Scalar Sheet
117dce22-a29a-5747-b950-0a66c7376dc7 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2B - Residential VX
8435a116-108c-5bab-8ba0-a847c40fdeba | note | VERIFICATION ACTIVITY: QA FORM
0a86e80f-d917-5dcd-9f27-1ea7a81c641c | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
56bfece6-51e1-5967-96e1-639cb317303c | note | FREQUENCY: 4 Cleggs per VX
a0c162a7-a993-5c12-bbfe-f0b052756eb3 | note | ACCEPTANCE CRITERIA: VX to be laid using on compacted 100mm min GAP40.
1b163744-d040-54b9-8c24-dcfbbef6872a | note | ○ CVI > 12
66b20e56-05bf-57d2-b6e3-820f510376fe | note | HOLD POINT: In process Inspection
4735aab6-7257-5f71-88dc-a2d12227782f | note | RECORDS: Clegg Sheet, Photos
d1702fd8-d84b-5632-a25f-72b39106610f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2C - Residential VX
1aa2a9a7-9c6a-58eb-aceb-bfaa1412e2b9 | note | VERIFICATION ACTIVITY: QA FORM
34f75734-bbd4-58b7-b234-b3d8b0e299e2 | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
c54b9fb7-627a-5c2b-a380-31dbaa53b307 | note | FREQUENCY: Every VX
d4686c70-9e02-506a-9d24-b37e5786c822 | note | ACCEPTANCE CRITERIA: Site set out as per construction drawings and heights and falls verified
bc04dffd-f300-5c35-bb6e-314bd758c079 | note | HOLD POINT: Mandatory HOLD POINT -
a1ead34a-20bc-54c5-89e3-3aa27ad67870 | note | RECORDS: Concrete Pre-pour Checklist
53b05a5b-cd28-524c-87c5-8cebdc95c81f | note | ONSITE RESPONSIBILITY: Site Engineer / MSQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | VX Material
149f6bfc-be0e-50a2-9604-16021a91c517 | note | VERIFICATION ACTIVITY: QA FORM
8c43a39d-6cd9-56c9-adfc-feb9275b030d | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
0756d50a-3af5-5ee1-9770-c03ea751b02e | note | FREQUENCY: Every VX
1b08e0bd-a4d4-519f-a180-2cfd6c6234e5 | note | ACCEPTANCE CRITERIA: 665 Mesh Required if 4 or more dwellings
c8fe4d38-78d2-5ba7-85d3-fcd34f9e5fb4 | note | HOLD POINT: In process Inspection
6a2a493b-6b1a-5c6a-9d5d-f12cf5d49333 | note | RECORDS: Photos
b6b929c1-5ac0-53ff-a3a9-f97bd1260a59 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2D - VX Material
f4f6d837-eb0d-50d3-b733-b9eec1401bf1 | note | VERIFICATION ACTIVITY: QA FORM
ce23f722-1f7b-5fc8-84ec-d09776f0e00a | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
0d498d5d-3af0-5f88-bd6b-d02e1185d34e | note | FREQUENCY: Every VX
f4b3e8c0-87b5-52ae-a2e5-c5bac89e97b2 | note | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days
78849114-06eb-5f71-b9a0-96c963649295 | note | ○ Thickness - 150mm
9add2ed5-3350-50c5-8a73-80741f783bd5 | note | ○ 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing)
852d979f-9b2f-557e-862f-ee94be78dbc4 | note | HOLD POINT: In process Inspection
6629e02b-128c-5d77-9f86-9bd07d1b1d3d | note | RECORDS: Concrete Docket
de9a7b9a-e2d9-5889-b6ae-b454920e611d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2E - Residential VX
a64d511c-c264-523e-9571-f9479f576267 | note | VERIFICATION ACTIVITY: QA FORM
bad96865-803b-59a0-8d6c-5dc5b08c9bad | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
0c88cde6-252b-5415-b760-27d2feadae38 | note | FREQUENCY: Every VX
d3c7e49b-8eef-5ba6-807b-7b0c6a873a59 | note | ACCEPTANCE CRITERIA: Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg
fa1b504c-e1ec-56ef-ab57-c03c8d0d0849 | note | HOLD POINT: In process Inspection
f4fe6a70-2447-5140-ac9e-5d88cc4f48ff | note | RECORDS: Photos
7d85ef4f-d162-5c3a-b902-bdf0e592cc3b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2D - Residential VX
0c24fe6f-3140-5ff4-a715-88c74141d863 | note | VERIFICATION ACTIVITY: QA FORM
18238588-6247-5cf6-b2f7-f010b0e2b976 | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
4ae295a1-06e3-5e3e-993b-73d39800467f | note | FREQUENCY: Every VX
59e8d854-8049-520e-9d3e-0cb27410116d | note | ACCEPTANCE CRITERIA: Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg
4ffdf3c2-60b5-5fc2-9fe5-5d9f3df6f4aa | note | ○ 1m reinstatement on carriageway
5a99b73c-8d68-57e9-980e-358c9b7f242a | note | HOLD POINT: In process Inspection
3e42cb2e-a576-5b27-9f67-c986aeae3763 | note | RECORDS: Photos
f17d9ae0-2c27-5b3e-9242-54df1ae0783d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Grass Berms
8037378e-b276-5612-a48a-53b575fd1f92 | note | VERIFICATION ACTIVITY: Visual
a2d32f7a-a67d-5a01-a10b-aca88cdfc069 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
7b6d3572-7542-5474-995c-0096a0775bc3 | note | FREQUENCY: 10m Intervals
a39546b0-f4d6-52a0-a6ed-4d771ac240e5 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
91eae4f6-47e3-50e2-a687-ea74bf85cf8d | note | HOLD POINT: In process Inspection
b9ca45a3-dc8d-5bf9-bb13-4819eb1bbb4f | note | RECORDS: Photos
ddf83711-1016-5335-a5f9-363e197dc511 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | As-builts
| checkpoint | 4 - As built information
5baada23-e50d-5e35-8f3f-7a456b5c9fd8 | note | VERIFICATION ACTIVITY: Drawings
62740f1e-4f0e-50e3-886e-d2adf001dcf5 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP
b7723ec7-60ab-5aca-81bf-c9d1e017f931 | note | FREQUENCY: Every Site
05db6444-64b7-57c9-b255-b1bbb59783ea | note | ACCEPTANCE CRITERIA: As-Built drawings
a72d370d-db53-52ea-86ca-d73fae3b919e | note | HOLD POINT: In Process Inspection
7d098185-1dfc-5d14-902c-fa703a35feef | note | RECORDS: As-built records
315868a8-3b18-5f01-b34c-61d6d2cb5718 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 5 - RAMM DATA
6adfb29a-bf91-5bd9-b66b-ef51b67dda4d | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
b6df0cf4-caae-555f-9d8c-a6bb4d69b8f5 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP
3f7f1317-1da0-5409-b998-215fc4f99e3b | note | FREQUENCY: Every Site
9f66039c-1cb2-5859-99fa-531a872958ba | note | ACCEPTANCE CRITERIA: RAMM SHEET
6939521f-3742-5064-b6c8-4708185dcf1f | note | HOLD POINT: In Process Inspection
8cb1904a-beac-5d82-89ad-61cd802ac45a | note | RECORDS: As-built records
bc85957b-04a9-5896-b69a-a3564ed02647 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
a95c1163-6fb9-5ba9-be91-8cf8253d58a8 | note | Prepared by: Daniel Tat
aa26d8f3-144b-587b-910f-8538b6f17490 | note | Approving Delegate: Daeyoung Jeong
| checklist | Generic - ITP - Stormwater Drainage | itp | ITP - Stormwater Drainage | fca8b23f-0592-4444-b4ac-3fae6b65521e
| section | Stormwater Drainage
| checkpoint | 1 - Permits & Services (1)
d9657bf7-0559-596f-b173-8156a76b9581 | note | ACTION (Hold, Monitor, Witness): H
aad2db34-0f7c-5a32-b4bd-d3e8a65415ea | note | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
504e12ae-a716-5516-9489-7bf31f5af5a4 | note | FREQUENCY: Prior to any construction commencing
3db0b98d-834b-5deb-ae18-2d5f95d2905a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
210d0a6f-754d-5eca-a5ec-7ffe1fcfd38a | note | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work.
036251e2-c2f1-5306-a6fb-692ae559a9b7 | note | ○ AT Access Authority approved and signed by RCA Authority.
b79ce247-28e5-52f4-b627-a12474086f3d | note | RECORDS: Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (2)
aa98ec73-8591-5f93-911b-982f3edfef56 | note | ACTION (Hold, Monitor, Witness): H
176ac649-7c32-58a7-a15c-b2767ad1269b | note | DETAIL: Locate and mark out all existing services
3937805c-45da-5e7a-93c3-4571e2e85e98 | note | FREQUENCY: Prior to any construction commencing
2e003d4e-7755-518e-88dc-105d61c21e00 | note | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols and GPR Report
60826fc1-ed88-52d7-9ccf-8ebb8d87c107 | note | RECORDS: B4u dig plans & GPR report attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
fdf6beda-f82c-5908-8b3c-00664dda814d | note | ACTION (Hold, Monitor, Witness): H
7e719661-877d-5c8c-9f87-44fb0d301673 | note | DETAIL: Sub-Contract and Supplier Agreements
01bae753-283b-5f45-a6cf-084f5b6b5ab7 | note | FREQUENCY: Prior to commencement.
ff1fb197-3689-5ee9-a780-ddca81c2ce3c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
8497c4bc-1c56-5caf-a80d-5c0dcf4e5f3a | note | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
affc836f-9a5d-5fc0-a47c-530742dc76f6 | note | RECORDS: Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
108a964d-20ab-5627-807d-f37b4c1064f0 | note | ACTION (Hold, Monitor, Witness): H
33ca76a0-3455-505b-8816-ec1465c5fea9 | note | DETAIL: Design is approved and Drawings are of the latest revision.
4c624232-7ddc-5396-9005-307f83335c0a | note | FREQUENCY: Prior to commencement.
fd48cf73-fea7-519b-94e4-a244d3723db5 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
06a2667d-8ae1-5589-ab49-a3a6821c57b2 | note | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
634cabee-a56e-59bf-907f-63a5d83c0438 | note | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
369fd83d-4a21-5236-8119-c1e59211a73e | note | ○ HOLD POINT of not issued to IFC.
1f9167ca-b36d-5fe8-8a91-50133fe1b00d | note | RECORDS: Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Setout
46b7873d-d589-57ff-9a96-149512b986ae | note | ACTION (Hold, Monitor, Witness): H
a3b3e953-9add-5cb1-bce7-c17de5ec8b4b | note | DETAIL: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
aeedebdf-5339-5dad-898d-21a658447050 | note | FREQUENCY: Prior to commencement.
1bf5f663-5dd4-5573-9bc7-5f27e1f1a9f6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
2cd2361b-44fc-5cbc-9097-bfce538ceb1b | note | CONFORMANCE CRITERIA: As per IFC Drawings and design AutoCAD file.
71811587-13d7-537b-87e1-7c2b419d011c | note | RECORDS: Survey Receipt.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
c2fda340-a0d4-5c4d-91eb-6f79dd6aee31 | note | ACTION (Hold, Monitor, Witness): H
37065efb-d081-5abe-af8e-5198f8f21a6a | note | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards
2796061a-b9bb-5549-9e29-460b7e802d0b | note | FREQUENCY: Prior to commencement.
da21c052-2ce8-5905-8d29-f82e1417e1db | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
c2c9c3a3-afb2-5b47-9b87-d87a809781e1 | note | CONFORMANCE CRITERIA: Pipe shall be check for freshly formed pipes and return if required
81e51974-b496-5ddc-9443-70932efb2b5a | note | 1) Class 4 RCRRJ pipes AS/NZS 4058
f4f33ee5-cfee-5067-a1c2-4f19a3b28872 | note | 2) All Concrete RCRRJ pipes to be fitted with Rubber rings
dd56c407-129d-58db-a507-1b49ab104291 | note | 3) Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
6aea91dd-b819-5f4c-be6e-782e15b6dbc6 | note | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards
3532b749-6bee-59cb-8abf-8344b7793017 | note | RECORDS: Manufacturers Data Sheets, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
83bdc7dd-f2ae-5037-882c-d66d5fa95726 | note | ACTION (Hold, Monitor, Witness): H
cb38dca6-881b-5e7d-8638-f65229ef4443 | note | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
6741b398-387b-549d-8bbe-f50fb119cf65 | note | FREQUENCY: Prior to commencement.
1db7f5cc-a496-5665-9f3e-ea6b4f35ae56 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
e720e941-18de-576b-bd14-63ead5e8f2b8 | note | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services.
f077fe5d-d9d9-5993-bcdc-ffc40c606ef3 | note | RECORDS: As-built Drawings. Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (1)
e84e010e-1b03-5e9e-9879-1cf20e2ed625 | note | ACTION (Hold, Monitor, Witness): H
d31e6df1-a791-5cec-95ca-9cd69eb0b02e | note | DETAIL: Excavation methodology
d2bab0f0-bf62-5f43-9842-13f26fa11cdf | note | FREQUENCY: Daily
4658c5af-9024-50a5-adf8-cbd663dd683c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
4a3c62ef-7fdf-519e-b815-ab89c4d57b8d | note | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016)
5e4e870d-c1a1-57a8-b465-dd5e12ef957d | note | RECORDS: Prestart RCP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (2)
67ed6917-09e9-5907-acac-83751b2cbb33 | note | ACTION (Hold, Monitor, Witness): M
1d29e5c4-0536-5265-80c8-e55fff357f02 | note | DETAIL: Trench Profile - Width
a648b4cf-76a0-5e0a-a731-01127815456c | note | FREQUENCY: Daily / as trenching takes place. Different depth methodology
d5b1df48-dfee-5d1f-8e2f-454e33681515 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methodology
4998c72f-4d4d-568e-b74b-c3e457a06fd1 | note | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
d0b5597a-8850-53c1-ae22-4a00bdf1030c | note | RECORDS: Construction Photos
| checkpoint | 7 - Trenching & Excavation (3)
ade2ed53-39f2-5988-bfa6-500d5daf56e9 | note | ACTION (Hold, Monitor, Witness): W
8ce57310-e086-519b-a5d6-8de7594d6ee9 | note | DETAIL: Trench Profile - Depth
7ba40026-8c2f-50a1-99e8-d986b1b685bf | note | FREQUENCY: Daily / as trenching takes place.
a40ea081-8a3a-5797-9b9f-fafe236f6b83 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
3f703f36-b8a7-510a-b9cd-d96d952a778b | note | CONFORMANCE CRITERIA: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
63878052-2478-52bd-83b0-04afff02c627 | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 7 - Trenching & Excavation (4)
3bca4336-2ad3-52a9-b3e1-19e24ee188e1 | note | ACTION (Hold, Monitor, Witness): M
a2c4a10b-d6cd-50e7-b081-25ca2902d3b9 | note | DETAIL: Trench Base
78b008d4-275f-5b3b-a9bd-e7433a4adeb5 | note | FREQUENCY: Every 10m
cbcc35f5-8fff-5d67-9e5b-0fdb44fe0f21 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Scalar testing
3490e826-74e9-5be7-9436-eb43408735d6 | note | CONFORMANCE CRITERIA: Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2.
730e7153-0b26-5153-9a17-a493b725b7bf | note | RECORDS: Test reports / Construction Photos
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
bde5bf4f-1377-59a5-b966-4c4626541b88 | note | ACTION (Hold, Monitor, Witness): W
770ad3f1-9ebf-545e-8b95-394dadcf1faa | note | DETAIL: Placing and compaction of Bedding Material.
f1f96cbd-d56a-5655-8c04-b3ea1fb04356 | note | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
5c6220c9-35c6-5dcd-8fe4-915ed179dfb8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
cb146afe-6f5e-5f26-8d92-df340a035400 | note | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725
8f9ef139-bf94-5cfc-b372-85d352c8541e | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 9 - Pipe Position Tolerance
2ca13bae-57b5-50c8-b409-89e9c6f6c52e | note | ACTION (Hold, Monitor, Witness): M
dcce34df-0598-548c-82d3-161be388e5f1 | note | DETAIL:
0a33ffc1-5c9e-5f6f-878e-4a53d6a8c78c | note | FREQUENCY: At any point of pipe
c8e13a75-782d-5de8-974f-6712f32d80c1 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review):
14380e5c-27f0-5ab9-8d56-fb5803079b44 | note | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design.
b1a983b6-de22-569f-8712-70b946ac025b | note | RECORDS: FH Drainage Line Record, Survey Data.
| checkpoint | 10 - Trench Backfill - Placing & Compacting
7d35f43e-caea-5e65-af60-4d13881fd400 | note | ACTION (Hold, Monitor, Witness): M
f650cdd9-e340-5af9-974a-7a4f94f1aa49 | note | DETAIL: Placing and compacting of Trench Backfill Material
fb75b25b-848f-578c-862d-a434744ac19f | note | FREQUENCY: Throughout Trench Backfilling operation.
f684c402-9df9-5006-bcde-a4814cd4dd56 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
9e29e5d2-e360-52f7-87f6-8052ec679e99 | note | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick.
3a46ea98-7bf9-566e-a3b4-854b0850eb48 | note | ○ Compacted backfill material to be free of Lumps > 150mm
31a3f656-5451-57d4-bdd2-b5d616af590c | note | ○ ATAP40 for subbase/basecourse.
1c245534-bfb1-539e-a8c0-27ea9898eea4 | note | RECORDS: Construction Photos
| section | Subsoil Construction
| checkpoint | 13 - Subsoil Material Compliance (1)
67092dd5-ce8f-5e21-a8a5-dafeb58e40b4 | note | ACTION (Hold, Monitor, Witness): H
9f11e025-1fc5-5c2a-b870-e80a9da2dd21 | note | DETAIL: Ensure Subsoil Drainage pipe complies with TDM RD010
05c732cc-5d51-5206-a5aa-181c2f011244 | note | FREQUENCY: Upon delivery to site
dff3c663-b27e-57d1-aa9b-0f881b1c7bb6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials delivered
97024ec8-7826-5382-a14e-fe24e5b6dd2e | note | CONFORMANCE CRITERIA: 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock
e7c1385a-0ac5-542f-ad7a-827e0172ad49 | note | RECORDS: Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Subsoil Material Compliance (2)
3c62a128-7553-5499-82fc-8b30f3c92dc3 | note | ACTION (Hold, Monitor, Witness): H
a344ae64-421f-5ec2-a009-0596283385b5 | note | DETAIL: Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate
757bf801-9730-5f72-ad56-e306e0e3e1ae | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
3f3734cc-4b24-57e1-ac6e-be97d49e742e | note | CONFORMANCE CRITERIA: Ensure clean drainage aggregate - F2 Sand
89716549-cffb-5e80-9ea2-12f0f2a03e75 | note | RECORDS: Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Trenching (1)
a6be9cff-a11a-5407-a51c-ca178d5a5084 | note | ACTION (Hold, Monitor, Witness): H
a610ffe4-52e0-5ae1-9425-7f69f65206b3 | note | DETAIL: Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade
1b4522d0-db49-5956-8d5e-ef604e6d1148 | note | FREQUENCY: 10m intervals
170b0429-b7e0-5a6a-97a6-edc3a064a3a2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
0a61720a-7946-566a-8569-79520f35f19b | note | CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet.
dbeee922-14c4-52cc-94bf-c88e18a9b4ea | note | RECORDS: Photo / subsoil log
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Trenching (2)
6b9efa27-0a62-5baf-9e98-84713707f8bd | note | ACTION (Hold, Monitor, Witness): H
b90f343a-a97d-5d16-b861-aab7843fe48e | note | DETAIL: Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
1139518d-346c-5276-b463-0d0c8727b26e | note | FREQUENCY: 10m intervals
1cd5c552-8af5-5ccf-9a57-9823a9850cc3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
a8c558d1-2090-5088-bc91-4b4c5d7a5573 | note | CONFORMANCE CRITERIA: Ensure trench line and levels match the design drawings
8486f481-c2fe-573f-bf77-7480a4c0ef81 | note | RECORDS: Photo / subsoil log
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Bedding, pipe installation and Backfill (1)
e5e3705e-3a93-56a7-b7a3-5ff0072b992a | note | ACTION (Hold, Monitor, Witness): W
86224cd0-daf9-51f9-a131-e8ee4b091049 | note | DETAIL: Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench.
0d085919-6cac-5379-96c2-7fe5f69b2cd4 | note | FREQUENCY: 10m intervals
afe7047e-27c9-5aa6-943e-20a6fa95d037 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
b678af7a-3daf-5977-af4b-9e6bda1ffff4 | note | CONFORMANCE CRITERIA: Record levels of top of bedding on dip sheet
f5d5e11f-82b1-539e-b83c-3c713fb4cd82 | note | RECORDS: Photo / subsoil log
| checkpoint | 15 - Bedding, pipe installation and Backfil (2)
fcc075c7-410d-577e-b809-debc5b9fc3c3 | note | ACTION (Hold, Monitor, Witness): W
9f08dd79-d59c-59f1-9a12-b708c88f8f47 | note | DETAIL: Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
8c24c07d-9cdf-5121-bb1f-49d1f4ace835 | note | FREQUENCY: 10m intervals
5ff5c979-ed6d-5335-ad8e-60b1e61567ef | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
ac778684-425d-50fd-a312-4e5c8c4fadbb | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
ad5205eb-c5a9-583b-9e19-b728e7e19061 | note | RECORDS: Photos
| checkpoint | 15 - Bedding, pipe installation and Backfill (3)
1926e600-94b7-593a-bda3-e8f970294513 | note | ACTION (Hold, Monitor, Witness): W
fe29e17a-d096-592f-8fae-4e5e28fc3175 | note | DETAIL: Backfill by tipping AP20 as bedding & ATAP40 as pavement structure into the trench
db994f66-38a5-587f-8e92-bb549d2d7d5d | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
4e51c836-52ad-5a1d-86b2-b8d5596ab046 | note | CONFORMANCE CRITERIA: Ensure good coverage
ce8fd680-466f-59c8-843c-ebcf8d2a6de8 | note | RECORDS: Photos
| checkpoint | 16 - Catchpit Connection (1)
0d176cb1-3c66-5582-94c3-b9b1e7959bc7 | note | ACTION (Hold, Monitor, Witness): W
a728849a-defb-51ef-8b91-ff95ad7bf335 | note | DETAIL: Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
6922785c-374e-5ddb-860d-b3218b6eaf3c | note | FREQUENCY: As required
bfa49746-e605-5396-beb5-8c25cc7fa26f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
27ea2d70-6190-57b3-b5a1-30d7c5171dbd | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
6376c198-c9b9-518a-8dd9-26db5636c3e2 | note | RECORDS: Photo
| checkpoint | 16 - Catchpit Connection (2)
0eadeffa-755d-53ca-8d3f-3e823f7408f4 | note | ACTION (Hold, Monitor, Witness): W
d0d191e6-61c1-549b-b16e-0e72d77351e6 | note | DETAIL: Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
4532f19f-34e6-556a-a30c-4f38ed4be978 | note | FREQUENCY: As required
59cca33c-a20c-545f-8605-ed5f5c0259a6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
e69dd3e8-17b2-5b71-a679-65a45bfa2e19 | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
1c83133a-8081-588c-9e41-75ef4573554e | note | RECORDS: Photos
| checkpoint | 17 - As-Built Drawings
99158f6c-2b7f-5cf5-a76f-fa0869deb968 | note | ACTION (Hold, Monitor, Witness): W
0fb19bbf-d006-5007-950c-98a47df1ca32 | note | DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction'
133ef5ea-a39b-54d4-883b-e8c22feb0124 | note | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
235309aa-844e-5a8b-8566-0396b0a50e32 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
bb5aaa10-7650-503c-a533-0a8d9ede4fc2 | note | CONFORMANCE CRITERIA: As Built and GIS Data
f141db4a-08fd-5206-8ef3-240b17473e2c | note | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
| section | ITP APPROVAL
| checkpoint | ITP Approval
8f491406-94ba-5b33-919a-e89b4c19cee6 | textbox | QA checked By Quality Manager:
76771dc8-f8ae-53dd-974b-278821f72d04 | textbox | Accepted By Engineers Rep:
| checklist | Generic - ITP - Traffic Islands | itp | ITP - Traffic Islands | 8d432edf-9a02-4dc2-b5a6-47ca24049b24
| section | Materials
| checkpoint | 1 - Kerb
b6b1331c-bee0-59dc-ba66-57b87ca51037 | note | VERIFICATION ACTIVITY: QA FORM
30c02fc5-83f1-5c05-ad84-bb422541657a | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
1a435718-8f7d-5a6f-af82-0cf5534e8ba0 | note | FREQUENCY: Every site
fd2fa1c0-5614-598e-91e9-46c1a9ce5d63 | note | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid
64bd602a-ab93-54e1-924b-259e5af3c9fc | note | HOLD POINT: In process Inspection
88d67bac-9b94-52f2-9fe5-1c713643d6ad | note | RECORDS: FH Concrete QA sheet, Photos
f6ac72ad-6e8c-52ef-85bb-9269b3175349 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
675ca2d7-3ec6-55da-81b2-13c6c52512e5 | note | VERIFICATION ACTIVITY: Survey
b587fd66-268e-5178-ab4b-4288e824130a | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
af3848bc-1c15-53c4-8277-f527e824e417 | note | FREQUENCY: Prior to commencement.
58f29129-6d1d-548f-b69c-0f32f35819ea | note | ACCEPTANCE CRITERIA: Survey
ea52c2c3-8c88-5175-a197-5b74c4dbb077 | note | HOLD POINT: In process Inspection
e2e66c26-7866-562f-b12e-51272e0c8dc4 | note | RECORDS: Survey Receipt.
7f76d810-4bfd-5ab5-a341-00f3cde33c77 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3A - In-Situ Concrete Island
81ea597e-97eb-5a46-a7b1-38b4f131e284 | note | VERIFICATION ACTIVITY: QA FORM
7201b883-eb67-5dfa-a49d-ae33df941fc8 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001
7629092c-acce-5a9f-a050-98abed965b7f | note | FREQUENCY: Each Site
f547a132-6bc7-522a-95ad-498613601383 | note | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm
c6c46c66-960b-5062-96c8-715354a085e3 | note | ○ CVI > 12
9a8bba41-8481-5b9d-8167-770529bb3c80 | note | HOLD POINT: In process Inspection
3a05ba5f-efe2-5ad9-afdb-c010d6d20987 | note | RECORDS: Photos
db0dd4ae-c15a-5639-8270-c2c1634f51e0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3B - Stick On Concrete Island
26f56ea0-e26e-5d42-8043-07931cbb0736 | note | VERIFICATION ACTIVITY: QA FORM
a07458e8-f959-58bb-ac09-cf9dfed34aac | note | METHODS OR REFERENCE: TDM Technical Standards - IS0002
89f506f0-4202-5e5d-b7e5-322739c7e969 | note | FREQUENCY: Each Site
01fca360-4f4f-5c3c-969a-15b5828a0d97 | note | ACCEPTANCE CRITERIA: Bonding Agent to be applied on existing surface
63ddb4b8-ae1b-5207-9c5e-99047a64eeb6 | note | ○ Mountable Kerbs laid flat to be sticked on to the existing road using Epoxy Mortar Mix.
63ec1ed4-a79b-51f1-847b-fe857882569e | note | ○ Gaps between kerbs shall be no larger that 10mm
9b345f5e-6dc9-5731-80f0-71922ac93a0a | note | HOLD POINT: In process Inspection
df5ec3be-06af-5166-aa6c-46ec16bb1e49 | note | RECORDS: Photos
264d0d2d-fda4-5d05-bc74-9ee74b5d4011 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infill
23a2fe1b-ca31-5c2a-8ed1-9dc72b55912b | note | VERIFICATION ACTIVITY: QA FORM
c3e01d96-d3d2-5818-95ce-b5253fd5efa3 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
abea870f-3419-5506-b035-c6665776aa1a | note | FREQUENCY: Each Site
cd6bd56e-b0cc-55fd-bea7-d1d065c5f1b5 | note | ACCEPTANCE CRITERIA: 150/180mm depth of 20MPa Concrete
ad3e73c8-1079-57af-b199-1e500b90f5c9 | note | ○ Surface finish to confirm with Engineer's Rep
d591df67-0f62-57d6-a229-30eb5b19dd89 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
19adb25f-1910-58f0-a721-0dfc2da68027 | note | HOLD POINT: In process Inspection
4439c73b-7ddc-515d-b2c9-3c0bf80e6fb1 | note | RECORDS: FH Concrete QA sheet. Concrete Delivery Dockets.
895da5e2-26ac-504a-b6e9-26c4072e465a | note | ONSITE RESPONSIBILITY: Site Engineer
| section | As-builts
| checkpoint | 7 - As built information
d76e706a-dee5-5dcd-a542-b1177fb5e830 | note | VERIFICATION ACTIVITY: Drawings
9b6cc1ea-9663-55fb-b68d-cf6b5532f0e9 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
b90a7cdf-3c9e-5f2e-a634-8b75636512f0 | note | FREQUENCY: Every Site
8d3623ae-d19c-5c73-a14c-f9cc0857f6c2 | note | ACCEPTANCE CRITERIA: As built drawings
269c5e51-270a-5a9f-9968-0a3f4ec5a88e | note | HOLD POINT: In Process Inspection
7492fb5f-b865-53ed-b48d-30a128c48063 | note | RECORDS: As-built records
90ec0da8-12fa-5722-a79c-73d93b62c688 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 7 - RAMM DATA
459f196e-3906-5e40-99f8-2f2c5c19ce94 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
dd577764-5f37-5f5d-914d-90e6dedd75bc | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
53204457-2828-500d-a8cc-c876428fb339 | note | FREQUENCY: Every Site
32f9d37c-004a-5e85-a0e0-94dfdeced8fb | note | ACCEPTANCE CRITERIA: RAMM SHEET
f35d9566-8cb2-503b-9934-ff9960b2c350 | note | HOLD POINT: In Process Inspection
258a79a9-782f-5858-a676-0377ccc05caf | note | RECORDS: As-built records
17e144b9-696e-59a3-a473-de66902585b2 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
36b7d6d5-b552-5438-815d-509e9fbdcda8 | textbox | Prepared by:
6704840e-23ed-5273-bcb6-899b08d23aca | textbox | Approving Delegate:
| checklist | Generic - ITP - Traffic Signal Ducting and Pole Erection | itp | ITP - Traffic Signal Ducting and Pole Erection | 2ecd5b50-ac21-4d8e-9b6e-c8170cc554d6
| section | Ducting
| checkpoint | 1 - Permits
3b5734d7-06da-5eee-9970-881157c5d371 | note | ACTION (Hold, Monitor, Witness): H
f2ee16c2-9cf6-5b13-940b-48d17495fb27 | note | DETAIL: Obtain Permits
4ba0e0f4-b961-577f-acb9-5733f6dbf132 | note | FREQUENCY: As required
80f46b79-0c99-5d69-938d-b4315c665af6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
813d294d-8542-580d-836e-16c278cd6ac8 | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and first gas permit obtained
5eafa57e-e1dc-5478-91f7-948b8e04e6a1 | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
c509cb16-afd5-5524-9a9c-6f2b0f8930af | note | ACTION (Hold, Monitor, Witness): H
ae9c463c-532e-5a6d-86ec-f87a42da12ab | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
18c590bc-a0e0-599f-a21b-ce62474ef87b | note | FREQUENCY: Prior to commencement
0e994853-a223-57ef-aae9-15179048af91 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
9f201086-355e-565a-a252-0b609587fc25 | note | CONFORMANCE CRITERIA:
ff88dcdd-df57-5ff0-bd35-3b94145a8efc | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey Setout (1)
bf7b3f76-bf53-5acf-adbf-9e08079c234b | note | ACTION (Hold, Monitor, Witness): H
16a29511-1d9b-5692-a6ad-33bcb4ad4ce1 | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
08b0ce5c-15c7-572b-b90f-dbaab33f4652 | note | FREQUENCY: Prior to commencement
0b789db4-6ab8-5f2a-8b00-5abede2e02e6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
18fe5986-b9f0-57cd-9024-46da31e75bea | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
a6326975-11be-5ea7-aec0-c6b27689137e | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey Setout (2)
14147ea1-90eb-57c6-a36c-4e609b76f071 | note | ACTION (Hold, Monitor, Witness): H
5fbc985a-cb45-549b-8879-1c71b39607e2 | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
71c82c4c-0f0e-5f95-89d0-ca6044e7ffe4 | note | FREQUENCY: Prior to commencement
0c6a45bc-1bbc-5d5a-acf1-4ccf69fa0e9a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
eb165579-fceb-5d1f-8b36-906614b3e39d | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
93220056-63f3-5c59-acb6-85d4c86e424d | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
0ce9df33-dd85-5843-85c9-865c5ab0d499 | note | ACTION (Hold, Monitor, Witness): W
170a294d-69f9-5dce-8c13-e9e3a3d728ed | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
2f167019-7e4f-5846-9fd5-c47c44ae3ae6 | note | FREQUENCY: Prior to Installation
f59eaebf-d7a8-52cd-947c-cd43c80bd7e8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
58a52e74-6900-5f81-a324-1861519a422c | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
f428f649-e4f1-5d6a-9e4e-a80315f3d3fe | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5 - Material Compliance (1)
b3e981e1-b504-5801-b590-4cb6e5af6a86 | note | ACTION (Hold, Monitor, Witness): H
214aff81-cdc6-5983-90ab-1edad995c239 | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
1abe4ac4-77c4-59b5-ab06-7d128c73cd4c | note | FREQUENCY: Upon delivery to site
597e9d72-140d-54cb-a139-f8ae92b770ba | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
d041da6b-5878-5b49-91ba-455d0819de03 | note | CONFORMANCE CRITERIA:
75f41205-b6f7-5244-905e-904ccbe36932 | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Material Compliance (2)
ad9e5cf0-5768-57c9-9916-75b5790531ef | note | ACTION (Hold, Monitor, Witness): H
1bee89ee-6f95-57f2-a434-a4dc6f0cade9 | note | DETAIL: Ensure all concrete used is 20MPa mix
4ac1184d-751d-5677-bc89-6e359def2ebb | note | FREQUENCY: Upon delivery to site
41b0b80f-0aa8-528c-b5c2-6f2575fbbf6f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
de9fba26-9d8b-516e-bde3-ef89af3129d3 | note | CONFORMANCE CRITERIA:
8ebd71fb-2fec-5f56-a59e-d3f768e21f9c | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Trenching
7f76e2b0-23e7-5849-b86a-030ac8cd5c5f | note | ACTION (Hold, Monitor, Witness): H
50735309-0009-536d-82e9-df135e9ac975 | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing)
3771b107-fc58-5f6d-94dd-f46382a08db1 | note | FREQUENCY: 10m Intervals
8a51b0e7-d741-58a1-9948-44cf0e91ae0f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
1376a80d-d528-56d0-8f28-bb69466fb9b8 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
b798af3f-aa7d-5312-b23d-e6b19c9dca02 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
af6ba2cf-6666-581a-97b2-50b60644b7e5 | note | ACTION (Hold, Monitor, Witness): H
8c1f2d86-2ef9-55b2-817f-d7dae22258e2 | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are laid at correct depths, grades and alignment as per design dwgs
6cd96e42-4653-5a8b-8861-35e6c69aab92 | note | FREQUENCY: 10m Intervals
abc08934-6594-514f-99d7-e6d167002a29 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
67c581ff-80bf-5491-a0c4-0a39a4745046 | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
52ad6a29-9aa9-533c-a423-84165512f811 | note | RECORDS: Dip sheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Duct Installation
34e867e2-a55b-5396-8904-c2d50f971d4e | note | ACTION (Hold, Monitor, Witness): W
02aa9ca1-0c85-5b59-bf1f-edd694e64bcf | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
270d539a-cb04-5575-ba16-76d81e32bb48 | note | FREQUENCY: Prior to Installation
8ec15d67-4d49-5d53-9e2b-290104551af6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
3c693cf1-dec3-5fcf-9dd2-c196f93300fe | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
5a68b619-b7b3-554f-844d-1b9133e9d344 | note | RECORDS: Photos
| checkpoint | 7.1 - Duct Installation
df50ae25-c0d8-50b7-939b-83777b3155d1 | note | ACTION (Hold, Monitor, Witness): H
187da16e-8fa6-571a-85a1-77eea1204c03 | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and Atop min spacing tables
ab3af74f-1d98-5e0d-8e31-9e0885708d60 | note | FREQUENCY: 10m Intervals
6531f0d0-b61f-543c-aaed-795d0241575c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
d5247c9b-2221-5532-be61-975f7d397ce8 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
56c374b3-5612-5042-aa8f-8261bad483dd | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 - Duct Installation
8484eec6-0725-5a1c-b309-e23f187fe9b5 | note | ACTION (Hold, Monitor, Witness): H
b4f549a3-a658-5bff-9c44-1c8724e3394f | note | DETAIL: As-built Survey
7c4c6537-f48e-5a99-888b-d06164bf3be6 | note | FREQUENCY: 20m Intervals
ccf5b2ea-819e-5df1-a0f3-628c9cf947a7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
79a6d0d1-ac5b-5db3-b765-9db0bc57acaa | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
aedf4d3b-5e29-5bc0-a5f7-85637b7c830a | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
786e7f21-4a9a-5df1-9849-e60197915b69 | note | ACTION (Hold, Monitor, Witness): H
4df2ad16-e3aa-5b97-a125-4afa6675e3a9 | note | DETAIL: Lay min. 150mm GAP<12 for bedding and haunching
5cf51500-a012-52ad-89bf-fe85f2fb26e0 | note | FREQUENCY: 10m Intervals
f94ebb91-d8fa-5d31-bddf-d84c22380415 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
0b6d3300-3860-596a-8a16-bde6ea933712 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
c7e663ee-4ad3-5e87-b197-fd9e26d117ae | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
effc4780-8506-55a7-8501-0d11461cc10b | note | ACTION (Hold, Monitor, Witness): H
df3fa227-0c5c-5272-889a-23a773e3cd32 | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
a5d9d127-9d0b-5470-b1d2-2b79cff362b8 | note | FREQUENCY: 10m Intervals
fe8729bd-da2d-55be-86fb-ce063303a57a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
cc204c6b-6fd3-5b78-b41f-7c4d7b6b09aa | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
7f5ed50e-39dc-596e-849c-99459248d153 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Traffic signal pole erection
3ec81107-ee76-579f-9c21-6d174fd573c8 | note | ACTION (Hold, Monitor, Witness): H
2299daa7-6664-51aa-a26f-d990c6cae8b4 | note | DETAIL: Ensure Design engineer as inspected pole locations prior to proceeding
b331737b-58f6-52b0-846c-0c77927a6184 | note | FREQUENCY: Per pole
c215dac7-30ac-5898-81a7-d5f93823ab45 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
251dd912-6438-5fea-acc8-018ad1b27a42 | note | CONFORMANCE CRITERIA: Sign off by design engineer
4efdfd48-c35d-5e0d-89e7-7396e57be12b | note | RECORDS: Engineer sign off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 - Traffic signal pole erection
1652bfb0-f65d-55b9-9e14-4e1574432bb5 | note | ACTION (Hold, Monitor, Witness): H
93756d7e-c93a-5178-9099-3f779c88948c | note | DETAIL: Ensure Pot hole is as per design with required depths and widths
7ec2d110-9466-5081-9ade-99979df4b494 | note | FREQUENCY: Per pole
b6d24561-ccc1-573e-a8dd-ebdba188ad66 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
a88e5ffd-7d7d-564a-895c-fa2564e4ce5f | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
7d5f8101-5a67-531c-b4c8-2e2789fcd598 | note | RECORDS: Dip sheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.2 - Traffic signal pole erection
bb6a3003-8a2c-5ebc-9d89-75eb7970f732 | note | ACTION (Hold, Monitor, Witness): H
9564b367-fd75-5cfd-b05a-51fa18d1222a | note | DETAIL: Ensure Poles are plumb and within design tolerances
aa3551cc-b636-5abd-80c5-fa2195924266 | note | FREQUENCY: Per pole
c3f1eb58-f7fb-5a10-bcdc-93b309b9704c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
0a106116-f05b-5f27-b860-0e59d44b3c86 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
2ecbd602-27fd-5e6d-9007-2799ef419ffe | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - As-builts
b092e487-5656-56b8-9fa4-b0baec5d9089 | note | ACTION (Hold, Monitor, Witness): H
b6df8043-ba37-58da-acbe-f6f8d6963174 | note | DETAIL: Red pen mark up drawings to be included in QA file
7fc23052-8b90-53d8-81df-1ac70f79db20 | note | FREQUENCY: At the completion of the Lot of work
18457e70-4ecc-534c-8f88-0cebf2c22826 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings
878f8de0-2c1b-5a86-9d32-32f83cba3de6 | note | CONFORMANCE CRITERIA:
3250c3b0-581c-57f0-8786-c3a2bc70a9f7 | note | RECORDS: As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
d392a3b6-8012-5994-a830-d61e3cbcdc8b | textbox | Drawings used for Construction incl. Rev numbers:
7cbabded-fdd3-566b-b7fa-e34eb7ea5b34 | textbox | Reference Documentation (Notices/OFIs etc):
77b34d7c-4b1c-53cb-83c2-ec51927f4fa6 | textbox | QA Compiled By:
94e5f33d-29c7-5c0e-a8e7-974fd95d6166 | textbox | QA checked By Project manager:
c25cfc0a-8890-5961-bff6-2785dd154609 | textbox | QA checked By Contract Manager:
93ffed73-55cb-5d92-8234-c8c4b0738bfc | textbox | Accepted By Design/AT Engineer:
| checklist | QA Photos |  | QA Photos | 2f5e868a-dbe1-470b-a4fa-ea5658af03f4
| checkpoint | Add photos here: