## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Generic - ITP - Enabling Works - Footpath, Kerb and Channel, Pram Crossing | itp | ITP - Enabling Works - Footpath, Kerb and Channel, Pram Crossing | 26b1df68-75ca-4d60-968f-f4eb8ad7bbf5
| section | Site Set Out
| checkpoint | 1 - Site Set out
37348add-c5a3-51c6-bdda-2b198cbd3eb9 | note | VERIFICATION ACTIVITY: Surveyor
741fa328-4969-5a30-aaa8-eafa4a9d807c | note | METHODS OR REFERENCE: Surveyor
1e18f068-af91-5705-b7b2-aa6affab2644 | note | FREQUENCY: Every site
3bc3215d-6800-5f1b-b82d-b20e5e4ebf39 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
d5e8afb3-14c4-584b-8479-0fe8a0a23ffd | note | HOLD POINT: Mandatory HOLD POINT -
cc2a8aff-38c4-52d4-8d4a-a783365a81bd | note | RECORDS: Onsite records/photos
6bc8d6b5-717d-5b93-bba8-ea524d6281d5 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Kerb and Channel
| checkpoint | 2A - Kerb & Channel
f2e3c2d7-8160-525a-a12c-36eddf756fb8 | note | VERIFICATION ACTIVITY: QA FORM
b311c14b-dcae-5e86-b94d-92419b5e196c | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
00b083d9-532c-56b1-8773-87375f88a9de | note | FREQUENCY: Every 10m for Scalar
49718849-30c3-56db-91f0-5a7876240eea | note | ACCEPTANCE CRITERIA: Subgrade CBR > 5
77a48ebf-13c1-5f8c-adf1-2f34627b89d8 | note | HOLD POINT: In process Inspection
5b3306c6-15de-5f2a-a31f-b4d01894c939 | note | RECORDS: Scalar Sheet
dbfa145b-7928-50ab-bcc0-bff00fa87f34 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2B - Kerb & Channel
9a48ee6d-91b0-5da3-909c-a4e02593c26b | note | VERIFICATION ACTIVITY: QA FORM
1ac037d2-de20-5774-b0be-fa4d84944dcc | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
15461fe5-bc4d-5ac9-a8d9-107b138f0dd5 | note | FREQUENCY: Every 10m for Clegg
356ab40b-3494-50c0-868a-d1310d8f03bf | note | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid on compacted GAP40.
978bd73a-88be-537d-9cc3-2f0c5afd4cff | note | ○ Thickness - 100mm on Footpath / 300mm on roads
095a8c5f-9573-532d-8744-57fb03170f93 | note | ○ CVI > 12
294f028d-3c5b-5b9d-aad7-379919f4c864 | note | HOLD POINT: In process Inspection
91c0420c-870e-5801-82dc-485eae46c192 | note | RECORDS: Clegg Sheet, Photos
427d9e3d-ef43-5618-aff8-43dac9ce9440 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2C - Kerb Setout
4624b3bf-a496-53d8-b381-6993575445e6 | note | VERIFICATION ACTIVITY: QA FORM
9d1031d6-7ce9-5cf7-b9be-d3a5abea9fd0 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
1ba52203-6b83-5386-800f-0c5e9417d9e6 | note | FREQUENCY: Every site
f9743e3f-b67e-59b8-aeee-b82ee9345079 | note | ACCEPTANCE CRITERIA: Site Setout as per construction drawings and heights and falls verified
04cebf37-522e-5f7a-a8e3-a923221cf68b | note | HOLD POINT: Mandatory HOLD POINT -
ee063951-e692-5784-a995-c55e4e3c650d | note | RECORDS: K&C Pre-pour Checklist
b4f249d5-26ba-575d-81ac-a70131af5126 | note | ONSITE RESPONSIBILITY: Site Engineer / MSQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2D - Channel Material
6e765a50-3dad-59b4-ad83-b597707f3b61 | note | VERIFICATION ACTIVITY: QA FORM
939fa9d4-f90c-52bc-91a5-3f1e06374e5f | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
b4d09b5a-16b1-5ef3-baed-a93b26e5eb06 | note | FREQUENCY: Every site
05eb1f79-5d88-5e24-8d1f-6090a182fc26 | note | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days
0db649a3-2fb0-5622-8ad4-33fe40c79e79 | note | HOLD POINT: In process Inspection
ce6c6184-6a6c-5fe2-afb0-d272436b0468 | note | RECORDS: Concrete Docket
2e6c777c-2d3c-5912-b083-adc1a3146857 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2E - Channel Level
53075479-3df6-5710-a88f-d642b0ea86ac | note | VERIFICATION ACTIVITY: QA FORM
90d7abc6-57df-58b3-a715-2b934eef7f4b | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
68be5fec-1cd0-5072-9cae-3bac6f57f1c1 | note | FREQUENCY: Every site
f3b94cf5-27de-5f55-94b0-376cc0e9ba74 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
67d23cdb-9c14-547b-9f5d-2936f661d41d | note | HOLD POINT: In process Inspection
cbce98d4-0d21-5d05-9f45-c99edbe7c90b | note | RECORDS: Photos
a7fcb097-cccc-5e49-9a71-b627a86ea386 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Footpath
| checkpoint | 3A - Concrete Footpaths
1f0c6cca-e8df-50ca-82ce-d5ae20bb18da | note | VERIFICATION ACTIVITY: QA FORM
aa03a965-a063-5f34-98ac-e8e2baa956ab | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
431fc44c-ed9f-50fc-9487-117650677329 | note | FREQUENCY: 10m intervals
ff615669-f94b-5b6f-9e09-7e9b0bd43c3b | note | ACCEPTANCE CRITERIA: Subgrade CBR > 3
f510cbbd-2256-56e0-b40a-da2654a82f78 | note | HOLD POINT: In process Inspection
200ead51-9b9d-5a8f-b216-716dafd2314d | note | RECORDS: Scalar Sheet
9259d270-1e6a-5713-b0cf-dda4979f7f41 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3B - Concrete Footpaths
8281f1ad-e748-5afc-9949-ce6475a695ed | note | VERIFICATION ACTIVITY: QA FORM
6488d403-02b9-53cc-8d94-59be7b2e7de5 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
cacca5e3-40e7-5282-bd4a-a02ce99dd4c2 | note | FREQUENCY: 10m intervals
3eb73cf1-1914-5e17-8790-0fc1c3a47b7c | note | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness
361f7126-f3b8-5906-9f25-ffdeb630c9a0 | note | ○ Clegg CIV > 12
2c96ee10-73e2-5acc-8f17-8a3b3d1997a9 | note | HOLD POINT: In process Inspection
fe743841-c62e-54bf-b93c-92cb9efd60bc | note | RECORDS: Clegg Sheet, Photos
3cd39fbd-dbcf-5070-90d8-805025993f30 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3C - Footpath Setout
794a7d94-e21b-5d18-abbb-e314fbe01e02 | note | VERIFICATION ACTIVITY: QA FORM
8a9eadad-f3ea-5d4f-802d-b0790c95c319 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
bfcac348-655c-5b4b-80a4-f763ae2d083f | note | FREQUENCY: 10m intervals
a7ceef4f-8d49-5069-802b-6ce1d41fb148 | note | ACCEPTANCE CRITERIA: Site set out as per construction drawings and heights and falls verified
04d04f9b-a03b-5e28-babf-330b7a7353de | note | HOLD POINT: Mandatory HOLD POINT -
6ece6da1-8d4a-5e9f-8ca2-ea0640f91fab | note | RECORDS: Pre-pour Concrete Sheet, Photos
1eaaf716-31f5-5a25-989a-9b7000cb316c | note | ONSITE RESPONSIBILITY: Site Engineer / MSQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3D - Footpath finishing
9bf1b369-000f-5de3-aecb-c4dcd4fd53d8 | note | VERIFICATION ACTIVITY: QA FORM
94c588da-837d-556f-8e6c-2882d98f0a63 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
a3b008c6-3408-59c5-aa29-4fcc60669334 | note | FREQUENCY: Every site
4a85379f-2c8f-5195-b2ac-50094bf90ed6 | note | ACCEPTANCE CRITERIA: Concrete Strength 20 MPa @ 28 days.
43613606-bfad-518e-8e6a-7fbf1740355a | note | ○ 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing)
77b8414b-5cc7-559c-a79c-23f56ca5db9f | note | ○ Standard Footpath - 100mm thick
f8cdd8e2-166b-5822-940e-8104cc3588d7 | note | ○ Heavy Duty - 150mm thick
dd4ce1b2-7dea-5241-87c1-52121b25956c | note | HOLD POINT: In process Inspection
5349694a-9639-5115-8897-733f8eb5aea3 | note | RECORDS: Concrete Docket, Photos
1385ca46-ab54-5a11-8945-636ac120a82b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Grass Berms
4b467a0b-0a35-5b05-a16d-376bbbe0b4cb | note | VERIFICATION ACTIVITY: Visual
e75a70c2-8adc-5e96-a22d-c3f0462812cc | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
c166e7b8-d418-556f-9881-e042d914042c | note | FREQUENCY: 10m Intervals
3a380300-f83f-5d24-951e-3fb9ca3ef34f | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
ad1f50c9-90d0-5af1-bbda-e66289f07811 | note | HOLD POINT: In process Inspection
af1ebbae-0f0c-5bf0-bb66-8f633fa00d7b | note | RECORDS: Photos
deb3f735-57fc-5484-ab62-061184420471 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Service Covers and Street Furniture
88287524-c2a7-51b6-8d40-1e08df0a2efc | note | VERIFICATION ACTIVITY: Visual
861d10a6-269c-55d3-b045-502d48452f49 | note | METHODS OR REFERENCE: AT Contract Specification 14000
877d3f87-d07d-5dd5-9819-06252bd47480 | note | FREQUENCY: Every site
b95016c2-ca36-567a-9a53-ea5f72775462 | note | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
942594f8-828e-5379-b048-19b02e73f05e | note | HOLD POINT: In process Inspection
3f8e2ee7-7bf8-579a-be1c-d0612513e436 | note | RECORDS: Nil
ddfabd5e-90f2-5d4d-9439-db805286f9d0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6A - Tactiles /Pram crossing
25cbbb58-c435-5f82-8384-d4907840dba7 | note | VERIFICATION ACTIVITY: Visual
3ec6ef76-a5ea-5684-868b-b9d3f08425a6 | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
9ccb8f92-122a-5381-a161-d2c49184979d | note | ○ TDM Technical Standards - FP0010
a7289436-a690-5e07-8912-b2bdb04478b2 | note | FREQUENCY: Every site
b293a988-6c92-5952-80af-9e607ef99ecf | note | ACCEPTANCE CRITERIA: Tactiles set out must be agreed with MSQA
12e42f24-a925-53f6-b342-21b730f29138 | note | ○ Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
d58073cf-e4b5-5637-a650-22f70bc972dc | note | ○ Warning TGSI tiles should have 100mm concrete slab underneath
32848c5c-75fc-5aa9-80ec-72370637bf3f | note | HOLD POINT: Mandatory HOLD POINT -
6b11d507-66e4-5f53-a91d-9740120173b2 | note | RECORDS: Photos
3f46f9bf-2ea9-5603-9343-6ca88fea8008 | note | ONSITE RESPONSIBILITY: Site Engineer / MSQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6B - Tactile Material
82e7f228-009b-5a79-9388-f1c1deeeafa5 | note | VERIFICATION ACTIVITY: Visual
83b2fdf9-82f3-5645-b909-68eed9879ae4 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
66f8bc46-93d8-5cfe-a169-0698385792fc | note | FREQUENCY: Every site
7af24fb0-aee6-546f-8aad-537360e180b7 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type - 300x300mmx60mm
ffd4fd1e-04da-512c-9768-04a2e8833cb6 | note | HOLD POINT: In process Inspection
c0dfbed5-e14b-5ca0-8532-ac5266c90eff | note | RECORDS: Photos
5c7e22d6-d671-5051-af3f-b52b1658d4f4 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6C - Tactile
06a93128-f936-5aaf-af49-868046347e49 | note | VERIFICATION ACTIVITY: Visual
6275b83f-e061-50dd-8c96-43558d63b7f4 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
69888d02-4ea5-56d4-8f19-8f5364985d1c | note | FREQUENCY: Every site
8208dc74-eb23-583f-bb80-648692bbcd06 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
492d1d45-38d0-58ae-bb47-795f1b55b4e1 | note | HOLD POINT: In process Inspection
c8af76b7-11d4-526e-b94e-3686514c504c | note | RECORDS: Photos
d1b58b30-0f49-5e51-866e-f09a3de1cda7 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | As-builts
| checkpoint | 7 - As built information
1aa74bc8-36b8-5205-aed5-54f5a0b353fb | note | VERIFICATION ACTIVITY: Drawings
7e9a9d1d-7ce9-5338-b72d-37af444666d4 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
ace26f81-f860-524e-af23-bcfc9068d2ee | note | FREQUENCY: Every Site
d689586a-bb74-5dc2-91c9-7b0a5700a9be | note | ACCEPTANCE CRITERIA: As-Built drawings
93ed5fa2-7d36-586e-965d-e24645044cf6 | note | HOLD POINT: In Process Inspection
046b2374-6c2f-5537-90c6-f8d8825b5f35 | note | RECORDS: As-built records
ec84a75e-c3da-5d07-bc1a-dc220b8405b9 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 8 - RAMM DATA
df32f3a6-1f2f-5fa2-98f7-2bf43db0ad0d | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
0b257ce2-23cd-53e9-ad82-a348028d4e93 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
dab57434-41fa-5e3f-8a08-e56937718bf9 | note | FREQUENCY: Every Site
8c7a4884-e585-5d88-b94c-d537c6dad5e0 | note | ACCEPTANCE CRITERIA: RAMM SHEET
f094e2a8-94db-5a13-ac87-41b803da9a6f | note | HOLD POINT: In Process Inspection
d0a67be1-081f-53ad-8aa9-97706b0e4c9c | note | RECORDS: As-built records
948d75ca-ebf3-53bd-a1ab-bfa90bb07d6e | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
0560b2a0-be32-5915-9716-db9a1702be3b | note | Prepared by: Daniel Tat
099508fc-8a77-5ec0-80b9-1a8c133094c3 | note | Approving Delegate: Daeyoung Jeong
| checklist | Generic - ITP - Enabling Works - Vehicle Crossing | itp | ITP - Enabling Works - Vehicle Crossing | e5312353-c81f-4ea3-b091-049573bc67b2
| section | Site Set Out
| checkpoint | 1 - Site Set out
bed02b40-dd4a-5f7a-8ce6-105a3b9d875d | note | VERIFICATION ACTIVITY: Surveyor
896ac3fd-84e3-5352-9d47-12cdb01aeba3 | note | METHODS OR REFERENCE: Surveyor
03381a6f-b18e-5c3c-9446-dd55026d541d | note | FREQUENCY: Every site
6e516294-c5a2-5564-b187-17f9bf372ce7 | note | ACCEPTANCE CRITERIA: Site set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
66054417-5178-58bb-9606-28df12d42ca8 | note | HOLD POINT: Mandatory HOLD POINT -
4260c472-7d0f-561d-9853-ecddbdfe3e19 | note | RECORDS: Onsite records/photos
17af8160-3767-552e-9a79-07d72f725adb | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Standard VX
| checkpoint | 2A - Residential VX
54ef2463-fcf6-59a3-beb7-d712b297b54a | note | VERIFICATION ACTIVITY: QA FORM
20896e55-e538-5d98-99c9-37c5f1913f54 | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
1fae260a-701c-5d61-86de-75b59cf1a4fd | note | FREQUENCY: Each VX
9dfca79b-51de-5438-b51c-8432d6727ac4 | note | ACCEPTANCE CRITERIA: Subgrade CBR > 3
e091bbe9-66a5-5375-82ae-b337c9f53aed | note | HOLD POINT: In process Inspection
d11e5d75-3f61-527d-95d4-3ba546dfa446 | note | RECORDS: Scalar Sheet
117dce22-a29a-5747-b950-0a66c7376dc7 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2B - Residential VX
8435a116-108c-5bab-8ba0-a847c40fdeba | note | VERIFICATION ACTIVITY: QA FORM
0a86e80f-d917-5dcd-9f27-1ea7a81c641c | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
56bfece6-51e1-5967-96e1-639cb317303c | note | FREQUENCY: 4 Cleggs per VX
a0c162a7-a993-5c12-bbfe-f0b052756eb3 | note | ACCEPTANCE CRITERIA: VX to be laid using on compacted 100mm min GAP40.
1b163744-d040-54b9-8c24-dcfbbef6872a | note | ○ CVI > 12
66b20e56-05bf-57d2-b6e3-820f510376fe | note | HOLD POINT: In process Inspection
4735aab6-7257-5f71-88dc-a2d12227782f | note | RECORDS: Clegg Sheet, Photos
d1702fd8-d84b-5632-a25f-72b39106610f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2C - Residential VX
1aa2a9a7-9c6a-58eb-aceb-bfaa1412e2b9 | note | VERIFICATION ACTIVITY: QA FORM
34f75734-bbd4-58b7-b234-b3d8b0e299e2 | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
c54b9fb7-627a-5c2b-a380-31dbaa53b307 | note | FREQUENCY: Every VX
d4686c70-9e02-506a-9d24-b37e5786c822 | note | ACCEPTANCE CRITERIA: Site set out as per construction drawings and heights and falls verified
bc04dffd-f300-5c35-bb6e-314bd758c079 | note | HOLD POINT: Mandatory HOLD POINT -
a1ead34a-20bc-54c5-89e3-3aa27ad67870 | note | RECORDS: Concrete Pre-pour Checklist
53b05a5b-cd28-524c-87c5-8cebdc95c81f | note | ONSITE RESPONSIBILITY: Site Engineer / MSQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | VX Material
149f6bfc-be0e-50a2-9604-16021a91c517 | note | VERIFICATION ACTIVITY: QA FORM
8c43a39d-6cd9-56c9-adfc-feb9275b030d | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
0756d50a-3af5-5ee1-9770-c03ea751b02e | note | FREQUENCY: Every VX
1b08e0bd-a4d4-519f-a180-2cfd6c6234e5 | note | ACCEPTANCE CRITERIA: 665 Mesh Required if 4 or more dwellings
c8fe4d38-78d2-5ba7-85d3-fcd34f9e5fb4 | note | HOLD POINT: In process Inspection
6a2a493b-6b1a-5c6a-9d5d-f12cf5d49333 | note | RECORDS: Photos
b6b929c1-5ac0-53ff-a3a9-f97bd1260a59 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2D - VX Material
f4f6d837-eb0d-50d3-b733-b9eec1401bf1 | note | VERIFICATION ACTIVITY: QA FORM
ce23f722-1f7b-5fc8-84ec-d09776f0e00a | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
0d498d5d-3af0-5f88-bd6b-d02e1185d34e | note | FREQUENCY: Every VX
f4b3e8c0-87b5-52ae-a2e5-c5bac89e97b2 | note | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days
78849114-06eb-5f71-b9a0-96c963649295 | note | ○ Thickness - 150mm
9add2ed5-3350-50c5-8a73-80741f783bd5 | note | ○ 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing)
852d979f-9b2f-557e-862f-ee94be78dbc4 | note | HOLD POINT: In process Inspection
6629e02b-128c-5d77-9f86-9bd07d1b1d3d | note | RECORDS: Concrete Docket
de9a7b9a-e2d9-5889-b6ae-b454920e611d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2E - Residential VX
a64d511c-c264-523e-9571-f9479f576267 | note | VERIFICATION ACTIVITY: QA FORM
bad96865-803b-59a0-8d6c-5dc5b08c9bad | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
0c88cde6-252b-5415-b760-27d2feadae38 | note | FREQUENCY: Every VX
d3c7e49b-8eef-5ba6-807b-7b0c6a873a59 | note | ACCEPTANCE CRITERIA: Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg
fa1b504c-e1ec-56ef-ab57-c03c8d0d0849 | note | HOLD POINT: In process Inspection
f4fe6a70-2447-5140-ac9e-5d88cc4f48ff | note | RECORDS: Photos
7d85ef4f-d162-5c3a-b902-bdf0e592cc3b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2D - Residential VX
0c24fe6f-3140-5ff4-a715-88c74141d863 | note | VERIFICATION ACTIVITY: QA FORM
18238588-6247-5cf6-b2f7-f010b0e2b976 | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
4ae295a1-06e3-5e3e-993b-73d39800467f | note | FREQUENCY: Every VX
59e8d854-8049-520e-9d3e-0cb27410116d | note | ACCEPTANCE CRITERIA: Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg
4ffdf3c2-60b5-5fc2-9fe5-5d9f3df6f4aa | note | ○ 1m reinstatement on carriageway
5a99b73c-8d68-57e9-980e-358c9b7f242a | note | HOLD POINT: In process Inspection
3e42cb2e-a576-5b27-9f67-c986aeae3763 | note | RECORDS: Photos
f17d9ae0-2c27-5b3e-9242-54df1ae0783d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Grass Berms
8037378e-b276-5612-a48a-53b575fd1f92 | note | VERIFICATION ACTIVITY: Visual
a2d32f7a-a67d-5a01-a10b-aca88cdfc069 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
7b6d3572-7542-5474-995c-0096a0775bc3 | note | FREQUENCY: 10m Intervals
a39546b0-f4d6-52a0-a6ed-4d771ac240e5 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
91eae4f6-47e3-50e2-a687-ea74bf85cf8d | note | HOLD POINT: In process Inspection
b9ca45a3-dc8d-5bf9-bb13-4819eb1bbb4f | note | RECORDS: Photos
ddf83711-1016-5335-a5f9-363e197dc511 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | As-builts
| checkpoint | 4 - As built information
5baada23-e50d-5e35-8f3f-7a456b5c9fd8 | note | VERIFICATION ACTIVITY: Drawings
62740f1e-4f0e-50e3-886e-d2adf001dcf5 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP
b7723ec7-60ab-5aca-81bf-c9d1e017f931 | note | FREQUENCY: Every Site
05db6444-64b7-57c9-b255-b1bbb59783ea | note | ACCEPTANCE CRITERIA: As-Built drawings
a72d370d-db53-52ea-86ca-d73fae3b919e | note | HOLD POINT: In Process Inspection
7d098185-1dfc-5d14-902c-fa703a35feef | note | RECORDS: As-built records
315868a8-3b18-5f01-b34c-61d6d2cb5718 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 5 - RAMM DATA
6adfb29a-bf91-5bd9-b66b-ef51b67dda4d | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
b6df0cf4-caae-555f-9d8c-a6bb4d69b8f5 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP
3f7f1317-1da0-5409-b998-215fc4f99e3b | note | FREQUENCY: Every Site
9f66039c-1cb2-5859-99fa-531a872958ba | note | ACCEPTANCE CRITERIA: RAMM SHEET
6939521f-3742-5064-b6c8-4708185dcf1f | note | HOLD POINT: In Process Inspection
8cb1904a-beac-5d82-89ad-61cd802ac45a | note | RECORDS: As-built records
bc85957b-04a9-5896-b69a-a3564ed02647 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
a95c1163-6fb9-5ba9-be91-8cf8253d58a8 | note | Prepared by: Daniel Tat
aa26d8f3-144b-587b-910f-8538b6f17490 | note | Approving Delegate: Daeyoung Jeong
| checklist | Generic - ITP - Stormwater Drainage | itp | ITP - Stormwater Drainage | fca8b23f-0592-4444-b4ac-3fae6b65521e
| section | Stormwater Drainage
| checkpoint | 1 - Permits & Services (1)
d9657bf7-0559-596f-b173-8156a76b9581 | note | ACTION (Hold, Monitor, Witness): H
aad2db34-0f7c-5a32-b4bd-d3e8a65415ea | note | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
504e12ae-a716-5516-9489-7bf31f5af5a4 | note | FREQUENCY: Prior to any construction commencing
3db0b98d-834b-5deb-ae18-2d5f95d2905a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
210d0a6f-754d-5eca-a5ec-7ffe1fcfd38a | note | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work.
036251e2-c2f1-5306-a6fb-692ae559a9b7 | note | ○ AT Access Authority approved and signed by RCA Authority.
b79ce247-28e5-52f4-b627-a12474086f3d | note | RECORDS: Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (2)
aa98ec73-8591-5f93-911b-982f3edfef56 | note | ACTION (Hold, Monitor, Witness): H
176ac649-7c32-58a7-a15c-b2767ad1269b | note | DETAIL: Locate and mark out all existing services
3937805c-45da-5e7a-93c3-4571e2e85e98 | note | FREQUENCY: Prior to any construction commencing
2e003d4e-7755-518e-88dc-105d61c21e00 | note | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols and GPR Report
60826fc1-ed88-52d7-9ccf-8ebb8d87c107 | note | RECORDS: B4u dig plans & GPR report attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
fdf6beda-f82c-5908-8b3c-00664dda814d | note | ACTION (Hold, Monitor, Witness): H
7e719661-877d-5c8c-9f87-44fb0d301673 | note | DETAIL: Sub-Contract and Supplier Agreements
01bae753-283b-5f45-a6cf-084f5b6b5ab7 | note | FREQUENCY: Prior to commencement.
ff1fb197-3689-5ee9-a780-ddca81c2ce3c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
8497c4bc-1c56-5caf-a80d-5c0dcf4e5f3a | note | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
affc836f-9a5d-5fc0-a47c-530742dc76f6 | note | RECORDS: Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
108a964d-20ab-5627-807d-f37b4c1064f0 | note | ACTION (Hold, Monitor, Witness): H
33ca76a0-3455-505b-8816-ec1465c5fea9 | note | DETAIL: Design is approved and Drawings are of the latest revision.
4c624232-7ddc-5396-9005-307f83335c0a | note | FREQUENCY: Prior to commencement.
fd48cf73-fea7-519b-94e4-a244d3723db5 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
06a2667d-8ae1-5589-ab49-a3a6821c57b2 | note | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
634cabee-a56e-59bf-907f-63a5d83c0438 | note | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
369fd83d-4a21-5236-8119-c1e59211a73e | note | ○ HOLD POINT of not issued to IFC.
1f9167ca-b36d-5fe8-8a91-50133fe1b00d | note | RECORDS: Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Setout
46b7873d-d589-57ff-9a96-149512b986ae | note | ACTION (Hold, Monitor, Witness): H
a3b3e953-9add-5cb1-bce7-c17de5ec8b4b | note | DETAIL: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
aeedebdf-5339-5dad-898d-21a658447050 | note | FREQUENCY: Prior to commencement.
1bf5f663-5dd4-5573-9bc7-5f27e1f1a9f6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
2cd2361b-44fc-5cbc-9097-bfce538ceb1b | note | CONFORMANCE CRITERIA: As per IFC Drawings and design AutoCAD file.
71811587-13d7-537b-87e1-7c2b419d011c | note | RECORDS: Survey Receipt.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
c2fda340-a0d4-5c4d-91eb-6f79dd6aee31 | note | ACTION (Hold, Monitor, Witness): H
37065efb-d081-5abe-af8e-5198f8f21a6a | note | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards
2796061a-b9bb-5549-9e29-460b7e802d0b | note | FREQUENCY: Prior to commencement.
da21c052-2ce8-5905-8d29-f82e1417e1db | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
c2c9c3a3-afb2-5b47-9b87-d87a809781e1 | note | CONFORMANCE CRITERIA: Pipe shall be check for freshly formed pipes and return if required
81e51974-b496-5ddc-9443-70932efb2b5a | note | 1) Class 4 RCRRJ pipes AS/NZS 4058
f4f33ee5-cfee-5067-a1c2-4f19a3b28872 | note | 2) All Concrete RCRRJ pipes to be fitted with Rubber rings
dd56c407-129d-58db-a507-1b49ab104291 | note | 3) Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
6aea91dd-b819-5f4c-be6e-782e15b6dbc6 | note | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards
3532b749-6bee-59cb-8abf-8344b7793017 | note | RECORDS: Manufacturers Data Sheets, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
83bdc7dd-f2ae-5037-882c-d66d5fa95726 | note | ACTION (Hold, Monitor, Witness): H
cb38dca6-881b-5e7d-8638-f65229ef4443 | note | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
6741b398-387b-549d-8bbe-f50fb119cf65 | note | FREQUENCY: Prior to commencement.
1db7f5cc-a496-5665-9f3e-ea6b4f35ae56 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
e720e941-18de-576b-bd14-63ead5e8f2b8 | note | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services.
f077fe5d-d9d9-5993-bcdc-ffc40c606ef3 | note | RECORDS: As-built Drawings. Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (1)
e84e010e-1b03-5e9e-9879-1cf20e2ed625 | note | ACTION (Hold, Monitor, Witness): H
d31e6df1-a791-5cec-95ca-9cd69eb0b02e | note | DETAIL: Excavation methodology
d2bab0f0-bf62-5f43-9842-13f26fa11cdf | note | FREQUENCY: Daily
4658c5af-9024-50a5-adf8-cbd663dd683c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
4a3c62ef-7fdf-519e-b815-ab89c4d57b8d | note | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016)
5e4e870d-c1a1-57a8-b465-dd5e12ef957d | note | RECORDS: Prestart RCP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (2)
67ed6917-09e9-5907-acac-83751b2cbb33 | note | ACTION (Hold, Monitor, Witness): M
1d29e5c4-0536-5265-80c8-e55fff357f02 | note | DETAIL: Trench Profile - Width
a648b4cf-76a0-5e0a-a731-01127815456c | note | FREQUENCY: Daily / as trenching takes place. Different depth methodology
d5b1df48-dfee-5d1f-8e2f-454e33681515 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methodology
4998c72f-4d4d-568e-b74b-c3e457a06fd1 | note | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
d0b5597a-8850-53c1-ae22-4a00bdf1030c | note | RECORDS: Construction Photos
| checkpoint | 7 - Trenching & Excavation (3)
ade2ed53-39f2-5988-bfa6-500d5daf56e9 | note | ACTION (Hold, Monitor, Witness): W
8ce57310-e086-519b-a5d6-8de7594d6ee9 | note | DETAIL: Trench Profile - Depth
7ba40026-8c2f-50a1-99e8-d986b1b685bf | note | FREQUENCY: Daily / as trenching takes place.
a40ea081-8a3a-5797-9b9f-fafe236f6b83 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
3f703f36-b8a7-510a-b9cd-d96d952a778b | note | CONFORMANCE CRITERIA: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
63878052-2478-52bd-83b0-04afff02c627 | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 7 - Trenching & Excavation (4)
3bca4336-2ad3-52a9-b3e1-19e24ee188e1 | note | ACTION (Hold, Monitor, Witness): M
a2c4a10b-d6cd-50e7-b081-25ca2902d3b9 | note | DETAIL: Trench Base
78b008d4-275f-5b3b-a9bd-e7433a4adeb5 | note | FREQUENCY: Every 10m
cbcc35f5-8fff-5d67-9e5b-0fdb44fe0f21 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Scalar testing
3490e826-74e9-5be7-9436-eb43408735d6 | note | CONFORMANCE CRITERIA: Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2.
730e7153-0b26-5153-9a17-a493b725b7bf | note | RECORDS: Test reports / Construction Photos
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
bde5bf4f-1377-59a5-b966-4c4626541b88 | note | ACTION (Hold, Monitor, Witness): W
770ad3f1-9ebf-545e-8b95-394dadcf1faa | note | DETAIL: Placing and compaction of Bedding Material.
f1f96cbd-d56a-5655-8c04-b3ea1fb04356 | note | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
5c6220c9-35c6-5dcd-8fe4-915ed179dfb8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
cb146afe-6f5e-5f26-8d92-df340a035400 | note | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725
8f9ef139-bf94-5cfc-b372-85d352c8541e | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 9 - Pipe Position Tolerance
2ca13bae-57b5-50c8-b409-89e9c6f6c52e | note | ACTION (Hold, Monitor, Witness): M
dcce34df-0598-548c-82d3-161be388e5f1 | note | DETAIL:
0a33ffc1-5c9e-5f6f-878e-4a53d6a8c78c | note | FREQUENCY: At any point of pipe
c8e13a75-782d-5de8-974f-6712f32d80c1 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review):
14380e5c-27f0-5ab9-8d56-fb5803079b44 | note | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design.
b1a983b6-de22-569f-8712-70b946ac025b | note | RECORDS: FH Drainage Line Record, Survey Data.
| checkpoint | 10 - Trench Backfill - Placing & Compacting
7d35f43e-caea-5e65-af60-4d13881fd400 | note | ACTION (Hold, Monitor, Witness): M
f650cdd9-e340-5af9-974a-7a4f94f1aa49 | note | DETAIL: Placing and compacting of Trench Backfill Material
fb75b25b-848f-578c-862d-a434744ac19f | note | FREQUENCY: Throughout Trench Backfilling operation.
f684c402-9df9-5006-bcde-a4814cd4dd56 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
9e29e5d2-e360-52f7-87f6-8052ec679e99 | note | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick.
3a46ea98-7bf9-566e-a3b4-854b0850eb48 | note | ○ Compacted backfill material to be free of Lumps > 150mm
31a3f656-5451-57d4-bdd2-b5d616af590c | note | ○ ATAP40 for subbase/basecourse.
1c245534-bfb1-539e-a8c0-27ea9898eea4 | note | RECORDS: Construction Photos
| section | Subsoil Construction
| checkpoint | 13 - Subsoil Material Compliance (1)
67092dd5-ce8f-5e21-a8a5-dafeb58e40b4 | note | ACTION (Hold, Monitor, Witness): H
9f11e025-1fc5-5c2a-b870-e80a9da2dd21 | note | DETAIL: Ensure Subsoil Drainage pipe complies with TDM RD010
05c732cc-5d51-5206-a5aa-181c2f011244 | note | FREQUENCY: Upon delivery to site
dff3c663-b27e-57d1-aa9b-0f881b1c7bb6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials delivered
97024ec8-7826-5382-a14e-fe24e5b6dd2e | note | CONFORMANCE CRITERIA: 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock
e7c1385a-0ac5-542f-ad7a-827e0172ad49 | note | RECORDS: Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Subsoil Material Compliance (2)
3c62a128-7553-5499-82fc-8b30f3c92dc3 | note | ACTION (Hold, Monitor, Witness): H
a344ae64-421f-5ec2-a009-0596283385b5 | note | DETAIL: Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate
757bf801-9730-5f72-ad56-e306e0e3e1ae | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
3f3734cc-4b24-57e1-ac6e-be97d49e742e | note | CONFORMANCE CRITERIA: Ensure clean drainage aggregate - F2 Sand
89716549-cffb-5e80-9ea2-12f0f2a03e75 | note | RECORDS: Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Trenching (1)
a6be9cff-a11a-5407-a51c-ca178d5a5084 | note | ACTION (Hold, Monitor, Witness): H
a610ffe4-52e0-5ae1-9425-7f69f65206b3 | note | DETAIL: Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade
1b4522d0-db49-5956-8d5e-ef604e6d1148 | note | FREQUENCY: 10m intervals
170b0429-b7e0-5a6a-97a6-edc3a064a3a2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
0a61720a-7946-566a-8569-79520f35f19b | note | CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet.
dbeee922-14c4-52cc-94bf-c88e18a9b4ea | note | RECORDS: Photo / subsoil log
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Trenching (2)
6b9efa27-0a62-5baf-9e98-84713707f8bd | note | ACTION (Hold, Monitor, Witness): H
b90f343a-a97d-5d16-b861-aab7843fe48e | note | DETAIL: Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
1139518d-346c-5276-b463-0d0c8727b26e | note | FREQUENCY: 10m intervals
1cd5c552-8af5-5ccf-9a57-9823a9850cc3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
a8c558d1-2090-5088-bc91-4b4c5d7a5573 | note | CONFORMANCE CRITERIA: Ensure trench line and levels match the design drawings
8486f481-c2fe-573f-bf77-7480a4c0ef81 | note | RECORDS: Photo / subsoil log
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Bedding, pipe installation and Backfill (1)
e5e3705e-3a93-56a7-b7a3-5ff0072b992a | note | ACTION (Hold, Monitor, Witness): W
86224cd0-daf9-51f9-a131-e8ee4b091049 | note | DETAIL: Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench.
0d085919-6cac-5379-96c2-7fe5f69b2cd4 | note | FREQUENCY: 10m intervals
afe7047e-27c9-5aa6-943e-20a6fa95d037 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
b678af7a-3daf-5977-af4b-9e6bda1ffff4 | note | CONFORMANCE CRITERIA: Record levels of top of bedding on dip sheet
f5d5e11f-82b1-539e-b83c-3c713fb4cd82 | note | RECORDS: Photo / subsoil log
| checkpoint | 15 - Bedding, pipe installation and Backfil (2)
fcc075c7-410d-577e-b809-debc5b9fc3c3 | note | ACTION (Hold, Monitor, Witness): W
9f08dd79-d59c-59f1-9a12-b708c88f8f47 | note | DETAIL: Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
8c24c07d-9cdf-5121-bb1f-49d1f4ace835 | note | FREQUENCY: 10m intervals
5ff5c979-ed6d-5335-ad8e-60b1e61567ef | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
ac778684-425d-50fd-a312-4e5c8c4fadbb | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
ad5205eb-c5a9-583b-9e19-b728e7e19061 | note | RECORDS: Photos
| checkpoint | 15 - Bedding, pipe installation and Backfill (3)
1926e600-94b7-593a-bda3-e8f970294513 | note | ACTION (Hold, Monitor, Witness): W
fe29e17a-d096-592f-8fae-4e5e28fc3175 | note | DETAIL: Backfill by tipping AP20 as bedding & ATAP40 as pavement structure into the trench
db994f66-38a5-587f-8e92-bb549d2d7d5d | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
4e51c836-52ad-5a1d-86b2-b8d5596ab046 | note | CONFORMANCE CRITERIA: Ensure good coverage
ce8fd680-466f-59c8-843c-ebcf8d2a6de8 | note | RECORDS: Photos
| checkpoint | 16 - Catchpit Connection (1)
0d176cb1-3c66-5582-94c3-b9b1e7959bc7 | note | ACTION (Hold, Monitor, Witness): W
a728849a-defb-51ef-8b91-ff95ad7bf335 | note | DETAIL: Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
6922785c-374e-5ddb-860d-b3218b6eaf3c | note | FREQUENCY: As required
bfa49746-e605-5396-beb5-8c25cc7fa26f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
27ea2d70-6190-57b3-b5a1-30d7c5171dbd | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
6376c198-c9b9-518a-8dd9-26db5636c3e2 | note | RECORDS: Photo
| checkpoint | 16 - Catchpit Connection (2)
0eadeffa-755d-53ca-8d3f-3e823f7408f4 | note | ACTION (Hold, Monitor, Witness): W
d0d191e6-61c1-549b-b16e-0e72d77351e6 | note | DETAIL: Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
4532f19f-34e6-556a-a30c-4f38ed4be978 | note | FREQUENCY: As required
59cca33c-a20c-545f-8605-ed5f5c0259a6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
e69dd3e8-17b2-5b71-a679-65a45bfa2e19 | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
1c83133a-8081-588c-9e41-75ef4573554e | note | RECORDS: Photos
| checkpoint | 17 - As-Built Drawings
99158f6c-2b7f-5cf5-a76f-fa0869deb968 | note | ACTION (Hold, Monitor, Witness): W
0fb19bbf-d006-5007-950c-98a47df1ca32 | note | DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction'
133ef5ea-a39b-54d4-883b-e8c22feb0124 | note | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
235309aa-844e-5a8b-8566-0396b0a50e32 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
bb5aaa10-7650-503c-a533-0a8d9ede4fc2 | note | CONFORMANCE CRITERIA: As Built and GIS Data
f141db4a-08fd-5206-8ef3-240b17473e2c | note | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
| section | ITP APPROVAL
| checkpoint | ITP Approval
8f491406-94ba-5b33-919a-e89b4c19cee6 | textbox | QA checked By Quality Manager:
76771dc8-f8ae-53dd-974b-278821f72d04 | textbox | Accepted By Engineers Rep:
| checklist | Generic - ITP - Traffic Islands | itp | ITP - Traffic Islands | 8d432edf-9a02-4dc2-b5a6-47ca24049b24
| section | Materials
| checkpoint | 1 - Kerb
b6b1331c-bee0-59dc-ba66-57b87ca51037 | note | VERIFICATION ACTIVITY: QA FORM
30c02fc5-83f1-5c05-ad84-bb422541657a | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
1a435718-8f7d-5a6f-af82-0cf5534e8ba0 | note | FREQUENCY: Every site
fd2fa1c0-5614-598e-91e9-46c1a9ce5d63 | note | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid
64bd602a-ab93-54e1-924b-259e5af3c9fc | note | HOLD POINT: In process Inspection
88d67bac-9b94-52f2-9fe5-1c713643d6ad | note | RECORDS: FH Concrete QA sheet, Photos
f6ac72ad-6e8c-52ef-85bb-9269b3175349 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
675ca2d7-3ec6-55da-81b2-13c6c52512e5 | note | VERIFICATION ACTIVITY: Survey
b587fd66-268e-5178-ab4b-4288e824130a | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
af3848bc-1c15-53c4-8277-f527e824e417 | note | FREQUENCY: Prior to commencement.
58f29129-6d1d-548f-b69c-0f32f35819ea | note | ACCEPTANCE CRITERIA: Survey
ea52c2c3-8c88-5175-a197-5b74c4dbb077 | note | HOLD POINT: In process Inspection
e2e66c26-7866-562f-b12e-51272e0c8dc4 | note | RECORDS: Survey Receipt.
7f76d810-4bfd-5ab5-a341-00f3cde33c77 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3A - In-Situ Concrete Island
81ea597e-97eb-5a46-a7b1-38b4f131e284 | note | VERIFICATION ACTIVITY: QA FORM
7201b883-eb67-5dfa-a49d-ae33df941fc8 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001
7629092c-acce-5a9f-a050-98abed965b7f | note | FREQUENCY: Each Site
f547a132-6bc7-522a-95ad-498613601383 | note | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm
c6c46c66-960b-5062-96c8-715354a085e3 | note | ○ CVI > 12
9a8bba41-8481-5b9d-8167-770529bb3c80 | note | HOLD POINT: In process Inspection
3a05ba5f-efe2-5ad9-afdb-c010d6d20987 | note | RECORDS: Photos
db0dd4ae-c15a-5639-8270-c2c1634f51e0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3B - Stick On Concrete Island
26f56ea0-e26e-5d42-8043-07931cbb0736 | note | VERIFICATION ACTIVITY: QA FORM
a07458e8-f959-58bb-ac09-cf9dfed34aac | note | METHODS OR REFERENCE: TDM Technical Standards - IS0002
89f506f0-4202-5e5d-b7e5-322739c7e969 | note | FREQUENCY: Each Site
01fca360-4f4f-5c3c-969a-15b5828a0d97 | note | ACCEPTANCE CRITERIA: Bonding Agent to be applied on existing surface
63ddb4b8-ae1b-5207-9c5e-99047a64eeb6 | note | ○ Mountable Kerbs laid flat to be sticked on to the existing road using Epoxy Mortar Mix.
63ec1ed4-a79b-51f1-847b-fe857882569e | note | ○ Gaps between kerbs shall be no larger that 10mm
9b345f5e-6dc9-5731-80f0-71922ac93a0a | note | HOLD POINT: In process Inspection
df5ec3be-06af-5166-aa6c-46ec16bb1e49 | note | RECORDS: Photos
264d0d2d-fda4-5d05-bc74-9ee74b5d4011 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infill
23a2fe1b-ca31-5c2a-8ed1-9dc72b55912b | note | VERIFICATION ACTIVITY: QA FORM
c3e01d96-d3d2-5818-95ce-b5253fd5efa3 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
abea870f-3419-5506-b035-c6665776aa1a | note | FREQUENCY: Each Site
cd6bd56e-b0cc-55fd-bea7-d1d065c5f1b5 | note | ACCEPTANCE CRITERIA: 150/180mm depth of 20MPa Concrete
ad3e73c8-1079-57af-b199-1e500b90f5c9 | note | ○ Surface finish to confirm with Engineer's Rep
d591df67-0f62-57d6-a229-30eb5b19dd89 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
19adb25f-1910-58f0-a721-0dfc2da68027 | note | HOLD POINT: In process Inspection
4439c73b-7ddc-515d-b2c9-3c0bf80e6fb1 | note | RECORDS: FH Concrete QA sheet. Concrete Delivery Dockets.
895da5e2-26ac-504a-b6e9-26c4072e465a | note | ONSITE RESPONSIBILITY: Site Engineer
| section | As-builts
| checkpoint | 7 - As built information
d76e706a-dee5-5dcd-a542-b1177fb5e830 | note | VERIFICATION ACTIVITY: Drawings
9b6cc1ea-9663-55fb-b68d-cf6b5532f0e9 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
b90a7cdf-3c9e-5f2e-a634-8b75636512f0 | note | FREQUENCY: Every Site
8d3623ae-d19c-5c73-a14c-f9cc0857f6c2 | note | ACCEPTANCE CRITERIA: As built drawings
269c5e51-270a-5a9f-9968-0a3f4ec5a88e | note | HOLD POINT: In Process Inspection
7492fb5f-b865-53ed-b48d-30a128c48063 | note | RECORDS: As-built records
90ec0da8-12fa-5722-a79c-73d93b62c688 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 7 - RAMM DATA
459f196e-3906-5e40-99f8-2f2c5c19ce94 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
dd577764-5f37-5f5d-914d-90e6dedd75bc | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
53204457-2828-500d-a8cc-c876428fb339 | note | FREQUENCY: Every Site
32f9d37c-004a-5e85-a0e0-94dfdeced8fb | note | ACCEPTANCE CRITERIA: RAMM SHEET
f35d9566-8cb2-503b-9934-ff9960b2c350 | note | HOLD POINT: In Process Inspection
258a79a9-782f-5858-a676-0377ccc05caf | note | RECORDS: As-built records
17e144b9-696e-59a3-a473-de66902585b2 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
36b7d6d5-b552-5438-815d-509e9fbdcda8 | textbox | Prepared by:
6704840e-23ed-5273-bcb6-899b08d23aca | textbox | Approving Delegate:
| checklist | Generic - ITP - Traffic Signal Ducting and Pole Erection | itp | ITP - Traffic Signal Ducting and Pole Erection | 2ecd5b50-ac21-4d8e-9b6e-c8170cc554d6
| section | Ducting
| checkpoint | 1 - Permits
3b5734d7-06da-5eee-9970-881157c5d371 | note | ACTION (Hold, Monitor, Witness): H
f2ee16c2-9cf6-5b13-940b-48d17495fb27 | note | DETAIL: Obtain Permits
4ba0e0f4-b961-577f-acb9-5733f6dbf132 | note | FREQUENCY: As required
80f46b79-0c99-5d69-938d-b4315c665af6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
813d294d-8542-580d-836e-16c278cd6ac8 | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and first gas permit obtained
5eafa57e-e1dc-5478-91f7-948b8e04e6a1 | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
c509cb16-afd5-5524-9a9c-6f2b0f8930af | note | ACTION (Hold, Monitor, Witness): H
ae9c463c-532e-5a6d-86ec-f87a42da12ab | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
18c590bc-a0e0-599f-a21b-ce62474ef87b | note | FREQUENCY: Prior to commencement
0e994853-a223-57ef-aae9-15179048af91 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
9f201086-355e-565a-a252-0b609587fc25 | note | CONFORMANCE CRITERIA:
ff88dcdd-df57-5ff0-bd35-3b94145a8efc | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey Setout (1)
bf7b3f76-bf53-5acf-adbf-9e08079c234b | note | ACTION (Hold, Monitor, Witness): H
16a29511-1d9b-5692-a6ad-33bcb4ad4ce1 | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
08b0ce5c-15c7-572b-b90f-dbaab33f4652 | note | FREQUENCY: Prior to commencement
0b789db4-6ab8-5f2a-8b00-5abede2e02e6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
18fe5986-b9f0-57cd-9024-46da31e75bea | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
a6326975-11be-5ea7-aec0-c6b27689137e | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey Setout (2)
14147ea1-90eb-57c6-a36c-4e609b76f071 | note | ACTION (Hold, Monitor, Witness): H
5fbc985a-cb45-549b-8879-1c71b39607e2 | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
71c82c4c-0f0e-5f95-89d0-ca6044e7ffe4 | note | FREQUENCY: Prior to commencement
0c6a45bc-1bbc-5d5a-acf1-4ccf69fa0e9a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
eb165579-fceb-5d1f-8b36-906614b3e39d | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
93220056-63f3-5c59-acb6-85d4c86e424d | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
0ce9df33-dd85-5843-85c9-865c5ab0d499 | note | ACTION (Hold, Monitor, Witness): W
170a294d-69f9-5dce-8c13-e9e3a3d728ed | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
2f167019-7e4f-5846-9fd5-c47c44ae3ae6 | note | FREQUENCY: Prior to Installation
f59eaebf-d7a8-52cd-947c-cd43c80bd7e8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
58a52e74-6900-5f81-a324-1861519a422c | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
f428f649-e4f1-5d6a-9e4e-a80315f3d3fe | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5 - Material Compliance (1)
b3e981e1-b504-5801-b590-4cb6e5af6a86 | note | ACTION (Hold, Monitor, Witness): H
214aff81-cdc6-5983-90ab-1edad995c239 | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
1abe4ac4-77c4-59b5-ab06-7d128c73cd4c | note | FREQUENCY: Upon delivery to site
597e9d72-140d-54cb-a139-f8ae92b770ba | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
d041da6b-5878-5b49-91ba-455d0819de03 | note | CONFORMANCE CRITERIA:
75f41205-b6f7-5244-905e-904ccbe36932 | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Material Compliance (2)
ad9e5cf0-5768-57c9-9916-75b5790531ef | note | ACTION (Hold, Monitor, Witness): H
1bee89ee-6f95-57f2-a434-a4dc6f0cade9 | note | DETAIL: Ensure all concrete used is 20MPa mix
4ac1184d-751d-5677-bc89-6e359def2ebb | note | FREQUENCY: Upon delivery to site
41b0b80f-0aa8-528c-b5c2-6f2575fbbf6f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
de9fba26-9d8b-516e-bde3-ef89af3129d3 | note | CONFORMANCE CRITERIA:
8ebd71fb-2fec-5f56-a59e-d3f768e21f9c | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Trenching
7f76e2b0-23e7-5849-b86a-030ac8cd5c5f | note | ACTION (Hold, Monitor, Witness): H
50735309-0009-536d-82e9-df135e9ac975 | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing)
3771b107-fc58-5f6d-94dd-f46382a08db1 | note | FREQUENCY: 10m Intervals
8a51b0e7-d741-58a1-9948-44cf0e91ae0f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
1376a80d-d528-56d0-8f28-bb69466fb9b8 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
b798af3f-aa7d-5312-b23d-e6b19c9dca02 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
af6ba2cf-6666-581a-97b2-50b60644b7e5 | note | ACTION (Hold, Monitor, Witness): H
8c1f2d86-2ef9-55b2-817f-d7dae22258e2 | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are laid at correct depths, grades and alignment as per design dwgs
6cd96e42-4653-5a8b-8861-35e6c69aab92 | note | FREQUENCY: 10m Intervals
abc08934-6594-514f-99d7-e6d167002a29 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
67c581ff-80bf-5491-a0c4-0a39a4745046 | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
52ad6a29-9aa9-533c-a423-84165512f811 | note | RECORDS: Dip sheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Duct Installation
34e867e2-a55b-5396-8904-c2d50f971d4e | note | ACTION (Hold, Monitor, Witness): W
02aa9ca1-0c85-5b59-bf1f-edd694e64bcf | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
270d539a-cb04-5575-ba16-76d81e32bb48 | note | FREQUENCY: Prior to Installation
8ec15d67-4d49-5d53-9e2b-290104551af6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
3c693cf1-dec3-5fcf-9dd2-c196f93300fe | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
5a68b619-b7b3-554f-844d-1b9133e9d344 | note | RECORDS: Photos
| checkpoint | 7.1 - Duct Installation
df50ae25-c0d8-50b7-939b-83777b3155d1 | note | ACTION (Hold, Monitor, Witness): H
187da16e-8fa6-571a-85a1-77eea1204c03 | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and Atop min spacing tables
ab3af74f-1d98-5e0d-8e31-9e0885708d60 | note | FREQUENCY: 10m Intervals
6531f0d0-b61f-543c-aaed-795d0241575c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
d5247c9b-2221-5532-be61-975f7d397ce8 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
56c374b3-5612-5042-aa8f-8261bad483dd | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 - Duct Installation
8484eec6-0725-5a1c-b309-e23f187fe9b5 | note | ACTION (Hold, Monitor, Witness): H
b4f549a3-a658-5bff-9c44-1c8724e3394f | note | DETAIL: As-built Survey
7c4c6537-f48e-5a99-888b-d06164bf3be6 | note | FREQUENCY: 20m Intervals
ccf5b2ea-819e-5df1-a0f3-628c9cf947a7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
79a6d0d1-ac5b-5db3-b765-9db0bc57acaa | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
aedf4d3b-5e29-5bc0-a5f7-85637b7c830a | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
786e7f21-4a9a-5df1-9849-e60197915b69 | note | ACTION (Hold, Monitor, Witness): H
4df2ad16-e3aa-5b97-a125-4afa6675e3a9 | note | DETAIL: Lay min. 150mm GAP<12 for bedding and haunching
5cf51500-a012-52ad-89bf-fe85f2fb26e0 | note | FREQUENCY: 10m Intervals
f94ebb91-d8fa-5d31-bddf-d84c22380415 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
0b6d3300-3860-596a-8a16-bde6ea933712 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
c7e663ee-4ad3-5e87-b197-fd9e26d117ae | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
effc4780-8506-55a7-8501-0d11461cc10b | note | ACTION (Hold, Monitor, Witness): H
df3fa227-0c5c-5272-889a-23a773e3cd32 | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
a5d9d127-9d0b-5470-b1d2-2b79cff362b8 | note | FREQUENCY: 10m Intervals
fe8729bd-da2d-55be-86fb-ce063303a57a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
cc204c6b-6fd3-5b78-b41f-7c4d7b6b09aa | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
7f5ed50e-39dc-596e-849c-99459248d153 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Traffic signal pole erection
3ec81107-ee76-579f-9c21-6d174fd573c8 | note | ACTION (Hold, Monitor, Witness): H
2299daa7-6664-51aa-a26f-d990c6cae8b4 | note | DETAIL: Ensure Design engineer as inspected pole locations prior to proceeding
b331737b-58f6-52b0-846c-0c77927a6184 | note | FREQUENCY: Per pole
c215dac7-30ac-5898-81a7-d5f93823ab45 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
251dd912-6438-5fea-acc8-018ad1b27a42 | note | CONFORMANCE CRITERIA: Sign off by design engineer
4efdfd48-c35d-5e0d-89e7-7396e57be12b | note | RECORDS: Engineer sign off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 - Traffic signal pole erection
1652bfb0-f65d-55b9-9e14-4e1574432bb5 | note | ACTION (Hold, Monitor, Witness): H
93756d7e-c93a-5178-9099-3f779c88948c | note | DETAIL: Ensure Pot hole is as per design with required depths and widths
7ec2d110-9466-5081-9ade-99979df4b494 | note | FREQUENCY: Per pole
b6d24561-ccc1-573e-a8dd-ebdba188ad66 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
a88e5ffd-7d7d-564a-895c-fa2564e4ce5f | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
7d5f8101-5a67-531c-b4c8-2e2789fcd598 | note | RECORDS: Dip sheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.2 - Traffic signal pole erection
bb6a3003-8a2c-5ebc-9d89-75eb7970f732 | note | ACTION (Hold, Monitor, Witness): H
9564b367-fd75-5cfd-b05a-51fa18d1222a | note | DETAIL: Ensure Poles are plumb and within design tolerances
aa3551cc-b636-5abd-80c5-fa2195924266 | note | FREQUENCY: Per pole
c3f1eb58-f7fb-5a10-bcdc-93b309b9704c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
0a106116-f05b-5f27-b860-0e59d44b3c86 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
2ecbd602-27fd-5e6d-9007-2799ef419ffe | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - As-builts
b092e487-5656-56b8-9fa4-b0baec5d9089 | note | ACTION (Hold, Monitor, Witness): H
b6df8043-ba37-58da-acbe-f6f8d6963174 | note | DETAIL: Red pen mark up drawings to be included in QA file
7fc23052-8b90-53d8-81df-1ac70f79db20 | note | FREQUENCY: At the completion of the Lot of work
18457e70-4ecc-534c-8f88-0cebf2c22826 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings
878f8de0-2c1b-5a86-9d32-32f83cba3de6 | note | CONFORMANCE CRITERIA:
3250c3b0-581c-57f0-8786-c3a2bc70a9f7 | note | RECORDS: As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
d392a3b6-8012-5994-a830-d61e3cbcdc8b | textbox | Drawings used for Construction incl. Rev numbers:
7cbabded-fdd3-566b-b7fa-e34eb7ea5b34 | textbox | Reference Documentation (Notices/OFIs etc):
77b34d7c-4b1c-53cb-83c2-ec51927f4fa6 | textbox | QA Compiled By:
94e5f33d-29c7-5c0e-a8e7-974fd95d6166 | textbox | QA checked By Project manager:
c25cfc0a-8890-5961-bff6-2785dd154609 | textbox | QA checked By Contract Manager:
93ffed73-55cb-5d92-8234-c8c4b0738bfc | textbox | Accepted By Design/AT Engineer:
| checklist | QA Photos |  | QA Photos | 2f5e868a-dbe1-470b-a4fa-ea5658af03f4
| checkpoint | Add photos here:
| checklist | Weymouth Construction - Mahia Road - ITP - Ducting | itp | ITP - Ducting | c461435d-266c-467f-93e4-1ec4b813646f
| section | Ducting
| checkpoint | 1 - Permits
c5ab7cd5-11cf-5d40-9f6a-948991dffeef | note | ACTION (Hold, Monitor, Witness): H
86f061c2-e28e-5716-8110-5c68a252afde | note | DETAIL: Obtain Permits
3d88a201-44b6-59ba-ace8-76d9afba35ca | note | FREQUENCY: As required
40ede74d-4006-575e-b99c-bac66c474614 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
00eeebab-1df0-5f86-ab29-84092f0117a6 | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
692bc24f-bb8d-599f-9c9d-f75f0832dac3 | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
1373f2cf-5a1e-51b4-bd3d-aef11fa2a9bd | note | ACTION (Hold, Monitor, Witness): H
5b0581e7-5b4e-5b4c-9ea7-8bd10c06c83e | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
006da8c1-bbb1-5da8-bd02-c3e1c4c65d23 | note | FREQUENCY: Prior to commencement
6186c630-08f6-5b95-9418-a7292dcbf6c6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
3aabb1fb-8208-5db2-bc2f-b26b5674212f | note | CONFORMANCE CRITERIA:
45f927bf-4bb6-534e-8273-5ba79001ca78 | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Survey Setout
189b1f2d-0429-5898-a015-aac7c117d3c3 | note | ACTION (Hold, Monitor, Witness): H
6fd2e227-6f4e-59a3-984c-ad1edba7068d | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
15271c32-681b-52c0-8bd8-b3ad0e2ab126 | note | FREQUENCY: Prior to commencement
4864b2c4-4057-5a83-9250-3ab026c326af | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
43a4bea6-92b3-5cb8-a3f2-a3e33ed5b3a2 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
15e26e17-2e2c-5bb0-bf96-773ab5ee766c | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 -
75b81d24-9ad6-502b-a481-1038a9a2a479 | note | ACTION (Hold, Monitor, Witness): H
4172c487-51d2-54e2-9d0c-09b7b733f301 | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
b823bcee-32db-5ccb-84b3-a68151558fc5 | note | FREQUENCY: Prior to commencement
5b617aef-edf4-5497-b167-1d2e4a95dceb | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
ac85d431-ab12-5329-9d1d-6175f1b8c42b | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
691a2a37-91a0-5cb8-8d5a-b5faa8e8624f | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
7da33ee6-91a5-586f-96fc-aafd8c1d1006 | note | ACTION (Hold, Monitor, Witness): W
97aa9163-056e-5ea1-9f68-7a083b6b814f | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
79bc805d-8b2b-5914-8f37-3a24bf573005 | note | FREQUENCY: Prior to Installation
a839faea-97c4-58fa-84e9-c2dcf43a6670 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
7f9db7ac-ebc5-526c-84ef-0adb2f4cfcc5 | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
d02d25ff-64e9-5ddf-85e2-b2e5224ff41c | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5.1 - Material Compliance
c22f0ff4-afa2-5495-ba79-58c0c3805aa1 | note | ACTION (Hold, Monitor, Witness): H
157a4daf-53d6-5801-95d6-dd5d737ef267 | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
86c42350-bd2a-54eb-9d15-27f51d43f7e4 | note | FREQUENCY: Upon delivery to site
f251f0ce-8ed3-5cd6-8ed3-38187ed12ac3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
a244baa4-f28b-5438-8fb6-94eb25cdda2d | note | CONFORMANCE CRITERIA: 50mm Ducts
937699b5-8230-5698-a3a4-b1aa1641c484 | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
9438b980-d66a-5487-8a07-80ce6b3dc9a5 | note | ACTION (Hold, Monitor, Witness): H
6d594c91-3982-561e-8d46-cd06a7009348 | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway
a0e5ed8c-f9be-503b-9483-3f61399930fd | note | FREQUENCY: 10m Intervals
d891371c-1438-5927-8cdd-d7f2b0c4f26c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
372f17ac-0685-5977-9e1c-70c1289f436d | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
94ba6ffa-1289-5665-8b76-10ca22aa5623 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 -
2a502064-bf50-58f1-9d52-4598cfcb3c07 | note | ACTION (Hold, Monitor, Witness): H
f68ae614-2f10-52e1-a453-f92fb01d02f6 | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
47b56f5e-183d-56c8-89fb-da38715b2252 | note | FREQUENCY: 10m Intervals
b3b89e08-bfc7-56e4-9d3b-8d99d3c42740 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
5c6af5b1-9aa3-564b-928d-01637e444baa | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
9afd833d-5e8b-52eb-8b95-074b5a04c50c | note | RECORDS: Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Duct Installation
520bd29e-6b1a-59dc-94bb-a656d62bd48e | note | ACTION (Hold, Monitor, Witness): W
558d7b78-68e2-576b-8bef-0aef9c92b576 | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
59c32466-044c-5b0b-9bd9-1ac1cc69bc53 | note | FREQUENCY: Prior to Installation
b70f08c2-7dfe-59df-8951-194d253fe33b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
3a2cbad6-49f2-5d8b-89d2-45164ad6ad47 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
44a4c2ea-4ac5-53b0-b607-10de9ee535ae | note | RECORDS: Photos
| checkpoint | 7.2 -
1af06f8a-a821-5484-9d62-91f9f58f7719 | note | ACTION (Hold, Monitor, Witness): H
723f4821-c50f-5cc6-974a-d8a13401cb39 | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
effa2a58-b040-5335-9bb9-374537cbfe0f | note | FREQUENCY: 10m Intervals
d46faa09-0276-595c-a635-dbef9aa50b82 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
4108b62f-7ddd-5df5-9b94-02aecd873db9 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
93b98b81-10fe-5ab6-88de-5da325e3c767 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
4c49b4d1-c2fe-5672-bb93-04c22a0286b1 | note | ACTION (Hold, Monitor, Witness): H
de44c03e-4b9f-5763-b604-8575a8f8bb21 | note | DETAIL: Asbuilt Survey
e0012547-7ef5-526e-b323-1613a00c2d0f | note | FREQUENCY: 20m Intervals
c36311c2-9fe6-52f0-a1a8-0429dd121c8a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
5cd34fdd-6fe7-5632-bcac-8123145f0c12 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
792cf62f-86a0-5090-9b50-15bc5fa38e3f | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
5cdfe692-bff0-5063-ae7e-b9d946dc2a85 | note | ACTION (Hold, Monitor, Witness): H
b69c09ab-b5d3-55ec-a80c-263533689a35 | note | DETAIL: Lay min. 100mm gap20 or finer for bedding and haunching
68606bd4-0148-5a75-a2ad-50d0f657cbc6 | note | FREQUENCY: 10m Intervals
eff654d6-013e-5e9f-bcfc-2dfb174ec2cd | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
921ea9ba-8540-52dc-ad8b-1dd773028ac1 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
9719cf48-31e0-5434-b663-c613d555b137 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
075193dd-1d38-5839-8d62-7e0f1b9cbc02 | note | ACTION (Hold, Monitor, Witness): H
cf6f223c-e15e-5fb7-8017-57b9650acf0f | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
ac323b51-3bf5-599e-8f05-862f68995929 | note | FREQUENCY: 10m Intervals
4f95cbff-a721-5bd9-bec8-40da4560862a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
657a081a-2a5d-5af1-9ace-afdbe03f9c8c | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
d157e430-c245-5b98-a5f6-f06ed2bafc72 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Reninstatment
34108a2f-35e9-57de-987d-25619de07ac0 | note | ACTION (Hold, Monitor, Witness): H
244f21bb-10a7-58b1-afa4-99adae7081cd | note | DETAIL: Ducts under berm reinstated with topsoil at the surface. Ducts running under any concrete structrues are carriageway need to be reinstated back to the same
da540adc-0146-5ba0-ab74-11dca839b079 | note | FREQUENCY: Eash Site
032db15f-6cd5-544c-ba46-e5370c273812 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure/Docket
86cdec97-7c67-59e0-9f66-47f687465607 | note | CONFORMANCE CRITERIA: Reinstatement as per designer acceptance
33ef5c13-283b-51a7-b972-586f920eb5e2 | note | RECORDS:
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
cd439d91-253b-5ac1-9929-98906fa174f7 | textbox | QA Compiled By:
b382a2fd-6014-55dd-96b1-5aa9b03d815a | textbox | QA checked By Project manager:
59e5e59e-5e18-54bd-b667-3ea918bd4124 | textbox | QA checked By Contract Manager:
cc91479e-63f5-5ecc-aeb0-5684a36bb9b3 | textbox | Accepted By Design/AT Engineer:
| checklist | Weymouth Construction - Mahia Road - ITP - Enabling Works - Footpath, Kerb and Channel | itp | ITP - Enabling Works - Footpath, Kerb and Channel | fe63e828-b5fd-4c2e-a258-83411c9575ec
| section | Site Set Out
| checkpoint | 1 - Site Set out
96848049-0747-5dc7-9f45-b04b8708869b | note | VERIFICATION ACTIVITY: Surveyor
b4b2ca2d-01f1-5caf-a76f-e842caa91678 | note | METHODS OR REFERENCE: Surveyor
1b073fab-b43d-521c-b08a-59ad53cbfe4d | note | FREQUENCY: Everysite
3a7a1987-cd58-5db2-a0cf-a1fc1d51e0a3 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
cc9a8914-c4c6-5548-8750-8d72b344f00c | note | HOLD POINT: Mandatory HOLD POINT -
07b9c511-370e-596f-b519-cb9e3d8464bb | note | RECORDS: Onsite records/photos
c8a96b79-b379-5afd-9da5-f484e2878826 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 1 - Kerb & Channel
936d9691-89a6-5bc5-ba9a-a36cd8a8e74c | note | VERIFICATION ACTIVITY: QA FORM
fa41c859-c062-57b9-aa02-e77ab0756077 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
68a2c501-520b-530f-9d20-dbe7b7c760f1 | note | FREQUENCY: Everysite
05fa5863-c85a-5ad7-bae2-e0124df69bf1 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (CBR>5).Concrete 20MPa @28 Days
cccbf212-c126-50cb-bca3-03cde65a1244 | note | HOLD POINT: Inprocess Inspection
725939d8-a404-5a24-821d-4772fca1dad8 | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
6077fba9-89c1-5014-8fd4-f2c0e7daf90a | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Channel Level
56cdc858-5ea3-514c-bc73-72c5f29e5028 | note | VERIFICATION ACTIVITY: QA FORM
456ec7d3-9430-59be-a130-302845385e6d | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
2d9a6e85-f44d-5871-8a36-62602230a65e | note | FREQUENCY: Everysite
908d618d-2127-52ea-ac76-c38a30dce150 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
73ffa330-a920-5821-ab40-dd853e16f438 | note | HOLD POINT: Inprocess Inspection
d0ebe95e-8e94-5e34-960f-a27507683f49 | note | RECORDS: FH concrete QA sheet
08afe1bb-a527-56b3-84fe-4f40b446d358 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 3 - Concrete Footpaths
1eaddcbf-fc6b-56be-a896-dbf2c3dc17eb | note | VERIFICATION ACTIVITY: QA FORM
7f4f6fe8-1981-5078-a8e9-aa45080a49a9 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
9db757ba-cc95-5875-af7f-0f3c65daa8a1 | note | FREQUENCY: 10m Intervals
9465c966-62d3-5962-9842-199d5d414b75 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
00a4d928-929c-5ecd-b1b1-6d3f0b51c1cd | note | ○ Basecourse - 100mm min. thickness
02c3b56a-468e-5533-b77c-5fa1ae664fda | note | ○ Clegg CIV > 12
0c8b0afd-7ffa-5506-8029-71c7b4e2f91c | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
1aa5603c-3ee9-5e52-9802-6c7453f7f43c | note | HOLD POINT: Inprocess Inspection
ad54f0d6-7353-5f42-92d0-5edd59e0fc4c | note | HOLD POINT: Prepour inspection
0166b964-42c1-5afe-9462-90d2049a4e47 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
9a893ce8-5dcc-5ac5-9144-a9366cd81b81 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Construction Joints
1fb2d1ca-1343-5b92-9202-43276ec5bd0a | note | VERIFICATION ACTIVITY: Visual
354006ae-696e-52e2-a3f7-fa2914b425c8 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0002
348b384e-fc33-570b-9a0e-21face051958 | note | FREQUENCY: Everysite
830645bc-0865-5d07-9df6-8ae1735969c3 | note | ACCEPTANCE CRITERIA: All the sawcuts to be aligned to the Kerb joints. Dowel bar 6mm thickness to be used for the construction joints on the shared path
b5e619a4-0742-5512-a515-c5c76128191f | note | HOLD POINT: Inprocess Inspection
2ddad824-554b-5bfc-bc5c-7ba1e3dbcd53 | note | RECORDS: Photos
f89c02b6-6855-5d3d-95d7-79c40e4c0a9d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Fall Gradients
fe117190-1b72-5214-8dae-478bb77dd945 | note | VERIFICATION ACTIVITY: Visual
2da29b19-f653-5732-9097-ef30d97f6c2f | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
4bcece6b-a1af-5558-95e3-bc39fef00420 | note | FREQUENCY: Everysite
bdeac491-4eb7-52e5-98f6-3d85170c74b0 | note | ACCEPTANCE CRITERIA: 2% preferred (Min 1% and Max 3%)
c75fa20f-d0f8-5993-831c-66060fc35607 | note | HOLD POINT: Pre-pour inspection
8311d52f-cd26-55cc-82c7-4c1bdf478a9c | note | RECORDS: Photos
c89a90f7-e48e-5da1-a4c2-bb05a653b40f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 7 - Grass Berms
891a3c7b-5067-556b-9e42-589bbac47c96 | note | VERIFICATION ACTIVITY: Visual
a2e53721-df37-5296-8cf0-ce2d19138585 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
ccd3f032-728d-5f35-b636-f12de205809c | note | FREQUENCY: 10m Intervals
84eb6755-d126-5860-8348-5acbfc151a46 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
82af732a-96cd-5ca5-9aa4-f288f84d6e3c | note | HOLD POINT: Inprocess Inspection
35599632-32a1-56d2-95d0-fb7ca27b7602 | note | RECORDS: Photos
322a610e-f6a6-5376-9c11-39f0712abe6c | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (1)
58ae846c-8ae6-5075-aded-a10159c4478c | note | VERIFICATION ACTIVITY: Visual
71d31abb-20f1-5641-80fc-dd47ec23bbc0 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
a35cfbdd-1509-579e-a1a9-7eb31e87388e | note | FREQUENCY: Each PX
348b8289-3f0c-5e02-a466-f516db7e33d6 | note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer.
fa74f1b7-7a87-57ee-96d4-419dfe1c695f | note | ○ Warning TGSI tiles should have 100mm concrete haunching underneath
c2066c44-f989-5812-b2b0-c252f3cbb058 | note | HOLD POINT: Inprocess Inspection, Measurement
21767062-8995-5a3a-acf8-28688b7fca57 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
a526df01-b4e9-5aa8-b32b-d97c31aeefa4 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (2)
66283c10-855a-5c2c-bbc9-7095dafead0b | note | VERIFICATION ACTIVITY: Visual
0b276594-a81f-5655-a6a0-c43904fa36ec | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
ba64472e-12a7-584d-a0cd-27e4ada7e5ad | note | FREQUENCY: Everysite
6890cfda-2a34-5b96-b917-c0fa784c93ff | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
74d92e8a-accd-5303-9886-145e0f8bf103 | note | HOLD POINT: Inprocess Inspection
f1eaf141-6a0e-51ce-af8b-9fa81ac2672d | note | RECORDS: Photos
ae2dce3e-b4ba-5f08-be32-7906af443daa | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (3)
9199592e-a69f-52bb-a3a3-9d3228e072ab | note | VERIFICATION ACTIVITY: Visual
0fda8703-a279-5a35-a5a2-f9e87466a125 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
51ae2992-d550-5556-b99e-75e83c3f50cd | note | FREQUENCY: Everysite
1cd9a8ed-b168-5ef8-822d-2e3ddc2cccfc | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
e64506cd-f114-53da-83e8-ee8d8ac095a8 | note | HOLD POINT: Inprocess Inspection
5964e790-62a0-598c-bf54-1884a2dbf9b5 | note | RECORDS: Photos
b38cb7c7-4f87-57a5-a8dd-dd0dbf87791f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (4)
37532c69-e204-5590-ac1b-03e2c5fc65c4 | note | VERIFICATION ACTIVITY: Visual
625501da-3919-5f93-b08c-b5ea43fa3242 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
3c859566-6ade-5271-bcde-b4cac6cd9f0c | note | FREQUENCY: Everysite
a5d2dfa8-0c09-5ad4-b5a6-79466c401ecd | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
dfd3e529-aa9e-58c8-8d86-851bcf7f8209 | note | HOLD POINT: Inprocess Inspection
a8a8b6c5-d024-5657-8fd0-f91396935650 | note | RECORDS: Materials Dockets
0a719033-7a33-5059-bf89-c0ef989cc6ee | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 9 - Pram Crossing
b0b0493d-173d-50eb-b8ca-078e68a8ff6e | note | VERIFICATION ACTIVITY: QA FORM
b650e797-1b61-5073-9193-3984732a286b | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
7cdf546e-899d-5796-ab35-c11338bfadb1 | note | FREQUENCY: Each Crossing
30cb8214-1bcb-5726-9830-b4e4d80aeb6b | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
e01fe79a-8844-5069-b003-94e17fedf675 | note | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
9081e882-6c6e-5cd2-a24d-3096c5857d20 | note | ○ Slope no greater than 1:12 where practicably possible
ad6a7fbf-5768-5d65-be4a-eadeaac83510 | note | ○ Clegg CIV > 12
9190214e-7971-5330-9ed1-83bd7347e185 | note | HOLD POINT: Inprocess Inspection
3ce8713d-26e6-52ff-95fb-a70a689ce0b7 | note | RECORDS: Photos
d37911be-47af-5f29-be5e-fb499eaf351c | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 10 - As built information
562156db-0947-5398-836d-89d5cf6334d2 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
ddc3fceb-41e0-5518-b634-eca95de4e971 | note | METHODS OR REFERENCE:
afad6005-6583-58ed-8ed5-4dab8fe4269b | note | FREQUENCY: Every Site
968693ae-8348-59d1-b816-33efb57b3668 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
6e49a71c-0e9d-5860-ac0c-89c24f5cafa7 | note | HOLD POINT: In Process Inspection
de8e8f1f-175e-5ad3-9279-60fcee2bbf29 | note | RECORDS: Asbuilt records
51bfa835-2cd4-5f0f-8ef2-29c7ade28ede | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 11 - RAMM DATA
1f1ad4ad-ed8b-582f-9eb3-9509a8cb96b7 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
a529e758-5546-5fe4-b3f8-31d4e6965efa | note | METHODS OR REFERENCE:
04f5b4e6-c805-58ad-aa29-f009e379a752 | note | FREQUENCY: Every Site
099316e0-2a44-5ebc-8740-c8163df11b08 | note | ACCEPTANCE CRITERIA: RAMM SHEET
6f306503-755a-56a4-930b-180b25ed4709 | note | HOLD POINT: In Process Inspection
0b017a23-7990-549e-b2a9-b2b12bc2d8b1 | note | RECORDS: RAMM Sheet
eb2d5127-bc08-57d2-85bb-53caf9b8b12d | note | ONSITE RESPONSIBILITY: Site Engineer & PM
| section | ITP APPROVAL
| checkpoint | ITP Approval
4ffb6063-e194-505f-be90-e55d7f0b2a25 | note | Prepared by: Ajithkumar Ayyanar
1e767eb2-6a41-5994-8dd3-a7f503ee71f1 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Mahia Road - ITP - Signage | itp | ITP - Signage | 4fa6065b-99e2-4b0f-820c-2098ed9b7202
| section | Site Set Out
| checkpoint | 1 - Site Set out
783f53c2-3b2b-505d-894b-2abe5ded9c7b | note | VERIFICATION ACTIVITY: Surveyor
255e519b-13b3-5109-b55a-763a7a46a8c3 | note | METHODS OR REFERENCE: Surveyor
cc07637a-d367-5ab0-8776-00c2cd5564fb | note | FREQUENCY: Everysite
36e71730-8319-58d1-8e9a-ae7b6a4948d2 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
c10defdc-cbb8-583b-be40-0353d30043c0 | note | ○ Alternatively like for like
eb0c6730-0e16-5a0f-a824-5ca60ac08858 | note | HOLD POINT: Mandatory HOLD POINT -
0bdc3286-a799-5ec6-b479-6499167aa1ac | note | RECORDS: Survey Receipt
831d3584-d41b-5da4-ac83-088786455994 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Signs/Belisha Disk
09f5f3e9-efce-5355-9f74-16bcce13a1ae | note | VERIFICATION ACTIVITY: QA FORM
866cb14e-c4fc-5bd1-9d4e-2f625dce11e0 | note | METHODS OR REFERENCE: TDM Technical Standards
ca04f91a-0466-5b7d-8e9a-c062eb8094a1 | note | FREQUENCY: Every site
16873573-110b-567d-83e3-0a67b7982443 | note | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
2391fc16-1a87-5e12-9388-89ed972ba756 | note | HOLD POINT: Inprocess Inspection
afc48459-dd47-5e98-952c-8538c9cbdcd0 | note | RECORDS: Dockets/Photos
8413b768-b88b-54fc-b689-e49ec7658259 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Pole, Impact recovery post and Ground Socket
15285099-b3cf-535d-afba-b490746cf833 | note | VERIFICATION ACTIVITY: QA FORM
843e60f2-647d-5cc5-a8bf-b31bb8020aaf | note | METHODS OR REFERENCE: TDM Technical Standards
29afdad7-6741-512e-8d07-cb6771a55e9d | note | FREQUENCY: Every site
c2dc911e-a926-5c19-91d2-d916af1c70fc | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
7ea49092-5b93-5d0e-8264-ff4d8ebec95f | note | HOLD POINT: Inprocess Inspection
71aa82f2-9727-5241-abfd-09c82d0518ff | note | RECORDS: Dockets/Photos
6cb1cdad-66af-5e3e-8983-7cdabc829d76 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 4a - Ground Socket
3c5afd7d-c1e8-50cd-a958-1b4bac9cc071 | note | VERIFICATION ACTIVITY: QA FORM
85363d50-4676-5202-abb2-5e2be86461b0 | note | METHODS OR REFERENCE: TDM Technical Standards
13c9b06f-f328-580e-b634-e2a16468d7b6 | note | FREQUENCY: Each Socket
ff6c1eea-e9c6-5eb9-be5c-0438490047d2 | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
1fbe9afb-e9b4-5ced-84d8-c94d99907c0c | note | HOLD POINT: Inprocess Inspection
1487b02e-4c9e-5ca6-b8b6-81ff34d69456 | note | RECORDS: Dockets/Photos with tape measurement
79a218ef-19ce-5cc1-b1f8-1b6160ee06d1 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4b - Pole and Impact recovery post
fdf7025f-c82c-584b-b818-4ebd54647d02 | note | VERIFICATION ACTIVITY: QA FORM
290c8d2c-7e86-5222-9d81-1720eac99cdf | note | METHODS OR REFERENCE: TDM Technical Standards
14c6892f-0458-5ef3-b15e-f1563db40e76 | note | FREQUENCY: Each Post or pole
0d41189a-079a-52c7-8fa0-01fcec73d15e | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
8b4871ca-e96a-503f-ab38-1109bad1f690 | note | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
ef43d370-2bcf-59c6-8504-eba2538767dc | note | HOLD POINT: Inprocess Inspection
f2a4d785-c5aa-5422-af97-3fdc49767c52 | note | RECORDS: Dockets/Photos
f7f10d67-e7ab-529a-9312-c91d50c5b1c5 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Signs/Belisha Disk
3c1ef5df-0341-514a-801e-9501df6049af | note | VERIFICATION ACTIVITY: QA FORM
ede061bf-304e-57e4-a730-f6992d221111 | note | METHODS OR REFERENCE: TDM Technical Standards
552776f1-2d98-5912-9fc3-242605dd08b7 | note | FREQUENCY: Each Sign
4ce19822-dd89-572e-aec4-ce84d5fc1329 | note | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
a6f65ba2-c41e-5ca8-b5cf-5546367ae82e | note | HOLD POINT: Inprocess Inspection
798d8840-0f4d-515d-8365-9fe8d404d77f | note | RECORDS: Dockets/Photos
29d99d81-1d82-5e5a-97ce-15b0152946ab | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 6 - As built information
d03af897-425b-5173-9429-adced6e73156 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
b4794797-d10d-5eb5-ac3c-12c6dcadbb1e | note | METHODS OR REFERENCE:
9abca91c-e269-5282-8ddb-8fa3e1c1e3be | note | FREQUENCY: Every Site
20dfe3f1-c97d-5bc4-8200-71a2a8ef5678 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
259226c7-42cb-5062-92e5-46c49f8e7741 | note | HOLD POINT: In Process Inspection
c00eb91b-22e8-509a-ae5e-014be024b986 | note | RECORDS: Asbuilt records
19da38e5-d839-5275-932e-f6950b0ab4ec | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
9b39b756-b87f-528e-8ef7-3c9315c1962e | note | Prepared by: Ajithkumar Ayyanar
ae13c77b-702e-5aeb-93a1-4c3596d9b945 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Mahia Road - ITP - Traffic Islands | itp | ITP - Traffic Islands | 3186035c-1722-49c7-acb5-0a0ed57a326b
| section | Materials
| checkpoint | 1 - Mountable Kerb
fe174a6b-6723-5158-8a17-3da66be3a6f2 | note | VERIFICATION ACTIVITY: QA FORM
5be71edd-df72-5ff9-9d59-9798dedd5d5e | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
05ffdd7a-d29b-5ff3-8e6e-570da65b8c9e | note | FREQUENCY: Everysite
eb13f27f-287e-5230-b8a5-287712bb887d | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
0c12f35e-2b2a-53fc-93f5-3dbaabe69266 | note | HOLD POINT: Inprocess Inspection
87b5e3b0-7889-5b24-bf8b-ebfe440aab0f | note | RECORDS: FH concrete QA sheet, photos.
e57d32b7-4b61-5558-93cb-5b523a9ae774 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
066b14b4-bfc2-576a-bc66-d04d1f216768 | note | VERIFICATION ACTIVITY: Survey
3d5e93dd-2f93-591a-a904-fef1538a6844 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
fb86f84a-5f8a-5dcc-a43e-b7f64a33a9a2 | note | FREQUENCY: Prior to commencement.
5f27d883-0058-5980-8a3d-0e1290bcdcb6 | note | ACCEPTANCE CRITERIA: Survey
66cc6992-2a4e-52f2-826a-b3c79d251718 | note | HOLD POINT: As per Construction Drawings
17d2a201-242e-588d-8566-9ab6edb1c194 | note | RECORDS: Survey Receipt.
8cdb16ee-2b2a-5bea-91eb-5deb67999374 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
6bd2dba6-569e-5de6-bd4b-ec520000a320 | note | VERIFICATION ACTIVITY: QA FORM
138ea537-68d1-581a-bc48-380bf1044c23 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
a7abd9af-82a5-5af0-b4cd-c729775fcb02 | note | FREQUENCY: Each Site
038fcaae-619d-5398-8875-a950ed690747 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
27667a82-5f04-5c55-8ecc-1efa7fc56cc8 | note | HOLD POINT: Inprocess Inspection
15eb0847-eae6-5ae9-841a-9178f1767615 | note | RECORDS: Photos
6e77a1b9-fc07-5475-acd9-b412aa8f4dcb | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
4dcd0b7f-4ccb-591c-8be3-2ffbef799750 | note | VERIFICATION ACTIVITY: QA FORM
21a4391d-50df-54a1-866a-82d9628f7e89 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
21c3e60e-5013-5739-a08f-86c57d63ebb3 | note | FREQUENCY: Each Site
c3517d4f-433d-54a6-bec8-f335ff5f0789 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
856bb750-859e-5972-920f-e3e1275febb5 | note | HOLD POINT: Inprocess Inspection
6860482e-4733-598c-999a-077100d4af05 | note | RECORDS: Photos
28302420-9c61-5692-9b9b-3a1fbbbe88a4 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
6e8a2146-c5fa-5d3d-85e1-538d723e8bb3 | note | VERIFICATION ACTIVITY: QA FORM
90e60718-aec6-598a-b584-dc4970389fb7 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
939e7332-8faa-51cd-8b78-932d566d3eaf | note | FREQUENCY: Each Site
a674be69-ed51-5e48-8f0d-e7249d09d821 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide
ae04f648-4f02-5f5f-b7e9-e8cbf6a95015 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
907cddde-62cc-5a7c-915e-14fc59dbb15c | note | HOLD POINT: Inprocess Inspection
e56cb83e-ec9a-5c06-bb34-ad42683efa63 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
6025ffb0-c8f6-58c1-b791-b782bcb51616 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
50d0a20c-6ed4-5163-9fe8-8dfc0fb0149f | note | VERIFICATION ACTIVITY: Drawings
067d36ec-3851-5ffc-bbd7-0cf15fca0e6d | note | METHODS OR REFERENCE:
ae01d63a-4b43-526d-a374-7702f1d4d6b2 | note | FREQUENCY: Every Site
c24ba52f-51b0-5410-973a-2eed5ce3f6ab | note | ACCEPTANCE CRITERIA: As built drawings
781202b4-3958-53fc-bc29-2ce30ec5372c | note | HOLD POINT: In Process Inspection
2d30cbc6-2527-5998-a74d-0f81f5fdcc13 | note | RECORDS: Asbuilt records
d2d88143-65b8-57c5-aa97-bd611d36b3e9 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
6f0586ab-c4c2-5365-a538-bcef564da5ff | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
5ee3a77a-9d97-5886-87a4-7f044bb945a4 | note | METHODS OR REFERENCE:
9c4cb526-99c1-5c18-aa8d-cda8877dc741 | note | FREQUENCY: Every Site
253ad8d1-cab8-5336-b3c4-e540e8f7b398 | note | ACCEPTANCE CRITERIA: RAMM SHEET
f7cf996d-ab63-5d1f-9e93-1fd713e2f55e | note | HOLD POINT: In Process Inspection
b63039a2-cb25-54a1-9cfb-2b5b7b857ceb | note | RECORDS: Asbuilt records
3559af44-7b26-5494-a68e-ad11a2ac8ce2 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
60cda86c-9a70-5ddb-a9a1-a1b88c0e4eee | note | Prepared by: Ajithkumar Ayyanar
be60142a-1fc4-5058-b84c-11ef05240f26 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Palmers Road - ITP - Ducting | itp | ITP - Ducting | cd112284-f56e-4c05-ae28-e8b8c96d1336
| section | Ducting
| checkpoint | 1 - Permits
87ac5ddb-faac-5cfc-8e4a-e39c0d717798 | note | ACTION (Hold, Monitor, Witness): H
e0ee80a5-f04c-5a8c-93bb-edc8a90387fb | note | DETAIL: Obtain Permits
1d5c047a-a4dc-59d5-9295-5416c4a78124 | note | FREQUENCY: As required
7cbf931c-ff79-50ad-8dbe-8919d6cbed68 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
4bc17724-b698-5a22-b9eb-a4afcb6f0bb1 | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
787b6029-d78b-58bd-bc82-8c24d51765c3 | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
056edd68-0fb7-5fd2-9c73-d19ca9e1a535 | note | ACTION (Hold, Monitor, Witness): H
713a3070-3546-588f-816e-3d5a52ce7fa0 | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
0f9c22e6-4805-5029-bb23-4bff06a3fb3e | note | FREQUENCY: Prior to commencement
e70f3948-5916-55d6-9740-ce4d4f58c856 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
299ce91a-7c9e-5df8-998a-1d282be6d237 | note | CONFORMANCE CRITERIA:
343dcc10-4096-5bb8-a68d-7fceeab81ba2 | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Survey Setout
25b63098-6689-527f-a475-87ce0bb2cf2a | note | ACTION (Hold, Monitor, Witness): H
e7b55f22-b28c-5595-b10c-c918bf670224 | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
e8681f87-5b47-5df2-a574-ac0becd88f2b | note | FREQUENCY: Prior to commencement
16272108-c899-5aef-80d4-b92ab30cbd37 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
9c75e188-1302-5190-b317-eeaa36d861cc | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
857c80cd-6ad1-5887-8bde-742f6abae934 | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 -
07c17487-42a9-545c-a44f-2f65aedb60da | note | ACTION (Hold, Monitor, Witness): H
008f8206-a5cf-5fe4-ad3e-c1f7d56c4f07 | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
011282a5-dc69-539c-9935-89b15ad79ffc | note | FREQUENCY: Prior to commencement
f4a7ba2a-5c57-5061-b633-693d0bbe03ca | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
bd601d40-2d2c-56d3-963f-686f16dc7035 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
5f8e6524-37be-5b76-8a38-6159262e317d | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
4861ec82-cf03-569b-85b0-0b209451abae | note | ACTION (Hold, Monitor, Witness): W
f9acec5e-4875-5945-a91d-c2b78d028d0c | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
8273dd72-8cc9-5889-b56d-acf6fad0f559 | note | FREQUENCY: Prior to Installation
485bde59-a4e3-5507-8fd3-22d22ec44f9c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
28f99703-fac2-5ab6-92f3-9e9e3d095738 | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
8c48ea42-4475-5e44-a1d2-203c7b3b24fd | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5.1 - Material Compliance
45f11850-1db3-5608-8085-7e44e85cfc93 | note | ACTION (Hold, Monitor, Witness): H
272a2242-5cbc-5a59-ae45-193b7421b11b | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
b7cd8bac-f64e-5c4e-bc3d-18b57a99be02 | note | FREQUENCY: Upon delivery to site
ceed8924-fa94-5130-99db-6db9238e6db3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
64002284-a910-5600-bf5d-05c70039af94 | note | CONFORMANCE CRITERIA: 50mm Ducts
c406663e-11db-504c-984a-ca90724de650 | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
e26755d7-c5c9-5750-8a85-544b7782a8a1 | note | ACTION (Hold, Monitor, Witness): H
aa8caafe-79ac-52b2-bd2c-87fd26fea574 | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway
52f0e170-ab5b-5a8a-94b4-4fd82fb8929d | note | FREQUENCY: 10m Intervals
9c5cbe83-b5c8-534f-bbe1-27792ddc5e23 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
b7fa8e10-c953-5a79-a0a0-399994d8a434 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
8550b33a-bba9-53e6-8674-730a3462528d | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 -
9b21b867-15d5-5894-b081-1e523b6e5814 | note | ACTION (Hold, Monitor, Witness): H
51b6f494-eb49-5653-8166-368d41e5de3c | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
5381ae36-b967-5804-9aca-04ca1fe48518 | note | FREQUENCY: 10m Intervals
5c9d4a69-799e-54bc-9497-fc7d7c929982 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
77336391-e873-55b5-bce1-db83f7b94a1e | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
06230039-f255-51f1-bf29-032079741642 | note | RECORDS: Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Duct Installation
2c2d5ca7-4f27-5e65-8e51-f96e17bbd782 | note | ACTION (Hold, Monitor, Witness): W
f9401567-3e4c-5300-9281-b56d7ae69dc6 | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
f2a42656-063b-5f71-8ba8-782a7c50b578 | note | FREQUENCY: Prior to Installation
821d78d9-f33d-52c6-84fd-97b1789e71bd | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
37d207ee-1c9a-5403-9f53-fd31348414e7 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
4cc1e001-6683-5eb3-8f6e-1cd0ea73f510 | note | RECORDS: Photos
| checkpoint | 7.2 -
1a6ae1b4-d526-5dff-a11d-fce5850feb81 | note | ACTION (Hold, Monitor, Witness): H
ef2f7050-c06d-586c-82ce-87f7fa56927e | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
01f135fe-4042-58d5-98dd-aada8d73ef69 | note | FREQUENCY: 10m Intervals
3aecd127-aff0-5c91-a64c-e0ce88ec9905 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
1fec1f72-cc0d-501a-96b2-43dcf6261733 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
c1a40eac-cbbe-565f-953b-f5710e1a77fc | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
580200c8-f16f-5f3e-8708-90c0467f746c | note | ACTION (Hold, Monitor, Witness): H
e0453632-f4f0-50fb-9d56-2f47a79d46b8 | note | DETAIL: Asbuilt Survey
e41fe8fe-1ab7-5445-adc8-b92e1d54ddd0 | note | FREQUENCY: 20m Intervals
8d4fcd84-28fb-519a-b735-e923caaf9ef7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
45fc1684-8ff9-5c9f-acdb-5cc6d51cb150 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
537aefe0-0ace-50b7-a77e-ae378491b02e | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
70696ad4-70c2-594c-9e5c-81fe785d0667 | note | ACTION (Hold, Monitor, Witness): H
a945d2d9-abff-51b7-b6c6-c2baa20fad15 | note | DETAIL: Lay min. 100mm gap20 or finer for bedding and haunching
db72c925-dd57-5eb1-a38b-a671f5d6ae54 | note | FREQUENCY: 10m Intervals
ab7a8650-2f76-51dd-8874-001ad7e5c3a1 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
19dd2111-55e7-51ed-a520-29e8df700f5e | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
aee434bf-44bd-537b-a3b6-cf30139dd797 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
14fee9ac-b605-5f13-a16c-8122944a16dd | note | ACTION (Hold, Monitor, Witness): H
6ab62827-cd04-5cad-8a3b-79ffe8e027e1 | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
41628328-d1ae-57ec-818f-39c76a1950da | note | FREQUENCY: 10m Intervals
39767205-671a-55be-a673-0f0e899ea6ec | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
59d9f3c2-09a5-5151-a358-06bb919d1db7 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
e97f4f21-6bc5-549f-a573-883e24bfc6bd | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Reninstatment
8096cbab-9536-51b4-a65b-768a073e01a6 | note | ACTION (Hold, Monitor, Witness): H
8f4928bc-423e-551f-bebe-cfbb2a80c6e9 | note | DETAIL: Ducts under berm reinstated with topsoil at the surface. Ducts running under any concrete structrues are carriageway need to be reinstated back to the same
eed9b7e6-4199-58bb-a0b8-7ef356468462 | note | FREQUENCY: Eash Site
bc68abf5-8c1a-5630-9463-49ae136a03bf | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure/Docket
0f5f1776-ae66-5438-a034-652fc3998840 | note | CONFORMANCE CRITERIA: Reinstatement as per designer acceptance
b06eadad-0368-589a-a8a8-cb78e6022335 | note | RECORDS:
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
97c0ab12-8efb-5da3-828d-acabd258e987 | textbox | QA Compiled By:
7221211d-bc35-551a-8ae3-830ad50f59c7 | textbox | QA checked By Project manager:
fe12e82d-7fa9-53de-a1a3-54a7ac82eb8e | textbox | QA checked By Contract Manager:
35917884-bcbc-5d6c-8000-0b708f5d064e | textbox | Accepted By Design/AT Engineer:
| checklist | Weymouth Construction - Palmers Road - ITP - Enabling Works - Footpath, Kerb and Channel | itp | ITP - Enabling Works - Footpath, Kerb and Channel | 545559bc-d335-4df1-b5a5-f17001837c7c
| section | Site Set Out
| checkpoint | 1 - Site Set out
6fbb5e43-e803-5146-9ab5-0de6d2bd18d8 | note | VERIFICATION ACTIVITY: Surveyor
73ec3169-0952-527d-a513-3c9f4d7e068a | note | METHODS OR REFERENCE: Surveyor
021baf75-fcbe-5a28-ac69-a52351ccda01 | note | FREQUENCY: Everysite
58b2bb2f-9249-5d91-8bcc-6731feda141c | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
3bd7f82c-cac0-519e-8e31-ebb144bee802 | note | HOLD POINT: Mandatory HOLD POINT -
e1c74e2c-b65a-5b9b-82c4-ad614e75c0df | note | RECORDS: Onsite records/photos
db776aeb-c8c7-5c8c-bcd0-9e621255e5b8 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 1 - Kerb & Channel
e6574596-d255-5650-a753-736a702b68fb | note | VERIFICATION ACTIVITY: QA FORM
18014137-e7dd-5c50-81f1-acfbc2a05c0a | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
c9028680-8617-54d2-b686-46ecfef6cb6a | note | FREQUENCY: Everysite
6951d833-8a4f-5344-b468-95fca65b3766 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (CBR>5).Concrete 20MPa @28 Days
46839cb7-3d9e-5c9b-8b5a-83faf3257a4f | note | HOLD POINT: Inprocess Inspection
1a1dc05b-b713-5502-83ee-790770b6424b | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
b0d1d4c7-e5dd-591c-bf25-9fb454c42da7 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Channel Level
2d45c041-414a-504c-ba0e-93b220faeba0 | note | VERIFICATION ACTIVITY: QA FORM
6d0963d8-b330-51a2-b8d9-42d8fdc861fe | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
3598aa00-d03f-5f30-b89b-4bbe480a655f | note | FREQUENCY: Everysite
611c14b4-b899-5b3c-a390-c1ab75f8a404 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
4b83d36c-cc51-58ca-9b78-2691ab323381 | note | HOLD POINT: Inprocess Inspection
841844ce-e3c0-5c7d-8273-77777b39fa3f | note | RECORDS: FH concrete QA sheet
743cefa1-e29b-51b9-9cf4-0f26544ef7b7 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 3 - Concrete Footpaths
4764375b-ba33-52fa-92cb-0b9973f00790 | note | VERIFICATION ACTIVITY: QA FORM
b77ad718-dcdd-5907-9e87-95accaf3cd59 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
283818eb-dea4-582d-afa3-f896a18f61b9 | note | FREQUENCY: 10m Intervals
0da893a1-4760-532a-89a9-44efa2893a23 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
3e51db9c-a881-545c-9018-fd3737aaf0bb | note | ○ Basecourse - 100mm min. thickness
51934837-e62d-5b03-95eb-228dfb66ce4b | note | ○ Clegg CIV > 12
1f8c23dc-0150-5f9f-bc8b-89eb0980178f | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
d38e8d72-3c89-5be9-b84c-45938119dcb8 | note | HOLD POINT: Inprocess Inspection
9cb3a87f-89ca-5f83-9d24-590cda58648e | note | HOLD POINT: Prepour inspection
60fdf6e3-ca5c-5291-8c2f-40d184bd33b9 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
915afa74-1866-5c34-ba91-0df5c3297dcf | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Construction Joints
08a293cb-3b80-5657-837a-8368040fb706 | note | VERIFICATION ACTIVITY: Visual
a75abd3f-55bd-50d4-bb90-04464f82e213 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0002
e79d2bb7-0e72-5802-ba07-2d3f45e13015 | note | FREQUENCY: Everysite
51a90bf5-7884-5553-903e-429cc7b381a7 | note | ACCEPTANCE CRITERIA: All the sawcuts to be aligned to the Kerb joints. Dowel bar 6mm thickness to be used for the construction joints on the shared path
ca1efac6-0bb9-5559-9500-6ad1fe2a18cc | note | HOLD POINT: Inprocess Inspection
2a390f13-d181-59bc-9a21-89e27d867df7 | note | RECORDS: Photos
98cba227-d61a-5c20-8561-dd090e01eeaf | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Fall Gradients
c944cae1-2c7b-559b-9893-cf67130ae175 | note | VERIFICATION ACTIVITY: Visual
f04f3da8-3d31-53dc-9893-0191c06c0c38 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
98100c3b-44d6-5321-bfe6-a9d0191d7a7a | note | FREQUENCY: Everysite
462cf4d2-2a47-5494-b1d3-ac41b29648ee | note | ACCEPTANCE CRITERIA: 2% preferred (Min 1% and Max 3%)
7aa34d42-410a-5433-9729-04128423a6de | note | HOLD POINT: Pre-pour inspection
49578548-1f75-5faa-b193-a8304289c384 | note | RECORDS: Photos
82b2f359-a2b6-54d5-a423-7c0c7200b2b0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 7 - Grass Berms
128c3e6d-6000-5dec-868d-87abf30289c4 | note | VERIFICATION ACTIVITY: Visual
20622b54-66bc-58f1-81d7-b25948603216 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
5e5117e1-e138-5767-9aaa-994769350388 | note | FREQUENCY: 10m Intervals
236fcf96-552c-5959-874d-3f2f89b4f655 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
442b4239-5ff8-592d-a6c0-9fc7ad2143f1 | note | HOLD POINT: Inprocess Inspection
6b26843e-c307-5e4f-8bfc-ad8a63181357 | note | RECORDS: Photos
e7ed6574-92ee-57fd-9114-c3be42b47558 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (1)
4142b104-bf71-5498-9f33-05d347413180 | note | VERIFICATION ACTIVITY: Visual
668279f9-e1e8-5a0a-925c-37cb0ea3d4c8 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
6947e3a9-be9f-5b1e-b646-258399c28484 | note | FREQUENCY: Each PX
4c0b4985-c492-5c94-a556-252b9c594c2b | note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer.
d7e415c0-5a52-5d31-b0a4-13b82dfb5a2c | note | ○ Warning TGSI tiles should have 100mm concrete haunching underneath
e8fe92d4-e781-57ce-bc9f-c5aa6dbc4961 | note | HOLD POINT: Inprocess Inspection, Measurement
20ec18b0-b329-5809-b609-c4e10bb5c808 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
bededd7e-c00e-5287-ad59-5d8471f36b5a | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (2)
67031294-3e15-5d9b-b571-b7b2107a5e81 | note | VERIFICATION ACTIVITY: Visual
1e1b1c13-a0f8-5173-a508-3003cc1161e7 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
5659468b-c018-5415-b6a5-ab0b54832e00 | note | FREQUENCY: Everysite
0a5885f2-a0c8-5d9d-881c-68c734abcbe4 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
bbe641e3-f1f8-53cf-809a-dda666bf823d | note | HOLD POINT: Inprocess Inspection
a728379b-83f3-5ca2-9d20-19a246d40b57 | note | RECORDS: Photos
fd78f1a5-3acc-5776-9b35-dd7333033e33 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (3)
36484a20-ca01-5b9e-942f-af550a6d84a8 | note | VERIFICATION ACTIVITY: Visual
91322380-7df1-588a-939c-28dbe6fcef5b | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
e4e73f47-5ccd-51ea-a166-b699bdd715aa | note | FREQUENCY: Everysite
2c0b7dae-4cca-5990-80db-b4fc86afb34d | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
97db0f0b-160a-5c5e-9c3d-020d6a39322a | note | HOLD POINT: Inprocess Inspection
60601f57-6852-5169-bec0-4574658a330b | note | RECORDS: Photos
68b3b0c6-578a-51e7-88a8-6b204003d338 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (4)
92b34fcd-596b-5caf-b768-79294cc4339e | note | VERIFICATION ACTIVITY: Visual
51e43a43-e9ad-57b4-8e5f-a90073da8583 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
b03ccc9c-7db3-5baf-879d-1b837d17101c | note | FREQUENCY: Everysite
b84666ac-b911-5548-be10-c0512349ca76 | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
25004537-5fb1-51d1-a42a-c7e3a908c8c5 | note | HOLD POINT: Inprocess Inspection
76da4592-6448-5c45-b9ef-71b28d4963b5 | note | RECORDS: Materials Dockets
1df9eead-262a-50ef-8b6c-eabb11f6e7f0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 9 - Pram Crossing
818582d1-61b2-59a4-a6a5-e39ff3b61663 | note | VERIFICATION ACTIVITY: QA FORM
020fa514-0a6e-5ac5-8348-779a4c564bdf | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
2f70c251-8606-53d7-9dee-bfdc0a6385b4 | note | FREQUENCY: Each Crossing
06c07ac5-2a69-50c3-a222-23c2e029bb33 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
a91f30af-ca2d-550a-89fd-433742478421 | note | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
b049b87f-86ff-5736-9e09-7081c09ad7e3 | note | ○ Slope no greater than 1:12 where practicably possible
8292caba-7dfa-5421-9e42-405c1a938940 | note | ○ Clegg CIV > 12
abc970df-2a26-5ad2-817d-c1f3cb90b3c5 | note | HOLD POINT: Inprocess Inspection
bbb640f9-3f50-58b8-ab54-0edf6c5866d7 | note | RECORDS: Photos
301defc7-9d74-55e4-82d4-aebd0ddb5981 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 10 - Timber Retaining Wall
70198eba-63bc-505e-a986-2ba20b0b9f17 | note | VERIFICATION ACTIVITY: Visual
40cc6f89-d0cc-5cfd-ae92-5fe32f2407bc | note | METHODS OR REFERENCE: TDM ST0004 - Version A, Timber Retaining Wall Detail
4e1a2d85-4abe-59f3-9805-0144e70f219b | note | FREQUENCY: Everysite
6d4ef828-1011-5774-855d-6d479d6fc55e | note | ACCEPTANCE CRITERIA: 125 x 125 H5 Timber Posts @ 1.5m centres installed with 20MPA concrete. Concrete footing to be 325mm diametre.
20e827fa-c72b-5077-bb57-f053079c7ea3 | note | ○ 150 x 50 RS Tanalised H5 Timber Rails. Provide 5-10mm gap between rails
804aaf30-eedf-5442-9932-c9672cf3b0e5 | note | ○ Retaining wall slope to be 10:1 grade.
ebbe8b97-ec4d-58b7-9394-e46b0b4394e9 | note | ○ Maximum height of wall = 1499mm.
8fa1dd8f-fcc2-5f96-801f-7d79dfe4bbfe | note | ○ Minimum embedded depth of post to be same as exposed height unless less than 300mm, then depth = 300mm.
0dca7510-a061-5f1b-b771-27c56a9f8237 | note | ○ Subsoil pipe to be lay as per TDM and connected to the nearest CP
c92f2868-2891-5933-86cc-3a70fa7cfed9 | note | HOLD POINT: Inprocess Inspection
77d275e8-c93e-5c16-a841-7bac4d8b8724 | note | RECORDS: Photos, Material Dockets, Dimension checks
15adf062-7166-52f9-b24a-b0524bd3a73c | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 10 - As built information
a0cd9137-a8dc-51be-9d1d-7aa24a506bae | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
48ee0d62-02fe-51e4-8ac1-98ec5c1d75d3 | note | METHODS OR REFERENCE:
9764b8be-55a0-5cae-b6be-891e01184fc9 | note | FREQUENCY: Every Site
3adf5a3b-2aeb-5160-a045-fe8e781f3939 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
6be55967-939e-5717-9b4a-6709636fe119 | note | HOLD POINT: In Process Inspection
504e3005-b7d4-57d7-978b-acaf452ab8be | note | RECORDS: Asbuilt records
a76dfb4b-8827-5afd-ad3f-eae1da471bdd | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 11 - RAMM DATA
1e08c428-cb7e-5183-9451-01c3dc7efc07 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
8a009a08-d339-5881-b68d-af9eef5d53ee | note | METHODS OR REFERENCE:
9842cb5b-e0c0-5498-a472-b49b23935c42 | note | FREQUENCY: Every Site
377ecb79-de3d-5035-ad20-0851cade6af3 | note | ACCEPTANCE CRITERIA: RAMM SHEET
1a27f0a0-b710-5840-bc3d-9a54e1f26acf | note | HOLD POINT: In Process Inspection
bcd314bb-f972-5715-b49a-38fa5d0b5aad | note | RECORDS: RAMM Sheet
13cf1956-8bd4-5bec-8929-0e35bce87e90 | note | ONSITE RESPONSIBILITY: Site Engineer & PM
| section | ITP APPROVAL
| checkpoint | ITP Approval
c7e2bbe4-e0d0-5fa7-8021-20881de3b19e | note | Prepared by: Ajithkumar Ayyanar
1b51dc0b-f5ec-59d9-af11-82d9a00e8104 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Palmers Road - ITP - Signage | itp | ITP - Signage | efc13daf-2942-4911-be3a-7881a99b8adb
| section | Site Set Out
| checkpoint | 1 - Site Set out
f64f24f8-3aac-56ba-b4f3-fb0c9dfff817 | note | VERIFICATION ACTIVITY: Surveyor
d836490c-496c-537a-96f7-584b5068e62b | note | METHODS OR REFERENCE: Surveyor
69a363a8-6e3e-583a-a84c-638ea5ebff03 | note | FREQUENCY: Everysite
e5c859c7-84ed-5e44-af08-0c03fc520d17 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
6afd4ffd-9a73-5038-81da-d660e38a4c96 | note | ○ Alternatively like for like
a1082aca-da44-578e-8cef-4cf4d72a9a2f | note | HOLD POINT: Mandatory HOLD POINT -
d514a795-ea21-5918-9f29-c03d6c7520e2 | note | RECORDS: Survey Receipt
a6c1237c-5b1d-5db7-81c6-c7fe03d63279 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Signs/Belisha Disk
6e52a0e4-5f4d-5c9d-a20d-e988c79608bf | note | VERIFICATION ACTIVITY: QA FORM
729278dc-37ef-5f2c-bff9-746ca9b13e02 | note | METHODS OR REFERENCE: TDM Technical Standards
4e6b3f2b-7bec-5587-b021-791616b0e7c4 | note | FREQUENCY: Every site
3f3d6026-57ae-54f7-8cd9-22040c9f745e | note | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
db85241e-78c2-57ee-b578-ea9b4326a831 | note | HOLD POINT: Inprocess Inspection
fb44889f-7432-5cf8-bf9e-8cd2e0b57e06 | note | RECORDS: Dockets/Photos
607304e2-2eda-5363-9cc9-8ac18a08fe7b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Pole, Impact recovery post and Ground Socket
d6e635cb-9070-5a7c-8759-5166092a29d3 | note | VERIFICATION ACTIVITY: QA FORM
d5649292-1ae9-5f86-a65a-24c3fada63f5 | note | METHODS OR REFERENCE: TDM Technical Standards
b11e5c8b-1af4-5a90-bace-c130fc8045f3 | note | FREQUENCY: Every site
78cbe1bc-f51f-51d8-a1ea-faf808e590c8 | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
e9a838f5-f512-5c71-917f-ecdab39bca4d | note | HOLD POINT: Inprocess Inspection
7d54ba78-cd9d-5f12-8fa0-b5bf2278dafd | note | RECORDS: Dockets/Photos
a94193eb-1afe-5f7c-9a84-5cbd39bcdcda | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 4a - Ground Socket
01a85680-e682-5ca1-a8e1-34d49b27a60a | note | VERIFICATION ACTIVITY: QA FORM
0172b7e2-8277-585c-ab97-11db5d28f474 | note | METHODS OR REFERENCE: TDM Technical Standards
c7b2fd4d-9392-5e33-8aa2-16ec0cad2f1f | note | FREQUENCY: Each Socket
ea1b6ee3-91d2-509d-925b-b6b454d21ad3 | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
9a94fd68-d307-5a96-b5fa-e5740f0e0955 | note | HOLD POINT: Inprocess Inspection
b056b44a-51de-526b-ad9d-41de1d1f52af | note | RECORDS: Dockets/Photos with tape measurement
61063e25-b95a-58a9-b4de-d61e929c7cd1 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4b - Pole and Impact recovery post
8c983a0a-bf83-5729-98c2-1fc6bec0e14a | note | VERIFICATION ACTIVITY: QA FORM
ad36abbc-59ea-500c-839e-f78c7a31238c | note | METHODS OR REFERENCE: TDM Technical Standards
912fe86d-de0b-5f12-a383-7a4440176696 | note | FREQUENCY: Each Post or pole
cf36d4ab-d0dc-5ee9-9c68-3475e485c393 | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
0d661d82-0d1b-5789-9d0f-d5fde7b320b0 | note | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
635432e5-428f-5ed7-a453-93dfec6e648c | note | HOLD POINT: Inprocess Inspection
b26c68ab-d252-515e-bd7b-d7e3736de3cb | note | RECORDS: Dockets/Photos
63b94e51-6a7a-5792-bf74-d0ea539b3a7d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Signs/Belisha Disk
1972820b-3024-5210-bf48-4ff0b0836a72 | note | VERIFICATION ACTIVITY: QA FORM
0e3a7412-3592-53a9-8cdc-ed68d8dae88d | note | METHODS OR REFERENCE: TDM Technical Standards
066274ab-4c7f-5e43-8fcc-c78153385dac | note | FREQUENCY: Each Sign
a129345a-bebd-5575-b57b-e97d5bb63878 | note | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
a11d4402-fe79-52a7-b8f3-7130429bf1db | note | HOLD POINT: Inprocess Inspection
9b23ff1e-f483-5e0f-bb58-32c9e89c3cab | note | RECORDS: Dockets/Photos
77556e56-34c9-56be-b6ca-6b1fb6d20593 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 6 - As built information
4b31a462-74b1-59ef-ba0f-39b832abc47f | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
a5ff20b9-8ba4-55a0-9f22-d951af397385 | note | METHODS OR REFERENCE:
3d74b0b7-5243-5e41-8f0a-1bac80b67f86 | note | FREQUENCY: Every Site
c26eb674-3d3e-516a-914c-14914ced5908 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
9b975f82-9acc-56e2-9bf3-b0f473840d51 | note | HOLD POINT: In Process Inspection
c32b0877-50e8-5bbd-97dd-d0bcac9ad2c0 | note | RECORDS: Asbuilt records
54d72810-5a83-537f-ad98-4442111753ec | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
0d5923f8-5a5a-5feb-83ee-857b934cacec | note | Prepared by: Ajithkumar Ayyanar
397cac36-39b5-5c11-baa2-1fe2ca158d92 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Palmers Road - ITP - Traffic Islands | itp | ITP - Traffic Islands | fc062a4c-ae42-42df-a2e7-748a1b4fe1cd
| section | Materials
| checkpoint | 1 - Mountable Kerb
1574b79b-b059-5965-8244-c0abe0aec4e2 | note | VERIFICATION ACTIVITY: QA FORM
ac82a58f-feae-5598-9f1f-63b4bbbbddb7 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
4f563a70-087b-5394-b976-9beb90d68ba3 | note | FREQUENCY: Everysite
6339b494-2682-5889-a368-6e5b40454005 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
ae72cae1-8063-5ef1-8b5d-14a3b7f6aa68 | note | HOLD POINT: Inprocess Inspection
76b6a873-19f0-57da-b70a-1a32a4159e4a | note | RECORDS: FH concrete QA sheet, photos.
88dc8494-a660-5a49-98cf-c8208483353d | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
6d33833c-6b60-5306-a8f5-8879ea98d1ac | note | VERIFICATION ACTIVITY: Survey
695ddb19-acd6-55c8-a497-c56f8ea47c8a | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
0c46a87c-0d59-5f05-be13-ae39125dbcb4 | note | FREQUENCY: Prior to commencement.
f0afd62a-481b-569d-93c4-3f45fc372116 | note | ACCEPTANCE CRITERIA: Survey
eabd0875-c8e6-5057-9a10-8be24cdb33fc | note | HOLD POINT: As per Construction Drawings
fec71435-8bc9-5192-b98b-af75042cadc7 | note | RECORDS: Survey Receipt.
681808ba-b4a6-56e8-9a97-9426c6eaa97f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
985d8752-a8cc-5f7f-95a3-763853f2261f | note | VERIFICATION ACTIVITY: QA FORM
d37b38bb-87d4-55d8-8d4a-a8477845212a | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
b9c4dde3-9069-55c9-8d51-fee12e7ab236 | note | FREQUENCY: Each Site
adef8c7a-550c-51c2-abcb-08634b972a6e | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
4d49ed79-2972-530c-a9f9-755a0abb2ec5 | note | HOLD POINT: Inprocess Inspection
39386409-8b6c-50b8-9f2d-28e88233ccfe | note | RECORDS: Photos
6c4a6e18-812a-596e-824b-2071e3783795 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
ae9e5a02-6380-50b4-96f6-9ede22c76a27 | note | VERIFICATION ACTIVITY: QA FORM
237e4ad9-3f91-590f-943c-13a55f3e819e | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
7757caed-05a4-5125-8b90-6a7fc5cc358f | note | FREQUENCY: Each Site
3a06c8f9-a847-5259-8345-6b3b80f9fa95 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
999fa942-39c0-538a-902d-77b8e44d94ad | note | HOLD POINT: Inprocess Inspection
9248efda-7f9e-5e52-bf4f-ff05f45f7ed6 | note | RECORDS: Photos
959cceb0-593b-5e56-8e0b-e2b57bfc518f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
40480d91-22b4-5a07-89b1-0c867238e2ae | note | VERIFICATION ACTIVITY: QA FORM
45fe81d2-12b8-5465-8194-115c7cf6f7bb | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
06ad5892-a3ad-5f1f-8a27-e38e198924d9 | note | FREQUENCY: Each Site
ff104520-26e0-568d-b66f-dfbabb8b46e7 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide
7fdea0cb-61cc-5a83-872f-4539676cfd97 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
908d6b78-c337-530f-b2ca-e1bcbbfcd8c9 | note | HOLD POINT: Inprocess Inspection
ab7e8efc-0856-55f3-ab95-98eaa92e8b29 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
1b943fd6-ea75-55ef-b14f-9a4c0c0f1be5 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
8e8a505c-354c-55bd-8309-b7c00d8c8bfc | note | VERIFICATION ACTIVITY: Drawings
f7062c09-9757-59e2-82e4-f269c1f694f2 | note | METHODS OR REFERENCE:
9d7d53f4-0826-5ee6-9856-5b8cfa7bb4e9 | note | FREQUENCY: Every Site
fb0bfcca-e3cc-5029-8582-5669098ab045 | note | ACCEPTANCE CRITERIA: As built drawings
9d249c01-6fde-5ef4-a4b7-48d3d2807920 | note | HOLD POINT: In Process Inspection
40cbf358-6aba-5b51-9ed6-f879a8331017 | note | RECORDS: Asbuilt records
797d12d3-7503-591d-a466-eeeedf571742 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
0c1be3f0-8460-55bd-a2b1-c56414aed892 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
ccd6c562-f58f-5b4b-82d3-9cea66021155 | note | METHODS OR REFERENCE:
d5d0ebc3-9c1f-5b05-bcd9-2427f917861f | note | FREQUENCY: Every Site
1b3e0d40-e529-5c1b-b27d-6d0b4aae2666 | note | ACCEPTANCE CRITERIA: RAMM SHEET
68152a24-3a16-5614-99a0-3d31fd3f3b20 | note | HOLD POINT: In Process Inspection
eaef7b36-0e8c-582d-b414-c13f80ff5d0e | note | RECORDS: Asbuilt records
7a5a015c-22a4-509e-b169-7bea50e7ecf2 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
7570a1e2-1892-545c-8e85-e50c08b66bd8 | note | Prepared by: Ajithkumar Ayyanar
c0973a17-1e1a-5622-947d-72e51844cdca | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Rosscommon Road - ITP - Ducting | itp | ITP - Ducting | 7f0fa349-e029-4e51-9d66-32fb3301743b
| section | Ducting
| checkpoint | 1 - Permits
4a221597-9bc0-5c8f-aa76-b99a60e57bf2 | note | ACTION (Hold, Monitor, Witness): H
d5ff6365-ba6f-5ab7-b5ed-d55333cca5de | note | DETAIL: Obtain Permits
34f0db00-e40a-54a2-9cd7-9693f7fda208 | note | FREQUENCY: As required
2380ec96-ac14-5451-97c8-fca715962e69 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
681d41c5-2f43-50c0-ac1a-1b5c4f081d52 | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
c5366427-d6d9-5c16-ab92-ed9948c2e20d | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
a5bc1782-d5a1-52ed-8c0d-72ea8bf8517f | note | ACTION (Hold, Monitor, Witness): H
79f07508-f36d-5f31-ad70-6992ef8c93fe | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
aa9ca726-be9c-549b-9a0b-76dbefaf6e56 | note | FREQUENCY: Prior to commencement
a645970c-b7df-5ed5-9c70-4e5aa3d79c33 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
31d50583-75cf-5ae7-a578-cab7c666ed8d | note | CONFORMANCE CRITERIA:
eeb69524-113d-5a80-84e7-e0503ec72407 | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Survey Setout
2a93afd3-24c3-5528-80d4-d6c394249b28 | note | ACTION (Hold, Monitor, Witness): H
ab38d576-9269-5651-88d0-d61b4cb408eb | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
8d1ef973-a301-5a41-a882-0178b3eedb73 | note | FREQUENCY: Prior to commencement
c33d2f0e-695e-5832-a7d8-ece50acb40f3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
299402f0-2e53-55bb-8eaa-4d9c74886000 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
b0c99f58-7f2c-5cdb-a344-f7aeb13bc619 | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 -
bd60b85a-b0e0-582e-8fbf-ac85eb01d6c3 | note | ACTION (Hold, Monitor, Witness): H
6bd5e31a-241f-5d8f-95db-30d472481571 | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
e503cbee-ec64-52f6-8362-07f610c2fac6 | note | FREQUENCY: Prior to commencement
f6f68020-26f1-5673-a35c-d19bf47232f7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
0df04988-95b8-50a1-9e54-008a5501c768 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
bd493de2-7b1c-58c2-b940-c853f89e61a9 | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
7113b9b2-d1f6-5c22-9b53-a3b08761cd9b | note | ACTION (Hold, Monitor, Witness): W
89b24d41-9718-5edf-bdaf-6bf40bff2e03 | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
ae4a6a12-5221-5553-84f7-2c8398608c37 | note | FREQUENCY: Prior to Installation
a2ca2205-596d-5e66-9560-64e2ee4ae46c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
6014a47d-80c5-57b4-8d88-56b01bf6d05e | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
7f2d8381-4b60-578d-a519-c7e7df76ef0a | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5.1 - Material Compliance
aed2c862-6cd3-5e49-a941-0b6dfb6b0964 | note | ACTION (Hold, Monitor, Witness): H
0666b199-925d-5493-9917-8d4168973544 | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
b79d54c7-380d-5924-8320-288f061b02c2 | note | FREQUENCY: Upon delivery to site
96367c2c-a4d2-5c45-9799-21569e509656 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
8985ed2b-e8ce-5aa4-812e-73bab90f3283 | note | CONFORMANCE CRITERIA: 50mm Ducts
e36446cf-30bc-5e69-9323-f786705c10ed | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
58e1a336-6176-5779-9bb2-47f39b5350ef | note | ACTION (Hold, Monitor, Witness): H
7a104d59-dfcf-5d30-b539-8be1bec7c9ef | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway
da7319c6-e873-58ea-9044-2146aae15873 | note | FREQUENCY: 10m Intervals
63962fb3-db87-58c7-b9b5-514a5469e329 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
e0208620-694e-5f1f-9320-d628c60397cd | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
93fc8904-6dd9-57b2-a47c-a3101f6ad399 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 -
9cf809aa-f599-5a68-b53e-f6cd70ac3e38 | note | ACTION (Hold, Monitor, Witness): H
29f645ac-19c7-5bf8-b34f-d941522bd487 | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
1d89d8d4-9534-51d3-bb0f-712859a81645 | note | FREQUENCY: 10m Intervals
2b30ffc4-1b3b-5007-a2d2-5983e55d8e31 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
bf80fa42-8a75-5ba5-ad55-fd53601d344d | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
ecf3643c-8846-59b0-b08a-9c5f540f441c | note | RECORDS: Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Duct Installation
33bda02d-20f4-5b38-a42c-8bf11a11b3d0 | note | ACTION (Hold, Monitor, Witness): W
8135dd66-183b-5045-9459-e28c80c78241 | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
d63304eb-86de-5d24-ad94-7e496c5fe561 | note | FREQUENCY: Prior to Installation
1ef96e12-163f-5544-8b19-bcbc4322e7fb | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
d530962a-4a08-5ce6-b9c4-465cbc41d6c9 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
282491a2-2df8-5caf-9769-592a5f88f790 | note | RECORDS: Photos
| checkpoint | 7.2 -
4c5cb439-9ef7-55ba-841d-6a33c2492e3d | note | ACTION (Hold, Monitor, Witness): H
6a030f02-c491-5bf8-814a-b45bd528c361 | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
3962bad5-d8bc-59e9-b322-7625086d83ed | note | FREQUENCY: 10m Intervals
b9f9d515-d031-5986-ab08-5936dae91b94 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
d0ba2a58-0058-5056-a3c0-52f1c559469f | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
ef714c03-3afc-5dad-ba76-33db5ab999b8 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
c98ec84d-e8c8-5653-bd17-133bd71a6f75 | note | ACTION (Hold, Monitor, Witness): H
bd13b432-0696-5656-b9f3-b7856200d43c | note | DETAIL: Asbuilt Survey
fe6cb270-d07b-5ae6-8893-8d2c3cb8a9a2 | note | FREQUENCY: 20m Intervals
90e79b25-c222-527e-98b7-dc64e997d985 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
b54b27ff-37d7-50ec-a68d-c35e36d40096 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
8ba697e1-e706-5e5d-aff7-1dfbcc4e46aa | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
449ea463-7d48-5760-a5a9-9c91faee65b0 | note | ACTION (Hold, Monitor, Witness): H
fcd93864-39d3-5629-95dc-c0960b026cc5 | note | DETAIL: Lay min. 100mm gap20 or finer for bedding and haunching
23391681-692d-5630-92d6-a8e909d86e2e | note | FREQUENCY: 10m Intervals
49f7b020-bb5b-5969-8ef5-55638d4a7146 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
c7d0405d-39e2-56cc-8724-d76c233245da | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
b356984d-ab31-529f-a4ab-d2050a7e3930 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
c2f3a9d3-c0e1-5ed2-9dcf-3d0736d496d6 | note | ACTION (Hold, Monitor, Witness): H
8bdcf7d2-16fc-5488-a430-1d0b9b6812ce | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
b54fd821-96ea-5783-9774-20fb5cf4c1be | note | FREQUENCY: 10m Intervals
12c84b78-6d60-5a1f-aba1-92be4e4988c4 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
9041da5c-e7f7-56c3-a541-79b8651a0802 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
d0616623-a263-5fe2-96dd-8864c97ad279 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Reninstatment
9aa1de18-4b96-5fa1-bd14-f545f1ac8c44 | note | ACTION (Hold, Monitor, Witness): H
5ba87367-d0da-51de-aedc-9221bcd3d5a0 | note | DETAIL: Ducts under berm reinstated with topsoil at the surface. Ducts running under any concrete structrues are carriageway need to be reinstated back to the same
5e3952da-ae28-5066-b2c7-402d344d2e11 | note | FREQUENCY: Eash Site
c63013aa-11fa-5aa2-8a4b-23de965d77ae | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure/Docket
a992c9fe-149c-5237-b46c-4787205ac716 | note | CONFORMANCE CRITERIA: Reinstatement as per designer acceptance
728ddd54-2667-5bcb-860d-0dc451c25911 | note | RECORDS:
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
17378975-b57f-5ee6-b14e-98d44666ce0b | textbox | QA Compiled By:
29ba0863-ee05-52ac-8303-b70583e994ce | textbox | QA checked By Project manager:
623a06a6-f1fa-5c3d-9069-4e8e959c094a | textbox | QA checked By Contract Manager:
1f81f9f3-003a-5684-911d-53d5d1e3469f | textbox | Accepted By Design/AT Engineer:
| checklist | Weymouth Construction - Rosscommon Road - ITP - Enabling Works - Footpath, Kerb and Channel | itp | ITP - Enabling Works - Footpath, Kerb and Channel | 5af6fe44-4e08-4912-a5a8-74c8bb573a45
| section | Site Set Out
| checkpoint | 1 - Site Set out
ad657e25-e5f6-5f3b-aa10-dbbb7b221141 | note | VERIFICATION ACTIVITY: Surveyor
5c8d16b6-a73f-5856-8465-abea0b823a92 | note | METHODS OR REFERENCE: Surveyor
8ddeb1c1-0c8d-5f4c-bb26-9dce66491480 | note | FREQUENCY: Everysite
55b037f3-e84b-59dd-bbb5-8c849db04a02 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
70085e01-db35-563a-86df-648b7aaa8800 | note | HOLD POINT: Mandatory HOLD POINT -
a27250e0-4a7c-5552-96b7-511efd3cff15 | note | RECORDS: Onsite records/photos
e75cb62a-48c0-5548-b592-918c87eec5fe | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 1 - Kerb & Channel
e688d384-bd51-593f-b627-f1c5234b0ebc | note | VERIFICATION ACTIVITY: QA FORM
f9fcbdb0-61a3-53ba-ad5c-c19053c45633 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
ba9d4ac5-505b-504d-bb0d-cf26c23bbef8 | note | FREQUENCY: Everysite
9db3b742-ece7-5fbb-a0d7-34edb85f1eac | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (CBR>5).Concrete 20MPa @28 Days
06c26e4e-4188-57a8-a5d0-e347a9139be5 | note | HOLD POINT: Inprocess Inspection
a347b743-aeb7-5281-a668-890f90cfe0a4 | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
37b667b4-5487-5467-bc88-8734a42fed5f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Channel Level
93e6a675-47c4-500f-b033-98723f093507 | note | VERIFICATION ACTIVITY: QA FORM
f147c23e-d2d8-5809-bd7d-7f142967d273 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
02ebee4a-baa5-50d6-a5b2-65fc5d9ca535 | note | FREQUENCY: Everysite
9d142f39-7a2e-57c7-8ff2-e380f691dff5 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
057b21a0-ff89-51e9-b88b-a73ee3ce4e34 | note | HOLD POINT: Inprocess Inspection
6f2cb095-1fd5-5207-8a1b-7124dca79df3 | note | RECORDS: FH concrete QA sheet
1d9d27cc-ef9c-5e64-8105-03d58e151d9b | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 3 - Concrete Footpaths
9335c84f-cadf-5a21-bcb0-039429112e68 | note | VERIFICATION ACTIVITY: QA FORM
9c4bcd75-48b9-521d-80b9-c1ff2471bcbb | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
1e46deca-2f91-5360-9461-de4bf216bf69 | note | FREQUENCY: 10m Intervals
c44b2cea-0847-5de2-ab22-b469fefedb60 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
272ac8d6-b03f-5a0b-bb9f-a8cac495e9ff | note | ○ Basecourse - 100mm min. thickness
d288566c-5f97-5d7f-8c4e-e521f732d884 | note | ○ Clegg CIV > 12
1e181211-1443-5fbf-928e-b576d148aa00 | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
eb8c946b-cf17-52fe-a817-86ab748843a5 | note | HOLD POINT: Inprocess Inspection
b6cb0330-3ff2-5073-bd0c-8a0a07a5991a | note | HOLD POINT: Prepour inspection
a0dedd2a-906d-56f5-b390-3c87366fee0b | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
eb6ae857-8438-5c07-88ef-fd7026bdfbde | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Shared Path Pavement
aad7e60d-2f09-5499-86be-f4db08d93b7d | note | VERIFICATION ACTIVITY: QA FORM
d8ca3500-a523-5abf-98d2-dd826a3ffb4f | note | METHODS OR REFERENCE: IFC
ad97bb8c-17da-5331-90ce-4175d8bc1a17 | note | FREQUENCY: 10m Intervals
dfef0460-9f83-5df9-b029-674c22b236c4 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
04dd2765-8a0d-51a9-955e-ae777c127ccf | note | ○ Basecourse - 100mm min. thickness
e0332ee2-e9f4-5f93-b397-476916974ce9 | note | ○ Clegg CIV > 12
805eed83-b8d4-535f-bf8c-b3645e3874b9 | note | ○ Surfacing - Concrete 150mm with single layer of 665 mesh(50mm cover) and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish
743e9b51-2856-5c5c-b9e2-c9f2a23a7af1 | note | HOLD POINT: Inprocess Inspection
4f2c5b7d-878e-5b08-978d-96e70e937da1 | note | HOLD POINT: Prepour inspection
526289c0-d291-5f29-a1af-ba7388b2bd83 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
e91fe197-2aa1-5bd3-b256-532f8e4bd2c7 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Construction Joints
71ec8d30-5efb-5939-9228-6bf75570061f | note | VERIFICATION ACTIVITY: Visual
48ffc612-7a85-5757-b3bf-0812e3c29964 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0002
ebe26c94-b68f-539a-b3af-cb37b1a97552 | note | FREQUENCY: Everysite
52ead3e4-67e5-5311-819a-385b560a4924 | note | ACCEPTANCE CRITERIA: All the sawcuts to be aligned to the Kerb joints. Dowel bar 6mm thickness to be used for the construction joints on the shared path
93364fd0-a886-5f39-b68d-eaabc1e57ba0 | note | HOLD POINT: Inprocess Inspection
c71e2f42-e887-516e-92d9-e25325d273a9 | note | RECORDS: Photos
f2f3db85-0812-53dd-9023-05f2e3408620 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Fall Gradients
423903bc-b2d7-5731-8a2f-6dd5cb26fcb4 | note | VERIFICATION ACTIVITY: Visual
40e0938d-0e01-5b42-8745-765c8d6d703c | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
f1bab4b6-773b-5d42-8d3a-f31cbe39d5ec | note | FREQUENCY: Everysite
da8bd5f8-f7e9-5985-bad0-d0c9d34c92fd | note | ACCEPTANCE CRITERIA: 2% preferred (Min 1% and Max 3%)
af995dfb-f397-5335-ad1d-1781bc4c46f4 | note | HOLD POINT: Pre-pour inspection
042c2dea-9881-5f30-b2c6-008be1e15052 | note | RECORDS: Photos
36bd5157-5ab4-53d5-8289-679eb34f8684 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 7 - Grass Berms
6a34858d-af78-5f5f-b57b-4fb0b8a8e9c7 | note | VERIFICATION ACTIVITY: Visual
24adfd9a-7599-5e49-b464-f94338f216fe | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
d7279d7a-1472-5fc3-b1f7-5a5b9cff34a7 | note | FREQUENCY: 10m Intervals
3aec6760-d1a0-5da1-b248-817ac387d4dd | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
7f1f77de-eaa0-550a-a3f5-9b40c662ff94 | note | HOLD POINT: Inprocess Inspection
55332ac3-5cb5-57a9-bfdd-ac061412df1e | note | RECORDS: Photos
6522c511-f49b-5c3d-a4e4-80e8b5c93a14 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (1)
cfb198ad-48f7-5300-9869-58044bf27ea9 | note | VERIFICATION ACTIVITY: Visual
cfed74a5-0387-5488-9d6b-588aadb38edb | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
67db75c0-125f-589d-942f-b5eb804dad47 | note | FREQUENCY: Each PX
850aadad-14db-5eba-800e-71b5640445ec | note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer.
d940eee6-a21d-5568-80ee-3efa06e215e4 | note | ○ Warning TGSI tiles should have 100mm concrete haunching underneath
b20fd525-d0fd-5bc7-b892-11ca36444199 | note | HOLD POINT: Inprocess Inspection, Measurement
c71cc9c4-f939-5cc1-81fe-9fea4cf75695 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
9a876590-bbcf-58a3-8785-5994b6848c7f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (2)
c2cc17d0-e899-505d-96c1-5cfbeec0a5c2 | note | VERIFICATION ACTIVITY: Visual
45e7419d-c87d-5fb0-94b8-67856ccb9cd9 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
68cd3f1f-4465-5f1f-b0d3-69c2767f9c05 | note | FREQUENCY: Everysite
69088a0d-0ebc-56a9-91ff-05524584f728 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
a6248d3a-b139-5e1e-bb37-cb478f68f79b | note | HOLD POINT: Inprocess Inspection
6038f1ab-741a-58e7-84f1-273eb6aab868 | note | RECORDS: Photos
46d8b2b4-d560-56ab-b818-8e01b199171d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (3)
d7714dbe-cd83-568f-83c9-1bd9e54dace2 | note | VERIFICATION ACTIVITY: Visual
47eb83a7-a595-5db4-9a0d-dde606dce3c1 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
25d45751-f512-5d20-a156-029016ca818d | note | FREQUENCY: Everysite
13e50a40-3a61-5d74-86c7-1c763666fc53 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
c4c346d1-ac49-59ab-ba87-fbc8603472a2 | note | HOLD POINT: Inprocess Inspection
63f762b6-8e76-5312-bcc7-5cdfff3e1c0f | note | RECORDS: Photos
f29fd258-460f-5a3e-bfc6-aad86e56698c | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (4)
162eb682-ba17-5318-8af1-ba7cdfa888c6 | note | VERIFICATION ACTIVITY: Visual
880ff57c-0324-5405-ba27-aa39e461d762 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
3210675c-870e-5fae-8499-00a75f1c3a72 | note | FREQUENCY: Everysite
9f1b9715-0272-5fb7-8d09-f168c6e15eb5 | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
c905bfc0-a3b6-50df-b904-0d4fe3595ec5 | note | HOLD POINT: Inprocess Inspection
b7760072-e8a5-5afe-b9f9-40e4eb3a7668 | note | RECORDS: Materials Dockets
371f1269-60e2-5135-9018-d9a63b63e364 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 9 - Pram Crossing
5b575850-84f3-5845-aca8-3ffae2ab42ba | note | VERIFICATION ACTIVITY: QA FORM
89d89e25-3092-545b-81ff-876daa76b115 | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
587e518a-8925-540d-90d1-05a0e2e50b54 | note | FREQUENCY: Each Crossing
d6dec8f1-c088-5ab6-bedc-c8f54aa11603 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
0244e018-740c-512b-8b20-4a5671ffbc82 | note | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
49bbe417-4902-5b93-b6c7-2c8bf94d640f | note | ○ Slope no greater than 1:12 where practicably possible
df304344-02f8-53f3-b1a8-c5e6356f782d | note | ○ Clegg CIV > 12
2f3739ba-7c06-52ff-9d11-a43489e0302e | note | HOLD POINT: Inprocess Inspection
cda5d1e8-d294-5ee3-9332-c58857fadf2f | note | RECORDS: Photos
60e3d030-c38b-5962-b719-a402335001ba | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 10 - As built information
f5623ea3-0c6d-5806-a95d-037ad9c33441 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
a38fbf3c-acf4-53f8-9078-74ba87459830 | note | METHODS OR REFERENCE:
bc56d303-2715-5640-8815-1f9e6343fd3c | note | FREQUENCY: Every Site
39fa6c41-e1f7-5d4d-b2a2-3d575879440d | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
4cb9ca49-a036-5cd0-a265-cb41b1ab3219 | note | HOLD POINT: In Process Inspection
df5f59e0-d413-5f40-b656-c0c93d6d480a | note | RECORDS: Asbuilt records
88e44dc6-d4d5-503a-9d95-632c432ab58a | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 11 - RAMM DATA
a1f831ae-3a4f-50cb-b248-5b094abf7d65 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
90139ece-d80c-5d4c-9e73-63215f7de54d | note | METHODS OR REFERENCE:
cb1e4fed-8cc6-549a-a9a8-7b019000ee75 | note | FREQUENCY: Every Site
26a4791a-bb80-51ff-9e7e-8cd902a1c77f | note | ACCEPTANCE CRITERIA: RAMM SHEET
eeb595d6-d254-5817-ab29-ce79790e0656 | note | HOLD POINT: In Process Inspection
0988b582-7897-5a2e-8651-939f0ac237b0 | note | RECORDS: RAMM Sheet
d3638afa-1a74-553b-a5bd-c8f6cd2e40ec | note | ONSITE RESPONSIBILITY: Site Engineer & PM
| section | ITP APPROVAL
| checkpoint | ITP Approval
d82b09cc-807d-5de2-8a2d-5f9957bf8862 | note | Prepared by: Ajithkumar Ayyanar
a232d79d-3af9-5b8a-8387-a2123dde2523 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Rosscommon Road - ITP - Signage | itp | ITP - Signage | b834e4ec-957d-457b-ad64-4c3b900b2ab1
| section | Site Set Out
| checkpoint | 1 - Site Set out
91e591c3-eea4-53e2-bf7b-5b45dd0311e6 | note | VERIFICATION ACTIVITY: Surveyor
081a38e7-0450-5d3d-9649-8d30af5ecf1f | note | METHODS OR REFERENCE: Surveyor
9e9590ce-ffd3-57eb-a587-a13f8acf76ea | note | FREQUENCY: Everysite
97ba3b04-1a46-54af-9db4-33fb594f8cf0 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
fc97f051-9ebe-5bbc-bfe3-65a4bf736ae8 | note | ○ Alternatively like for like
0c4cf3d0-0507-57a5-a339-77c806d54c5d | note | HOLD POINT: Mandatory HOLD POINT -
912b2c61-2db0-57a1-8ffb-361eb8151b13 | note | RECORDS: Survey Receipt
2498ddc5-f96f-527b-80b5-ca132f2a89f8 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Signs/Belisha Disk
fa5e5290-8a4a-5b2d-a5da-0c4365eff2a5 | note | VERIFICATION ACTIVITY: QA FORM
4dd16ce5-32d5-545e-81f3-7b0a064a4896 | note | METHODS OR REFERENCE: TDM Technical Standards
1caf06e4-d3ec-52a6-8832-9ee94755872b | note | FREQUENCY: Every site
9cf8cc79-a179-5685-94da-8eebb904bf0f | note | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
702b33fd-135e-572a-b14f-eefbb1703ba3 | note | HOLD POINT: Inprocess Inspection
b82e81b3-7772-5dcf-962b-19ff9c2313ca | note | RECORDS: Dockets/Photos
1e122543-13d1-5e58-8e16-fef8b950c3be | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Pole, Impact recovery post and Ground Socket
67748084-11f6-5da3-a7cc-bb0462a1dea5 | note | VERIFICATION ACTIVITY: QA FORM
efe4453c-bb77-539e-a9bc-b31104890154 | note | METHODS OR REFERENCE: TDM Technical Standards
d40d1b5f-5741-5dab-9d4e-49d13d990971 | note | FREQUENCY: Every site
763d897d-4042-588f-9606-e94fbb4294d4 | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
917ac5f8-90e2-5445-b50b-b3438bfcadba | note | HOLD POINT: Inprocess Inspection
269db4d3-7c3f-5d09-b54d-5664a4ee1eea | note | RECORDS: Dockets/Photos
ac8819df-2b5e-5664-83cc-b529f2b043f1 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 4a - Ground Socket
2b873446-0557-55db-899c-aa75472529de | note | VERIFICATION ACTIVITY: QA FORM
e8240590-7dec-5962-b838-fa38d2f6d0f8 | note | METHODS OR REFERENCE: TDM Technical Standards
8cf0caea-b44a-5749-9a96-7a3f188b126a | note | FREQUENCY: Each Socket
f2f04472-2ed0-57da-9fd4-6478faa7aa39 | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
02497600-a14f-548c-8f62-a597765a4433 | note | HOLD POINT: Inprocess Inspection
6b49a861-e9b6-5346-a359-0abc2f1f077a | note | RECORDS: Dockets/Photos with tape measurement
d81f4a07-0ece-54d4-8dcb-60e1b7d73c76 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4b - Pole and Impact recovery post
5162e6df-ed97-562c-a502-7b0aa603b10d | note | VERIFICATION ACTIVITY: QA FORM
ec373dd9-02a5-56bb-bae7-eb4ab5e07eb4 | note | METHODS OR REFERENCE: TDM Technical Standards
91182b53-93ab-509a-8f49-03b3edf4b287 | note | FREQUENCY: Each Post or pole
2c9bce8e-f56b-5e5e-8efc-9ce14a57e3ab | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
4e53f6a7-71b4-535f-833b-a52b80773364 | note | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
71889895-1fcd-50bc-9c8b-41458e3c41e7 | note | HOLD POINT: Inprocess Inspection
33cb9fda-d699-57ae-948f-8c1049d58140 | note | RECORDS: Dockets/Photos
d96c2760-46d5-5359-a037-7f3eca2bec40 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Signs/Belisha Disk
c443bc2c-14fd-54d9-b641-b425deb78258 | note | VERIFICATION ACTIVITY: QA FORM
afc7a1f7-01e2-5d28-9d84-f7d8132a94bd | note | METHODS OR REFERENCE: TDM Technical Standards
69a2cde0-c1dd-5772-a835-9b0050efae8c | note | FREQUENCY: Each Sign
92befb44-210a-58ba-bd6f-eb6dab66e17f | note | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
581bac7b-a913-5f99-82f1-019ee62665f7 | note | HOLD POINT: Inprocess Inspection
29d3b6a2-74f7-526c-851b-ede102700419 | note | RECORDS: Dockets/Photos
9e80646a-ba4c-5a3e-a862-2b07963e8f2b | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 6 - As built information
75e4ce3c-6908-5ec6-99d8-bc520f5f9264 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
a21fbd9e-2fc6-56d6-aacc-ef2addcb4c6c | note | METHODS OR REFERENCE:
3754a573-fe01-5d08-aef0-2f27f0c06a18 | note | FREQUENCY: Every Site
0fa5be3f-44ac-5ee4-afba-90f5fd0cb101 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
4cc85ad9-05a9-5445-ac36-49682ba7002d | note | HOLD POINT: In Process Inspection
2e2e7499-f534-556d-b4fe-6ef197b2795e | note | RECORDS: Asbuilt records
9a77713a-e213-5bc6-b6cb-2136d42ef612 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
b2f0ab71-1eac-566a-a618-5e23e7f24490 | note | Prepared by: Ajithkumar Ayyanar
66555f31-9353-53f9-ba6d-0c98daf7fbd2 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Rosscommon Road - ITP - Stormwater Drainage | itp | ITP - Stormwater Drainage | 44a38bae-26fc-49a0-92c3-7197341c1660
| section | Stormwater Drainage
| checkpoint | 1 - Permits & Services (1)
45ef7703-effe-548a-a1f2-746e2f96ce56 | note | ACTION (Hold, Monitor, Witness): H
e067f26d-e47e-54de-9c27-572079b4e029 | note | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
2e806ee0-2412-583e-8f9c-ef6567860495 | note | FREQUENCY: Prior to any construction commencing
d4a677c7-5051-51b4-b609-05e7f1d7c275 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
112943d8-d6dc-5cef-bad4-b65e62c29728 | note | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work.
bc3de477-1d17-5a49-b006-e3e51aacef62 | note | ○ AT Access Authority approved and signed by RCA Authority
0538e900-4074-5c89-81ac-7ed7b540a0ec | note | RECORDS: Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (2)
d1736ff5-3b6a-5d02-8e80-b9a4ee042d3f | note | ACTION (Hold, Monitor, Witness): H
40796680-a219-5ded-b4f6-d52210916d5c | note | DETAIL: Locate and mark out all existing services
d9eabb99-0403-5fba-a6fd-39e6100ca4af | note | FREQUENCY: Prior to any construction commencing
cf7fb2a2-381a-55c7-967e-141ca07cdcea | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review):
f9d17918-aed8-5db8-b8d6-91a0e718524d | note | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols
d2e3da43-0f92-51ec-bbf1-24363067f580 | note | RECORDS: B4u dig plans & GPR report attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
174eef8e-2bbd-50ba-bfb9-1cc96c3dd403 | note | ACTION (Hold, Monitor, Witness): H
02e24a0e-2997-57c9-95ef-9f8001e71b88 | note | DETAIL: Sub-Contract and Supplier Agreements
200f994d-d1b0-5a79-a97f-01e88fa86fcd | note | FREQUENCY: Prior to commencement.
1a6ac4a7-500d-5af9-ac44-68b25ba3228c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
0c12f079-680d-50cb-a914-de6c88b4a4c6 | note | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
6978a445-9a72-5991-afa6-b258014b3c6d | note | RECORDS: Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
f32ebffa-ff95-588a-8ec3-faf9f15c9f5e | note | ACTION (Hold, Monitor, Witness): H
5884806d-5434-5c69-871a-93741be97931 | note | DETAIL: Design is approved and Drawings are of the latest revision.
d30fe687-b521-5d68-8b42-88707da45c99 | note | FREQUENCY: Prior to commencement.
3bee52dd-8b56-559a-84ce-93b8e341779e | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
a66140bf-8ef7-5922-b2c1-f061637a02cd | note | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
a2d83bf4-f8e6-5df3-8409-dff8bd005db1 | note | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
b0397d17-8d83-5953-8f15-b99ad1838ff3 | note | ○ HOLD POINT of not issued to IFC.
c0c0844f-6dfb-5736-a48a-1615c5f0d4fc | note | RECORDS: Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Setout
172429f5-2a61-5a1f-911d-74d75a917746 | note | ACTION (Hold, Monitor, Witness): H
11ac8c2c-d258-5ea4-ae17-65ac6a7f66f8 | note | DETAIL: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
abeffc44-8bfc-5c3e-8933-45909ef448a4 | note | FREQUENCY: Prior to commencement.
fc6abf30-de75-5465-8f35-51e6d044618f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
97ceca21-2a2e-5cd4-b56e-1aaf09057483 | note | CONFORMANCE CRITERIA: As per Stellar Engineering Drawings: 2789-C3060 or setout files
a0c178cc-12a4-5434-b6e0-d2caba700076 | note | RECORDS: Survey Receipt.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
054f02d8-1890-5d51-88a5-c22e56cc2f69 | note | ACTION (Hold, Monitor, Witness): H
0454d2e7-3788-5f7c-9cfe-829937b8acb6 | note | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
91ffff7c-2bbb-5e38-bfed-5de2b8b6d2c5 | note | FREQUENCY: Prior to commencement.
85a6a3b3-1357-5b0e-a10c-790d06aa9cc7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
3329fd54-5558-55fe-9fcb-fcc4cf9e762d | note | CONFORMANCE CRITERIA: Pipe shall be
e414fe3d-cc69-5bc8-8d91-6c97af992b9a | note | ○ Check for freshyly formed pipes and return if required
48431ef2-c1ef-506b-8c3a-bd042029ab7e | note | 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058
aa0d8d2f-7edb-5c88-bbfe-53f870be4c8d | note | 2) All Concrete RCRRJ pipes to be fitted with Rubber rings
aa8e44ff-523c-5d6f-9dd2-2d0c6e75286e | note | 3) Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
7b87e185-1402-55bb-a4a9-b1a7f36945dc | note | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
2f25addd-55c7-5e63-b272-94bd20f4f100 | note | RECORDS: Manufacturers Data Sheets, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
50a1c066-0b87-56b7-b1f5-ab914a0bb562 | note | ACTION (Hold, Monitor, Witness): H
3c814e2c-7714-5c5a-b22a-c68f0280e0c9 | note | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
4a07b826-fccd-5595-91ce-cef90037590e | note | FREQUENCY: Prior to commencement.
91998f0c-84b0-5525-979d-e8ed0d95ad7c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
6b32e11a-d3fe-5266-b737-5b3295446b4c | note | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
b8da985e-a33c-5019-883a-a5d55be951e4 | note | RECORDS: As-built Drawings. Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (1)
92a1fd0b-01bd-573e-ac4d-985e5df2e6fe | note | ACTION (Hold, Monitor, Witness): H
54b4b7ae-d18b-5f61-bb0c-9990fcc0a7a9 | note | DETAIL: Excavation methodology
64a00bde-debd-5f01-8ed2-343160804a65 | note | FREQUENCY: Daily
6793c19b-c048-5e0f-844e-506f3d4497d7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
f86ea05f-7bb2-5413-a393-9c6fcf681a6b | note | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
04cf1eaa-38c5-545b-9f61-db13d055e9ea | note | RECORDS: Prestart RCP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (2)
530e34f0-6c14-5fc0-bd5e-95d1aaa6f161 | note | ACTION (Hold, Monitor, Witness): M
63ef0df0-cb2c-567d-a0fd-364fa3097369 | note | DETAIL: Trench Profile - Width
4b76146a-b823-53c2-b82c-99c8507ca6a8 | note | FREQUENCY: Daily / as trenching takes place. Different depth methodology
3474aad9-4db1-5159-8e67-e6069a6450a4 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methdology
6851eb76-458c-5d98-8462-f5be7db3df46 | note | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
5b9553fc-c013-5479-899a-d93b055eef75 | note | RECORDS: Construction Photos
| checkpoint | 7 - Trenching & Excavation (3)
b9be021f-c196-54e8-ac52-bc759134bc13 | note | ACTION (Hold, Monitor, Witness): W
9ecc1708-de6c-5bc0-877b-60bca2bbbb61 | note | DETAIL: Trench Profile - Depth
2773f667-4c70-577b-9965-8c8b0dd6db0f | note | FREQUENCY: Daily / as trenching takes place.
dc96d7e7-629a-5d4c-9477-58e47477e0ea | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
1fea4f9e-53e7-57ba-8888-39c6efb19a78 | note | CONFORMANCE CRITERIA: Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
9bc5012f-a423-504e-850f-080aba509e3b | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
4ad623f9-9d37-5b9f-9b83-9f9ec310cfec | note | ACTION (Hold, Monitor, Witness): W
0b460172-59d5-55c5-ad23-80b98b2f784d | note | DETAIL: Placing and compaction of Bedding Material.
f1fad383-2045-50fd-9bc8-f6e882ac7186 | note | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
f6f17a13-2221-51ce-b9bc-f68083c72631 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
6a88b4f7-6ba1-5d5d-975f-55781a081765 | note | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
1860770d-bffd-5920-a5ef-1ad81a1944c6 | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 9 - Pipe Position Tolerance
08113572-acb6-574c-8717-e78aee899e6c | note | ACTION (Hold, Monitor, Witness): M
78ef0c2a-e891-5e3d-b5ca-c0faa59ce0c6 | note | FREQUENCY: At any point of pipe
cc4d2c14-5aa7-5bd8-a665-3b8a59f07e73 | note | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
a2d37038-331c-5f9e-8a2c-0abe1901f5e4 | note | RECORDS: FH Drainage Line Record, Survey Data.
| checkpoint | 10 - Trench Backfill - Placing & Compacting
f2241d25-a121-5f1b-8b3b-cd1f277d17ee | note | ACTION (Hold, Monitor, Witness): M
2f3937d5-4785-5d60-aa82-366116bb4f8e | note | DETAIL: Placing and compacting of Trench Backfill Material
bee91f60-91b2-5e30-88ee-24667b0525fe | note | FREQUENCY: Throughout Trench Backfilling operation.
68e3067e-3c1c-533f-a8db-c820c4c3c0e1 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
bf141f95-003e-5628-81ec-cdfbfe28de39 | note | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
f0880356-bf8f-512c-a81c-03acf7dacba3 | note | RECORDS: Construction Photos
| checkpoint | 11 - As-Built Drawings
f5a7f5e5-afc0-5180-b1d4-0224ba00765c | note | ACTION (Hold, Monitor, Witness): W
538968df-bf0f-57f1-99b5-e04bb7ae68ad | note | DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
243dcbc4-8c12-5292-9c05-a3e5b74f5329 | note | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
18a8c7a8-04a4-58d2-b2bc-5be6af6309f2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
2bae34b0-ae97-5e8e-9077-f67b69c0ce34 | note | CONFORMANCE CRITERIA: As Built and GIS Data
e73f11a6-0366-50c7-b49b-cff027f337c9 | note | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
| section | ITP APPROVAL
| checkpoint | ITP Approval
5bb41e59-87e5-50d3-ae37-5393e0105fe6 | textbox | QA checked By Quality Manager:
f60c1b92-747d-5654-9d35-56c7303d03de | textbox | Accepted By Engineers Rep:
| checklist | Weymouth Construction - Rosscommon Road - ITP - Traffic Islands | itp | ITP - Traffic Islands | 45426574-f069-4464-b547-fcdd8f961101
| section | Materials
| checkpoint | 1 - Mountable Kerb
7dfcc24f-c123-5e79-8c1a-e4a7f9fa491a | note | VERIFICATION ACTIVITY: QA FORM
eb165097-4e47-5fa0-8ef4-73163f2cfcd9 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
b9fb4e4d-1a45-5ac1-b245-b1df92cc2c7a | note | FREQUENCY: Everysite
f6e76216-ef90-543b-978a-aeafd8613b97 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
f3e94928-dce3-5324-a3ac-a280c2397651 | note | HOLD POINT: Inprocess Inspection
ede2b78d-88ef-58cd-8879-b2e1fbb7ee4b | note | RECORDS: FH concrete QA sheet, photos.
e02d037f-634b-5a88-b1fd-79f8f39f93cd | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
20255afe-fd57-5095-9b48-3fe9320dfea9 | note | VERIFICATION ACTIVITY: Survey
1d6df150-ae37-5932-be5e-840f59b8f2b2 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
5520b1f2-7052-5f84-b3ab-874b69b53644 | note | FREQUENCY: Prior to commencement.
7ce61fe2-22be-55b9-b37c-23fac4e52b4d | note | ACCEPTANCE CRITERIA: Survey
2e9860e0-ae89-5227-bfb5-13a28c3ffd61 | note | HOLD POINT: As per Construction Drawings
466c20a2-1bcb-590c-8faf-f528af527e34 | note | RECORDS: Survey Receipt.
8c09ae75-d425-51bd-8c3c-81a17494938b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
c011890f-5237-5268-b369-1c11454d3683 | note | VERIFICATION ACTIVITY: QA FORM
e92b3ff4-3bea-5c41-9f72-1c0e5cfe9125 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
9a1e417d-d3c8-54e9-94cb-889ad7e9b71f | note | FREQUENCY: Each Site
3ee86d5b-9395-5a5f-9891-9e321f7d6085 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
77cc449d-7ff2-514a-82cc-6ff26a4ebe1e | note | HOLD POINT: Inprocess Inspection
e5b7d5b3-fde8-5a2d-8c76-af02af1308a8 | note | RECORDS: Photos
416217ab-8d03-5eb9-b1f8-18253d76d1fe | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
9ad4eb3e-3b98-56ba-98b2-76da4597dad6 | note | VERIFICATION ACTIVITY: QA FORM
782882ba-bc06-51e0-b254-04e0c8162723 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
941793cf-3fa0-54ac-8d0e-b49fafb63e21 | note | FREQUENCY: Each Site
ce05fd15-86d7-597d-a773-e6b87627c517 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
cf6c953b-398d-5d50-8540-227d6b62a2ee | note | HOLD POINT: Inprocess Inspection
6461118a-93b9-5da0-864d-1ca8af4c6cac | note | RECORDS: Photos
040ff9f4-2440-5e2e-b527-429e96c383a7 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
cf053852-6eae-5b05-9efd-759e500e4212 | note | VERIFICATION ACTIVITY: QA FORM
bd8d163f-aa2e-534f-8cb2-8ba278a58c55 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
d20ce8a5-f21f-5d75-a35c-c5557ab9d630 | note | FREQUENCY: Each Site
c7e107db-3f3f-570f-a20d-cff3dba2ee2f | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide
b9bfd73c-47ab-5f73-95df-8192dabb5748 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
0ca10de5-2512-5e65-abf1-0351819fd25e | note | HOLD POINT: Inprocess Inspection
8ba69030-4c59-5457-b285-40c0d603369f | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
aac44e50-fe33-5ba6-8d8f-263f8abf5e86 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
3badcebb-464a-59cb-9169-7c22035ef4a4 | note | VERIFICATION ACTIVITY: Drawings
7bd0ee5f-5c01-5c0b-9e5f-7d34f717e2a3 | note | METHODS OR REFERENCE:
a4d22258-19bb-541a-af9b-c5092afcf925 | note | FREQUENCY: Every Site
208bceaf-92b9-5e6b-96dd-43a9cb212c48 | note | ACCEPTANCE CRITERIA: As built drawings
0d8a160c-ac1d-57b6-975f-db29e2b8ff4c | note | HOLD POINT: In Process Inspection
fb07b86e-e8b7-5f08-8494-f8bd1b8ecac9 | note | RECORDS: Asbuilt records
e6bf600b-2eb9-5e6a-8728-29fe89200799 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
2f108d70-6277-51c6-8f57-1fbbee3dd22a | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
77f52180-3579-53ea-8f88-72f3f05a6b0a | note | METHODS OR REFERENCE:
a0283409-ad63-581e-bc2b-5e45bc5cd3ec | note | FREQUENCY: Every Site
b5403cd6-0edd-5df6-b7d0-e5f8ef4ac2ed | note | ACCEPTANCE CRITERIA: RAMM SHEET
54b6908b-0c47-51e9-9001-4abf099e7071 | note | HOLD POINT: In Process Inspection
af51f6a8-bd6b-5a7e-8c02-20528150788e | note | RECORDS: Asbuilt records
f5178392-8e0f-5ee0-a541-308950276057 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
27ebe6f0-eeac-55de-86a5-71f1b6e03595 | note | Prepared by: Ajithkumar Ayyanar
830874c5-ed76-5f1e-8d7b-00835a0fbd9c | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Weymouth East - ITP - Ducting | itp | ITP - Ducting | 9db362c6-2ff9-40b7-bf89-e3a99e56aef5
| section | Ducting
| checkpoint | 1 - Permits
9b807ea2-71d8-5a65-9a1a-43780a0dd313 | note | ACTION (Hold, Monitor, Witness): H
6d0eee13-7c66-5bc4-9160-707c45e0c304 | note | DETAIL: Obtain Permits
c5c89645-f32b-5355-965c-3cb9da63a109 | note | FREQUENCY: As required
16e14ab9-3a8c-50b5-b6e0-2458d721ba23 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
e9e8b52f-3624-5c9b-bb8f-945eea0e81fb | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
1009f135-6507-5696-9a16-5b0477b685cf | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
ac4e755e-7408-59b0-a8cf-efb36893d335 | note | ACTION (Hold, Monitor, Witness): H
4df5ae24-02e8-531e-8451-f858f67f8d4d | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
fdf3a2e6-d7ec-55cf-834a-5ceff82a93ff | note | FREQUENCY: Prior to commencement
a1071c44-093c-5a5d-9f4d-5247c7456ae5 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
e26d652b-38f9-5bdb-a0d0-5b8306b06f3a | note | CONFORMANCE CRITERIA:
ac4cf49d-ac2b-5b59-a860-02101f71b078 | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Survey Setout
7bfd2893-e908-5ffa-bf7e-84943ed90400 | note | ACTION (Hold, Monitor, Witness): H
3bc6bee7-9e4d-57cd-bf39-e2e7f48be370 | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
575c68db-a39b-5782-ae75-719888cba936 | note | FREQUENCY: Prior to commencement
7e448c11-35cb-5356-950f-d1c8dabe9539 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
bd5b8dcb-27e2-5902-9d17-d2f98c2ce954 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
54125066-6a6f-5829-8ca5-ff2256a8ddfc | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 -
87d69396-0d82-5e32-b4d0-fe4857293fc4 | note | ACTION (Hold, Monitor, Witness): H
b6d2a170-10e7-59b1-b9c5-bf664f7ccc0c | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
9686a1df-07f9-5a15-83cd-b9e383e06994 | note | FREQUENCY: Prior to commencement
39cdb821-2993-5fee-bf30-59d865080c3a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
07994887-073d-5aae-af64-4669b264dc38 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
c74d4aef-2e19-556d-9024-674c27b06ae1 | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
eed985a2-ce41-5b2b-aeaa-46a9f3cc8ed3 | note | ACTION (Hold, Monitor, Witness): W
7080eb20-6117-5805-bf07-f9cd007c3d3b | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
c6d09318-9b99-5454-a100-06c345928d3a | note | FREQUENCY: Prior to Installation
f78de4f2-c230-56d8-b5a2-80ad11bdef0a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
603d02ac-c575-5bc5-9dd0-3eb543020797 | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
a6e87ad5-4811-587c-8f93-f7be89388d79 | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5.1 - Material Compliance
f239d5a3-5385-530a-9753-3305d94758b2 | note | ACTION (Hold, Monitor, Witness): H
ae1a60bc-824d-5cab-9d13-2fa8d2725275 | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
1cc2ca67-39a9-5c43-a2f6-a9875f029cba | note | FREQUENCY: Upon delivery to site
911db722-a943-5692-b64d-71d60097605b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
c2015ea2-5314-5b87-a026-a169b2bb71eb | note | CONFORMANCE CRITERIA: 50mm Ducts
977a2b3d-1434-5a9d-a539-c389a9501cb9 | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
e3a8cee6-0170-5bbb-942a-57f05d95ebec | note | ACTION (Hold, Monitor, Witness): H
6eb8b300-e2ed-5a5d-bb7e-c3334ac92144 | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway
80dfdbaf-3a93-576e-9390-f16dae3516eb | note | FREQUENCY: 10m Intervals
74b06afa-ff7e-5f52-8276-efa4ff6acda9 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
4ca2027d-419a-5715-842a-5f14124dcf7e | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
40bcb3d3-8996-53fc-abd8-c75c31997d6e | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 -
91ff3f7d-7c26-56ba-afb1-8a9294b35c33 | note | ACTION (Hold, Monitor, Witness): H
cf9bdf8e-d7a0-5176-8627-371d269259ab | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
dd2650a2-efad-5795-82cb-c6c2f42ccc28 | note | FREQUENCY: 10m Intervals
28e1cf6a-8d94-5656-a984-a2ea6ee4b3e2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
ff39eb06-1922-5d35-a929-eabfc7817c46 | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
40113de4-7606-5e70-ae74-e1a4f6a02e6d | note | RECORDS: Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Duct Installation
7d670fdc-765e-5ba9-a5b3-06d59167cc47 | note | ACTION (Hold, Monitor, Witness): W
41d8aeb2-6d0e-5972-82c2-51c9889701a2 | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
5b05feed-dfb5-58b2-b66e-1342133f06ac | note | FREQUENCY: Prior to Installation
b43732ec-0cd4-5399-a4de-2e5181448ef8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
ebd090c5-547c-528a-bc92-9e3f9621eb7b | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
68847a10-cf56-5e9d-a3ce-cda9d4413d57 | note | RECORDS: Photos
| checkpoint | 7.2 -
0206b909-ff8b-5013-b1ee-2c923d225c9c | note | ACTION (Hold, Monitor, Witness): H
6cbe10ce-6d41-57d1-bb3d-5856023f0c63 | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
b628a70a-4dcb-50e7-9770-5502fd4fc914 | note | FREQUENCY: 10m Intervals
ac81c0df-d192-5e46-9756-fd057c5850d2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
b7658e76-4b44-58cc-9c8f-3558713e9317 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
3283431d-340b-5152-81e2-dc1bbeddeecc | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
d9c778ea-05bd-5bbb-ae90-9eb4cc311159 | note | ACTION (Hold, Monitor, Witness): H
20261377-560e-58a5-9a4d-fbe4146c35a4 | note | DETAIL: Asbuilt Survey
eb221943-f4c2-50e9-89b8-23572d392154 | note | FREQUENCY: 20m Intervals
99696d74-bc38-5aff-86d7-8956ad619084 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
1dd247f5-211b-5a8d-b922-b428a6d72b88 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
3386ba66-d25b-5c45-95a1-d8d60d45f54b | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
cda1dbe3-5335-5627-b8e1-051fb1ab2d0b | note | ACTION (Hold, Monitor, Witness): H
b5e5a0c3-1e66-5a75-bbd2-42bb89925046 | note | DETAIL: Lay min. 100mm gap20 or finer for bedding and haunching
fd477d12-5b09-568d-b220-345fd83b72f7 | note | FREQUENCY: 10m Intervals
5c7dff9c-2f9b-5aae-bb63-4c0c18dca589 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
c416f9fa-9096-5658-add1-b42e80a653d7 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
403e3488-cc9d-5896-a162-8edf3e1f4b1f | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
33c6a9a1-8c49-59e3-9171-d088bff08860 | note | ACTION (Hold, Monitor, Witness): H
5c6ae00c-09b0-5db8-babc-189e7267750f | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
3fe1bff0-812d-57d3-bad6-b030039f5d0e | note | FREQUENCY: 10m Intervals
46f40fab-3228-5d6a-8060-35af7c46452a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
d2a73287-d36f-5856-a499-a6cabdbf872f | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
c8563e19-552a-5def-8694-61f29e5af09b | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Reninstatment
515a691d-4d58-50ae-bd40-991ae29a0323 | note | ACTION (Hold, Monitor, Witness): H
5c4bb835-9a18-576c-9984-3245b76f4b3b | note | DETAIL: Ducts under berm reinstated with topsoil at the surface. Ducts running under any concrete structrues are carriageway need to be reinstated back to the same
258ebbd8-1670-5cea-a117-11367b37f529 | note | FREQUENCY: Eash Site
7fbcf8c5-7532-577c-8bd8-e10d276c3c8d | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure/Docket
1c5e4bfc-1567-58e1-8876-416d7dff7fae | note | CONFORMANCE CRITERIA: Reinstatement as per designer acceptance
df3ee9bd-70b2-51b1-a25b-3afd950e3e01 | note | RECORDS:
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
719a5bf4-2d4e-5741-a3a4-7fcdf0f15085 | textbox | QA Compiled By:
eebc3237-f64b-5707-8d41-cbb0b8cfbe25 | textbox | QA checked By Project manager:
b9d7fb39-79d5-50f5-b190-4ef8dcd83339 | textbox | QA checked By Contract Manager:
24e7dfe1-62d3-5015-8342-870aabfe1d48 | textbox | Accepted By Design/AT Engineer:
| checklist | Weymouth Construction - Weymouth East - ITP - Enabling Works - Footpath, Kerb and Channel | itp | ITP - Enabling Works - Footpath, Kerb and Channel | 628aadbd-9df4-41b9-bbbd-d1c274422efc
| section | Site Set Out
| checkpoint | 1 - Site Set out
a94bc035-b09a-5ea7-b283-5c2679066de4 | note | VERIFICATION ACTIVITY: Surveyor
c6c7b602-d45b-5e5a-9e2d-8f06722b10d9 | note | METHODS OR REFERENCE: Surveyor
f121836e-f925-5f79-8178-b47c6f3ffc9d | note | FREQUENCY: Everysite
3aa57f08-a7a4-5b72-b1e8-13729e67145b | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
015e60af-108a-5351-bc95-82f9c24a6acb | note | HOLD POINT: Mandatory HOLD POINT -
baa004e0-6da6-5b3e-927c-4cf35d6d10d8 | note | RECORDS: Onsite records/photos
d2f4f5e4-38f7-504f-b298-5e08401d74a7 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 1 - Kerb & Channel
032e1c21-21ae-5090-ad79-a9276118b823 | note | VERIFICATION ACTIVITY: QA FORM
b27a031b-68d9-5224-a9a1-435cec941881 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
84f6b402-bbd2-5edd-8ab9-9ebe11fa4017 | note | FREQUENCY: Everysite
cb5b5085-3c44-563e-8db1-a5e464968660 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (CBR>5).Concrete 20MPa @28 Days
c777481c-9723-5266-97b7-3ef95b55c48a | note | HOLD POINT: Inprocess Inspection
e78b6fcf-52f6-5387-aa81-9b5ec6dc46f1 | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
2b79d070-8357-59b9-8a6b-e8ab220a7818 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Channel Level
26f3626e-2530-5c78-b66b-d65e94dd1785 | note | VERIFICATION ACTIVITY: QA FORM
b0dbfa9c-ff55-5b65-908a-e8ce9fd213c2 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
9bea2d40-7680-5431-b212-f3e471be6e4d | note | FREQUENCY: Everysite
c4edcb6b-5d42-57e1-9338-c3a9f6c5a30e | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
506a9b8d-7fb2-55a3-96ad-633459fa0ca0 | note | HOLD POINT: Inprocess Inspection
db402f3f-52bd-5782-8bb1-d391588d8bff | note | RECORDS: FH concrete QA sheet
c427a503-028a-5839-a66a-d1e26575bf10 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 3 - Concrete Footpaths
f5cb94ab-9aee-5132-b107-44e82e2d3897 | note | VERIFICATION ACTIVITY: QA FORM
b0a832a0-37cf-5d45-a792-a093e24e0469 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
47ac6833-c759-5862-827d-3fb3874014f4 | note | FREQUENCY: 10m Intervals
d347a46c-5b12-5bed-acbb-2b2f119f0c70 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
fe1987d5-98b6-5232-966d-d6fc6ebf5aeb | note | ○ Basecourse - 100mm min. thickness
f2f07ca4-b600-5b35-a777-c01e851efeb3 | note | ○ Clegg CIV > 12
e5d58e90-42c2-54ac-8696-b84c38154327 | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
f0e31569-7507-56ad-92a4-6a54d57d0e90 | note | HOLD POINT: Inprocess Inspection
1685148e-207b-5680-89a5-814268b2d16e | note | HOLD POINT: Prepour inspection
9100ddc4-71cb-5937-a401-a38fa3e6b634 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
d2663a29-531a-5246-8055-26122993adee | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Shared Path Pavement
6c4894bc-6613-59b1-a205-8dfe01665ce1 | note | VERIFICATION ACTIVITY: QA FORM
3a78134e-b513-5f45-ac17-5214dfaaffb8 | note | METHODS OR REFERENCE: IFC
ba4e0185-9490-5656-9938-0f76ad6e1142 | note | FREQUENCY: 10m Intervals
15971630-325a-5e71-9000-8460767fe9c2 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
dbc15019-fe42-500d-b9ad-292d80aea1c2 | note | ○ Basecourse - 100mm min. thickness
6cc63b98-5435-5da3-9d6a-f18eb8915f83 | note | ○ Clegg CIV > 12
552fea38-0d21-58bc-afec-b02de25b6589 | note | ○ Surfacing - Concrete 150mm with single layer of 665 mesh(50mm cover) and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish
a9e701ea-f70c-5cc8-8c2e-28a9b851e83b | note | HOLD POINT: Inprocess Inspection
08c4ee3d-d3d4-5fd4-8a40-aabe4e6df512 | note | HOLD POINT: Prepour inspection
9446736d-1b63-5ada-9294-8eca5a7057d5 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
0a9e0fb4-8f45-570f-9453-d609ea1b132e | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Construction Joints
d66e8b15-f719-5b99-880e-a629dff6b89a | note | VERIFICATION ACTIVITY: Visual
f398da86-a711-5abc-b1b1-bd20465492ec | note | METHODS OR REFERENCE: TDM Technical Standards - FP0002
0237a66c-fed4-52f6-8d6e-03b09a2c2f40 | note | FREQUENCY: Everysite
c0ba60a3-9764-5484-b2f1-0bb1e748081e | note | ACCEPTANCE CRITERIA: All the sawcuts to be aligned to the Kerb joints. Dowel bar 6mm thickness to be used for the construction joints on the shared path
5d67d8d8-d030-5a2d-aa1f-502f5f375020 | note | HOLD POINT: Inprocess Inspection
38ece486-0460-5350-9f3c-72a5571d60bd | note | RECORDS: Photos
6fccfec6-cc2a-596f-b20d-fe2047de6296 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Fall Gradients
0ad5f189-c9b5-5d50-881e-be0833399143 | note | VERIFICATION ACTIVITY: Visual
f148a2d2-07c7-5dc8-ab00-f4ace0f533a2 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
3243b5cc-9f5f-5502-9fbe-635c31e33720 | note | FREQUENCY: Everysite
f2c6e28c-157d-500c-9eee-c627f8f4dc2b | note | ACCEPTANCE CRITERIA: 2% preferred (Min 1% and Max 3%)
e7106fa5-d93d-5b00-b3a1-95e708c7ad1c | note | HOLD POINT: Pre-pour inspection
2452db04-f382-58e8-b2f5-305ffadf73cc | note | RECORDS: Photos
ceac15d9-9981-59da-a83c-e9ed1214af5d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 7 - Grass Berms
a5744ce0-1821-5152-b3db-da0cbb4fa7c4 | note | VERIFICATION ACTIVITY: Visual
d50ffb1d-10c8-519d-b4d4-08c9bc510e2b | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
f17e7dc5-18e1-5887-a2c9-4edb834396d7 | note | FREQUENCY: 10m Intervals
0ef0eb42-0c02-5322-9d6e-a85b44cba127 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
0d60d001-0bf7-5500-9dbc-bbdb4eb00f75 | note | HOLD POINT: Inprocess Inspection
9448cff0-6064-5f74-b1ef-4d7518b3e403 | note | RECORDS: Photos
cce440c2-ae0c-55af-8364-42c855107113 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (1)
f01f5b16-f18a-54bb-9607-145ca62f64a6 | note | VERIFICATION ACTIVITY: Visual
b857e7de-1fe0-5b9c-ac97-41243a3f498d | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
a8c2e6b9-526a-5f8c-a1b8-a87b92fe7e9a | note | FREQUENCY: Each PX
4a0fa73f-1c24-515a-a01c-f60358f4e0f2 | note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer.
064079e3-4ebe-5b75-96f5-fdfb3ae9647b | note | ○ Warning TGSI tiles should have 100mm concrete haunching underneath
7fde4fac-f7ef-53e4-bf87-e830801b8790 | note | HOLD POINT: Inprocess Inspection, Measurement
6751e40c-6421-51ff-9f56-0426144709f2 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
89e63ab3-747a-53ad-bb29-b6cdba12db55 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (2)
dc7f6b02-4616-5660-9683-1f6022b041d3 | note | VERIFICATION ACTIVITY: Visual
700f3224-6ed6-55cd-be81-e8cd9b205ee0 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
f4d5dce0-bfdf-586e-8d47-88ae109cfe4f | note | FREQUENCY: Everysite
b30df0c6-b84c-50a9-a555-b20c25b8b1d7 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
4de5b7aa-cc85-53ad-a6f9-b08ebc61ed72 | note | HOLD POINT: Inprocess Inspection
609dbf3e-b4ba-50c2-986a-36fd278341ea | note | RECORDS: Photos
78d94d85-0c02-5957-8d39-e7f877b1731f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (3)
af0ede81-0b65-5100-8ad8-a771233d851b | note | VERIFICATION ACTIVITY: Visual
fe52156c-a09f-57c9-91e9-c65f728688cd | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
a19119e7-ffb7-5fbb-ae62-5fb008bd056e | note | FREQUENCY: Everysite
2d084ddb-bd0a-5383-8b73-6897357c67f4 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
07318148-f63e-52b0-97b4-c3e451e4f9f0 | note | HOLD POINT: Inprocess Inspection
634c0c28-99d5-5a2b-aff9-4d34561bb0d8 | note | RECORDS: Photos
57d53bf9-1cfb-5f60-a63b-52eef1a5d7bf | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (4)
39e23c6f-98a5-5596-ad47-085eb64bde3a | note | VERIFICATION ACTIVITY: Visual
a3ebddb6-37b7-5ab8-a961-dc3a144e4bde | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
fb125a4c-424c-5e51-b19f-c0ed45bfe45c | note | FREQUENCY: Everysite
31eb8248-30f6-5853-9b0a-df27fe424f49 | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
4d720514-a4ee-55cb-900d-0f26701ea29b | note | HOLD POINT: Inprocess Inspection
7ab4d1fc-5761-5deb-9f17-9b57b664c6d4 | note | RECORDS: Materials Dockets
e0ffa713-bda0-5fbc-8f0c-b07c2946c249 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 9 - Pram Crossing
9cdbaafd-e34e-5fdb-8c2d-4cf3f490d26a | note | VERIFICATION ACTIVITY: QA FORM
4c054007-326d-5e67-8e02-a5b65e5fa71a | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
f0d1eafc-8e8b-5fcc-a97c-ee2b04beba37 | note | FREQUENCY: Each Crossing
08f56218-5714-53a5-877b-1a99cb63c25a | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
86b651b4-9963-5081-857f-3d99524b87d1 | note | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
8791efdb-867e-5ed5-b87e-439686eeb7ae | note | ○ Slope no greater than 1:12 where practicably possible
cb8edaec-c829-592a-a813-d31706232e4d | note | ○ Clegg CIV > 12
6ee6c2e2-67d6-5694-8dbb-c659d050a4f8 | note | HOLD POINT: Inprocess Inspection
f5974dea-618f-5109-807c-0004f113468c | note | RECORDS: Photos
f77301d5-3e45-5d72-8ecd-c5d5bea70d4c | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 10 - Timber Retaining Wall
04ec1e1b-1925-5f51-929a-5b57ecf1610b | note | VERIFICATION ACTIVITY: Visual
12756a54-38c5-5335-bf25-10a91c80b4ed | note | METHODS OR REFERENCE: TDM ST0004 - Version A, Timber Retaining Wall Detail
21f1fd1d-d34a-5acd-8550-f9f01b9a421a | note | FREQUENCY: Everysite
3e122755-5b2a-52d6-959d-60f20b6cd86d | note | ACCEPTANCE CRITERIA: 125 x 125 H5 Timber Posts @ 1.5m centres installed with 20MPA concrete. Concrete footing to be 325mm diametre.
3b62563d-4d9d-58b1-8fdc-6e0bef15434d | note | ○ 150 x 50 RS Tanalised H5 Timber Rails. Provide 5-10mm gap between rails
ae1d3178-0837-54bf-8e2e-ebfcefa79c69 | note | ○ Retaining wall slope to be 10:1 grade.
8d6e007d-451b-50a3-a8f1-a4e56a4ffb9c | note | ○ Maximum height of wall = 1499mm.
2afe07ab-a39b-54f6-ad9d-53a75a1e07f1 | note | ○ Minimum embedded depth of post to be same as exposed height unless less than 300mm, then depth = 300mm.
32664cc1-0a66-5425-8149-1689e9cfabaf | note | ○ Subsoil pipe to be lay as per TDM and connected to the nearest CP
f40927f6-7e9a-50bd-a3a7-572569b78605 | note | HOLD POINT: Inprocess Inspection
ad060678-cee8-5aa4-85b7-50d382352335 | note | RECORDS: Photos, Material Dockets, Dimension checks
814aa5db-9301-5998-9bf3-8d47330a881f | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 10 - As built information
8396548d-2ee0-524a-b049-10226fe032f5 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
95db9887-e4a4-5bfd-a7e7-026d3350d23c | note | METHODS OR REFERENCE:
8f31f604-6c9a-57e4-8bb1-89508998e8df | note | FREQUENCY: Every Site
4529fc5a-f08e-5f06-a75e-1ff8e75bf0d3 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
1629156d-dcba-527e-b796-f1ee12bbe07d | note | HOLD POINT: In Process Inspection
bedaef92-d251-562e-b9d3-543b867c9d06 | note | RECORDS: Asbuilt records
9518fc34-9c00-5b85-9a6b-ef90a529fe16 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 11 - RAMM DATA
21292868-239f-5d0c-a169-d1bcdc343cc7 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
28276547-cc74-5410-8afc-6e742e6ad824 | note | METHODS OR REFERENCE:
ef094016-5a8b-5654-a835-c34a560ae99f | note | FREQUENCY: Every Site
53ddeabc-060a-5a12-b9e2-354949d2ac2d | note | ACCEPTANCE CRITERIA: RAMM SHEET
07e0c822-24f1-5c20-968d-75fc99bd36b0 | note | HOLD POINT: In Process Inspection
e87a190c-7d67-5b24-af0f-a0140f471357 | note | RECORDS: RAMM Sheet
4d4bafce-a08c-5e34-8114-24b71496c046 | note | ONSITE RESPONSIBILITY: Site Engineer & PM
| section | ITP APPROVAL
| checkpoint | ITP Approval
854c9b17-b232-5637-8144-db80ee06611c | note | Prepared by: Ajithkumar Ayyanar
2809910b-fb6f-5c1e-b2d0-03244cb3884e | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Weymouth East - ITP - Signage | itp | ITP - Signage | 66ae37c5-8c94-4a28-b0f2-da1a10c97edb
| section | Site Set Out
| checkpoint | 1 - Site Set out
e5f6ac79-3181-565e-a639-cb2878372c0e | note | VERIFICATION ACTIVITY: Surveyor
dc99f033-6793-572f-8557-2b8cd098c0a7 | note | METHODS OR REFERENCE: Surveyor
40e554c4-6e1d-5cda-8f20-6d0930e82aee | note | FREQUENCY: Everysite
d90c5f6a-794d-5526-82c8-b9ed598bf8b0 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
b21ede61-554f-50b8-a590-c8a1d22085f2 | note | ○ Alternatively like for like
2071508e-f479-53d4-a7d4-ff72de0c0708 | note | HOLD POINT: Mandatory HOLD POINT -
1fd25641-4708-5446-8a28-2277c2247c34 | note | RECORDS: Survey Receipt
c9be92bf-4315-5e69-a9b7-44fd462c5b04 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Signs/Belisha Disk
98a76ffa-f08c-5784-a4b9-f5b1b7f347a8 | note | VERIFICATION ACTIVITY: QA FORM
7360ec93-4da8-5550-83f0-b7f8961128de | note | METHODS OR REFERENCE: TDM Technical Standards
eb49850c-06b6-5f87-bf04-088490f86661 | note | FREQUENCY: Every site
7c400452-94f7-57a0-b3f2-b47c31d5e714 | note | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
ab494d3f-229c-587c-b6a3-1fe576b6b95b | note | HOLD POINT: Inprocess Inspection
0d7d628a-22b9-5072-9965-f1989b5f8451 | note | RECORDS: Dockets/Photos
42a1571c-4ccb-5641-b943-d992615055c5 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Pole, Impact recovery post and Ground Socket
73408980-e1a7-54d9-a3d8-7bd2c3d6a291 | note | VERIFICATION ACTIVITY: QA FORM
9dd4186f-d6ad-5b41-a87b-f909bb0f0795 | note | METHODS OR REFERENCE: TDM Technical Standards
86da8450-4fac-564f-9ccb-56650c69cf3f | note | FREQUENCY: Every site
0d9ea1e4-4372-51fd-9c1c-64b354a7407f | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
8a0aceb8-edcb-55a7-b8a8-4290dbd5aab2 | note | HOLD POINT: Inprocess Inspection
466ca0b3-965b-5123-aeeb-0508beef92ac | note | RECORDS: Dockets/Photos
df29ef60-e927-5580-8674-3e89987796d0 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 4a - Ground Socket
a4f2ad25-ea8a-5fd7-8017-6c63504fb6fc | note | VERIFICATION ACTIVITY: QA FORM
26cff03b-2010-599f-831c-ebb51484605d | note | METHODS OR REFERENCE: TDM Technical Standards
54cc56b9-7a32-5a52-b5d7-e29e2f1e35de | note | FREQUENCY: Each Socket
2677dd8d-32e7-5102-8c4b-b75ea96949bd | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
43abe010-35a4-5264-b36b-590ff2a0d948 | note | HOLD POINT: Inprocess Inspection
a52407c6-a1df-5b69-ad18-6962495c316b | note | RECORDS: Dockets/Photos with tape measurement
3ce7b0a0-dd11-5d5c-af2a-47f8908e1103 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4b - Pole and Impact recovery post
603a59bd-a5ae-5af0-817f-ded6a0d08d6e | note | VERIFICATION ACTIVITY: QA FORM
180db986-177e-5860-aeb8-4b0a139c080d | note | METHODS OR REFERENCE: TDM Technical Standards
64501ea9-1f5f-530f-9929-f874c7b5df1f | note | FREQUENCY: Each Post or pole
3ce5e804-e662-5bc0-9d9e-d785c95ac315 | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
a5cea427-9ce2-5472-8b62-d4c115b1df85 | note | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
1c8b22e5-a028-5061-936e-414ee77d287f | note | HOLD POINT: Inprocess Inspection
e0e44798-f682-58da-bd89-30489fd149b7 | note | RECORDS: Dockets/Photos
20ae47f3-203a-51fa-ae16-353f5a3b5754 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Signs/Belisha Disk
c74db19e-c0d9-5664-b016-1f051ae33a15 | note | VERIFICATION ACTIVITY: QA FORM
d79e77ac-4195-570f-9491-41b324ac347c | note | METHODS OR REFERENCE: TDM Technical Standards
9e01c9ab-c3c4-5571-8b01-1ec5ee623896 | note | FREQUENCY: Each Sign
e64c5003-7b95-55e1-94a6-f71f0c390407 | note | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
b9351626-45e7-5057-9150-4c6a0e2d2842 | note | HOLD POINT: Inprocess Inspection
45460aa0-b592-5581-99bd-1c877aa53332 | note | RECORDS: Dockets/Photos
30e72ebf-d9c4-51a4-8812-8596402b4224 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 6 - As built information
e8ecb998-daa3-5f4a-827b-00131fcdcb87 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
7358e8a4-a6da-5403-9a97-5ecf5fc5aa72 | note | METHODS OR REFERENCE:
5fbc199e-f26f-5a6e-9b65-a16ca3d27063 | note | FREQUENCY: Every Site
b3d44311-9817-5c4f-bcd7-cbc6755e0582 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
cf79c8dd-e167-57b0-aa6c-857bd61b6d2c | note | HOLD POINT: In Process Inspection
b83e17dd-321e-5498-9d52-2d75cb877af7 | note | RECORDS: Asbuilt records
002330fc-bd33-5775-8072-eee287a7c302 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
c19bde38-e5ac-53f9-b6de-88e378534ac8 | note | Prepared by: Ajithkumar Ayyanar
c3cf0019-0817-58ec-94d1-d6e9ef1710e9 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Weymouth East - ITP - Traffic Islands | itp | ITP - Traffic Islands | 7a3b007d-8b94-4f8a-9dd0-1d9b60b9ae5a
| section | Materials
| checkpoint | 1 - Mountable Kerb
86333c33-b12b-5580-9f55-9c9571429a97 | note | VERIFICATION ACTIVITY: QA FORM
096bed7c-4b79-57e5-920e-87d1006c4541 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
8d63a8f0-b137-5601-af32-8eda4bff5fd1 | note | FREQUENCY: Everysite
358e43b4-3384-5a5e-bded-272acfd560e0 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
add294b5-8ccb-5115-8e4c-a7dcc766a113 | note | HOLD POINT: Inprocess Inspection
a4dec873-cab1-50c0-b7eb-2a5f33dac1ae | note | RECORDS: FH concrete QA sheet, photos.
26ac3195-9cfa-5182-812c-159ae91a9156 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
86d33652-706c-5dc7-bc2b-890d38104abc | note | VERIFICATION ACTIVITY: Survey
1776878a-f034-5f49-9f60-fcfbc25f8c27 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
b8b01a24-24be-5ebe-8d91-cc750f105d8d | note | FREQUENCY: Prior to commencement.
917020de-becd-50d2-aae2-fb2a4f1b0e84 | note | ACCEPTANCE CRITERIA: Survey
e01bda92-b0d6-5d08-be66-833909af7bc1 | note | HOLD POINT: As per Construction Drawings
bc61fe24-ea2c-5169-a838-167e8bce5673 | note | RECORDS: Survey Receipt.
828333b6-5ea6-514f-8cd8-130c07e50e23 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
408b8571-88b5-5f61-824d-0d62edf3bead | note | VERIFICATION ACTIVITY: QA FORM
2053b9ca-fa0d-501a-9b0e-9efa40cad169 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
d1575aab-77e5-5b7c-ad39-4b1c4453186c | note | FREQUENCY: Each Site
0eab1648-38dd-5353-b077-0ff771280269 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
2a2be2a9-5ee3-58ee-8c41-9381c61cb1a5 | note | HOLD POINT: Inprocess Inspection
1de8c30b-d02e-5e39-8029-a27304a045a9 | note | RECORDS: Photos
1bd3caf1-2f0c-5401-b5c5-5d934cbe9ca5 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
5b46629f-5de1-586c-965d-518fcd7c7931 | note | VERIFICATION ACTIVITY: QA FORM
69b308e7-7d55-5ffb-9070-e2afb9ce781a | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
db67df97-6f7e-547f-a85c-c25e5bf56382 | note | FREQUENCY: Each Site
3dcb4a3b-d5ff-59f3-a365-838dc4f30704 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
fc7fbd43-7c10-5c10-8bea-9cd2e81935ba | note | HOLD POINT: Inprocess Inspection
3da26340-f4a7-55f8-82ec-c596bfe0c48e | note | RECORDS: Photos
42d28032-60a7-501d-9f24-46eaae7a6c02 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
3f188c96-4a47-52cd-b83d-4b98d25ac532 | note | VERIFICATION ACTIVITY: QA FORM
faf48686-4d5a-5d45-9a5c-ec05af8629f4 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
82e97a20-c69d-56c4-abd6-e1cc7f475fe9 | note | FREQUENCY: Each Site
7853691f-2c55-5c35-b3d1-616ad6170d72 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide
168a77f6-20e6-5446-ae0e-fb5df20c5d79 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
a8a0faf6-4a38-5216-97de-198e9d8dbc90 | note | HOLD POINT: Inprocess Inspection
bce17100-6980-5774-ae4a-90fe8e258c69 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
2999edde-8329-5093-ad0d-d6a8d34271e8 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
e75f0b14-24b2-56c6-9011-76fd50c5f8ca | note | VERIFICATION ACTIVITY: Drawings
026ea312-86f0-5e31-8110-83a388aff236 | note | METHODS OR REFERENCE:
a4b7e16d-00e4-5c3a-98ce-ce95534da794 | note | FREQUENCY: Every Site
733a74d6-6479-552b-868c-c82138e81dc1 | note | ACCEPTANCE CRITERIA: As built drawings
6c34abfa-214a-5913-a23b-ecb115651382 | note | HOLD POINT: In Process Inspection
67251e32-f723-5a95-92a4-03b6e0e6e799 | note | RECORDS: Asbuilt records
c00f0d34-3c53-5daf-8880-1a8f1299e6c9 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
b09f4cd7-19ce-5377-a48f-2258161721c3 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
aab49d85-f563-57d4-b82b-d342ed9eac3e | note | METHODS OR REFERENCE:
7722a918-ce42-5162-a6f3-dd6e633a0d9a | note | FREQUENCY: Every Site
6eeefda4-9f71-59b4-b8f2-2a54a1f9e317 | note | ACCEPTANCE CRITERIA: RAMM SHEET
55097bbd-6d8c-55b0-ad68-806c0a4aab08 | note | HOLD POINT: In Process Inspection
ce2bf05c-d46c-5e53-b39c-15a9e546d89c | note | RECORDS: Asbuilt records
cf902edf-09ed-519a-8a4e-143cb748952b | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
f1555a79-7fe7-5d4d-b85c-dd2c70f9a651 | note | Prepared by: Ajithkumar Ayyanar
1536909a-99a7-58ef-97d2-609e3d8fefa5 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Weymouth South - ITP - Ducting | itp | ITP - Ducting | 686445e1-39d1-4fdf-8c80-bea280db15c2
| section | Ducting
| checkpoint | 1 - Permits
5aabf0c3-cca6-5522-94d3-b73be0137251 | note | ACTION (Hold, Monitor, Witness): H
0647d631-840d-5e5f-99fa-12b897837fc7 | note | DETAIL: Obtain Permits
2716b0ed-8823-58b6-a779-396152d684e2 | note | FREQUENCY: As required
22b1addd-baca-532c-8175-b393116b5cb3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
8730b573-e3a2-5aea-9f9c-19ab319ddc32 | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
6e18668d-ba74-5bce-8d94-a4b68d09ff64 | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
26295997-5211-51ab-b7b3-67f84bf5a30c | note | ACTION (Hold, Monitor, Witness): H
b20f71f4-cdfe-5669-9da2-e0ae2aedbb87 | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
0808dc61-1742-537e-86bc-75de09f5a130 | note | FREQUENCY: Prior to commencement
5dca8ad6-3e39-54ed-8d8a-d1fb4af9e979 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
9b9947b6-b2e1-5166-8b14-f3c080a2bc80 | note | CONFORMANCE CRITERIA:
2f071623-0d42-5806-b30e-bf030c517316 | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Survey Setout
d03c4f1d-12bd-5ea9-b4af-9bfa4ab2a952 | note | ACTION (Hold, Monitor, Witness): H
c5427c09-373d-56ad-acf0-e4c3ff70e582 | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
33ffc2b9-3eed-50ca-a467-dbd9a3c991c7 | note | FREQUENCY: Prior to commencement
2e71b4e6-b94f-5dff-ad18-26bcd2da7c58 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
796d2938-5a65-5b38-a8b1-be3ccc646174 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
cdad5664-6102-567b-be4a-0b679d83770c | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 -
86ac315c-270b-5206-a319-3fff71813fad | note | ACTION (Hold, Monitor, Witness): H
25623ce3-3b9e-579f-825a-e3964cfdbfe4 | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
320d9dd4-55e6-5ae6-b221-79751d0f68e9 | note | FREQUENCY: Prior to commencement
c0fcecb6-df80-58c9-a2ec-233a8ed90a28 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
cc633d51-2b30-5244-8597-62dcd48bcf15 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
728fc16d-2e5f-5d30-8985-bae7184acb06 | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
7c457df1-c3ea-58a3-ac28-bfd6695e0da9 | note | ACTION (Hold, Monitor, Witness): W
cb2053d4-0d2c-5d21-b78e-8d896975236c | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
3bcf42f4-723a-5173-baa7-100ee08224c5 | note | FREQUENCY: Prior to Installation
618dc871-896f-5e33-945f-d114919e6d98 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
176a078d-0de3-5c4e-9578-54bebf13b0c9 | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
e38ff649-5247-5e07-bdd1-9379826582ed | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5.1 - Material Compliance
058adc2b-b3c1-5323-be43-36514a0b358c | note | ACTION (Hold, Monitor, Witness): H
bf44ebd9-a658-592d-980e-8256d5d33006 | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
05f4b565-e4e5-50f0-aedb-ae3e14e81ea2 | note | FREQUENCY: Upon delivery to site
9d46bce3-cf13-5557-8315-53890bfee5d4 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
8455480d-882d-5bd9-a854-e8ba5a25600d | note | CONFORMANCE CRITERIA: 50mm Ducts
0160eab4-687e-5243-8dc2-7ac61f96af64 | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
6758cc27-db28-58d4-b43a-0739f0240ccf | note | ACTION (Hold, Monitor, Witness): H
6136aa38-65d2-5305-9545-bb019cb7c104 | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway
c5ad7d70-f3b0-5d01-8486-9ba7334ac4e3 | note | FREQUENCY: 10m Intervals
9fee4cce-33d7-513a-bf4e-6e46fce8232b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
0ca57976-7dcc-5689-8ea7-9766814482ab | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
ccb596e7-5921-5ba2-8545-3fe9910e2537 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 -
8ba84b78-6dd9-5d25-94d3-47b64158e333 | note | ACTION (Hold, Monitor, Witness): H
f7f7180b-21a4-5830-808d-2a6d6f11a8f0 | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
92cfa6b7-4640-5914-a5e1-3ef61fbd367d | note | FREQUENCY: 10m Intervals
16cda0ec-b2e3-568c-98b7-61bb44842446 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
6df28d6c-e051-5468-8c3f-c6db365b4bd0 | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
e594adf7-1412-5724-93ee-f7f4684e0450 | note | RECORDS: Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Duct Installation
44224d1d-ac27-5b09-8e16-0f3497776d8a | note | ACTION (Hold, Monitor, Witness): W
be600061-fade-56b9-842b-4467699e9ea8 | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
6b9d40f3-78e6-5ac3-9236-634d672043a8 | note | FREQUENCY: Prior to Installation
1fcdfdd7-3d1f-5fbe-b9d3-c449bfaf4a21 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
c15cf689-fb90-5afb-94b0-0b264233a2a2 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
f712b3dc-b216-5ddc-b8b4-4570649941ae | note | RECORDS: Photos
| checkpoint | 7.2 -
4d28f053-beb2-5a78-9099-3b61cd612785 | note | ACTION (Hold, Monitor, Witness): H
6801448c-28c6-569e-a6f5-aa060677f4ce | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
fd0404e8-10de-5ac4-ae27-521f77fc9c57 | note | FREQUENCY: 10m Intervals
25c5ef22-92f7-5b85-bb2b-2d3ff36bec3b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
66b471d4-94d8-5810-bb0b-5e72f66dc48a | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
383fc081-fe42-5e40-8159-99d4ea64b5f0 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
410381ac-f14b-5ed5-9f37-b78ad886f93a | note | ACTION (Hold, Monitor, Witness): H
dd7dd7cf-cf4a-5fe0-b14d-98c998a1efdb | note | DETAIL: Asbuilt Survey
c3596b90-6990-53ce-bafa-cbe1f6aaab1d | note | FREQUENCY: 20m Intervals
22eb4d83-88fd-575d-9c2c-507dcd264f88 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
7008f6fc-4a20-5c89-a346-900ac5ebe472 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
0c6f5587-9ac9-5b0b-9ce0-94d45720be12 | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
0c57e2b6-3461-5a3a-a812-ea0476b7405d | note | ACTION (Hold, Monitor, Witness): H
475310c2-08d8-5267-9838-f894f6565ce3 | note | DETAIL: Lay min. 100mm gap20 or finer for bedding and haunching
94068669-325d-5a6c-95f0-13c161eb19ee | note | FREQUENCY: 10m Intervals
7e56833e-752c-5cad-b659-4d5b9c29b85c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
d4139e50-3039-53ca-a0f6-04685c2cd2a8 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
4aa05c95-c915-5656-b11b-2942fa62da69 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
3917cdcb-659b-5f4c-a44a-97fa954ac23a | note | ACTION (Hold, Monitor, Witness): H
e93b872a-3b9b-50bd-b4ce-deb54fb02e30 | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
98145071-a085-57c4-9505-e51327cef56c | note | FREQUENCY: 10m Intervals
b7d83f42-2750-5741-88b7-b4485ab57571 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
5c6601ab-8f3d-581d-a386-159e05ff4933 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
0949d168-4f67-5f4b-810e-ec0f5b1e07f0 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Reninstatment
4097a72d-3937-5dd6-b25c-71fcea60c59c | note | ACTION (Hold, Monitor, Witness): H
c0eef33c-10e6-557e-bc94-f7bd215caef1 | note | DETAIL: Ducts under berm reinstated with topsoil at the surface. Ducts running under any concrete structrues are carriageway need to be reinstated back to the same
d40a0af8-6861-55fd-91ef-8f5c970a4ff9 | note | FREQUENCY: Eash Site
2ee65bac-f407-5c34-acf6-d67e1cb60e44 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure/Docket
cce9bd30-022e-55ca-8b3c-7367a775f158 | note | CONFORMANCE CRITERIA: Reinstatement as per designer acceptance
3b0e7671-abdb-5f14-b05c-6eb492b073d3 | note | RECORDS:
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
79d183e0-f9f4-5a02-9bd3-a0ca99a7e74f | textbox | QA Compiled By:
f4215fc5-cc67-52bf-89ad-f45d2c32111d | textbox | QA checked By Project manager:
7d8c5e3f-4f90-548d-ae2a-943de722f453 | textbox | QA checked By Contract Manager:
5d5d29d4-298b-5d65-ba5f-326e2661871f | textbox | Accepted By Design/AT Engineer:
| checklist | Weymouth Construction - Weymouth South - ITP - Enabling Works - Footpath, Kerb and Channel | itp | ITP - Enabling Works - Footpath, Kerb and Channel | 1d1c9176-2e73-4a98-9933-88fbf752575d
| section | Site Set Out
| checkpoint | 1 - Site Set out
0d4842d9-f011-54a3-b349-49975f6bdf9f | note | VERIFICATION ACTIVITY: Surveyor
748d30b9-3848-503b-b94e-b331b5e50dd2 | note | METHODS OR REFERENCE: Surveyor
23685882-e87b-5043-b82a-2b2407083033 | note | FREQUENCY: Everysite
ce069b12-1954-57b9-aebc-de80464fc138 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
00910858-59db-5d1b-b8b7-868764ad655f | note | HOLD POINT: Mandatory HOLD POINT -
930fd935-4d8c-5102-9f33-6ccee2ab61a2 | note | RECORDS: Onsite records/photos
8089c1bd-edc5-5641-b3d4-5715d0a5eaa2 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 1 - Kerb & Channel
07403f31-3697-59f5-95c9-0b8fcca9188e | note | VERIFICATION ACTIVITY: QA FORM
6904de3c-3d94-56c2-b62b-4a247e20aaca | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
9631aae8-a821-51ce-a6d5-ac98f7337e1d | note | FREQUENCY: Everysite
d31a36ef-c0fa-5728-8de8-b1d5fb549fa7 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (CBR>5).Concrete 20MPa @28 Days
4332df30-0f4e-5e27-a2dc-4def604d6ee4 | note | HOLD POINT: Inprocess Inspection
c971ef88-a93a-5326-8704-86c01bf6005e | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
8e054c6a-a855-5a27-be58-d9121acfafda | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Channel Level
31da5293-3a93-5880-9aa9-0f14ee2028be | note | VERIFICATION ACTIVITY: QA FORM
74c7e08e-1078-5b5f-b16d-2daedaa6b957 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
d406a762-6e89-5b23-ad20-e14725eca4e4 | note | FREQUENCY: Everysite
cf81901f-ab31-5496-86b1-f5669b64d774 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
b12350fa-ece0-5fe1-98c4-b1eb6dd931a6 | note | HOLD POINT: Inprocess Inspection
279aaf67-959c-5e49-8c7b-65ace7d176f4 | note | RECORDS: FH concrete QA sheet
86f1cad0-aaa5-5bf3-9f92-ec1ec5bd007c | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 3 - Concrete Footpaths
987692b4-aff5-5397-9ae9-0a7ad65a688f | note | VERIFICATION ACTIVITY: QA FORM
6a4cb816-ccba-5ed4-9f8b-e4666ff389e9 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
1b93c64a-fe7f-56bc-8c92-15761e3fa6c4 | note | FREQUENCY: 10m Intervals
c9a30815-a782-576b-9ad7-666fe38ee83d | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
9b73456f-5c7b-527e-b3ce-b04c00f0eb47 | note | ○ Basecourse - 100mm min. thickness
85210446-e398-5234-87ad-12bb9688b150 | note | ○ Clegg CIV > 12
b30146c0-14c2-580f-8351-ca2c797c0dcc | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
d910e8a5-6d54-5f32-802e-a26bd3d216cf | note | HOLD POINT: Inprocess Inspection
47ac82e5-69e6-58c9-ae79-d17d9e847c65 | note | HOLD POINT: Prepour inspection
ec76aeb3-0d2c-53e8-af51-5b22b0aa48d6 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
11a65969-84d2-59d0-8590-e3874243479b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Shared Path Pavement
5c942633-5929-5c2a-9e98-27b8544625d9 | note | VERIFICATION ACTIVITY: QA FORM
59d99243-2aa5-5cfc-92cf-93aaa1cfda8a | note | METHODS OR REFERENCE: IFC
677ef081-5ea7-5859-83be-a69748885c09 | note | FREQUENCY: 10m Intervals
9e66d1af-a761-578d-b95b-291329317e43 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
b63b1f3a-c406-56f8-9ff1-b1a5aa4e5885 | note | ○ Basecourse - 100mm min. thickness
84e9239e-7885-58c4-82a5-f868156db9c2 | note | ○ Clegg CIV > 12
34aac1e3-59c5-5466-88e7-ba16768901a4 | note | ○ Surfacing - Concrete 150mm with single layer of 665 mesh(50mm cover) and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish
119b20e5-376f-5a91-aa3e-a46c3550e834 | note | HOLD POINT: Inprocess Inspection
c845e232-27e5-5798-a454-20f4fdf4f839 | note | HOLD POINT: Prepour inspection
06aaa21b-70ac-5d3d-9d34-2112e9e9ad7d | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
848ce040-9175-5b0e-b19e-6e7d6262fea0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Construction Joints
4a3d9e50-d5d8-5caf-8717-6df818bc28dc | note | VERIFICATION ACTIVITY: Visual
f2a9a077-a2f1-5839-bcf0-cd17890fb797 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0002
31001c10-0027-587a-b299-30949bbd3762 | note | FREQUENCY: Everysite
85181def-7748-5237-83bb-2333d7456588 | note | ACCEPTANCE CRITERIA: All the sawcuts to be aligned to the Kerb joints. Dowel bar 6mm thickness to be used for the construction joints on the shared path
ba247323-72eb-5e4a-963c-2c6c6f5b663b | note | HOLD POINT: Inprocess Inspection
e2c90e41-ea68-55ad-95c7-8747b2956a04 | note | RECORDS: Photos
338dc1cd-01bb-5388-bf3b-05731c9a1ec7 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Fall Gradients
d2ab389e-87ae-5618-bc14-d74a3e138e59 | note | VERIFICATION ACTIVITY: Visual
c84e3876-d5ca-5bb5-b24c-fef4d5337f72 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
6409bf64-fa7f-5a96-8bb9-4f4df0699c54 | note | FREQUENCY: Everysite
cbe4fedb-5346-5875-a225-25c076dc52ce | note | ACCEPTANCE CRITERIA: 2% preferred (Min 1% and Max 3%)
20c69df8-5667-5f61-811a-d73cb0c0a366 | note | HOLD POINT: Pre-pour inspection
d6463c72-0000-52b8-baf4-df4c86b72a1e | note | RECORDS: Photos
345b7c98-8352-5c25-a4b4-6a9795816cbf | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 7 - Grass Berms
da926d37-ed1d-5bc4-aa81-7eef3ae872d3 | note | VERIFICATION ACTIVITY: Visual
17fd003e-5227-50a2-96f5-a4303fa71b1f | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
9badac76-5481-5c4c-b668-e0b3e4606e3c | note | FREQUENCY: 10m Intervals
f9a7ef60-fb74-52a5-a01a-1b2c60fd57ae | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
6b56fa0e-f0b8-51dd-a72e-c0b1fbd42eea | note | HOLD POINT: Inprocess Inspection
0751b942-b589-5269-a237-addd9e56c1ad | note | RECORDS: Photos
bb2b97c4-8e35-5481-bc76-4842b720dff3 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (1)
c2b673ef-4371-5fb2-bd27-7d0a07a2cb0b | note | VERIFICATION ACTIVITY: Visual
017262f9-5b02-5159-a57a-3adb16cd9c47 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
6ec1dc76-4bf6-568c-ac4e-3fbcd09ac6a5 | note | FREQUENCY: Each PX
edb25951-7a8a-5e69-aa5e-f32e57a5da04 | note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer.
a493f0d9-afe1-5960-8362-aa010e360cb4 | note | ○ Warning TGSI tiles should have 100mm concrete haunching underneath
6f18d20c-40d5-549c-9f10-17e6069d2f28 | note | HOLD POINT: Inprocess Inspection, Measurement
6ffd6f50-f0b2-5769-b7b4-c9f05f79dcad | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
29036952-3b40-5380-9c47-fc6964743976 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (2)
59a354ed-c2bb-5bc1-a2f9-3863d1386ff7 | note | VERIFICATION ACTIVITY: Visual
488e31fd-36b9-5ebe-93be-aed58029c371 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
b9a99f05-030b-5ed6-a780-17457824e296 | note | FREQUENCY: Everysite
2afc965c-7508-5852-9946-ca2d4e9c023a | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
3c8d4fd4-ee2c-590d-a8cd-c95607cc0422 | note | HOLD POINT: Inprocess Inspection
251c7435-b521-5669-8a25-e6d999bf58a5 | note | RECORDS: Photos
f2762284-bac9-576e-a437-2359c0f8bd7d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (3)
c14ad57d-2b61-5965-9e8c-663a76e7326e | note | VERIFICATION ACTIVITY: Visual
e9e78e45-081e-5626-8ee5-1e43afa89e5a | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
5408a905-2214-5bed-9c45-7dace03491a4 | note | FREQUENCY: Everysite
37645a48-ef77-5e02-8d06-350582203895 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
ef86a2bf-c6d1-5613-a538-c9bfc9afaf2b | note | HOLD POINT: Inprocess Inspection
01dd7b86-706f-51e6-8b28-358025f3d5da | note | RECORDS: Photos
c42e3a2f-7a2b-5ee4-bf92-ea53e85621dc | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (4)
3e52f43d-08d5-5784-a3ed-cb0dff83a064 | note | VERIFICATION ACTIVITY: Visual
688915a4-6280-550b-b689-229c0916d5ff | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
1597507f-e359-5062-a50b-3ed927fd4f9f | note | FREQUENCY: Everysite
d2f5a04d-894f-5930-be5c-b02e152e8ddc | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
6bc6f10a-3243-5c45-96f8-7083ace2a434 | note | HOLD POINT: Inprocess Inspection
03f64a7a-9fe5-55fb-95ab-6239b2829f81 | note | RECORDS: Materials Dockets
20185da8-07c2-5b62-bc44-36fcd1b5bbb6 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 9 - Pram Crossing
1332103b-d2cf-5b90-80fc-76e973eed319 | note | VERIFICATION ACTIVITY: QA FORM
fb4854c0-0f9c-5bea-aed3-b4ab218819ca | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
539be584-f1e1-51fc-bd75-3ee73e74684e | note | FREQUENCY: Each Crossing
478355bd-0eaa-5b2f-a722-e9418bd358ca | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
9c69eafb-e59d-53ca-af51-60360df9d772 | note | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
ca23747c-ddad-562d-9fdb-31f1dc578ec8 | note | ○ Slope no greater than 1:12 where practicably possible
d507b680-8153-51d7-8cf7-117d092bb4ae | note | ○ Clegg CIV > 12
7b79050b-d5d4-5a39-bbc8-1d0c4c8ab131 | note | HOLD POINT: Inprocess Inspection
ace8b7e2-ab95-55d3-b305-4aafb6bd5fe6 | note | RECORDS: Photos
afe45e05-e7f9-5b97-a753-778165034a7f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 10 - Timber Retaining Wall
059e68e8-7c76-5486-806e-8a58fbe348ab | note | VERIFICATION ACTIVITY: Visual
af8e2100-6f74-5751-a956-dfc9b75bf6d9 | note | METHODS OR REFERENCE: TDM ST0004 - Version A, Timber Retaining Wall Detail
495e2cef-e2d5-5922-9ee9-2db378412d81 | note | FREQUENCY: Everysite
67dab360-b190-5fb3-a4b1-49c2fed771fe | note | ACCEPTANCE CRITERIA: 125 x 125 H5 Timber Posts @ 1.5m centres installed with 20MPA concrete. Concrete footing to be 325mm diametre.
0dc5f0a8-0085-54de-982d-d102fcc00299 | note | ○ 150 x 50 RS Tanalised H5 Timber Rails. Provide 5-10mm gap between rails
b05438cd-723c-5b9a-971f-05721b4b510e | note | ○ Retaining wall slope to be 10:1 grade.
07f3a4fe-0a92-51a1-a4d1-d973591871f2 | note | ○ Maximum height of wall = 1499mm.
ed32b94e-09f1-5200-a482-5610330be5f6 | note | ○ Minimum embedded depth of post to be same as exposed height unless less than 300mm, then depth = 300mm.
c37a4a68-c021-5a73-984b-b8f0a9fd1a25 | note | ○ Subsoil pipe to be lay as per TDM and connected to the nearest CP
e690eec2-dea6-50c1-8a29-5492166915fe | note | HOLD POINT: Inprocess Inspection
441c6f52-7157-50aa-9473-5d5caafb211a | note | RECORDS: Photos, Material Dockets, Dimension checks
d3563640-65fb-53f0-a636-b52e81b98462 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 10 - As built information
cb3c0cab-058e-57d2-b306-6d0cbdd0f320 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
f5386829-9e8d-5829-a06d-206ba9a85328 | note | METHODS OR REFERENCE:
80dd6c5e-f38c-594f-8465-e876c0d898b1 | note | FREQUENCY: Every Site
90c14987-8ce3-51a2-a437-a5d43379f7b4 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
a751012b-64be-5574-ae9a-fcee26965303 | note | HOLD POINT: In Process Inspection
d658f976-2ccd-584e-a72e-13755f6fa07d | note | RECORDS: Asbuilt records
7f53c330-b4bb-5e7c-8213-e97c742d5c56 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 11 - RAMM DATA
da124138-dee8-5b3d-b8c0-819d376c81ad | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
22004979-a0f5-5aae-a060-0c23c8557133 | note | METHODS OR REFERENCE:
c0e5e726-4b0d-5705-8faf-6d44a792166a | note | FREQUENCY: Every Site
94d523ac-9ae8-5283-80fc-d312b17d09e1 | note | ACCEPTANCE CRITERIA: RAMM SHEET
9ae0abbe-add7-5c69-8df0-950151a2623a | note | HOLD POINT: In Process Inspection
bfebc8cc-6742-5b12-927f-3e7531263a83 | note | RECORDS: RAMM Sheet
adb6962c-dfbe-5529-bd84-eb391983fbce | note | ONSITE RESPONSIBILITY: Site Engineer & PM
| section | ITP APPROVAL
| checkpoint | ITP Approval
29fadf26-f928-5a34-9416-35d123801a4a | note | Prepared by: Ajithkumar Ayyanar
b61ae10b-5126-5ed8-9764-794f9910f7aa | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Weymouth South - ITP - Signage | itp | ITP - Signage | bf1c1504-f859-43ad-bba2-ffc07462371d
| section | Site Set Out
| checkpoint | 1 - Site Set out
04d96e71-19d1-5785-80e4-3f3a23a94f03 | note | VERIFICATION ACTIVITY: Surveyor
82b989d3-1845-5b9a-b92c-99099b6c67b2 | note | METHODS OR REFERENCE: Surveyor
1dfc32cf-13cb-5d9e-af14-1cb6c9d1a055 | note | FREQUENCY: Everysite
7eaad833-41c7-52ac-9a8c-d3c490519cc3 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
8912b0f6-a191-591b-8d8e-e489e662f6c9 | note | ○ Alternatively like for like
308afdf5-4d06-5499-b177-3d0bf2ed5daa | note | HOLD POINT: Mandatory HOLD POINT -
fcd7a17d-6bc1-565f-a37a-bf7900968d08 | note | RECORDS: Survey Receipt
623014a1-9b03-52bc-b611-f79bbf2b53e6 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Signs/Belisha Disk
05175e83-56ca-5135-89b7-76fb65fd2f7b | note | VERIFICATION ACTIVITY: QA FORM
39092f94-14dd-5df4-bb01-7b0fea599e39 | note | METHODS OR REFERENCE: TDM Technical Standards
04183389-9321-5770-aaf4-12cfaa17050c | note | FREQUENCY: Every site
7af39b0b-dfa0-5328-8ce3-dfd621a97d85 | note | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
057ca105-fb14-56e7-964f-9c57cb84c3b6 | note | HOLD POINT: Inprocess Inspection
b4da26d9-5ed6-53bd-8d89-28488133a60a | note | RECORDS: Dockets/Photos
cf9daa99-b100-5bde-ab82-6d8457dcd380 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Pole, Impact recovery post and Ground Socket
c169f8f0-99b3-58b9-a771-d9db3e1a9d08 | note | VERIFICATION ACTIVITY: QA FORM
6a12091e-107c-5f09-86aa-da442710a5f1 | note | METHODS OR REFERENCE: TDM Technical Standards
7baede81-4bdd-5893-aacb-76460b73b939 | note | FREQUENCY: Every site
937d1881-6b39-5d37-8050-409af99879b6 | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
27044d4b-7138-5f04-8288-4f9b986af073 | note | HOLD POINT: Inprocess Inspection
98e44e59-2651-5a69-9d48-1fe9a1a174b8 | note | RECORDS: Dockets/Photos
305b9a98-6e11-5973-b77a-2b12e3f176f9 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 4a - Ground Socket
ac77fd9e-7742-52b0-83ce-e2dce6c63648 | note | VERIFICATION ACTIVITY: QA FORM
fa8fa943-7439-5042-bbfa-ccc2af074dbd | note | METHODS OR REFERENCE: TDM Technical Standards
84da4a26-2daf-56ad-8a19-18f1043ce2c4 | note | FREQUENCY: Each Socket
1203ec35-8f97-527f-958f-e889707d2529 | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
ca5191e0-0e32-5408-b156-068f011697d1 | note | HOLD POINT: Inprocess Inspection
617f5932-ba58-5efe-9cd8-61b5670f300a | note | RECORDS: Dockets/Photos with tape measurement
5a8e5d9d-1ce3-5864-aa5c-81d9f2b68a52 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4b - Pole and Impact recovery post
0975dfde-a8e1-52c5-9bd2-13fc00852cc8 | note | VERIFICATION ACTIVITY: QA FORM
5ee648b8-d270-5753-a849-2a57efc08535 | note | METHODS OR REFERENCE: TDM Technical Standards
91fa60b9-7ab8-5659-81f9-652482fac6f4 | note | FREQUENCY: Each Post or pole
29bbafd3-b21f-5bc0-acac-bd1f989ca967 | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
12daad83-c69a-535e-b99c-5684697d3713 | note | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
6bcb213c-3a70-5d4b-a5a0-747e8d6b2a11 | note | HOLD POINT: Inprocess Inspection
f6293e92-9c4e-5c86-a03f-e0921f181316 | note | RECORDS: Dockets/Photos
794b1e76-8c1a-5c80-86f5-0ded649cafa2 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Signs/Belisha Disk
aec55d4f-4ba5-529f-aa91-e6cd28dc807e | note | VERIFICATION ACTIVITY: QA FORM
0969fa17-1180-512e-8b02-bb624d5b199f | note | METHODS OR REFERENCE: TDM Technical Standards
f8f7ad4b-3f6b-5dae-8dda-f4ec6f255dce | note | FREQUENCY: Each Sign
29a10319-235b-5452-9be6-14b71521fb7c | note | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
fe13e9cc-e906-5dd3-ab01-c06d768d5277 | note | HOLD POINT: Inprocess Inspection
1362a4f3-80b7-5491-ba31-d5dd2854b18e | note | RECORDS: Dockets/Photos
adf6dd15-746a-5af2-a8f8-94c3d079b866 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 6 - As built information
747dba81-6217-5331-9a65-fa7764609e2b | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
83dc5f45-241f-58b3-a1ce-796015303625 | note | METHODS OR REFERENCE:
b345d2c8-955f-5598-a11b-5b5295f0fa30 | note | FREQUENCY: Every Site
44b23300-0317-5cd4-9db2-b549817c8637 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
9a1db382-d430-5424-8cf4-9f5df6823046 | note | HOLD POINT: In Process Inspection
79dce571-7e3e-5293-965b-a367c258c0bd | note | RECORDS: Asbuilt records
e5824c87-82ec-5e9c-bf19-da1a3a7359ff | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
2662f4a9-ec32-55c9-a759-76660bb9cbc3 | note | Prepared by: Ajithkumar Ayyanar
edef619d-b297-51bc-a480-465dd7cdc793 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Weymouth South - ITP - Traffic Islands | itp | ITP - Traffic Islands | 98d89019-31d5-4012-a4d4-6d26600fbc1c
| section | Materials
| checkpoint | 1 - Mountable Kerb
f4310728-6289-5f61-b8fb-74a8212ea5c6 | note | VERIFICATION ACTIVITY: QA FORM
f84430ed-3a1e-5917-a049-2b6bef355ea1 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
0c9e4bf3-0058-5d1e-8922-f58891ce2e27 | note | FREQUENCY: Everysite
73f964a1-1b5f-5ad1-a9a4-52b8b96ffa4f | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
a353a48f-d697-542b-b338-95b6ad84fb3b | note | HOLD POINT: Inprocess Inspection
34184c54-db29-5921-b15b-9dd464bed4cd | note | RECORDS: FH concrete QA sheet, photos.
41a69fa8-964f-52d7-99c7-22a5f516d290 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
b1d857a3-3fb7-5852-b4a5-7cb0ab3ecebd | note | VERIFICATION ACTIVITY: Survey
fc5b6e9f-cd1b-5def-ad65-b58ebc981352 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
519279ad-31a7-5945-a593-a3b72a5a8b45 | note | FREQUENCY: Prior to commencement.
ac1ffda1-18a0-5880-a551-6ab24ba6830c | note | ACCEPTANCE CRITERIA: Survey
724e7953-9f4b-5d69-8be8-a3a9de78fd51 | note | HOLD POINT: As per Construction Drawings
b1e1fd92-758f-5393-a885-76eedff1e7d4 | note | RECORDS: Survey Receipt.
2ab0492d-8bd7-55cc-865a-264a332ecad8 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
64de5567-5ca7-5725-afdf-e66b4f6a1f88 | note | VERIFICATION ACTIVITY: QA FORM
d0fbb1e9-c3ec-5288-84eb-f433e659e3d9 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
acce7681-bed5-5066-b8d7-d0050dc54881 | note | FREQUENCY: Each Site
cee491c1-e3d6-5186-bd2d-1552539ae483 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
310d0283-41c1-5cd8-9f44-24ca6f90686d | note | HOLD POINT: Inprocess Inspection
a327090d-f500-559e-94af-1bc231826cf3 | note | RECORDS: Photos
0c3381a9-613b-5dd5-84ac-99f11729bd63 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
6f9e63a3-6759-59f9-8b99-4c86bdfde873 | note | VERIFICATION ACTIVITY: QA FORM
79988d9f-6561-5577-ba79-a352e9d0991c | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
bbaefa3f-64ec-542e-b94a-131b2e809eb7 | note | FREQUENCY: Each Site
439a7658-99c6-5373-b30f-f7bb972aef8b | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
2c0c9ac4-e5ec-568e-9e7b-a81620888910 | note | HOLD POINT: Inprocess Inspection
ac406a47-c4c6-55ce-bbb0-7c6d2a599dc6 | note | RECORDS: Photos
a773be43-1ae6-54f8-a222-063cd7cb4f03 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
28ed9cb7-04f2-5cc9-9e37-9d0bf6ef20e9 | note | VERIFICATION ACTIVITY: QA FORM
d5b96304-a992-571e-bbb9-245a28b23604 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
17be5442-7b4f-54b5-8ae2-47cea48cea8b | note | FREQUENCY: Each Site
4cff1460-5919-5c3e-95af-4a24b5b40b41 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide
d79a3918-80bc-5ab6-bca1-95939d24dcf5 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
dcf057dc-4909-511d-92d5-14d99935c63b | note | HOLD POINT: Inprocess Inspection
195f65b6-5406-5720-a170-60ab4bdc5f70 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
74f8dbe2-4bd3-5bb6-9295-a877935d2c37 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
aac2a09f-da04-5fb9-b3f0-b4cfdd1fbba7 | note | VERIFICATION ACTIVITY: Drawings
614a0b90-fc0c-5745-8029-3ed1214b7430 | note | METHODS OR REFERENCE:
a308d870-9c3e-5ac6-aac5-c9285752fb27 | note | FREQUENCY: Every Site
6352c9b6-4807-5599-a7bf-4ab15808b183 | note | ACCEPTANCE CRITERIA: As built drawings
ce2960de-aca8-54f3-ba61-40a1cb274804 | note | HOLD POINT: In Process Inspection
3f91a999-7872-5969-93be-190be25d7754 | note | RECORDS: Asbuilt records
38f55436-9b25-53ca-a5bb-dadc974c971d | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
d8b46ebb-85e8-5e86-b3c2-65983ae4cff9 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
6f51fe80-8c40-5341-ac77-9c8f4b9fbc2b | note | METHODS OR REFERENCE:
ad8907f3-71e9-5adf-b023-f1ecc97c524d | note | FREQUENCY: Every Site
90ff0c1a-3a61-526b-94b7-6c060d036cf3 | note | ACCEPTANCE CRITERIA: RAMM SHEET
f49c2aec-b38a-51d6-a623-ee776a6e26c6 | note | HOLD POINT: In Process Inspection
897511bb-9b4e-5e74-afef-f79bb81206af | note | RECORDS: Asbuilt records
fa93818f-d1b5-5006-9d84-ac531fbda0e1 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
586bf40a-2856-54f0-8ec9-7bf5ca126013 | note | Prepared by: Ajithkumar Ayyanar
0ad1fe3d-37b4-56dd-bf02-a88d9a0b5653 | note | Approving Delegate: Sumesh Sharma