## Enabling Works
ITP
Site Location |  |  | Weymouth Road
Enabling Works - Footpath, Kerb and channel
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer
Materials
1 | Kerb & Channel | QA FORM | TDM Technical Standards - KC0001 | Everysite | Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (CBR>5).Concrete 20MPa @28 Days | Inprocess Inspection | FH concrete QA sheet, photos. Concrete Plant Docket | Site Engineer
2 | Channel Level | QA FORM | TDM Technical Standards - KC0001 | Everysite | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set. | Inprocess Inspection | FH concrete QA sheet | Site Engineer
Construction
3 | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m Intervals | Subgrade - (CBR > 3) Basecourse - 100mm min. thickness Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish | Inprocess Inspection HOLD POINT Prepour inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
4 | Shared Path Pavement | QA FORM | IFC | 10m Intervals | Subgrade - (CBR > 3) Basecourse - 100mm min. thickness Clegg CIV > 12 Surfacing - Concrete 150mm with single layer of 665 mesh(50mm cover) and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish | Inprocess Inspection HOLD POINT Prepour inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
5 | Construction Joints | Visual | TDM Technical Standards - FP0002 | Everysite | All the sawcuts to be aligned to the Kerb joints. Dowel bar 6mm thickness to be used for the construction joints on the shared path | Inprocess Inspection | Photos | Site Engineer
6 | Fall Gradients | Visual | TDM Technical Standards - FP0001 | Everysite | 2% preferred (Min 1% and Max 3%) | Pre-pour inspection | Photos | Site Engineer
7 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | 10m Intervals | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones. | Inprocess Inspection | Photos | Site Engineer
8 | Tactiles | Visual | TDM Technical Standards - FP0010 | Each PX | Tile set out position to be agreed with ATOC and Engineer. Warning TGSI tiles should have 100mm concrete haunching underneath | Inprocess Inspection, Measurement | FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos | Site Engineer
|  | Visual | NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Everysite | Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. | Inprocess Inspection | Photos | Site Engineer
|  | Visual | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Everysite | Edge of warning indicators to set back 300mm from the face of the kerb or lane. | Inprocess Inspection | Photos | Site Engineer
|  | Visual | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Everysite | TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing | Inprocess Inspection | Materials Dockets | Site Engineer
9 | Pram Crossing | QA FORM | TDM Technical Standards - FP006 | Each Crossing | Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. Tactiles Directional & warning - 40mm; 600mm flares;width as per design; Slope no greater than 1:12 where practicably possible Clegg CIV > 12 | Inprocess Inspection | Photos | Site Engineer
10 | Timber Retaining Wall | Visual | TDM ST0004 - Version A Timber Retaining Wall Detail | Everysite | 125 x 125 H5 Timber Posts @ 1.5m centres installed with 20MPA concrete. Concrete footing to be 325mm diametre. 150 x 50 RS Tanalised H5 Timber Rails. Provide 5-10mm gap between rails Retaining wall slope to be 10:1 grade. Maximum height of wall = 1499mm. Minimum embedded depth of post to be same as exposed height unless less than 300mm, then depth = 300mm. Subsoil pipe to be lay as per TDM and connected to the nearest CP | Inprocess Inspection | Photos Material Dockets Dimension checks | Site Engineer
Asbuilts
10 | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | Asbuilt records | Supervisor and Engineer
11 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | RAMM Sheet | Site Engineer & PM
ITP APPROVAL
Prepared By |  | Ajithkumar Ayyanar | Initial | AA |  | Date: | 2024-08-01
Approving Delegate |  | Sumesh Sharma | Initial | SS |  | Date: | 2024-08-02

## Traffic Islands
ITP -Weymouth Road
Site Location |  |  | Weymouth Road
Traffic Islands
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Materials
1 | Mountable Kerb | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Everysite | Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint | Inprocess Inspection | FH concrete QA sheet, photos. | Site Engineer
Construction
2 | Survey Setout | Survey | Setout Kerb Alignment required to construct to design | Prior to commencement. | Survey | As per Construction Drawings | Survey Receipt. | Site Engineer
3 | Concrete Island | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | Kerbs to be haunced with 20MPa Concrete | Inprocess Inspection | Photos | Site Engineer
|  | QA FORM | TDM Technical Standards - IS0001 & IS0003 | Each Site | Basecourse to be 150mm min thickness of GAP65 | Inprocess Inspection | Photos | Site Engineer
4 | Concrete Infil | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide Cross Fall of 2% or max rise in centre of 180mm | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
Asbuilts
5 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Supervisor and Engineer
6 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Ajithkumar Ayyanar | Initial | AA |  | Date: | 2024-08-01
Approving Delegate |  | Sumesh Sharma | Initial | SS |  | Date: | 2024-08-02

## Ducting
|  |  |  | ITP |  |  | Approved |  | Signature
|  |  |  | Contract Name: | Weymouth Road |  | FH Engineer |  | AA
|  |  |  | Procedure: | Ducting for streetlight works |  | FH Project Engineer |  | SS
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | Traffic signal installation |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
Ducting
1 | Permits | H | Obtain Permits | As required | Document Review | Authorisation to work, dig permit and service provider permits | This ITP signed | Site Engineer
2 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
3.1 | Survey Setout | H | Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor. | Prior to commencement | Survey | Consistency with Drawings and Specifiactions | Survey Records | Site Engineer
3.2 |  | H | Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation. | Prior to commencement | Visual Inspection | Consistency with Drawings and Specifiactions | Photos / Engineers approval documentation | Site Engineer
4 | Locate existing services by hand digging/ hydrovac | W | Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation | Prior to Installation | Potholing | All conflicts have been located and survey as built recorded | Digging/Excavating Control Checklist | Site Engineer
5.1 | Material Compliance | H | Ensure duct pipes and poles are as per drawings and specification | Upon delivery to site | Ensure delivery docket matches materials | 50mm Ducts | Delivery Docket | Site Engineer
5.2
6.1 | Trenching | H | Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway | 10m Intervals | Visual Inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
6.2 |  | H | Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs | 10m Intervals | Measure | Ensure trench alignment and levels match the design drawings | Dipsheet & Photos | Site Engineer
7.1 | Duct Installation | W | Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct. | Prior to Installation | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
7.2 |  | H | Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
7.3 |  | H | Asbuilt Survey | 20m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Survey Records | Site Engineer
8 | Bedding | H | Lay min. 100mm gap20 or finer for bedding and haunching | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
9 | Warning Tape | H | Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines. | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
10 | Reninstatment | H | Ducts under berm reinstated with topsoil at the surface. Ducts running under any concrete structrues are carriageway need to be reinstated back to the same | Eash Site | Measure/Docket | Reinstatement as per designer acceptance
Comments:
Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Project manager |  |  |  |  | Signature: |  |  | Date:
QA checked By Contract Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design/AT Engineer: |  |  |  |  | Signature: |  |  | Date:
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ??

## Signage
ITP - Weymouth Road
Site Location |  |  | Weymouth Road
Signage
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like | Mandatory HOLD POINT - | Survey Receipt | Site Engineer
Materials
2 | Signs/Belisha Disk | QA FORM | TDM Technical Standards | Every site | All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers. | Inprocess Inspection | Dockets/Photos | Site Engineer
3 | Pole, Impact recovery post and Ground Socket | QA FORM | TDM Technical Standards | Every site | Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep | Inprocess Inspection | Dockets/Photos | Site Engineer
Construction
4a | Ground Socket | QA FORM | TDM Technical Standards | Each Socket | The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket. | Inprocess Inspection | Dockets/Photos with tape measurement | Site Engineer
4b | Pole and Impact recovery post | QA FORM | TDM Technical Standards | Each Post or pole | All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent thr pole rotation. The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation | Inprocess Inspection | Dockets/Photos | Site Engineer
5 | Signs/Belisha Disk | QA FORM | TDM Technical Standards | Each Sign | All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately. | Inprocess Inspection | Dockets/Photos | Site Engineer
Asbuilts
#REF! | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Ajithkumar Ayyanar | Initial | AA |  | Date: | 2024-08-01
Approving Delegate |  | Sumesh Sharma | Initial | SS |  | Date: | 2024-08-02

## Street Lighting
TO Be Provided