## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Enabling Works - Footpath, Kerb and Channel | itp |  |  |  |  | Weymouth Construction - Mahia Road - ITP - Enabling Works - Footpath, Kerb and Channel
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 1 - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (CBR>5).Concrete 20MPa @28 Days
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2 - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 3 - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
label | ○ Basecourse - 100mm min. thickness
label | ○ Clegg CIV > 12
label | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | HOLD POINT: Inprocess Inspection
label | HOLD POINT: Prepour inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Construction Joints
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TDM Technical Standards - FP0002
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: All the sawcuts to be aligned to the Kerb joints. Dowel bar 6mm thickness to be used for the construction joints on the shared path
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6 - Fall Gradients
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: 2% preferred (Min 1% and Max 3%)
label | HOLD POINT: Pre-pour inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 7 - Grass Berms
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 8 - Tactiles (1)
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TDM Technical Standards - FP0010
label | FREQUENCY: Each PX
label | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer.
label | ○ Warning TGSI tiles should have 100mm concrete haunching underneath
label | HOLD POINT: Inprocess Inspection, Measurement
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 8 - Tactiles (2)
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 8 - Tactiles (3)
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 8 - Tactiles (4)
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Materials Dockets
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 9 - Pram Crossing
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP006
label | FREQUENCY: Each Crossing
label | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
label | ○ Slope no greater than 1:12 where practicably possible
label | ○ Clegg CIV > 12
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 10 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 11 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: RAMM Sheet
label | ONSITE RESPONSIBILITY: Site Engineer & PM
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Ajithkumar Ayyanar
note | Approving Delegate: Sumesh Sharma
checklist | ITP - Traffic Islands | itp |  |  |  |  | Weymouth Construction - Mahia Road - ITP - Traffic Islands
section | Materials
checkpoint | 1 - Mountable Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, photos.
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 2 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: As per Construction Drawings
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Concrete Island (1)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Concrete Island (2)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Concrete Infil
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide
label | ○ Cross Fall of 2% or max rise in centre of 180mm
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 5 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 6 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Ajithkumar Ayyanar
note | Approving Delegate: Sumesh Sharma
checklist | ITP - Ducting | itp |  |  |  |  | Weymouth Construction - Mahia Road - ITP - Ducting
section | Ducting
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Obtain Permits
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
label | RECORDS: This ITP signed
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA:
label | RECORDS: Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Survey Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 -
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos / Engineers approval documentation
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Locate existing services by hand digging/ hydrovac
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
label | FREQUENCY: Prior to Installation
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
label | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
label | RECORDS: Digging/Excavating Control Checklist
checkpoint | 5.1 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure duct pipes and poles are as per drawings and specification
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
label | CONFORMANCE CRITERIA: 50mm Ducts
label | RECORDS: Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1 - Trenching
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 -
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
label | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
label | RECORDS: Dipsheet & Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.1 - Duct Installation
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
label | FREQUENCY: Prior to Installation
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
checkpoint | 7.2 -
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3 -
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Asbuilt Survey
label | FREQUENCY: 20m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Survey Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Bedding
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Lay min. 100mm gap20 or finer for bedding and haunching
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Warning Tape
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Reninstatment
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ducts under berm reinstated with topsoil at the surface. Ducts running under any concrete structrues are carriageway need to be reinstated back to the same
label | FREQUENCY: Eash Site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure/Docket
label | CONFORMANCE CRITERIA: Reinstatement as per designer acceptance
label | RECORDS:
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | QA Compiled By:
textbox | QA checked By Project manager:
textbox | QA checked By Contract Manager:
textbox | Accepted By Design/AT Engineer:
checklist | ITP - Signage | itp |  |  |  |  | Weymouth Construction - Mahia Road - ITP - Signage
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | ○ Alternatively like for like
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Survey Receipt
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Signs/Belisha Disk
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Pole, Impact recovery post and Ground Socket
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 4a - Ground Socket
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Socket
label | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos with tape measurement
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4b - Pole and Impact recovery post
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Post or pole
label | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
label | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Signs/Belisha Disk
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Sign
label | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 6 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Ajithkumar Ayyanar
note | Approving Delegate: Sumesh Sharma