## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
DTM-ITP-001- Clearing and Grubbing
| Scope |  |  | Clearing and Grubbing
Rows
|  | South of Davey - Clearing and Grubbing | dynamic | South of Davey | Clearing and Grubbing
|  | North of Davey - Clearing and Grubbing | dynamic | North of Davey | Clearing and Grubbing
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Preliminary Works
|  | 1.2 - Limits of work |  | 1.2 - Limits of work | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 1.3 - Implementation of environmental measures and controls |  | 1.3 - Implementation of environmental measures and controls | 1 - Preliminary Works
|  | 1.4 - Flora and Fauna |  | 1.4 - Flora and Fauna | 1 - Preliminary Works
|  | 1.5 - Protection of Existing Vegetation |  | 1.5 - Protection of Existing Vegetation | 1 - Preliminary Works
|  | 1.6 - Cultrual Heritage |  | 1.6 - Cultrual Heritage | 1 - Preliminary Works
|  | 1.7 - Authorisation for works |  | 1.7 - Authorisation for works | 1 - Preliminary Works
|  | 1.8 - Utilities |  | 1.8 - Utilities | 1 - Preliminary Works
|  | 1.9 - Traffic Management |  | 1.9 - Traffic Management | 1 - Preliminary Works
|  | 2.1 - Clear and grub trees and vegetation |  | 2.1 - Clear and grub trees and vegetation | 2 - Clear & Grub
|  | 2.3 - Clear and grub trees and vegetation |  | 2.3 - Clear and grub trees and vegetation | 2 - Clear & Grub
|  | 2.4 - Clear and grub trees and vegetation (embankment areas) |  | 2.4 - Clear and grub trees and vegetation (embankment areas) | 2 - Clear & Grub
|  | 2.5 - Clear and grub trees and vegetation at culvert sites |  | 2.5 - Clear and grub trees and vegetation at culvert sites | 2 - Clear & Grub
|  | 2.6 - Backfill holes |  | 2.6 - Backfill holes | 2 - Clear & Grub
|  | 2.7 - Dispose of Trees and vegetation |  | 2.7 - Dispose of Trees and vegetation | 2 - Clear & Grub
|  | 2.8 - Damage to Fencing |  | 2.8 - Damage to Fencing | 2 - Clear & Grub
|  | 2.9 - Salvage of Vegetation |  | 2.9 - Salvage of Vegetation | 2 - Clear & Grub
|  | ITP completed in accordance with FH’s Quality system Procedures & verifies lot compliance with specs. |  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 2 - Clear & Grub
|  | QAV - Print Name: | QAV - Print Name: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 2 - Clear & Grub
|  | QAV - Position: | QAV - Position: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 2 - Clear & Grub
|  | Fulton Hogan - Print Name: | Fulton Hogan - Print Name: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 2 - Clear & Grub
|  | Fulton Hogan - Position: | Fulton Hogan - Position: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 2 - Clear & Grub
DTM-ITP-003- Earthworks Demolition
| Scope |  |  | Earthworks Demolition
Rows
|  | South of Davey - Earthworks Demolition | dynamic | South of Davey | Earthworks Demolition
|  | North of Davey - Earthworks Demolition | dynamic | North of Davey | Earthworks Demolition
Columns
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation | 1 - Preliminary Works
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls | 1 - Preliminary Works
|  | 2.1 Survey Set-Out |  | 2.1 Survey Set-Out | 2 - Construction Works
|  | 2.2 Excavation Permit |  | 2.2 Excavation Permit | 2 - Construction Works
|  | 2.3 Material Categorisation |  | 2.3 Material Categorisation | 2 - Construction Works
|  | 2.4 Stripping of Topsoil |  | 2.4 Stripping of Topsoil | 2 - Construction Works
|  | 2.5 Type A Material |  | 2.5 Type A Material | 2 - Construction Works
|  | 2.5 Type B Material |  | 2.5 Type B Material | 2 - Construction Works
|  | 2.6 Acceptance of Rock Subgrade (when applicable) |  | 2.6 Acceptance of Rock Subgrade (when applicable) | 2 - Construction Works
|  | 2.7 Unsuitable Material |  | 2.7 Unsuitable Material | 2 - Construction Works
|  | 2.8 Groundwater |  | 2.8 Groundwater | 2 - Construction Works
|  | 2.9 Trimming and Level conformity |  | 2.9 Trimming and Level conformity | 2 - Construction Works
|  | 3.1 Proof Rolling |  | 3.1 Proof Rolling | 3 - Testing
|  | 3.2 Compaction Testing |  | 3.2 Compaction Testing | 3 - Testing
|  | 3.3 Materials Property Testing |  | 3.3 Materials Property Testing | 3 - Testing
|  | Final Inspection |  | Final Inspection | 3 - Testing
|  | Final Inspection - Name: | Print Name: | Final Inspection | 3 - Testing
|  | Final Inspection - Position: | Position: | Final Inspection | 3 - Testing