## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
FH-ZU2-QU-ITP001 - Demolition of Existing Pavements
| Scope |  |  | FH-ZU2-QU-ITP001 - Demolition of Existing Infrastructure
Rows
|  | FH-ZU2-QU-ITP001 - Demolition of Existing Infrastructure | dynamic | FH-ZU2-QU-ITP001 - Demolition of Existing Infrastructure
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities
|  | 1.2 - Demolition Work Plan |  | 1.2 - Demolition Work Plan | 1.0 - Preliminary Activities
|  | 1.3 - Dilapidation Report |  | 1.3 - Dilapidation Report | 1.0 - Preliminary Activities
|  | 1.4 - Existing Service Identification & Protection |  | 1.4 - Existing Service Identification & Protection | 1.0 - Preliminary Activities
|  | 1.5 - Execution of Demolition works |  | 1.5 - Execution of Demolition works | 1.0 - Preliminary Activities
|  | 1.6 - Implementation of all measures and controls |  | 1.6 - Implementation of all measures and controls | 1.0 - Preliminary Activities
|  | 1.7 - Testing of Demolition Materials |  | 1.7 - Testing of Demolition Materials | 1.0 - Preliminary Activities
|  | 1.8 - Excavation Permits |  | 1.8 - Excavation Permits | 1.0 - Preliminary Activities
|  | 2.1 - Definition of a works area (survey) |  | 2.1 - Definition of a works area (survey) | 2.0 - Demolition of Existing Pavement Works
|  | 2.2 - Temporary Supports |  | 2.2 - Temporary Supports | 2.0 - Demolition of Existing Pavement Works
|  | 2.3 - Disposal of Material |  | 2.3 - Disposal of Material | 2.0 - Demolition of Existing Pavement Works
|  | 2.4 - Asbestos Materials |  | 2.4 - Asbestos Materials | 2.0 - Demolition of Existing Pavement Works
|  | 2.5 - Made Good |  | 2.5 - Made Good | 2.0 - Demolition of Existing Pavement Works
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP002 - Site Establishment
| Scope |  |  | FH-ZU2-QU-ITP002 - Site Establishment
Rows
|  | FH-ZU2-QU-ITP002 - Site Establishment | dynamic | FH-ZU2-QU-ITP002 - Site Establishment
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities
|  | 1.2 - Dilapidation Report |  | 1.2 - Dilapidation Report | 1.0 - Preliminary Activities
|  | 1.3 - Existing Service Identification & Protection |  | 1.3 - Existing Service Identification & Protection | 1.0 - Preliminary Activities
|  | 1.4 - Implementation of control measures |  | 1.4 - Implementation of control measures | 1.0 - Preliminary Activities
|  | 1.5 - Testing |  | 1.5 - Testing | 1.0 - Preliminary Activities
|  | 1.6 - Excavation Permits |  | 1.6 - Excavation Permits | 1.0 - Preliminary Activities
|  | 1.7 - Geotechnical Testing |  | 1.7 - Geotechnical Testing | 1.0 - Preliminary Activities
|  | 2.1 - Definition of a works area (survey) |  | 2.1 - Definition of a works area (survey) | 2.0 - Building Hardstands
|  | 2.2 - Preparing subgrade |  | 2.2 - Preparing subgrade | 2.0 - Building Hardstands
|  | 2.3 - Disposal of Material |  | 2.3 - Disposal of Material | 2.0 - Building Hardstands
|  | 2.4 - Building Hardstand |  | 2.4 - Building Hardstand | 2.0 - Building Hardstands
|  | 2.5 - Building Crossways |  | 2.5 - Building Crossways | 2.0 - Building Hardstands
|  | 2.6 - Installing Fencing |  | 2.6 - Installing Fencing | 2.0 - Building Hardstands
|  | 3.1 - Landing and Levelling Sheds |  | 3.1 - Landing and Levelling Sheds | 3.0 - Mobilization and Set Up
|  | 3.2 - Erecting Hayshed |  | 3.2 - Erecting Hayshed | 3.0 - Mobilization and Set Up
|  | 3.3 - Connecting electrical and plumbing services and appliances |  | 3.3 - Connecting electrical and plumbing services and appliances | 3.0 - Mobilization and Set Up
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP003 - Stripping Topsoil and Bulk Excavation
| Scope |  |  | FH-ZU2-QU-ITP003 - Stripping Topsoil and Bulk Excavation
Rows
|  | FH-ZU2-QU-ITP003 - Stripping Topsoil and Bulk Excavation | dynamic | FH-ZU2-QU-ITP003 - Stripping Topsoil and Bulk Excavation
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities
|  | 1.3 - Survey |  | 1.3 - Survey | 1.0 - Preliminary Activities
|  | 1.4 - APAM permits |  | 1.4 - APAM permits | 1.0 - Preliminary Activities
|  | 1.5 - Fulton Hogan Permits |  | 1.5 - Fulton Hogan Permits | 1.0 - Preliminary Activities
|  | 1.8 - Plant and Equipment |  | 1.8 - Plant and Equipment | 1.0 - Preliminary Activities
|  | 2.1 - Site Preparation |  | 2.1 - Site Preparation | 2.0 - Stripping / Bulk Excavation
|  | 2.2 - Dust & FOD control |  | 2.2 - Dust & FOD control | 2.0 - Stripping / Bulk Excavation
|  | 2.3 - Stripping Top Soil |  | 2.3 - Stripping Top Soil | 2.0 - Stripping / Bulk Excavation
|  | 2.4 - Excavation |  | 2.4 - Excavation | 2.0 - Stripping / Bulk Excavation
|  | 2.5 - Batters & Temporary Support |  | 2.5 - Batters & Temporary Support | 2.0 - Stripping / Bulk Excavation
|  | 2.6 - Excavation – Detailed Trim |  | 2.6 - Excavation – Detailed Trim | 2.0 - Stripping / Bulk Excavation
|  | 2.6 - Contaminated Materials (if found) |  | 2.6 - Contaminated Materials (if found) | 2.0 - Stripping / Bulk Excavation
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP004 - Select Fill Placement
| Scope |  |  | FH-ZU2-QU-ITP004 - Select Fill Placement
Rows
|  | FH-ZU2-QU-ITP004 - Select Fill Placement | dynamic | FH-ZU2-QU-ITP004 - Select Fill Placement
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities
|  | 1.3 - Survey |  | 1.3 - Survey | 1.0 - Preliminary Activities
|  | 1.4 - Select Fill Material Source (Under Pavements, Imported) |  | 1.4 - Select Fill Material Source (Under Pavements, Imported) | 1.0 - Preliminary Activities
|  | 1.4 - Checked by: Principles Representative - Aconex: | Checked by: Principles Representative - Aconex: | 1.4 - Select Fill Material Source (Under Pavements, Imported) | 1.0 - Preliminary Activities
|  | 1.5 - Select Fill Material Source (Other Locations, Site Won) |  | 1.5 - Select Fill Material Source (Other Locations, Site Won) | 1.0 - Preliminary Activities
|  | 1.5 - Checked by: Principles Representative - Aconex: | Checked by: Principles Representative - Aconex: | 1.5 - Select Fill Material Source (Other Locations, Site Won) | 1.0 - Preliminary Activities
|  | 1.6 - Submission of Select Fill Methodology Plan |  | 1.6 - Submission of Select Fill Methodology Plan | 1.0 - Preliminary Activities
|  | 1.7 - Starting Works |  | 1.7 - Starting Works | 1.0 - Preliminary Activities
|  | 1.7 - Checked by: Principles Representative - SP8 Aconex: | Checked by: Principles Representative - SP8 Aconex: | 1.7 - Starting Works | 1.0 - Preliminary Activities
|  | 1.7 - Checked by: Principles Representative - SP9 Aconex: | Checked by: Principles Representative - SP9 Aconex: | 1.7 - Starting Works | 1.0 - Preliminary Activities
|  | 1.7 - Checked by: Principles Representative - SP10 Aconex: | Checked by: Principles Representative - SP10 Aconex: | 1.7 - Starting Works | 1.0 - Preliminary Activities
|  | 1.8 - Preparation of Underlying Surface Layer |  | 1.8 - Preparation of Underlying Surface Layer | 1.0 - Preliminary Activities
|  | 1.9 - Cut Floor Level |  | 1.9 - Cut Floor Level | 1.0 - Preliminary Activities
|  | 2.1 - Select Fill Placement |  | 2.1 - Select Fill Placement | 2.0 - Select Fill Works – Imported Material - Under Pavements
|  | 2.1 - First layer of placed material is dropped & spread using dozer/grader/similar plant to prevent trafficking 7mm seal | ○ The first layer of placed material is dropped and spread using a dozer, grader, or similar plant to prevent trafficking 7mm seal | 2.1 - Select Fill Placement | 2.0 - Select Fill Works – Imported Material - Under Pavements
|  | 2.1 - Plant & equipment does not traffic 7mm Aggregate Seal | ○ Plant and equipment does not traffic 7mm Aggregate Seal | 2.1 - Select Fill Placement | 2.0 - Select Fill Works – Imported Material - Under Pavements
|  | 2.2 - Proof Rolling & Compaction |  | 2.2 - Proof Rolling & Compaction | 2.0 - Select Fill Works – Imported Material - Under Pavements
|  | 2.3 - Final Trimming and Surface Finishing |  | 2.3 - Final Trimming and Surface Finishing | 2.0 - Select Fill Works – Imported Material - Under Pavements
|  | 3.1 - Select Fill Placement |  | 3.1 - Select Fill Placement | 3.0 - Select Fill Works – Site Won Material – Other Areas (Not Under Pavements)
|  | 3.2 - Proof Rolling & Compaction |  | 3.2 - Proof Rolling & Compaction | 3.0 - Select Fill Works – Site Won Material – Other Areas (Not Under Pavements)
|  | 3.2 - Proof Rolling & Compaction |  | 3.2 - Proof Rolling & Compaction | 3.0 - Select Fill Works – Site Won Material – Other Areas (Not Under Pavements)
|  | 4.1 - Classification and Testing (imported material, under pavements only) |  | 4.1 - Classification and Testing (imported material, under pavements only) | 4.0 - Testing & Acceptance
|  | 4.2 - Lot Acceptance |  | 4.2 - Lot Acceptance | 4.0 - Testing & Acceptance
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP005 - Stormwater Drainage
| Scope |  |  | FH-ZU2-QU-ITP005 - Stormwater Drainage
Rows
|  | FH-ZU2-QU-ITP005 - Stormwater Drainage | dynamic | FH-ZU2-QU-ITP005 - Stormwater Drainage
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities
|  | 1.3 - Excavation Permit |  | 1.3 - Excavation Permit | 1.0 - Preliminary Activities
|  | 2.1 - Drainage Pipes (RCPs) |  | 2.1 - Drainage Pipes (RCPs) | 2.0 - Stormwater Products and Materials
|  | 2.2 - Pipe Support Cradles |  | 2.2 - Pipe Support Cradles | 2.0 - Stormwater Products and Materials
|  | 2.3 - Encasement Material |  | 2.3 - Encasement Material | 2.0 - Stormwater Products and Materials
|  | 2.4 - Backfill Material |  | 2.4 - Backfill Material | 2.0 - Stormwater Products and Materials
|  | 3.1 - RCP Delivery |  | 3.1 - RCP Delivery | 3.0 - Stormwater Delivery
|  | 4.1 - Survey Setout |  | 4.1 - Survey Setout | 4.0 - Construction Activities
|  | 4.2 - Excavation |  | 4.2 - Excavation | 4.0 - Construction Activities
|  | 4.3 - Site Dewatering |  | 4.3 - Site Dewatering | 4.0 - Construction Activities
|  | 4.4 - Confirm Ground Conditions |  | 4.4 - Confirm Ground Conditions | 4.0 - Construction Activities
|  | 4.5 - Bedding |  | 4.5 - Bedding | 4.0 - Construction Activities
|  | 4.6 - Laying of Pipes (Sample) |  | 4.6 - Laying of Pipes (Sample) | 4.0 - Construction Activities
|  | 4.7 - Laying and Jointing of Pipes |  | 4.7 - Laying and Jointing of Pipes | 4.0 - Construction Activities
|  | 4.8 - Survey |  | 4.8 - Survey | 4.0 - Construction Activities
|  | 4.9 - Backfill Materials |  | 4.9 - Backfill Materials | 4.0 - Construction Activities
|  | 5.1 - Compaction Requirements (RCPs) |  | 5.1 - Compaction Requirements (RCPs) | 5.0 - Testing and Inspection
|  | 5.2 - Inspection of drainage lines |  | 5.2 - Inspection of drainage lines | 5.0 - Testing and Inspection
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP006 - Subsoil Drainage
| Scope |  |  | FH-ZU2-QU-ITP006 - Subsoil Drainage
Rows
|  | FH-ZU2-QU-ITP006 - Subsoil Drainage | dynamic | FH-ZU2-QU-ITP006 - Subsoil Drainage
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities
|  | 1.3 - Excavation Permit |  | 1.3 - Excavation Permit | 1.0 - Preliminary Activities
|  | 2.1 - Subsoil Drainage Pipes |  | 2.1 - Subsoil Drainage Pipes | 2.0 - Subsoil Materials
|  | 2.2 - Bedding and Backfill |  | 2.2 - Bedding and Backfill | 2.0 - Subsoil Materials
|  | 2.3 - Geotextile Fabric |  | 2.3 - Geotextile Fabric | 2.0 - Subsoil Materials
|  | 3.1 - Trench Excavation |  | 3.1 - Trench Excavation | 3.0 - Excavation and Installation
|  | 3.2 - Geotextile Placement |  | 3.2 - Geotextile Placement | 3.0 - Excavation and Installation
|  | 3.3 - Bedding |  | 3.3 - Bedding | 3.0 - Excavation and Installation
|  | 3.4 - Laying and Jointing of Pipes |  | 3.4 - Laying and Jointing of Pipes | 3.0 - Excavation and Installation
|  | 3.5 - Backfill |  | 3.5 - Backfill | 3.0 - Excavation and Installation
|  | 3.6 - Geotextile Protection |  | 3.6 - Geotextile Protection | 3.0 - Excavation and Installation
|  | 3.7 - Subsoil Drain Outlet |  | 3.7 - Subsoil Drain Outlet | 3.0 - Excavation and Installation
|  | 3.8 - Flush out Risers |  | 3.8 - Flush out Risers | 3.0 - Excavation and Installation
|  | 4.1 - Flushing Test |  | 4.1 - Flushing Test | 4.0 - Post Construction
|  | 4.2 - Records |  | 4.2 - Records | 4.0 - Post Construction
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP007 - Precast Drainage Structures
| Scope |  |  | FH-ZU2-QU-ITP007 - Precast Drainage Structures
Rows
|  | FH-ZU2-QU-ITP007 - Precast Drainage Structures | dynamic | FH-ZU2-QU-ITP007 - Precast Drainage Structures
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminaries
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminaries
|  | 1.3 - Excavation Permit |  | 1.3 - Excavation Permit | 1.0 - Preliminaries
|  | 2.1 - Precast Structures |  | 2.1 - Precast Structures | 2.0 - Material Approvals
|  | 2.2 - Access Cover and Grates |  | 2.2 - Access Cover and Grates | 2.0 - Material Approvals
|  | 2.3 - Box Culverts Bedding, Side, Overlay and Backfill Zone Materials. |  | 2.3 - Box Culverts Bedding, Side, Overlay and Backfill Zone Materials. | 2.0 - Material Approvals
|  | 2.4 - Blinding for Drainage Pits and Headwalls |  | 2.4 - Blinding for Drainage Pits and Headwalls | 2.0 - Material Approvals
|  | 2.5 - Geotextile Fabric |  | 2.5 - Geotextile Fabric | 2.0 - Material Approvals
|  | 3.1 - Precast Structure Delivery |  | 3.1 - Precast Structure Delivery | 3.0 - Material Receival
|  | 4.1 - Survey Setout |  | 4.1 - Survey Setout | 4.0 - Drainage Pit, Headwall and Culvert Installation
|  | 4.2 - Excavation |  | 4.2 - Excavation | 4.0 - Drainage Pit, Headwall and Culvert Installation
|  | 4.3 - Confirm Ground Conditions |  | 4.3 - Confirm Ground Conditions | 4.0 - Drainage Pit, Headwall and Culvert Installation
|  | 4.4 - Blinding for Drainage Pits and Headwalls |  | 4.4 - Blinding for Drainage Pits and Headwalls | 4.0 - Drainage Pit, Headwall and Culvert Installation
|  | 4.5 - Bedding for Box Culverts |  | 4.5 - Bedding for Box Culverts | 4.0 - Drainage Pit, Headwall and Culvert Installation
|  | 4.6 - Positioning of Precast Structures |  | 4.6 - Positioning of Precast Structures | 4.0 - Drainage Pit, Headwall and Culvert Installation
|  | 4.7 - Backfill Materials for Box Culverts |  | 4.7 - Backfill Materials for Box Culverts | 4.0 - Drainage Pit, Headwall and Culvert Installation
|  | 4.8 - Compaction Requirements (Box Culvert) |  | 4.8 - Compaction Requirements (Box Culvert) | 4.0 - Drainage Pit, Headwall and Culvert Installation
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP008 - Lime Stabilisation / Subgrade Improvement
| Scope |  |  | FH-ZU2-QU-ITP008 - Lime Stabilisation / Subgrade Improvement
Rows
|  | FH-ZU2-QU-ITP008 - Lime Stabilisation / Subgrade Improvement | dynamic | FH-ZU2-QU-ITP008 - Lime Stabilisation / Subgrade Improvement
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Materials and Trials
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Materials and Trials
|  | 1.3 - Current excavation permit |  | 1.3 - Current excavation permit | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Materials and Trials
|  | 1.4 - Preceding Lots Satisfactory |  | 1.4 - Preceding Lots Satisfactory | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Materials and Trials
|  | 1.5 - Test Pits |  | 1.5 - Test Pits | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Materials and Trials
|  | 1.6 - Stabilised Lime Content |  | 1.6 - Stabilised Lime Content | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Materials and Trials
|  | 1.6 - Principles Rep - Aconex Ref: | Principles Rep - Aconex Ref: | 1.6 - Stabilised Lime Content | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Materials and Trials
|  | 1.7 - Stabilised Soil Trial |  | 1.7 - Stabilised Soil Trial | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Materials and Trials
|  | 2.0 - Pre-treatment of earthworks |  | 2.0 - Pre-treatment of earthworks | 2.0 - Subgrade Preparation & Replacement
|  | 2.1 - Rip Subgrade |  | 2.1 - Rip Subgrade | 2.0 - Subgrade Preparation & Replacement
|  | 3.1 - Layer Parameters |  | 3.1 - Layer Parameters | 3.0 - Layer Placement
|  | 3.2 - Prior to Works Starting |  | 3.2 - Prior to Works Starting | 3.0 - Layer Placement
|  | 3.3 - Spreading of Lime |  | 3.3 - Spreading of Lime | 3.0 - Layer Placement
|  | 3.4 - Spreading of Lime |  | 3.4 - Spreading of Lime | 3.0 - Layer Placement
|  | 3.5 - Mixing |  | 3.5 - Mixing | 3.0 - Layer Placement
|  | 3.6 - Mixing |  | 3.6 - Mixing | 3.0 - Layer Placement
|  | 3.7 - Joints |  | 3.7 - Joints | 3.0 - Layer Placement
|  | 3.8 - Compaction |  | 3.8 - Compaction | 3.0 - Layer Placement
|  | 3.9 - Trimming |  | 3.9 - Trimming | 3.0 - Layer Placement
|  | 3.10 - Protection |  | 3.10 - Protection | 3.0 - Layer Placement
|  | 3.11 - Curing |  | 3.11 - Curing | 3.0 - Layer Placement
|  | 4.1 - Proof Roll |  | 4.1 - Proof Roll | 4.0 - Acceptance – Lime Stabilisation
|  | 4.2 - Surface Smoothness |  | 4.2 - Surface Smoothness | 4.0 - Acceptance – Lime Stabilisation
|  | 4.3 - Strength Testing (CBR) |  | 4.3 - Strength Testing (CBR) | 4.0 - Acceptance – Lime Stabilisation
|  | 4.4 - Field Dry Density |  | 4.4 - Field Dry Density | 4.0 - Acceptance – Lime Stabilisation
|  | 4.5 - Surface Level |  | 4.5 - Surface Level | 4.0 - Acceptance – Lime Stabilisation
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP009 - Unbound Pavements (FCR & RCC)
| Scope |  |  | FH-ZU2-QU-ITP009 - Unbound Pavements (FCR & RCC)
Rows
|  | FH-ZU2-QU-ITP009 - Unbound Pavements (FCR & RCC) | dynamic | FH-ZU2-QU-ITP009 - Unbound Pavements (FCR & RCC)
Columns
|  | 1.1 - The current revision drawings are being used including subcontractors copy. |  | 1.1 - The current revision drawings are being used including subcontractors copy. | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.2 - Implementation of all measures and controls, weather, and material properties. |  | 1.2 - Implementation of all measures and controls, weather, and material properties. | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.3 - Material Report - Fine Crushed Rock (FCR) Material & Recycle Crushed Concrete (RCC) |  | 1.3 - Material Report - Fine Crushed Rock (FCR) Material & Recycle Crushed Concrete (RCC) | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.4 - Reference Samples |  | 1.4 - Reference Samples | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.5 - Trial Section |  | 1.5 - Trial Section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.6 - Compaction Equipment |  | 1.6 - Compaction Equipment | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.7 - Testing Determinations |  | 1.7 - Testing Determinations | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 2.1 - Layer Placement Parameters |  | 2.1 - Layer Placement Parameters | 2.0 - Placement of Sub-basecourse and Basecourse
|  | 2.2 - Placement Checks |  | 2.2 - Placement Checks | 2.0 - Placement of Sub-basecourse and Basecourse
|  | 2.3 - Compaction Check |  | 2.3 - Compaction Check | 2.0 - Placement of Sub-basecourse and Basecourse
|  | 2.4 - Services & Culverts |  | 2.4 - Services & Culverts | 2.0 - Placement of Sub-basecourse and Basecourse
|  | 2.5 - Protection of Layer |  | 2.5 - Protection of Layer | 2.0 - Placement of Sub-basecourse and Basecourse
|  | 2.6 - Proof Rolling |  | 2.6 - Proof Rolling | 2.0 - Placement of Sub-basecourse and Basecourse
|  | 2.7 - Completion of Remedial Works (if required) |  | 2.7 - Completion of Remedial Works (if required) | 2.0 - Placement of Sub-basecourse and Basecourse
|  | 3.1 - Survey Conformance |  | 3.1 - Survey Conformance | 3.0 - Testing, Lot Size and Compliance
|  | 3.2 - Surface Smoothness |  | 3.2 - Surface Smoothness | 3.0 - Testing, Lot Size and Compliance
|  | 3.3 - Layer Thickness |  | 3.3 - Layer Thickness | 3.0 - Testing, Lot Size and Compliance
|  | 3.4 - Degree of Saturation - Sub-Basecourse or Basecourse |  | 3.4 - Degree of Saturation - Sub-Basecourse or Basecourse | 3.0 - Testing, Lot Size and Compliance
|  | 3.5 - Field Dry Density |  | 3.5 - Field Dry Density | 3.0 - Testing, Lot Size and Compliance
|  | 3.6 - Quality Assurance Records |  | 3.6 - Quality Assurance Records | 3.0 - Testing, Lot Size and Compliance
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP010 - Cement Treated Base
| Scope |  |  | FH-ZU2-QU-ITP010 - Cement Treated Base
Rows
|  | FH-ZU2-QU-ITP010 - Cement Treated Base | dynamic | FH-ZU2-QU-ITP010 - Cement Treated Base
Columns
|  | 1.1 - The current revision drawings are being used including subcontractors copy. |  | 1.1 - The current revision drawings are being used including subcontractors copy. | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 2.1 - Submission of Mix Design |  | 2.1 - Submission of Mix Design | 2.0 - Cement Treated Base Documentation & Trial
|  | 2.2 - Supply of Information on Materials Source |  | 2.2 - Supply of Information on Materials Source | 2.0 - Cement Treated Base Documentation & Trial
|  | 2.3 - Production and Construction Trial |  | 2.3 - Production and Construction Trial | 2.0 - Cement Treated Base Documentation & Trial
|  | 2.4 - Placement of CTB Methodology |  | 2.4 - Placement of CTB Methodology | 2.0 - Cement Treated Base Documentation & Trial
|  | 2.5 - Provision of Material Samples |  | 2.5 - Provision of Material Samples | 2.0 - Cement Treated Base Documentation & Trial
|  | 3.1 - Subgrade, Basecourse Preparation |  | 3.1 - Subgrade, Basecourse Preparation | 3.0 - Placement of Cement Treated Base
|  | 3.2 - Layer Placement Parameters |  | 3.2 - Layer Placement Parameters | 3.0 - Placement of Cement Treated Base
|  | 3.3 - CTB Placement – Weather |  | 3.3 - CTB Placement – Weather | 3.0 - Placement of Cement Treated Base
|  | 3.4 - CTB Placement – Checks |  | 3.4 - CTB Placement – Checks | 3.0 - Placement of Cement Treated Base
|  | 3.5 - CTB Compaction – Checks |  | 3.5 - CTB Compaction – Checks | 3.0 - Placement of Cement Treated Base
|  | 3.6 - Curing & Protection |  | 3.6 - Curing & Protection | 3.0 - Placement of Cement Treated Base
|  | 3.7 - Post Placement CTB Inspection |  | 3.7 - Post Placement CTB Inspection | 3.0 - Placement of Cement Treated Base
|  | 4.1 - Field Dry Density |  | 4.1 - Field Dry Density | 4.0 - Acceptance, Compliance, Controls and Quality Assurance
|  | 4.2 - Moisture Tests |  | 4.2 - Moisture Tests | 4.0 - Acceptance, Compliance, Controls and Quality Assurance
|  | 4.3 - Strength Testing |  | 4.3 - Strength Testing | 4.0 - Acceptance, Compliance, Controls and Quality Assurance
|  | 4.4 - Process Control |  | 4.4 - Process Control | 4.0 - Acceptance, Compliance, Controls and Quality Assurance
|  | 4.5 - CTB Layer Thickness |  | 4.5 - CTB Layer Thickness | 4.0 - Acceptance, Compliance, Controls and Quality Assurance
|  | 4.6 - Quality Assurance Records |  | 4.6 - Quality Assurance Records | 4.0 - Acceptance, Compliance, Controls and Quality Assurance
|  | 4.7 - Survey As-Built Report |  | 4.7 - Survey As-Built Report | 4.0 - Acceptance, Compliance, Controls and Quality Assurance
|  | 4.8 - Surface Smoothness |  | 4.8 - Surface Smoothness | 4.0 - Acceptance, Compliance, Controls and Quality Assurance
|  | 4.9 - Correction of Nonconforming Work |  | 4.9 - Correction of Nonconforming Work | 4.0 - Acceptance, Compliance, Controls and Quality Assurance
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP011 - Concrete Production
| Scope |  |  | FH-ZU2-QU-ITP011 - Concrete Production
Rows
|  | FH-ZU2-QU-ITP011 - Concrete Production | dynamic | FH-ZU2-QU-ITP011 - Concrete Production
Columns
|  | 1.1 - AS1379 4.2.1 |  | 1.1 - AS1379 4.2.1 | 1 - Plant
|  | 1.2 - HOL QMS PN6.1 |  | 1.2 - HOL QMS PN6.1 | 1 - Plant
|  | 1.3 - AS1379.3.3.2 |  | 1.3 - AS1379.3.3.2 | 1 - Plant
|  | 1.4 - AS1379.3.4.2 |  | 1.4 - AS1379.3.4.2 | 1 - Plant
|  | 1.5 - AS1379.3.4.2 |  | 1.5 - AS1379.3.4.2 | 1 - Plant
|  | 2.1 - AS1379.2.2 |  | 2.1 - AS1379.2.2 | 2 - Cementitous materials
|  | 2.1 - BECA Cl 11.4.7, 11.24.5 |  | 2.1 - BECA Cl 11.4.7, 11.24.5 | 2 - Cementitous materials
|  | 2.2 - AS1379.2.2 |  | 2.2 - AS1379.2.2 | 2 - Cementitous materials
|  | 2.3 - AS1379.2.2 |  | 2.3 - AS1379.2.2 | 2 - Cementitous materials
|  | 3.1 - AS1379.2.3 |  | 3.1 - AS1379.2.3 | 3 - Coarse Aggregate
|  | 3.2 - AS1379.2.3 |  | 3.2 - AS1379.2.3 | 3 - Coarse Aggregate
|  | 3.3 - AS1379.2.3 |  | 3.3 - AS1379.2.3 | 3 - Coarse Aggregate
|  | 3.4 - AS1379.2.3 |  | 3.4 - AS1379.2.3 | 3 - Coarse Aggregate
|  | 3.5 - AS1379.2.3 |  | 3.5 - AS1379.2.3 | 3 - Coarse Aggregate
|  | 3.6 - AS1379.2.3 |  | 3.6 - AS1379.2.3 | 3 - Coarse Aggregate
|  | 3.7 - AS1379.2.3 |  | 3.7 - AS1379.2.3 | 3 - Coarse Aggregate
|  | 3.8 - AS1379.2.3 |  | 3.8 - AS1379.2.3 | 3 - Coarse Aggregate
|  | 3.9 - BECA Cl 11.4.6.2 |  | 3.9 - BECA Cl 11.4.6.2 | 3 - Coarse Aggregate
|  | 4.1 - AS1379.2.3 |  | 4.1 - AS1379.2.3 | 4 - Fine Aggregate
|  | 4.2 - AS1379.2.3 |  | 4.2 - AS1379.2.3
|  | 4.3 - AS1379.2.3 |  | 4.3 - AS1379.2.3 | 4 - Fine Aggregate
|  | 4.4 - AS1379.2.3 |  | 4.4 - AS1379.2.3 | 4 - Fine Aggregate
|  | 4.5 - AS1379.2.3 |  | 4.5 - AS1379.2.3 | 4 - Fine Aggregate
|  | 4.6 - AS1379.2.3 |  | 4.6 - AS1379.2.3 | 4 - Fine Aggregate
|  | 4.7 - AS1379.2.3 |  | 4.7 - AS1379.2.3 | 4 - Fine Aggregate
|  | 4.8 - AS1379.2.3 |  | 4.8 - AS1379.2.3 | 4 - Fine Aggregate
|  | 4.9 - BECA Cl 11.4.6.2 |  | 4.9 - BECA Cl 11.4.6.2 | 4 - Fine Aggregate
|  | 5.1 - AS1379.2.4 |  | 5.1 - AS1379.2.4 | 5 - Water
|  | 5.2 - AS1379.2.4 |  | 5.2 - AS1379.2.4 | 5 - Water
|  | 6.1 - AS1379.2.5 |  | 6.1 - AS1379.2.5 | 6 - Admixtures
|  | 6.2 - AS1379.2.5 |  | 6.2 - AS1379.2.5 | 6 - Admixtures
|  | 6.3 - AS1379.2.5 |  | 6.3 - AS1379.2.5 | 6 - Admixtures
|  | 6.4 - AS1379.2.5 |  | 6.4 - AS1379.2.5 | 6 - Admixtures
|  | 7.1 - HOL QMS PN6.1 |  | 7.1 - HOL QMS PN6.1 | 7 - Transport
|  | 7.2 - AS1379 3.5.1 (a) |  | 7.2 - AS1379 3.5.1 (a) | 7 - Transport
FH-ZU2-QU-ITP012 - High Early Strength Lean Concrete Pavement Production
| Scope |  |  | FH-ZU2-QU-ITP012 - High Early Strength Lean Concrete Pavement Production
Rows
|  | FH-ZU2-QU-ITP012 - High Early Strength Lean Concrete Pavement Production | dynamic | FH-ZU2-QU-ITP012 - High Early Strength Lean Concrete Pavement Production
Columns
FH-ZU2-QU-ITP013 - PCC Pavements
| Scope |  |  | FH-ZU2-QU-ITP013 - PCC Pavements
Rows
|  | FH-ZU2-QU-ITP013 - PCC Pavements | dynamic | FH-ZU2-QU-ITP013 - PCC Pavements
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities
|  | 1.7 - Impermeable Blanket Material Submission |  | 1.7 - Impermeable Blanket Material Submission | 1.0 - Preliminary Activities
|  | 2.1 - Formwork Installation |  | 2.1 - Formwork Installation | 2.0 - Pre-Placement Activities
|  | 2.2 - Pre-pour checklist |  | 2.2 - Pre-pour checklist | 2.0 - Pre-Placement Activities
|  | 2.3 - Pre-pour inspection |  | 2.3 - Pre-pour inspection | 2.0 - Pre-Placement Activities
|  | 2.4 - Weather Forecast Checks |  | 2.4 - Weather Forecast Checks | 2.0 - Pre-Placement Activities
|  | 3.1 - Place, Spread and Compact Concrete |  | 3.1 - Place, Spread and Compact Concrete | 3.0 - Placing Concrete
|  | 3.2 - Concrete Deliveries |  | 3.2 - Concrete Deliveries | 3.0 - Placing Concrete
|  | 3.3 - Evaporation Rate |  | 3.3 - Evaporation Rate | 3.0 - Placing Concrete
|  | 3.4 - Hot Weather Concreting |  | 3.4 - Hot Weather Concreting | 3.0 - Placing Concrete
|  | 3.5 - Cold Weather Concreting |  | 3.5 - Cold Weather Concreting | 3.0 - Placing Concrete
|  | 3.6 - Concrete Surface Finishing |  | 3.6 - Concrete Surface Finishing | 3.0 - Placing Concrete
|  | 4.1 - Slump |  | 4.1 - Slump | 4.0 - Sampling and Testing Concrete
|  | 4.2 - Temperature |  | 4.2 - Temperature | 4.0 - Sampling and Testing Concrete
|  | 4.3 - Flexural Strength (7 day) |  | 4.3 - Flexural Strength (7 day) | 4.0 - Sampling and Testing Concrete
|  | 4.3 - Flexural Strength (28 day) |  | 4.3 - Flexural Strength (28 day) | 4.0 - Sampling and Testing Concrete
|  | 4.4 - Air Content |  | 4.4 - Air Content | 4.0 - Sampling and Testing Concrete
|  | 4.5 - Mass Per Unit Volume |  | 4.5 - Mass Per Unit Volume | 4.0 - Sampling and Testing Concrete
|  | 4.6 - Wet Analysis |  | 4.6 - Wet Analysis | 4.0 - Sampling and Testing Concrete
|  | 4.7 - Concrete Core Analysis (Density & Compressive Strength) |  | 4.7 - Concrete Core Analysis (Density & Compressive Strength) | 4.0 - Sampling and Testing Concrete
|  | 5.1 - Curing |  | 5.1 - Curing | 5.0 - Post-Placement
|  | 5.2 - Cold Weather Concreting Concrete Protection |  | 5.2 - Cold Weather Concreting Concrete Protection | 5.0 - Post-Placement
|  | 5.3 - Inducement Saw Cutting |  | 5.3 - Inducement Saw Cutting | 5.0 - Post-Placement
|  | 5.4 - Formwork Removal |  | 5.4 - Formwork Removal | 5.0 - Post-Placement
|  | 6.1 - Surface Smoothness Testing |  | 6.1 - Surface Smoothness Testing | 6.0 - Completion
|  | 6.2 - Pavement Surface Levels |  | 6.2 - Pavement Surface Levels | 6.0 - Completion
|  | 6.3 - Protection of Slabs |  | 6.3 - Protection of Slabs | 6.0 - Completion
|  | 6.4 - Defects to Slabs |  | 6.4 - Defects to Slabs | 6.0 - Completion
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP014 - Sawcutting & Joint Sealing
| Scope |  |  | FH-ZU2-QU-ITP014 - Sawcutting & Joint Sealing
Rows
|  | FH-ZU2-QU-ITP014 - Sawcutting & Joint Sealing | dynamic | FH-ZU2-QU-ITP014 - Sawcutting & Joint Sealing
Columns
|  | 1.1 - Check for Correct Documentation |  | 1.1 - Check for Correct Documentation | 1.0 - Preliminary Activities
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities
|  | 2.1 - Define Area of Works |  | 2.1 - Define Area of Works | 2.0 - Installation
|  | 2.2 - PCC Curing |  | 2.2 - PCC Curing | 2.0 - Installation
|  | 2.3 - Cleaning of Joints |  | 2.3 - Cleaning of Joints | 2.0 - Installation
|  | 2.4 - Backing Rod Install |  | 2.4 - Backing Rod Install | 2.0 - Installation
|  | 2.5 - Sealant Install |  | 2.5 - Sealant Install | 2.0 - Installation
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP015 - High Early Strength Lean Concrete Placement
| Scope |  |  | FH-ZU2-QU-ITP015 - High Early Strength Lean Concrete Placement
Rows
|  | FH-ZU2-QU-ITP015 - High Early Strength Lean Concrete Placement | dynamic | FH-ZU2-QU-ITP015 - High Early Strength Lean Concrete Placement
Columns
FH-ZU2-QU-ITP016 - Asphalt Production - Airport Mix
| Scope |  |  | FH-ZU2-QU-ITP016 - Asphalt Production - Airport Mix
Rows
|  | FH-ZU2-QU-ITP016 - Asphalt Production - Airport Mix | dynamic | FH-ZU2-QU-ITP016 - Asphalt Production - Airport Mix
Columns
FH-ZU2-QU-ITP017 - Asphalt Production - 14H Mix
| Scope |  |  | FH-ZU2-QU-ITP017 - Asphalt Production - 14H Mix
Rows
|  | FH-ZU2-QU-ITP017 - Asphalt Production - 14H Mix | dynamic | FH-ZU2-QU-ITP017 - Asphalt Production - 14H Mix
Columns
|  | 1.1 - Temperature |  | 1.1 - Temperature | 1.0 - Production of Asphalt
|  | 1.2 - Temperature |  | 1.2 - Temperature | 1.0 - Production of Asphalt
|  | 1.3 - Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating |  | 1.3 - Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating | 1.0 - Production of Asphalt
|  | 1.4 - Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating |  | 1.4 - Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating | 1.0 - Production of Asphalt
|  | 1.5 - Maximum density |  | 1.5 - Maximum density | 1.0 - Production of Asphalt
|  | 1.6 - Binder content |  | 1.6 - Binder content | 1.0 - Production of Asphalt
|  | 1.7 - Full sieve analysis |  | 1.7 - Full sieve analysis | 1.0 - Production of Asphalt
|  | 1.8 - Moisture content |  | 1.8 - Moisture content | 1.0 - Production of Asphalt
|  | 2.1 - Moisture content of RAP |  | 2.1 - Moisture content of RAP | 2.0 - RAP Testing - RAP Level 1 and 2 (as per Table 407.121 Section 407)
|  | 2.2 - Binder content of RAP |  | 2.2 - Binder content of RAP | 2.0 - RAP Testing - RAP Level 1 and 2 (as per Table 407.121 Section 407)
|  | 2.3 - Sieve analysis of RAP |  | 2.3 - Sieve analysis of RAP | 2.0 - RAP Testing - RAP Level 1 and 2 (as per Table 407.121 Section 407)
|  | 3.1 - Binder viscosity |  | 3.1 - Binder viscosity | 3.0 - RAP Testing - RAP Level 2 (as per Table 407.121 Section 407)
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP018 - Asphalt Placement
| Scope |  |  | FH-ZU2-QU-ITP018 - Asphalt Placement
Rows
|  | FH-ZU2-QU-ITP018 - Asphalt Placement | dynamic | FH-ZU2-QU-ITP018 - Asphalt Placement
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities
|  | 1.3 - Plant & Equipment Check |  | 1.3 - Plant & Equipment Check | 1.0 - Preliminary Activities
|  | 1.4 - Tack Coat Material Submission |  | 1.4 - Tack Coat Material Submission | 1.0 - Preliminary Activities
|  | 2.1 - Surface Preparation |  | 2.1 - Surface Preparation | 2.0 - Tack Coat
|  | 2.2 - Weather Limitations |  | 2.2 - Weather Limitations | 2.0 - Tack Coat
|  | 2.3 - Application of Tack Coat |  | 2.3 - Application of Tack Coat | 2.0 - Tack Coat
|  | 2.4 - Test Certificates |  | 2.4 - Test Certificates | 2.0 - Tack Coat
|  | 3.1 - Construction Trial |  | 3.1 - Construction Trial | 3.0 - Hot Mix Asphalt Placement
|  | 3.2 - Ambient Conditions for Placing |  | 3.2 - Ambient Conditions for Placing | 3.0 - Hot Mix Asphalt Placement
|  | 3.3 - Surface Preparation |  | 3.3 - Surface Preparation | 3.0 - Hot Mix Asphalt Placement
|  | 3.4 - Asphalt Placement |  | 3.4 - Asphalt Placement | 3.0 - Hot Mix Asphalt Placement
|  | 3.5 - Longitudinal Joints |  | 3.5 - Longitudinal Joints | 3.0 - Hot Mix Asphalt Placement
|  | 3.6 - Surface Finish of Wearing Course |  | 3.6 - Surface Finish of Wearing Course | 3.0 - Hot Mix Asphalt Placement
|  | 4.1 - Compaction Testing (AfPA Mix) |  | 4.1 - Compaction Testing (AfPA Mix) | 4.0 - Compaction Testing
|  | 4.2 - Compaction Testing (Type H Shoulder Mix) |  | 4.2 - Compaction Testing (Type H Shoulder Mix) | 4.0 - Compaction Testing
|  | 5.1 - Surface Smoothness Testing |  | 5.1 - Surface Smoothness Testing | 5.0 - Completion
|  | 5.2 - Finished Surface Levels |  | 5.2 - Finished Surface Levels | 5.0 - Completion
|  | 5.3 - Surveyed Average Layer Thicknesses |  | 5.3 - Surveyed Average Layer Thicknesses | 5.0 - Completion
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP019 - Spray Seal Placement
| Scope |  |  | FH-ZU2-QU-ITP019 - Spray Seal Placement
Rows
|  | FH-ZU2-QU-ITP019 - Spray Seal Placement | dynamic | FH-ZU2-QU-ITP019 - Spray Seal Placement
Columns
|  | 1.1 - Check for Correct Documentation |  | 1.1 - Check for Correct Documentation | 1.0 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Works
|  | 1.3 - Plant & Equipment Check |  | 1.3 - Plant & Equipment Check | 1.0 - Preliminary Works
|  | 2.3 - Material Approval |  | 2.3 - Material Approval | 2.0 - Materials
|  | 3.1 - Underlying Surface |  | 3.1 - Underlying Surface | 3.0 - Construction
|  | 3.3 - Binder and Aggregate Application |  | 3.3 - Binder and Aggregate Application | 3.0 - Construction
|  | 3.4 - Aggregate Spreading |  | 3.4 - Aggregate Spreading | 3.0 - Construction
|  | 3.4 - Rolling of Aggregate |  | 3.4 - Rolling of Aggregate | 3.0 - Construction
|  | 3.5 - Removal of Loose Aggregate |  | 3.5 - Removal of Loose Aggregate | 3.0 - Construction
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP020 - Prime Coat
| Scope |  |  | FH-ZU2-QU-ITP020 - Prime Coat
Rows
|  | FH-ZU2-QU-ITP020 - Prime Coat | dynamic | FH-ZU2-QU-ITP020 - Prime Coat
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities
|  | 1.3 - Plant & Equipment Check |  | 1.3 - Plant & Equipment Check | 1.0 - Preliminary Activities
|  | 1.4 - Weather Conditions |  | 1.4 - Weather Conditions | 1.0 - Preliminary Activities
|  | 2.1 - Cut-back Bitumen |  | 2.1 - Cut-back Bitumen | 2.0 - Materials
|  | 2.2 - Cutter |  | 2.2 - Cutter | 2.0 - Materials
|  | 2.3 - Bitumen Emulsion |  | 2.3 - Bitumen Emulsion | 2.0 - Materials
|  | 2.4 - Blinding Sand |  | 2.4 - Blinding Sand | 2.0 - Materials
|  | 2.5 - Test Certificates |  | 2.5 - Test Certificates | 2.0 - Materials
|  | 3.1 - Trial Application |  | 3.1 - Trial Application | 3.0 - Construction
|  | 3.2 - Surface Preparation |  | 3.2 - Surface Preparation | 3.0 - Construction
|  | 3.3 - Application of Bituminous Material |  | 3.3 - Application of Bituminous Material | 3.0 - Construction
|  | 3.5 - Job Samples |  | 3.5 - Job Samples | 3.0 - Construction
|  | 3.6 - Spray Rates |  | 3.6 - Spray Rates | 3.0 - Construction
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP021 - Tack Coat
| Scope |  |  | FH-ZU2-QU-ITP021 - Tack Coat
Rows
|  | FH-ZU2-QU-ITP021 - Tack Coat | dynamic | FH-ZU2-QU-ITP021 - Tack Coat
Columns
FH-ZU2-QU-ITP022 - Hatelit Install
| Scope |  |  | FH-ZU2-QU-ITP022 - Hatelit Install
Rows
|  | FH-ZU2-QU-ITP022 - Hatelit Install | dynamic | FH-ZU2-QU-ITP022 - Hatelit Install
Columns
FH-ZU2-QU-ITP023 - RBB Install
| Scope |  |  | FH-ZU2-QU-ITP023 - RBB
Rows
|  | FH-ZU2-QU-ITP023 - RBB | dynamic | FH-ZU2-QU-ITP023 - RBB
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.3 - Definition of the work area |  | 1.3 - Definition of the work area | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 2.1 - Rubberised Bituminous Sealant |  | 2.1 - Rubberised Bituminous Sealant | 2.0 - Materials
|  | 2.2 - Material Sources – Conformance Test Certificates/Reports |  | 2.2 - Material Sources – Conformance Test Certificates/Reports | 2.0 - Materials
|  | 3.1 - Applying Sealant |  | 3.1 - Applying Sealant | 3.0 - Sealing
|  | 3.2 - Protection of Applied Sealant |  | 3.2 - Protection of Applied Sealant | 3.0 - Sealing
|  | 3.3 - Cleaning up |  | 3.3 - Cleaning up | 3.0 - Sealing
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP024 - Line Marking
| Scope |  |  | FH-ZU2-QU-ITP024 - Line Marking
Rows
|  | FH-ZU2-QU-ITP024 - Line Marking | dynamic | FH-ZU2-QU-ITP024 - Line Marking
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities
|  | 1.2 - Linemarking Plan Approval |  | 1.2 - Linemarking Plan Approval | 1.0 - Preliminary Activities
|  | 1.3 - Implementation of all measures and controls |  | 1.3 - Implementation of all measures and controls | 1.0 - Preliminary Activities
|  | 1.3 - Plant and Equipment |  | 1.3 - Plant and Equipment | 1.0 - Preliminary Activities
|  | 1.4 - Materials |  | 1.4 - Materials | 1.0 - Preliminary Activities
|  | 1.5 - Material Handling |  | 1.5 - Material Handling | 1.0 - Preliminary Activities
|  | 1.6 - Survey and setting out |  | 1.6 - Survey and setting out | 1.0 - Preliminary Activities
|  | 2.1 - Removal of Existing Line Marking |  | 2.1 - Removal of Existing Line Marking | 2.0 - Construction
|  | 2.2 - Surface preparation |  | 2.2 - Surface preparation | 2.0 - Construction
|  | 2.3 - Weather Conditions |  | 2.3 - Weather Conditions | 2.0 - Construction
|  | 2.4 - Application |  | 2.4 - Application | 2.0 - Construction
|  | 2.5 - Application Rate and Conformity of Application |  | 2.5 - Application Rate and Conformity of Application | 2.0 - Construction
|  | 3.1 - Records |  | 3.1 - Records | 3.0 - Post Construction
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP025 - AGL Conduit and Boring Installation
| Scope |  |  | FH-ZU2-QU-ITP025 - AGL Conduit Installation
Rows
|  | FH-ZU2-QU-ITP025 - AGL Conduit Installation | dynamic | FH-ZU2-QU-ITP025 - AGL Conduit Installation
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.3 - Definition of the work area (survey) |  | 1.3 - Definition of the work area (survey) | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.4 - Check conduit compliance |  | 1.4 - Check conduit compliance | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.5 - Check bedding material compliance |  | 1.5 - Check bedding material compliance | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.6 - Locate and prove existing services |  | 1.6 - Locate and prove existing services | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 2.1 - Excavate trenches for conduits |  | 2.1 - Excavate trenches for conduits | 2.0 - Construction
|  | 2.2 - Existing services crossing new conduits |  | 2.2 - Existing services crossing new conduits | 2.0 - Construction
|  | 2.3 - Laying and jointing of conduits |  | 2.3 - Laying and jointing of conduits | 2.0 - Construction
|  | 2.4 - Survey as-built |  | 2.4 - Survey as-built | 2.0 - Construction
|  | 2.5 - Pre-backfill inspection |  | 2.5 - Pre-backfill inspection | 2.0 - Construction
|  | 2.6 - Backfilling conduits |  | 2.6 - Backfilling conduits | 2.0 - Construction
|  | 2.7 - Conduit markers & warning tape |  | 2.7 - Conduit markers & warning tape | 2.0 - Construction
|  | 2.8 - Checking of conduit lines |  | 2.8 - Checking of conduit lines | 2.0 - Construction
|  | 2.9 - Conduit draw cord |  | 2.9 - Conduit draw cord | 2.0 - Construction
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP026 - AGL General, Testing & Commissioning
| Scope |  |  | FH-ZU2-QU-ITP026 - AGL General, Testing & Commissioning
Rows
|  | FH-ZU2-QU-ITP026 - AGL General, Testing & Commissioning | dynamic | FH-ZU2-QU-ITP026 - AGL General, Testing & Commissioning
Columns
FH-ZU2-QU-ITP027 - AGL Cabling
| Scope |  |  | FH-ZU2-QU-ITP027 - AGL Cabling
Rows
|  | FH-ZU2-QU-ITP027 - AGL Cabling | dynamic | FH-ZU2-QU-ITP027 - AGL Cabling
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Works
|  | 1.3 - Existing service location |  | 1.3 - Existing service location | 1.0 - Preliminary Works
|  | 1.4 - Cable route |  | 1.4 - Cable route | 1.0 - Preliminary Works
|  | 2.1 - Primary cable |  | 2.1 - Primary cable | 2.0 - Material / Equipment Approvals
|  | 2.2 - Secondary cable |  | 2.2 - Secondary cable | 2.0 - Material / Equipment Approvals
|  | 2.3 - Cable connectors |  | 2.3 - Cable connectors | 2.0 - Material / Equipment Approvals
|  | 2.4 - Series isolation transformers |  | 2.4 - Series isolation transformers | 2.0 - Material / Equipment Approvals
|  | 3.1 - Primary cabling connections |  | 3.1 - Primary cabling connections | 3.0 - Cable Installation
|  | 3.2 - Secondary cabling connections |  | 3.2 - Secondary cabling connections | 3.0 - Cable Installation
|  | 3.3 - Secondary slotting |  | 3.3 - Secondary slotting | 3.0 - Cable Installation
|  | 3.4 - Max conduit capacity |  | 3.4 - Max conduit capacity | 3.0 - Cable Installation
|  | 3.5 - Secondary sealing |  | 3.5 - Secondary sealing | 3.0 - Cable Installation
|  | 4.1 - Protection of existing cabling |  | 4.1 - Protection of existing cabling | 4.0 - General Works
|  | 4.2 - Slack |  | 4.2 - Slack | 4.0 - General Works
|  | 4.3 - SIT pit earthing rod |  | 4.3 - SIT pit earthing rod | 4.0 - General Works
|  | 4.5 - Identification of configuration |  | 4.5 - Identification of configuration | 4.0 - General Works
|  | 5.1 - As-built Documentation |  | 5.1 - As-built Documentation | 5.0 - Post Construction
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP028 - AGL MAG Signs
| Scope |  |  | FH-ZU2-QU-ITP028 - AGL MAG Signs
Rows
|  | FH-ZU2-QU-ITP028 - AGL MAG Signs | dynamic | FH-ZU2-QU-ITP028 - AGL MAG Signs
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Works
|  | 1.3 - Material/Equipment Approvals |  | 1.3 - Material/Equipment Approvals | 1.0 - Preliminary Works
|  | 2.1 - MAG Sign Base |  | 2.1 - MAG Sign Base | 2.0 - Installation of MAG Sign Footing
|  | 3.1 - Luminaire Circuit |  | 3.1 - Luminaire Circuit | 3.0 - Installation of MAG Sign
|  | 3.2 - MAG Sign Face |  | 3.2 - MAG Sign Face | 3.0 - Installation of MAG Sign
|  | 4.1 - As-Built |  | 4.1 - As-Built | 4.0 - Post Construction
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP029 - Topsoil and Grassing
| Scope |  |  | FH-ZU2-QU-ITP029 - Topsoil and Grassing
Rows
|  | FH-ZU2-QU-ITP029 - Topsoil and Grassing | dynamic | FH-ZU2-QU-ITP029 - Topsoil and Grassing
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities
|  | 1.3 - Material Approval |  | 1.3 - Material Approval | 1.0 - Preliminary Activities
|  | 2.1 - Topsoil Material |  | 2.1 - Topsoil Material | 2.0 - Herbicide
|  | 3.1 - Topsoil placement |  | 3.1 - Topsoil placement | 3.0 - Placement of top soil
|  | 4.1 - Grass Seeds |  | 4.1 - Grass Seeds | 4.0 - Hydro seeding
|  | 4.2 - Coverage / Tolerances |  | 4.2 - Coverage / Tolerances | 4.0 - Hydro seeding
|  | 4.3 - Stabilisation Treatment |  | 4.3 - Stabilisation Treatment | 4.0 - Hydro seeding
|  | 4.4 - Hydro seeding |  | 4.4 - Hydro seeding | 4.0 - Hydro seeding
|  | Reinstatement of Disturbed Surfaces |  | Reinstatement of Disturbed Surfaces | 4.0 - Hydro seeding
|  | 5.1 - Reinstatement of Disturbed Surfaces |  | 5.1 - Reinstatement of Disturbed Surfaces | 5.0 - Post Construction
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP030 - Precast Concrete Walls
| Scope |  |  | FH-ZU2-QU-ITP030 - Precast Concrete Walls
Rows
|  | FH-ZU2-QU-ITP030 - Precast Concrete Walls | dynamic | FH-ZU2-QU-ITP030 - Precast Concrete Walls
Columns
FH-ZU2-QU-ITP031 - Electrical and Communications Conduits Install
| Scope |  |  | FH-ZU2-QU-ITP031 - Electrical and Communications Conduits Install
Rows
|  | FH-ZU2-QU-ITP031 - Electrical and Communications Conduits Install | dynamic | FH-ZU2-QU-ITP031 - Electrical and Communications Conduits Install
Columns
FH-ZU2-QU-ITP032 - Sewer Pipe Install
| Scope |  |  | FH-ZU2-QU-ITP032 - Sewer Pipe Install
Rows
|  | FH-ZU2-QU-ITP032 - Sewer Pipe Install | dynamic | FH-ZU2-QU-ITP032 - Sewer Pipe Install
Columns
FH-ZU2-QU-ITP033 - Building Fitout
| Scope |  |  | FH-ZU2-QU-ITP033 - Building Fitout
Rows
|  | FH-ZU2-QU-ITP033 - Building Fitout | dynamic | FH-ZU2-QU-ITP033 - Building Fitout
Columns
FH-ZU2-QU-ITP034 - HV Conduits
| Scope |  |  | FH-ZU2-QU-ITP034 - HV Conduits
Rows
|  | FH-ZU2-QU-ITP034 - HV Conduits | dynamic | FH-ZU2-QU-ITP034 - HV Conduits
Columns
FH-ZU2-QU-ITP035 - HV Cabling
| Scope |  |  | FH-ZU2-QU-ITP035 - HV Cabling
Rows
|  | FH-ZU2-QU-ITP035 - HV Cabling | dynamic | FH-ZU2-QU-ITP035 - HV Cabling
Columns
FH-ZU2-QU-ITP036 - HV Testing & Commissioning
| Scope |  |  | FH-ZU2-QU-ITP036 - HV Testing & Commissioning
Rows
|  | FH-ZU2-QU-ITP036 - HV Testing & Commissioning | dynamic | FH-ZU2-QU-ITP036 - HV Testing & Commissioning
Columns
FH-ZU2-QU-ITP037 - Miscellaneous Concrete Structures
| Scope |  |  | FH-ZU2-QU-ITP037 - Miscellaneous Concrete Structures
Rows
|  | FH-ZU2-QU-ITP037 - Miscellaneous Concrete Structures | dynamic | FH-ZU2-QU-ITP037 - Miscellaneous Concrete Structures
Columns
|  | 1.1 - The current revision drawings are being used including subcontractors copy. |  | 1.1 - The current revision drawings are being used including subcontractors copy. | 1.0 - Preliminaries
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminaries
|  | 1.3 - Excavation Permit |  | 1.3 - Excavation Permit | 1.0 - Preliminaries
|  | 2.1 - Reinforcement |  | 2.1 - Reinforcement | 2.0 - Supply of Materials
|  | 2.2 - Concrete Mix |  | 2.2 - Concrete Mix | 2.0 - Supply of Materials
|  | 3.1 - Setout |  | 3.1 - Setout | 3.0 - Construction\Erection of Formwork
|  | 3.2 - Excavate |  | 3.2 - Excavate | 3.0 - Construction\Erection of Formwork
|  | 3.3 - Confirm Ground |  | 3.3 - Confirm Ground | 3.0 - Construction\Erection of Formwork
|  | 3.4 - Formwork |  | 3.4 - Formwork | 3.0 - Construction\Erection of Formwork
|  | 3.5 - Penetrations/Cast in items |  | 3.5 - Penetrations/Cast in items | 3.0 - Construction\Erection of Formwork
|  | 4.1 - Reinforcement installation |  | 4.1 - Reinforcement installation | 4.0 - Reinforcement
|  | 5.1 - Pre-pour Inspection |  | 5.1 - Pre-pour Inspection | 5.0 - Pre-pour Planning and Inspections and Placement (1st Pour)
|  | 5.2 - Pour in-situ |  | 5.2 - Pour in-situ | 5.0 - Pre-pour Planning and Inspections and Placement (1st Pour)
|  | 5.3 - Concrete Testing |  | 5.3 - Concrete Testing | 5.0 - Pre-pour Planning and Inspections and Placement (1st Pour)
|  | 5.5 - Finishing & Curing |  | 5.5 - Finishing & Curing | 5.0 - Pre-pour Planning and Inspections and Placement (1st Pour)
|  | 6.1 - Removal of Formwork |  | 6.1 - Removal of Formwork | 6.0 - Post Pour Details and Inspections
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP038 - Native Grass Protection
| Scope |  |  | FH-ZU2-QU-ITP038 - Native Grass Protection
Rows
|  | FH-ZU2-QU-ITP038 - Native Grass Protection | dynamic | FH-ZU2-QU-ITP038 - Native Grass Protection
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities
|  | 1.2 - Check the Google Earth Mapping |  | 1.2 - Check the Google Earth Mapping | 1.0 - Preliminary Activities
|  | 3.1 - Mark out the exact Significant Native Grass Boundary area |  | 3.1 - Mark out the exact Significant Native Grass Boundary area | 3.0 - Implementation of Controls to Protect the Native Grasses
|  | 3.2 - Use temporary fencing/bollards and signage to block access to the Significant native grasses where we are working in close proximity. |  | 3.2 - Use temporary fencing/bollards and signage to block access to the Significant native grasses where we are working in close proximity. | 3.0 - Implementation of Controls to Protect the Native Grasses
|  | 3.3 - Implementation of control measures required to protect the significant native grasses around our project area |  | 3.3 - Implementation of control measures required to protect the significant native grasses around our project area | 3.0 - Implementation of Controls to Protect the Native Grasses
|  | 4.1 - Release of Hold Point for Native grass Protection |  | 4.1 - Release of Hold Point for Native grass Protection | 4.0 - APAM Hold Point Release - Second Inspection
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP039 - AGL Boring Installation
| Scope |  |  | FH-ZU2-QU-ITP039 - AGL Boring Installation
Rows
|  | FH-ZU2-QU-ITP039 - AGL Boring Installation | dynamic | FH-ZU2-QU-ITP039 - AGL Boring Installation
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.3 - Definition of the work area (survey) |  | 1.3 - Definition of the work area (survey) | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.4 - Material Submissions |  | 1.4 - Material Submissions | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.5 - Methodology |  | 1.5 - Methodology | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 1.6 - Locate and prove existing services |  | 1.6 - Locate and prove existing services | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
|  | 2.1 - Excavate trenches for Entry and Exit Pits |  | 2.1 - Excavate trenches for Entry and Exit Pits | 2.0 - Construction
|  | 2.2 - Existing services crossing new conduits |  | 2.2 - Existing services crossing new conduits | 2.0 - Construction
|  | 2.3 - Survey as-built |  | 2.3 - Survey as-built | 2.0 - Construction
|  | 2.4 - Cover |  | 2.4 - Cover | 2.0 - Construction
|  | 2.5 - Conduit draw cord |  | 2.5 - Conduit draw cord | 2.0 - Construction
|  | 2.6 - Grout |  | 2.6 - Grout | 2.0 - Construction
|  | 2.7 - Bore Logs |  | 2.7 - Bore Logs | 2.0 - Construction
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP040 - AGL Pit Installation
| Scope |  |  | FH-ZU2-QU-ITP040 - AGL Pit Installation
Rows
|  | FH-ZU2-QU-ITP040 - AGL Pit Installation | dynamic | FH-ZU2-QU-ITP040 - AGL Pit Installation
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Works
|  | 1.3 - Definition of the work area & survey check |  | 1.3 - Definition of the work area & survey check | 1.0 - Preliminary Works
|  | 2.1 - Pit excavation and placement |  | 2.1 - Pit excavation and placement | 2.0 - Installation of SIT Pits
|  | 2.2 - Conduit positioning |  | 2.2 - Conduit positioning | 2.0 - Installation of SIT Pits
|  | 2.3 - Bedding and backfill of pit surrounds |  | 2.3 - Bedding and backfill of pit surrounds | 2.0 - Installation of SIT Pits
|  | 2.4 - Pit close out |  | 2.4 - Pit close out | 2.0 - Installation of SIT Pits
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP041 - AGL Pit Fit Out
| Scope |  |  | FH-ZU2-QU-ITP041 - AGL Pit Fit Out
Rows
|  | FH-ZU2-QU-ITP041 - AGL Pit Fit Out | dynamic | FH-ZU2-QU-ITP041 - AGL Pit Fit Out
Columns
|  | 1.1 - Check for Correct Documentation |  | 1.1 - Check for Correct Documentation | 1.0 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Works
|  | 1.3 - Definition of the work area & survey check |  | 1.3 - Definition of the work area & survey check | 1.0 - Preliminary Works
|  | 2.1 - Pit excavation and placement |  | 2.1 - Pit excavation and placement | 2.0 - Installation of SIT Pits
|  | 2.2 - Conduit positioning |  | 2.2 - Conduit positioning | 2.0 - Installation of SIT Pits
|  | 2.3 - Bedding and backfill of pit surrounds |  | 2.3 - Bedding and backfill of pit surrounds | 2.0 - Installation of SIT Pits
|  | 2.4 - Pit number labelling |  | 2.4 - Pit number labelling | 2.0 - Installation of SIT Pits
|  | 2.5 - Pit close out |  | 2.5 - Pit close out | 2.0 - Installation of SIT Pits
|  | 3.1 - Earthing & pit fit out |  | 3.1 - Earthing & pit fit out | 3.0 - Earthing & Fit Out
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP042 - AGL Shallow Base Cans
| Scope |  |  | FH-ZU2-QU-ITP042 - AGL Shallow Base Cans
Rows
|  | FH-ZU2-QU-ITP042 - AGL Shallow Base Cans | dynamic | FH-ZU2-QU-ITP042 - AGL Shallow Base Cans
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Works
|  | 1.3 - Material/equipment approvals |  | 1.3 - Material/equipment approvals | 1.0 - Preliminary Works
|  | 1.4 - Setting out for airfield luminaires |  | 1.4 - Setting out for airfield luminaires | 1.0 - Preliminary Works
|  | 1.5 - Installation of Initial Light Base |  | 1.5 - Installation of Initial Light Base | 1.0 - Preliminary Works
|  | 2.1 - Removal of existing AGL can |  | 2.1 - Removal of existing AGL can | 2.0 - Removal of Existing Can
|  | 2.1 - Steel Reinforcement Mesh and Reo Cage |  | 2.1 - Steel Reinforcement Mesh and Reo Cage | 2.0 - Installation of Base Canister
|  | 2.2 - Base Canister and Conduit Installation |  | 2.2 - Base Canister and Conduit Installation | 2.0 - Installation of Base Canister
|  | 3.1 - Inset luminaire base can |  | 3.1 - Inset luminaire base can | 3.0 - Installation of Shallow Base Can
|  | 3.1 - Top Canister Installation |  | 3.1 - Top Canister Installation | 3.0 - Installation of Top Canister
|  | 3.2 - Top Canister Close out |  | 3.2 - Top Canister Close out | 3.0 - Installation of Top Canister
|  | 3.4 - Elevated Luminaire Base |  | 3.4 - Elevated Luminaire Base | 3.0 - Installation of Top Canister
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP043 - AGL Deep Base Cans
| Scope |  |  | FH-ZU2-QU-ITP043 - AGL Deep Base Cans
Rows
|  | FH-ZU2-QU-ITP043 - AGL Deep Base Cans | dynamic | FH-ZU2-QU-ITP043 - AGL Deep Base Cans
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1.0 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1.0 - Preliminary Works
|  | 1.3 - Material/equipment approvals |  | 1.3 - Material/equipment approvals | 1.0 - Preliminary Works
|  | 1.4 - Setting out for airfield luminaires |  | 1.4 - Setting out for airfield luminaires | 1.0 - Preliminary Works
|  | 1.5 - Installation of Initial Light Base |  | 1.5 - Installation of Initial Light Base | 1.0 - Preliminary Works
|  | 2.1 - Steel Reinforcement Mesh and Reo Cage |  | 2.1 - Steel Reinforcement Mesh and Reo Cage | 2.0 - Installation of Base Canister
|  | 2.2 - Base Canister and Conduit Installation |  | 2.2 - Base Canister and Conduit Installation | 2.0 - Installation of Base Canister
|  | 3.1 - Top Canister Installation |  | 3.1 - Top Canister Installation | 3.0 - Installation of Top Canister
|  | 3.2 - Top Canister Close out |  | 3.2 - Top Canister Close out | 3.0 - Installation of Top Canister
|  | 3.4 - Elevated Luminaire Base |  | 3.4 - Elevated Luminaire Base | 3.0 - Installation of Top Canister
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
FH-ZU2-QU-ITP044 - AGL Luminaires
| Scope |  |  | FH-ZU2-QU-ITP044 - AGL Luminaires
Rows
|  | FH-ZU2-QU-ITP044 - AGL Luminaires | dynamic | FH-ZU2-QU-ITP044 - AGL Luminaires
Columns
FH-ZU2-QU-ITP045 - AGL CCRs
| Scope |  |  | FH-ZU2-QU-ITP045 - AGL CCRs
Rows
|  | FH-ZU2-QU-ITP045 - AGL CCRs | dynamic | FH-ZU2-QU-ITP045 - AGL CCRs
Columns