## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
69a39f7e-54d1-4ea4-ae35-a7e8d97c3cbc | checklist | Equus Chevaline Dexx QA |  | Equus Chevaline Dexx QA
aada4e0c-2d3a-4d71-a32c-221dd73fbe05 | section | Sequence steps
a639668e-4838-4927-8346-e3c1d282a4fa | checkpoint | All Substrate prep work completed
8106eee4-09a4-48af-8bc4-a7480b8d7e49 | checkpoint | Equus Chevaline Dexx Primer Applied
55c9419d-6e21-485f-be9c-d6c94a856e0c | checkpoint | Equus Dymonic NT applied as a fillet
8f344dbe-062f-4082-8454-6f8a094f623c | checkpoint | 1st coat Equus Dexx with GSM 300 matt Embedded
d0cfe51b-b8cf-4cb4-9d15-6a26acdd58f1 | checkpoint | 2nd coat Equus Dexx
8dc4d411-f853-43b8-9dea-c83f19ff1f57 | checkpoint | 3rd coat Equus Dexx
c526541c-0e2b-44a5-859d-447045991fb9 | checkpoint | Protective coat Traxx 2000
33017768-21c8-450c-aa05-715b75a0c508 | checkpoint | Line Markings Traxx 2000 Tinted
59f35934-eeda-4f5e-8ed9-cb73b91684c4 | checkpoint | Area left clean and rubbish removed
32663313-c3b0-4581-8fae-c73f52bcec09 | checklist | Equus Duotherm Warm Roof System Sequence |  | Equus Duotherm Warm Roof System Sequence
c7d44774-7735-42ed-8c0f-9083915f74a4 | checkpoint | Substrate installed as per standard Required
dd621f2a-8e31-4a70-97be-4fba06aa3b04 | checkpoint | Outlets/Overflows Installed
ae9089b3-68ee-455b-bff7-349f52e1a974 | checkpoint | Sopradere quick dry primer Applied
28fe29d4-7999-49f2-9b17-bce40d9d570a | checkpoint | Tapered PIR Insulation Board installed
2bbae505-b320-449d-bdd4-edb5fa14281d | checkpoint | Permabase Roof Board installed
ea9d992b-6953-4622-ae06-26ae7af8f4e0 | checkpoint | Primer Applied
540e588f-c119-4bc9-aee8-e6c52cf42e39 | checkpoint | Equus Deboer Base sheet installed
a1fd34dc-a253-49de-9bb6-eafb302ed6ad | checkpoint | Equus Deboer Cap sheet installed
a7d80731-8d84-442d-9637-eca47a4f1aff | checkpoint | Terminations Details/Matacryl completed
fed8bfa2-1116-4295-b75a-4597aa650a1c | checkpoint | Membrane details checked
96b8257a-769a-4171-be55-f9c980fd6009 | checklist | Equus Matacryl System Sequence |  | Equus Matacryl System Sequence
5f09603c-faac-42f5-9c58-8c83ab528b32 | checkpoint | Preparation of area completed
2e49553e-c485-40b4-a478-f0b5fd20d9a8 | checkpoint | All outlets and penetrations installed
8fcee51c-0ac2-4ca6-9516-c7aa0e6c3fb6 | checkpoint | 108 Duracon primer applied
285806a9-e316-4ee1-baab-5e49ad094410 | checkpoint | 107 Duracon primer applied (steel only)
61f47702-dace-4292-abe4-98b311780b1e | checkpoint | Matacryl Manual 1st layer
a5815249-8da3-4fcb-8a4e-3f055d517af6 | checkpoint | Quarts sand applied
5a1075f1-92be-4b0a-a937-61950c4183b4 | checkpoint | Matacryl STC 1st coat applied
8a05fa2f-6823-44e8-82ab-223e4b483ef9 | checkpoint | Matacryl STC top coat applied
eef6ebe2-4e9b-42c3-81ac-5e71754ad576 | checkpoint | Area left clean and clear
5c261983-55df-47e2-9283-588b74ff76e2 | checklist | Equus Two Layer System on Concrete Sequence |  | Equus Two Layer System on Concrete Sequence
1b124416-00ee-4f4f-b1a6-ed1d66b2fe28 | checkpoint | Area Preparation works completed
1c0979ce-244b-43f5-be05-67cb55bae8f1 | checkpoint | Substrate Checked & Acceptable
d0e121df-86fa-42b4-b961-edfa199391f8 | checkpoint | Outlets/ Overflows installed
f3abb304-aba2-464f-907e-a507527e4850 | checkpoint | Membrane primer applied
eda7873e-8ba8-47b2-a944-be99eb407fed | checkpoint | Angle fillet Installed
ea9ae111-2674-4660-9257-49159d820606 | checkpoint | Base sheet installed
381ca17b-c64b-486f-886d-b8fddfd26c9a | checkpoint | Cap sheet installed
bb8406e6-95e4-4749-a660-98cebf23c9b5 | checkpoint | membrane details checked
1816e060-f7d7-4d84-8c3e-ebf1d6fbd55d | checkpoint | Terminations/ flashings completed
9bd212cc-e8dc-4ad2-bde4-603887165ac6 | checkpoint | Area left clear of materials/ Rubbish
92a29c45-265b-484b-835c-be180fe5f44b | checkpoint | ILD Test Completed
bff54798-93ef-49ac-b8fb-50d07c4c674f | checklist | Equus Two Layer System on Plywood Sequence |  | Equus Two Layer System on Plywood Sequence
3766e63e-4de4-4931-80ae-2227773e39bc | checkpoint | Substrate Clean and Dry
6fa70ab9-cecc-4100-8546-04be4e821219 | checkpoint | Outlets / penetrations installed
454897e7-b0d5-42f5-bce5-aa3d7fb7599f | checkpoint | ILD Mesh and Test plate installed
e7e8b203-5f68-4c34-96f0-ee920c7b5e8a | checkpoint | Duo Bitumen primer applied
8674db8e-5ed3-4168-810d-39e43205def5 | checkpoint | Angle fillet installed
56a9dbf9-fa94-40a1-a2f7-73a3946f7928 | checkpoint | Equus Deboplast base sheet installed
93a21582-36a3-4ee0-98f7-988cfc0a71a1 | checkpoint | Equus Duo Cap sheet installed
233e0e41-fe10-4fa5-b7de-6b72de7c1098 | checkpoint | Terminations / Details completed
f8630755-482a-44ee-a912-517ba214c733 | checkpoint | Membrane details checked
863b647a-ff37-4a1d-bdb3-bfec7cf32585 | checkpoint | Area left clear of materials / rubbish
183404a4-9e24-45ee-b9f0-1badf4f2de03 | checkpoint | ILD Testing completed
0bc8b793-8cab-40a0-bb4c-120679628f4a | checklist | QA - Torch On Membrane |  | Torch On Membrane
c6d14088-b8e8-48b6-a77c-5a1cff9ac4f8 | section | Details
a104a6dc-b248-42e8-ab3c-6fdb9b407c5b | checkpoint | Substrate, inspect/clean
443ef495-df31-41e7-beff-5cf8f2dfe649 | checkpoint | Membrane primer
a52f7036-6036-4f1c-89ae-7daa779f90dc | checkpoint | IlD mesh/plates
3e27f11f-20cb-43da-a6a4-1bc38441fd86 | checkpoint | Base sheet fully torched/Self adhesive
a4220fff-56b5-4cec-b620-05dfc23bec25 | checkpoint | Cap sheet
e95b6012-4283-4f49-9f8c-ac7f61c7b3e6 | checkpoint | Penetration detailing
0648b885-f654-4aee-8894-46f67162177f | checkpoint | Termination bar/sealant if required
c3a81ebe-0a77-4645-a3b1-0524b8ec9c98 | checkpoint | Completion photos
cd9c345c-3cf8-4e5c-b4ed-9939958760d0 | checkpoint | ILD test completed
945e7cba-0f0a-4156-8f30-20bd4cea8728 | checklist | Sikaproof A Installation |  | Sikaproof A installation
6e55aee0-c260-4fcd-8f80-ce10877d536c | section | Details
af11bba8-5dee-446f-bee5-0334fb93f0e9 | checkpoint | Substrate acceptable
3a34f09d-772b-43e6-a73a-73af1b3eccc9 | checkpoint | Membrane installed as per manufactures spec
2423c46a-d08c-413d-9ebf-430c1bd2333e | checkpoint | Waterbars installed