## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource ID
checklist | ITP-195-CIV-SSB-Kerb and Channel | itp |  |  |  |  | ITP-195-CIV-SSB-Kerb and Channel Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-195-CIV-SSB-Kerb and Channel
label | ITP Description: SSB-Kerb and Channel
label | Discipline (e.g. CIV/STR/RAIL): 195-CIV
label | Revision Number: 0
label | Revision Date: 27/08/2024
label | ITP created by: Isaac El Zayat
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 703, VR SD2001, VR SD2102, AS 2876, AS1379
section | Preliminary Works - Materials
checkpoint | 2.2 Mix design
label | REFERENCE: SD2001, AS1379
label | ○ Section 703.05, 703.06, 703.07
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Approved VR mix design to be used.
label | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
label | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
textbox | TeamBinder Material approval number for the Concrete Mix:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
date | Date Completed:
checkpoint | 2.3 Bedding Material
label | REFERENCE: Section 703.21, IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete. Or as per IFC drawings.
textbox | TeamBinder Material approval number for Bedding:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
date | Date Completed:
checkpoint | 2.4 Curing Compound
label | REFERENCE: Section 703.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Curing compound shall comply with AS3799
textbox | TeamBinder Material approval number for Curing Compound:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
date | Date Completed:
section | Preliminary Works - Documents
checkpoint | 2.1 Check for correct documentation
label | REFERENCE: Drawing and Drawing Register
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
label | – Using the correct and complete set of drawings
label | – All drawings are the latest version
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | Lot Map
label | REFERENCE: MRPA Lot Management Procedure
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Upload a Marked up drawing which indicates the Location of this Lot:
label | Attach: Lot Map
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: For Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Lot Map
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 3.1 Setting out
label | REFERENCE: Section 703.17
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawing.
label | ○ The superintendent will review and confirm set out.
label | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | Attach: Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to start
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed, Survey Report
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Temporary drainage provisions
label | REFERENCE: Section 703.18
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
label | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: If required
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 4.1 Bedding
label | REFERENCE: Section 703.21
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bedding to be compacted to a thickness of not less than 100mm.
label | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
date | Date Completed:
checkpoint | 4.2 Formwork
label | REFERENCE: Section 703.12, AS3610
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Joints in formwork shall be constructed such that loss of mortar is prevented.
label | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
date | Date Completed:
checkpoint | 4.3 Pre Pour Check
label | REFERENCE: Section 703.09
label | ○ Section 703.21
label | ○ Section 610.17a), b) & c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
textbox | Ambient temperature |  |  | °C
date | Date Completed:
checkpoint | 4.4 Concrete placement
label | REFERENCE: Section 703.08, Section 703.23
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
label | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
label | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
textbox | Concrete Temperature |  |  | °C
date | Date Completed:
checkpoint | 4.5 Transitions
label | REFERENCE: Section 703.24
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Site inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 4.6 Surface Finish
label | REFERENCE: Section 703.25
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
label | ○ Renderings shall be applied within 30 minutes of extrusion.
label | ○ Concrete to have a neat appearance and uniform colour.
label | ○ Class 3 finish required for external surfaces.
label | ○ Class 4 finish required for permanently hidden surfaces.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
date | Date Completed:
checkpoint | 4.7 Formwork Stripping
label | REFERENCE: Section 703.12, AS3610
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Formwork shall not be stripped before the minimum time of:
label | – External faces 2 days
label | – Permanently hidden faces 1 day
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
date | Date Completed:
checkpoint | 4.8 Tolerance
label | REFERENCE: Section 703.15
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width, for dimension less than 25mm tolerance to be ±3mm.
label | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
label | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
label | – – – – – – – – – – – – – – – – –
label | METHOD: verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
date | Date Completed:
checkpoint | 4.9 Curing
label | REFERENCE: Section 703.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
label | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
date | Date Completed:
checkpoint | 4.10 Joints
label | REFERENCE: Section 703.26
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each joint
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
date | Date Completed:
checkpoint | 4.12 Proteciton of Concrete
label | REFERENCE: Section 703.27
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 4.11 Backfilling
label | REFERENCE: Vic Road spec 703.29
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
date | Date Completed:
checkpoint | 4.13 Cracking of Concrete
label | REFERENCE: Section 703.30
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
label | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP signed
date | Date Completed:
checkpoint | 5.1 Survey Conformance
label | REFERENCE: Section 703.15
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey to as built the works and to confirm the works are within the specified tolerances.
label | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
label | Attach: Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Completion of each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: As-built survey records
date | Date Completed:
checkpoint | 5.2 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-197-CIV-SSB-Unbound Flexible Pavement-Scale C (Carpark) | itp |  |  |  |  | ITP-197-CIV-SSB-Unbound Flexible Pavement-Scale C (Carpark) Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-197-CIV SSB-Unbound Flexible Pavement Scale C (Carpark)
label | ITP Description: SSB-Unbound Flexible Pavement Scale C (Carpark)
label | Discipline (e.g. CIV/STR/RAIL): 197-CIV
label | Revision Number: 0
label | Revision Date: 27/08/2024
label | ITP created by: Victor Mira
label | ITP approved for use by: Aldrin Guinchoma
label | 1.1 Non Dependent
label | Reference: IFC Drawings
label | 1.2 Non Dependent
label | Reference: VicRoads Section 173 (10/9/2008)
label | 1.3 Non Dependent
label | Reference: VicRoads Section 304 (13/8/13)
label | 1.4 Non Dependent
label | Reference: VicRoads Section 801 (19/07/18)
label | 1.5 Non Dependent
label | Reference: VicRoads Section 812 (13/07/16)
section | Preliminaries-Materials
checkpoint | 2.1 Crushed Rock Mix Design
label | REFERENCE: Section 304.03
label | ○ Section 304.05
label | ○ Section 812.04
label | ○ Table 812.121
label | ○ IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Material conformance as per Table 812.121
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: NA
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: TeamBinder Material Approval Number
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries-Documentation
checkpoint | 3.1 Subgrade Preparation
label | REFERENCE: 304.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
label | Reference: Subgrade Preparation/Type fill Lot Number:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Underlying layer Lot number
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set-out and Lot size
label | REFERENCE: IFC Drawings, Section 304.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Lot size shall be the lesser of 4000sqm or a days production.
label | ○ Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
label | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Survey, Document Review, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Placement of Material
label | REFERENCE: Section 304.03
label | ○ Section 304.06
label | ○ Section 304.08
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
label | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
label | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | ○ At no location shall water pond on the surface of any pavement layer.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual and Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 5.2 Construction - Jointing
label | REFERENCE: Section 304.07
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The layout of joints shall conform to the following requirements:
label | (a) material shall be spread in such a manner as to minimize the number of joints;
label | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
label | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual and Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 5.3 Compaction test (Frequency)
label | REFERENCE: 304 .11 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
label | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
label | – Scale C: 3 Samples
label | – Pass: Tested
label | – NA: Not Tested
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot Where applicxable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 5.4 Proof Roll
label | REFERENCE: Section 304.08
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 Protection of compacted layer
label | REFERENCE: Section 304.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 Compaction Testing (results)
label | REFERENCE: Section 173
label | ○ Section 304.08
label | ○ Table 304.081
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
label | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
label | Scale C:
label | – Mean Value of Density Ratio (3 tests):
label | – Subbase Layers >98%
label | – Base Layers >100%
label | ATTACH: Compaction Test Results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot Where applicxable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Compaction Test Rersults
date | Date Completed:
checkpoint | 6.2 Survey As-Built - Width and alignment
label | REFERENCE: 304.06 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
label | Attach: Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Survey Conformance Report
date | Date Completed:
checkpoint | 6.3 Survey As-Built Thickness of Pavement Layers
label | REFERENCE: 304.06 (c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Subbase course shall be not less than the specified thickness by more than 15 mm.
label | – Base Course shall be not less than the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be less than specified thickness.
label | – The combined thickness of subbase and base courses shall be not be less than the specified thickness by more than 15 mm.
label | Attach: Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Survey Conformance Report
date | Date Completed:
checkpoint | 6.4 Survey As-Built - Surface Level
label | REFERENCE: IFC Drawings
label | ○ Section 304.06 (b)
label | ○ VR 304.06 (d)
label | ○ Table 304.061
label | ○ Table 304.062
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
label | ○ At no location shall water pond on the surface of any pavement layer.
label | ○ Scale B: A minimum of 40 measurements per lot
label | ○ Subbase: mean range +8mm to -16mm, maximum Standard Deviation of 15mm
label | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
label | Attach: Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Survey Conformance Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP