## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - 012 - Concrete Culvert | itp |  |  |  | Yes | ITP-012 - Concrete Culvert | 4f45d31a-7812-407a-96f9-09c844036807
section | 1.1.0 Pre-construction approvals
checkpoint | 1.1.1 - Construction Environmental Management Plan
label | Method/Description - Document Review
label | Test frequency - Prior to work starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed CEMP
checkpoint | 1.1.2 - Construction Work Plan
label | Method/Description - Document Review
label | Test frequency - Prior to work starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.1.3 - IANZ accredited testing organisation
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.4 - IFC's specification
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.5 - IFC drawings
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.6 - Approved Drainage Strings
label | Method/Description - Document Review
label | Test frequency - Every new Drainage Line and prior to work commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC Cover Form
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.7 - Approval of stockpile location
label | Method/Description - Document Review & Approval
label | Test frequency - Prior to works commencing
label | Contractor - H
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
section | 1.2.0 Material compliance
checkpoint | 1.2.1 - Materials Approval- pipes and fittings
label | Method/Description - Material Submittal to DSR review
label | Test frequency - Prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.2 - Materials Delivery- pipes and fittings
label | Method/Description - Inspection the new Delivery and review the Dockets and test certificates
label | Test frequency - Each delivery to site
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Material Delivered Check Sheet, Dockets, Compliance Certificates
checkpoint | 1.2.3 - Materials Approval – pre-cast Concrete Manhole units and wingwalls
label | Method/Description - Specification compliance – manufacturer’s certificate to TNZ F/3 for pipe and pre-cast units
label | Test frequency - Prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.4 - Materials Delivery – pre-cast Concrete Manhole units and wingwalls
label | Method/Description - Inspection the new Delivery and review the Dockets and test certificates
label | Test frequency - Each delivery to site
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Material Delivered Check Sheet, Dockets, Compliance Certificates
checkpoint | 1.2.5 - Materials Delivery – Lids and Grates for Manholes
label | Method/Description - Inspection the new Delivery and review the Dockets and test certificates
label | Test frequency - Each delivery to site
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Material Delivered Check Sheet, Dockets, Compliance Certificates
checkpoint | 1.2.6 - Materials Approval – Weathering Index for Bedding, Haunch Material AP20 aggregate
label | Method/Description - Weathering Index test
label | Test frequency - Two tests per source 4 weeks before use in the works
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Weathering quality index Test Report
checkpoint | 1.2.7 - Materials Approval – Crushing Resistance for Bedding, Haunch Material AP20 aggregate
label | Method/Description - Crushing Resistance test
label | Test frequency - Two tests per source 4 weeks before use in the works
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Crushing Resistance test Report
checkpoint | 1.2.8 - Materials Delivery – Grading for Bedding, Haunch Material AP20 aggregate
label | Method/Description - Grading Testing Inspection the new Delivery and review the Dockets and test certificates
label | Test frequency - 2 per 400m3, 3 per 400-1500m3, 4 per 1500-4000m3 and for over 4000m3, 1 additional test per 1000 m3
label | – – – – – – – – – – – – – – –
label | Aggregate Size (mm) ¦¦ Wight Passing (%)
label | – – – – – – – – – – – – – – –
label | 19 ¦¦ 100
label | 13.2 ¦¦ 80-95
label | 9.5 ¦¦ 64-76
label | 4.75 ¦¦ 37-58
label | 2.36 ¦¦ 30-40
label | 1.18 ¦¦ 18-28
label | 0.6 ¦¦ 12-22
label | 0.3 ¦¦ 6-14
label | 0.15 ¦¦ 2-7
label | 0.075 ¦¦ 0-3
label | – – – – – – – – – – – – – – –
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
checkpoint | 1.2.9 - Materials Approval – Maximum Dry Density for Bedding, Haunching AP20 Aggregate
label | Method/Description - Standard MDD Test
label | Test frequency - 3 no. tests per source with minimum 5 points
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint | 1.2.10 - Materials - Structural Fill for Overlay Zones (AP65)
label | Method/Description - As Per MMA-CON-CMA-ITP-31067
label | Test frequency - As Per MMA-CON-CMA-ITP-31067
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test Reports
checkpoint | 1.2.11 - Material Approval – Rip Rap
label | Method/Description - Test
label | Test frequency - Prior to works commencing
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.12 - Materials Delivery – Weathering Index of a Coarse Aggregate for Rip Rap
label | Method/Description - Weathering Index test
label | Test frequency - One test per 1000 m3
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Weathering quality index Test Report
checkpoint | 1.2.13 - Materials Approval – Crushing Resistance of Coarse Aggregate for Rip Rap
label | Method/Description - Crushing Resistance test
label | Test frequency - One test per 1000 m3
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Crushing Resistance test Report
checkpoint | 1.2.14 - Materials Approval – Solid Density of Aggregate for Rip Rap
label | Method/Description - Solid Density of Aggregate test
label | Test frequency - One test per 1000 m3
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Solid Density of Aggregate test Report
checkpoint | 1.2.15 - Materials Delivery – Grading for Rip Rap
label | Method/Description - Grading Testing
label | Test frequency - 1 per 500 m3
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
checkpoint | 1.2.16 - Materials Approval –Point Load Strength for Rip Rap
label | Method/Description - Point Load Strength test
label | Test frequency - One test per 1000 m3
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Point Load Strength test Report
checkpoint | 1.2.17 - Materials Delivery – UCS Rock for Rip Rap
label | Method/Description - UCS Rock Test
label | Test frequency - One test per 1000 m3
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - UCS Rock Test Report
section | 1.3.0 Geosynthetics
checkpoint | 1.3.1 - Designer Visual inspection of the bottom of the excavation
label | Method/Description - Inspection
label | Test frequency - Check each lot
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checklist, Daily Site Inspection
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.2 - Geotextiles
label | Method/Description - Inspection
label | Test frequency - Ongoing
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checklist, Manufactures Certificate
section | 2.1.0 Trench Excavation
checkpoint | 2.1.1 - Trench Subgrade
label | Method/Description - Testing trench foundation material to assess is undercut is required. Scala penetrometer test as per NZS4402.6.5.2:1988 for non-cohesive materials. Table 18
label | ○ The CBR value of the subgrade soils shall also be measured using the in-situ CBR test in accordance with NZS4402 Test 6.1.3.
label | Test frequency - 2 nos. Dynamic Cone Penetrometer tests / 5m of trench, 1 per ancillary structure
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Dynamic Cone Penetrometer Test Report
checkpoint | 2.1.2 - Trench Benching
label | Method/Description - 1.5m benches to be constructed starting from rock face
label | Test frequency - Daily
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check List
section | 2.2.0 Pipe Bedding and Construction
checkpoint | 2.2.1 - Construction of embedment, bed, haunch using AP20
label | Method/Description - DI (Density Index) applied to cohesionless material
label | Test frequency - Two test “sets” per layer, 10m evenly spaced intervals on combined lifts upto 300mm lift
label | Contractor - W
label | Designer - W
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 2.2.2 - Construction of embedment side zones using AP20
label | Method/Description - Test 4.2.1 Nuclear Densometer Direct Mode or NZS 4407:1991 or Test 4.2.2 Nuclear Densometer Backscatter Mode and NZS 4407:1991;
label | Test frequency - Two test “sets” per layer, 10m evenly spaced intervals on combined lifts upto 300mm lift
label | Contractor - W
label | Designer - W
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 2.2.3 - Construction of Overlay Zone
label | Method/Description - Test 4.2.1 Nuclear Densometer Direct Mode or NZS 4407:1991 or Test 4.2.2 Nuclear Densometer Backscatter Mode and NZS 4407:1991; Undrained shear Strength
label | Test frequency - 1no NDM and 1no Shear Vane Test per 20m max canters at 300mm lifts
label | Contractor - W
label | Designer - W
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - NDM Test Report
checkpoint | 2.2.4 - Construction of pipe
label | Method/Description - Visual test prior to backfill above the side zones – line and level, correct installation, and joints are all sealed.
label | Test frequency - Review every 10m and witness every 25m
label | Contractor - W
label | Designer - W
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.5 - Construction of Wingwalls
label | Method/Description - Wingwalls shall be constructed on a compacted, 150 mm layer of AP65 granular material. Jointing between the connecting pipe and the back of the wingwall shall be completed using mass concrete.
label | ○ Visual inspection of joints between pipe and wingwall
label | Test frequency - Each Wingwall
label | Contractor - W
label | Designer - W
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test report, Onsite Check sheet
checkpoint | 2.2.6 - Construction of Antiseep Collars
label | Method/Description - Antiseep collars to be embedded 200mm horizontally into side of trench and 400mm below base of trench. To be located every second pipe joint. The collars shall be constructed using 25 MPa concrete.
label | Test frequency - Each Anti Seep Collar
label | Contractor - W
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - DSR Inspection (Pre-Pour), Pre-Pour Check sheet, Concrete Dockets, Concrete Test results
checkpoint | 2.2.7 - Construction of Cut Off Toes
label | Method/Description - Cut off Toe to be embedded 1m (or note 4) from top of wingwall base, to be constructed as per IFC Drawings
label | Test frequency - Cut Off Toe
label | Contractor - W
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Pre-Pour Check sheet, Detail Sheets
checkpoint | 2.2.8 - Construction of Inlet/Outlet Channels
label | Method/Description - DSR to inspect geotextiles before rip - rap is laid. Max drop heights to be adhered to when placing rip-rap
label | Test frequency - Each Channels
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Geotextile Installation Check Sheet
checkpoint | 2.2.9 - Fish Passage
label | Method/Description - 25% embedment depth with meandering low flow path from void filled riprap. Spat ropes for CU-17
label | Test frequency - Review every 10m and witness every 25m
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check sheet
checkpoint | 2.2.10 - Construction of Safety Rail
label | Method/Description - Constructed as per IFC Drawings
label | Test frequency - Each Fence
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check sheet
section | 3.0 Post Construction
checkpoint | 3.1 - Survey/as-builts
label | Method/Description - As built survey of coordinates and invert levels, structures, and pipe ends
label | Test frequency - Every 100m
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Survey As-built Data
checkpoint | 3.2 - Post Construction CCTV inspection
label | Method/Description - Check conformance with the specification and assess the asset condition post construction
label | Test frequency - For all pipelines > 225 mm Diameter
label | ○ At completion of trench backfill of minimum 5 m fill prior to final surfacing
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - CCTV log Report as per the standard
section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
label | Site Engineer/Project Engineer
label | Zone Manager Approval
label | Construction Manager Approval
label | Quality Manager Approval
date | Date:
holdpoint | SIGNATURE