## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | CFA Piles |  |  |  |  | Yes | CFA Piles | 12629db9-6b6b-4d76-97bd-fe2b6a67cb79
checkpoint-group |  |  | section | Pre-Commencement
checkpoint-status |  |  | checkpoint | Working Platform Certification Signed off with 175 kPa minimum.
label | e2cf5e4c-b62a-5af6-96cf-2b4421cc38c2 |  | note | Sign off PCA-SF-052
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Excavation Approval, Underground Services Check (DBYD, Service Scan, Pothole as required)
label | 33aaa53a-b681-5316-bc04-13193f7e10c7 |  | note | Permit issue and Sign off (PCA-QF-070);
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 95%/ IFC Drawings issued
label | 9a0ee2db-6eb1-5a99-b766-1297e207277a |  | note | IFC Issue
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Material Procurement and Verification
checkpoint-status |  |  | checkpoint | Reinforcing Steel to AS 4671:2019
label | 27ae3121-4680-5d9e-8c4a-761579c85d56 |  | note | Material Test Certificate
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Verify pile cage fabrication matches PCA design drawings.
label | 5e659736-2d8d-5acf-bdb9-a021f912a1e1 |  | note | PCA-QF-028 Checklist
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Concrete CFA Mix as per design provided by PCA's concrete supplier. Characteristic strength 40 MPa @ 28 days.
label | e3948a41-7285-5492-99c1-510bd7572dcc |  | note | Mix Design Confirmation
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Survey setting out
checkpoint-status |  |  | checkpoint | Pile Install Sequence identified
label | b48a7109-1500-5658-a2d4-72e0d1346807 |  | note | Pile Sequencing / Set out piles as per sequence
checkpoint-status |  |  | checkpoint | Set out of piles/ offset pegs
label | 3e821596-6d50-579b-8bf8-c7fed664f161 |  | note | Pile Sequencing / Set out piles as per sequence
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Piling
checkpoint-status |  |  | checkpoint | Alignment - tolerance Position AS 2159:2009 75mm
label | 6e574491-8a7d-504b-9d97-98cef6f1f036 |  | note | Pile installation records / Position As-built
checkpoint-status |  |  | checkpoint | Alignment - tolerance Verticality AS 2159:2009 4%
label | d43f4b8c-0e3c-5b8d-8496-c10b86ee6419 |  | note | Pile installation records
checkpoint-status |  |  | checkpoint | Drill auger to target pile toe depth.
label | c2a939e1-f232-55f8-ab6f-5db6f29363a2 |  | note | Pile installation records
checkpoint-status |  |  | checkpoint | Pile concrete supply
label | 8e6d98a7-82b7-5760-a5fa-e39ced6b337d |  | note | Batch certificate / Delivery Docket
label | f7ad9856-efc1-5295-8752-6d81776e0168 |  | note | Slump Tests
label | 16a56c1f-7cf2-5676-b076-805a09a88568 |  | note | Cylinder Taken, 1@ 7 day 2@ 28 day
checkpoint-status |  |  | checkpoint | Concrete volume placed during auger extraction
label | 830611d7-3ba2-5339-b551-287575f5bc86 |  | note | Pile installation records & Jean Lutz Records
checkpoint-status |  |  | checkpoint | Check concrete is set to level
checkpoint-status |  |  | checkpoint | Place correct reinforcement cage type, correct height & ensure proper cover and orientation
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Post Construction
checkpoint-status |  |  | checkpoint | Spoil Removal
label | f943281c-9844-5ff8-80c2-21c837e5e4ec |  | note | Dispose of spoil To correct facility
checklist-sectioned |  |  | checklist | Clearing & Grubbing |  |  |  |  | Yes | Clearing & Grubbing | 1e51d11a-81d7-4256-bc84-48f5ca9eb31f
checkpoint-group |  |  | section | Environmental Management
checkpoint-status |  |  | checkpoint | Construction and Environmental Management (CEM) plan is to be submitted and approved by CoGC Superintendent as per MRTS51 Cl- 6 Erosion and Sediment Control Plan Any amendments made to the CEM plan must be approved by CoGC Superintendent as per MRTS51 Cl 6.4.
label | ba2cf62c-cba5-5da8-9dfd-d38a527cdfde |  | note | Management plan
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Fauna pre-clearing report to be prepared and submitted to the CoGC Superintendent as per MRTS51.1 Cl 8.2.1 for approval.
label | 76e4e221-2d2b-59ed-84af-f8050e161dca |  | note | Fauna pre-clearing report
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Installation of Erosion and Sediment Control lines in accordance with the CEM and MRTS51 Cl 7.1- Installation- to be implemented.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Clearing & Grubbing
checkpoint-status |  |  | checkpoint | All clearing and grubbing work to comply with section 7 of MRTS04.
checkpoint-status |  |  | checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked by the PCA. This marking shall be carried out prior to clearing operations reaching the areas concerned as per MRTS04 Cl 7.2.2.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | PCA to maintain an environmental record to be made available to the CoGC Superintendent upon request as per MRTS51 Cl 7.8.
holdpoint |  |  | signoff | HOLD POINT
checklist-sectioned |  |  | checklist | Pile installation records & Jean Lutz Records |  |  |  |  | Yes | Pile installation records & Jean Lutz Records | 426c0da1-5540-4117-ad74-9ee4cdadbea6
checkpoint-group |  |  | section | Submission
checkpoint-status |  |  | checkpoint | Submit grout mix design (0.4 w/c ratio)
label | ad14ec01-c39a-5ae5-80e1-7a87c5ceeefd |  | note | Grout mix chart
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Submit PCA-QF-059 Method Statement- Hollow Bar
label | f267fc5a-1584-54e3-9c7a-0f058b1bbacc |  | note | Method Statement
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Submit Manufacturer's Certificate of Conformity as per R64 cl2.1- Materials
label | 2a78c68c-4390-5f32-b5e5-e59c205f154f |  | note | Certification
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Supply
checkpoint-status |  |  | checkpoint | Bar / fittings correct size, as per design dwgs .
label | 85fac19b-cc31-579a-ac1d-042698f5e39b |  | note | Delivery Schedule.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Ensure galvanised and epoxy coating is intact on delivery.
checkpoint-status |  |  | checkpoint | Components stored on dunnage and segregated to avoid coating damage to pre finished elements.
checkpoint-group |  |  | section | Ground Anchor Setout
checkpoint-status |  |  | checkpoint | Permits to excavate
label | 49517302-5ec6-5746-a0c6-a90312e4c538 |  | note | DBYD, PCA-QF-070
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Entry points determined, accounting for 15o and 20o rake and ensuring no clash with other anchors
label | f670af3d-8a33-5a43-9f4c-28338879201e |  | note | Survey by third party surveyor/ PCA Trimble
checkpoint-status |  |  | checkpoint | Refer to latest version of dwgs
label | 5121ca25-5f88-5dab-9995-f87f27b498af |  | note | Design Drawings
checkpoint-status |  |  | checkpoint | Protection of existing infrastructure, services by PCA. PCA to conduct DBYD to locate services and potholing investigation.
label | 8342e9c4-d36f-525a-9b22-1d2bc28421f9 |  | note | DBYD, PCA-QF-070
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Ground Anchor Installation
checkpoint-status |  |  | checkpoint | 40/16 Hollow Bar Ground Anchors installed to the required tolerances (reference to TfNSW R64 Cl 3.4.2) ±25mm of its design position on the cut face ±5 degree of the drill hole alignment- BEWARE OF POTENTIAL CLASH -Hole length/depth must be -0mm of design -Max deviation of the hole diameter -0mm of design
label | 9b052de8-c4e6-522c-971f-175b2c7c15fc |  | note | Install Records - Offsets/ angles/ levels checked
checkpoint-status |  |  | checkpoint | One set of grout cubes to be taken at start of works (and each subsequent week of grout operations). Ensure all cubes are labelled correctly once set. Baroid Mud Balance to be carried out 3 times daily.
label | 224021c7-c24f-5050-96ed-4b47b5ea6b88 |  | note | Install Records - Mud Balance Test. Target Specific Gravity 1.95. Allowable Range 1.89 - 2.01.
label | ffa48386-ecbe-5a0f-83ff-944c92148921 |  | note | Grout Compressive Strength results- 40 MPa at 28 days.
checkpoint-status |  |  | checkpoint | Ground Anchors installed as per design documentation.
label | 840541fa-69fa-56d3-a45c-e0cf730c5d8b |  | note | Completed signed off Install Records
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | As-constructed details picked up by surveyor.
label | fb52c83f-ecf7-5f17-be1f-7b1613da9b3d |  | note | Signed off survey
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Drawings modified to AS-CONSTRUCTED status and submitted
label | b2ee949c-6314-5cba-8387-006ad9ca00b0 |  | note | Drawing transmittal, As builts
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Handover documentation
label | 08051aa7-73c7-52ac-a8fe-7614a672fec7 |  | note | Installation Records, Load Test Results, Engineers Certification
holdpoint |  |  | signoff | HOLD POINT
checklist-flat |  |  | checklist | Traffic Management |  |  |  |  | Yes | Traffic Management | 7a0b1c94-0704-4d03-9cb7-176d12a7c279
checkpoint-status |  |  | checkpoint | Any work controlling and directing traffic on the Site.
label | a94c9224-bea9-50ed-a1c7-fb02ec599fe0 |  | note | Submission of traffic control personnel details - DTMR Manual of Uniform Traffic Control Devices (MUTCD)
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Submission of application for Road Closure Pavement
label | c618898c-4d3c-5d44-9501-6138980c5533 |  | note | Submission of Traffic Management Plan (TMP) and associated documents in accordance with MUTCD
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Any activity which will affect traffic conditions for a particular section of the Site.
label | 09fa1c54-6920-52d5-bc50-4e0fd50c6397 |  | note | Submission of Traffic Control Plan (TCP), where submitted separately from TMP .
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Opening of temporary roadway or detour to traffic
label | abbad035-e2fc-58fd-a419-083491eaba16 |  | note | At least one day prior to the intended date of opening the temporary roadways to traffic, notify the Principal in writing that the traffic control measures is conforming and ready for inspection by the Principal
holdpoint |  |  | signoff | HOLD POINT
checklist-sectioned |  |  | checklist | Capping beam |  |  |  |  | Yes | Capping beam | f68ee4ce-54d6-4804-ab0e-1146ccfd7d48
checkpoint-group |  |  | section | Supply
checkpoint-status |  |  | checkpoint | Reinforcing bars
label | 99aa8970-7d80-559b-a0b0-8dab42ca05d1 |  | note | ACRS certification and accreditation in accordance with MRTS71
label | 33942cd8-835f-5ab9-99c3-7cc0548cdd5f |  | note | Correct size and quantity, as per design dwg
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Concrete Mix Design- supplied and approved
checkpoint-status |  |  | checkpoint | Concrete Curing
label | c94dfb4d-48ef-5cf8-9a41-17af766e8892 |  | note | Formwork- Doka System, and accessories
checkpoint-group |  |  | section | Set Out
checkpoint-status |  |  | checkpoint | Latest drawings used for setout
checkpoint-status |  |  | checkpoint | Setout survey by PCA completed.
checkpoint-group |  |  | section | Blinding Layer
checkpoint-status |  |  | checkpoint | Blinding layer poured to level (+0/ -15)
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Reinforcement placed and tied
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Cover and laps
checkpoint-status |  |  | checkpoint | Ground Anchors head plates and spider bars installed
checkpoint-status |  |  | checkpoint | Reinforcement Inspected by PCA Engineering
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Capping Beam Concreting
checkpoint-status |  |  | checkpoint | Formwork to be inspected
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Place concrete in presence of administrator. Ensure concrete cylinders are taken as per below
label | 7170c5db-20a4-5b7b-9c18-4f426f0edd7c |  | note | Total Number of Batches in Lot (n) (number of trucks per day) & Number of Samples (sets of cylinders)
label | d57a9e1b-e9ad-513c-80a1-105a4ffa4051 |  | note | 1-3
label | 02f7d2df-9bd8-58e1-a853-e40b519baa37 |  | note | One set from every truck
label | 2872dd79-ee11-5953-b484-32eec877f5bb |  | note | 4-10
label | aa45404e-a1c8-5849-ac71-53e7a8b06dd4 |  | note | 4
checkpoint-status |  |  | checkpoint | Curing to commence a maximum of one hour after completion of concrete works.
checkpoint-status |  |  | checkpoint | Remove formwork in accordance with MRTS70 Cl 17.16.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Any Rectification works as instructed by superintendent, as per MRTS70 Cl 17.17.1.
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | Drawings modified to AS-CONSTRUCTED status and submitted
checkpoint-status |  |  | checkpoint | Handover documentation
holdpoint |  |  | signoff | HOLD POINT