## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Add Stormwater checks |  | Stormwater
f339f425-bcec-5e00-916a-b230da94676b | section | Storm Water
b519a3d6-528e-56ad-9cbe-1d5aa50e8c4c | checkpoint | Plans correct issue and construction set
5d802f8a-4408-5081-8d90-e7297e2d8141 | checkpoint | Check set out from builders
1c35e006-e055-56c0-8759-1a389e6072e2 | checkpoint | Check Plans for correct sizing and pipe material
82018cb6-2f71-5667-bb4d-d3de9a34628e | checkpoint | All Falls achieved as per plans
f4cbcd85-de33-5d5a-9021-8783ca5a393f | checkpoint | All Manholes hauched as per code
5c466659-68a6-5586-9936-3b8d53c51a11 | checkpoint | All Cesspits, Manholes installed to correct heights
9c6eda90-de39-562e-b6aa-41edacf4e03e | checkpoint | All Trenches compacted with compactor
cbda2a42-9dd8-5a20-baa5-477be756ed81 | checkpoint | Subgrade Scala test ever 10m - 3 Blows per 100mm
4ad2e5a9-6125-526c-89d9-fa7bb2201af9 | checkpoint | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
03d19b84-64a3-504c-9a0e-0dd7b9ab7639 | checkpoint | Pipes tested for inspection
caf0ab4f-382f-5f2e-a615-01e18f361472 | checkpoint | Rainwater Tank installed as per engineers report
484e0585-569a-57ba-acaa-547731a10b02 | checkpoint | Photos Taken
6dd94540-b727-577f-a50a-65cdd18ab664 | checkpoint | Inspection passed
0df12610-e59e-5413-a836-bddeb60ce91b | checkpoint | Engineer Inspected
031ca681-bc70-5712-ab0f-edb8818a4f08 | checkpoint | Mark up drawings Done
| checklist | Add Sewer checks |  | Sewer
3d4d185c-07ae-54b0-be6d-8bfc78a811bf | section | Sewer
698e34ba-edf9-4f20-8ac2-c8509e9163ce | checkpoint | Plans correct issue and construction set
4e982c04-0a64-4e95-8d9b-9440912b7eb9 | checkpoint | Check Plans for correct sizing and pipe material
235ab823-5dad-4186-bdf2-3d001cfd1ab6 | checkpoint | All Falls achieved as per plans
f9253ff0-759f-4090-8c06-f1df926299c1 | checkpoint | All Manholes hauched as per code
415bfd0f-ce08-553c-8553-52583790a790 | checkpoint | All Manholes installed to correct heights
c9923cfb-dc72-4901-918b-92070b0d3ebc | checkpoint | All Trenches compacted with compactor
d672d884-43c1-4b42-a434-efe2a24ea227 | checkpoint | Subgrade Scala test ever 10m - 3 Blows per 100mm
65099e60-5d0a-4ed9-9e9f-d3483ce32fef | checkpoint | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
a8f1670d-5e2f-5591-8e2d-d85e5d0aa20f | checkpoint | All ORG and RE installed as per plan
07bc8982-ff21-4aec-9ef8-2650b94303fb | checkpoint | Pipes tested for inspection
e0ef6ab6-6327-45fc-b64d-5572d6597a31 | checkpoint | Inspection passed
e3e6f59c-128b-475f-abf9-b59907a26be8 | checkpoint | Mark up drawings Done
2c07aa1c-17ef-4666-a8a2-a61ce3864ac2 | checkpoint | Photos Taken
| checklist | Add Water checks |  | Water
5907f8f9-ea3e-5c11-963b-cab22210e551 | section | Water Mains and Infrastructure
b0dfeb94-9514-4621-9740-78b1dfbb4f04 | checkpoint | Plans correct issue and construction set
4be3874d-4db8-4ff6-b0b7-b69076223aab | checkpoint | Check Plans for correct sizing and pipe material
a349c3a7-160f-5434-832e-1837ac52629a | checkpoint | EF welding completed by a certified welder
3addc341-b291-42cc-8d75-2e393fbf5a13 | checkpoint | Subgrade Scala test ever 10m - 3 Blows per 100mm
3ed2200d-5e56-404f-a555-8f8c88f7392b | checkpoint | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
003e33ad-2dfe-5495-ba85-654ce35af18a | checkpoint | Water Main flushed ready for connection - Fire Main 1600L/Min at 250KPA
76eef447-2c8f-450b-8f9e-0745216e83bd | checkpoint | Pipes tested for inspection
89a7df22-a89f-5112-b51f-ceff98bce047 | checkpoint | Chlorination of Pipe work completed as per TCC IDC Code
c40cf8c6-446a-5830-8033-8785200332f5 | checkpoint | E Coli Test done and Passed
8bafab90-62cc-5737-9cfc-e5761dd4c7a7 | checkpoint | Warning tape installed
d669af90-dbd6-45b7-a481-9e73bc51a2a8 | checkpoint | All Trenches compacted with compactor
c02670d9-ddba-499f-b0b8-ee21f0d6b763 | checkpoint | Inspection passed
a1161da3-c3ef-45d8-a6e6-7c4ed18aa0da | checkpoint | Mark up drawings Done
e4370a67-8b40-4200-a106-c6231c13d615 | checkpoint | Photos Taken
5b84a8b0-d5ba-56cc-b499-4286ca5f6a9c | section | Dewatering
1b3dba13-1e08-597c-beec-8f42b851d310 | checkpoint | Pumps supplied able to do flow rates required
cfcb7907-0ac8-5bb8-8afd-91e9d4a22632 | checkpoint | Wells installed to heights slightly lower than cut
1eacd13a-65fb-5d2a-baf9-1d5c8d2a97bc | checkpoint | Storage tanks install and linked dup to prevent overflow to street
7fff73ab-f219-5ca1-acf4-63c0a99c979e | checkpoint | Valves installed on tanks for Sludge removal
6ae7f704-de62-53c4-8671-eaab68f7e4f3 | checkpoint | Water Quanilty Monitored and checked daily
0ed9bbc2-d6fa-5dad-87fb-a77c424b308f | checkpoint | Balance pipes installed between tanks
9bb5a2c2-a79f-530d-b0f4-e42471b14282 | checkpoint | Water Flow rate checked daily
22832c03-201d-5456-b8a3-c7517f7ffd70 | checkpoint | Power supply checked for reliability