## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | POST - S - Fire door installation |  |  |  |  | Yes | POST - S - Fire door installation | 1f794a36-4bb2-46ef-aa6a-06e4b9afb3d1
checkpoint-status |  |  | checkpoint | Door Number(s) / Location checked and accurate
checkpoint-status |  |  | checkpoint | Floor clearance - Adequate for proposed floor coverings
checkpoint-status |  |  | checkpoint | Services/Mechanisms & FRR/Acoustic requirements considered & applied (where applicable)
checkpoint-status |  |  | checkpoint | Fixings - Consider Jamb/Hinges, all installed & secure (Size & type)
checkpoint-status |  |  | checkpoint | Door leaf to jamb gaps parallel & correct (Consider paint thickness(s))
checkpoint-status |  |  | checkpoint | Door opening as required & is plumb
checkpoint-status |  |  | checkpoint | Door tags installed
checkpoint-status |  |  | checkpoint | All doors installed, damage free & completed correctly to specification in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | POST - S - Joinery and Cabinets Installation - Kitchen, Ensuite, Bathroom and Wardrobes |  |  |  |  | Yes | POST - S - Joinery and Cabinets Installation - Kitchen, Ensuite, Bathroom and Wardrobes | 8d619e7d-b014-4e0b-a0a1-9141a44b6e67
checkpoint-status |  |  | checkpoint | All units & scribers in apartment
checkpoint-status |  |  | checkpoint | Joinery free from damage pre install
checkpoint-status |  |  | checkpoint | Joinery installed free from defect and damage
checkpoint-status |  |  | checkpoint | Silicone installed, correct colour & clean and tidy
checkpoint-status |  |  | checkpoint | Joinery and Cabinets installation completed - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | PRE - S - Nogs |  |  |  |  | Yes | PRE - S - Nogs | ec4a0299-fa3a-41ec-92d7-6b81c0da0a32
checkpoint-group |  |  | section | Service Nogs Toilet
checkpoint-status |  |  | checkpoint | Wall Vanity nogs installed
checkpoint-status |  |  | checkpoint | Handrail and Toilet roll holder Nogs installed
checkpoint-group |  |  | section | Bathroom
checkpoint-status |  |  | checkpoint | Mirror cabinet nogs installed
checkpoint-status |  |  | checkpoint | Wall Vanity nogs installed
checkpoint-status |  |  | checkpoint | Toilet: Handrail nogs Installed
checkpoint-status |  |  | checkpoint | Shower: Handrails nogs (3 areas) installed
checkpoint-status |  |  | checkpoint | Wall Mounted Heater nog installed
checkpoint-status |  |  | checkpoint | Towel rail nogs installed
checkpoint-status |  |  | checkpoint | Shower head nog installed
checkpoint-status |  |  | checkpoint | Shower mixer nog installed
checkpoint-group |  |  | section | Laundry
checkpoint-status |  |  | checkpoint | Dryer nogs installed
checkpoint-status |  |  | checkpoint | Cupboard nogs installed
checkpoint-group |  |  | section | Service Nogs General
checkpoint-status |  |  | checkpoint | Nogs / Service Nogs installed correctly as per plan
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | POST - S - Internal door installation |  |  |  |  | Yes | POST - S - Internal door installation | f2d661cb-ba60-491c-ada3-2290be981425
checkpoint-status |  |  | checkpoint | Door Number(s) / Location checked and accurate
checkpoint-status |  |  | checkpoint | Floor clearance - Adequate for proposed floor coverings
checkpoint-status |  |  | checkpoint | Fixings - Consider Jamb/Hinges/Door Packer, all installed & secure (Size & type)
checkpoint-status |  |  | checkpoint | Door leaf to jamb gaps parallel & correct (Consider paint thickness(s))
checkpoint-status |  |  | checkpoint | Door opening as required & is plumb
checkpoint-status |  |  | checkpoint | All doors installed, damage free & completed correctly to specification in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | POST - S - Skirting/ Architraves & Trims |  |  |  |  | Yes | POST - S - Skirting/ Architraves & Trims | fcb1b952-b78f-4457-89b0-f874f1d50650
checkpoint-status |  |  | checkpoint | Architraves/ skirtings & trims are the correct size and profile
checkpoint-status |  |  | checkpoint | Skirting boards have been properly scribed, sanded, glued and mitred
checkpoint-status |  |  | checkpoint | Architraves/skirtings & trims have been installed with consistent even margins
checkpoint-status |  |  | checkpoint | Skirting/Architraves & trim work completed - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS