## Table 1
|  | The Contract INSPECTION AND TEST PLAN | [5 empty] | Doc No: DI-PM-TP022 Rev: 3 Page Prepared: 30/06/2023 Reviewed Date Authorised Date
ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY |  | METHODS OR REFERENCE | FREQ. | ACCEPTANCE CRITERIA |  | INSPECTORATE* V/W/H |  |  |  |  | RECORDS / REMARKS incl NCR ref
[7 empty] | S/C |  | DNZ | CLIE T | Other
Rip & Remake and Stabilising Repairs Downer Activity #39 | Visual - Levelling pavements |  | As per work procedure: HDC WMS STABILISED REPAIR | As Programmed | C2 MINOR SURFACE LEVELLING |  | = |  | V | W |  | Record on: HDC Pavement Repairs QA Spreadsheet and hand in to supervisor
AC Levelling Downer Activity #52 | Surface Levelling |  | As per work procedure: DN-GD-GP039 Repair Surface Depression – Hand Premix | As Programmed | C2 MINOR SURFACE LEVELLING |  | = |  | V | W |  | Record on: DN-GD-GP236 Surface Depression and hand in to supervisor
Edge breaks Downer Activity #108 | Size of repair |  | As per work procedure: DN-GD-GP036 Edgebreak Repair - Formed Shoulder (Manual Premix Method) | As Programmed | C4 EDGE BREAK REPAIRS |  | = |  | V | W |  | Record on: DN-GD-GP207 Edgebreak Repair and hand in to supervisor
Dig outs Downer Activity #036 | Identify and method |  | As per work procedure: HDC WMS DIGOUT REPAIR | As Programmed | C5 DIG-OUT REPAIRS IN SEALED PAVEMENTS |  | = |  | V | W |  | Record on: HDC Pavement Repairs QA Spreadsheet and hand in to supervisor
Shoulder Repairs: Low Shoulder / Shoulder Strengthening Downer Activity #110 | Size of repair |  | As per work procedure: DN-GD-GP038 Repair Low Shoulder-Material Replacement | As Programmed | C6 RECONSTRUCTION & MAINTENANCE OF UNSEALED SHOULDERS |  | = |  | V | W |  | Record on: DN-GD-GP235 Shoulder Repair and hand in to supervisor
Culverts / Drop chambers / Flumes Downer Activity #134 | Repair and replacement |  | As per work procedure: DN-GD-GP082 Install a Concrete Culvert Less Than 900mm in Diameter | As programmed or reactive | E3 CULVERT INSTALLATION |  | = |  | V | W |  | Record on: DN-GD-GP205 Culvert Cleaning.docx and hand in to supervisor
Headwall Repairs Downer Activity #134 | Repair and replacement |  | As per work procedure: DN-GD-GP083 Install a Culvert Headwall Constructed of Dry Concrete Sand Bags | As programmed or reactive | E3 CULVERT INSTALLATION |  | = |  | V | W |  | Record on: DN-GP-GP202 Construct a Sandbag Headwall and hand in to supervisor
Drain Cleaning / Drain Re-Profiling Downer Activity #140 | Visual check for effectiveness of drainage |  | As per work procedure: HDC WMS WATER CHANNEL RECONSTRUCTION | As programmed or reactive | E2 MAINTAIN ROADSDE SHOULDER PROFILES / RECONSTRUCTION & DRAIN INVERT CLEANING |  | = |  | V | W |  | Record on: HDC WMS WATER CHANNEL RECONSTRUCTION work procedure and hand in to supervisor
High Shoulder Downer Activity #109 | Removal of built up material |  | As per work procedure: DN-GD-GP091 Removal of High Shoulders | As programmed | E2 MAINTAIN ROADSDE SHOULDER PROFILES / RECONSTRUCTION & DRAIN INVERT CLEANING |  | = |  | V | W |  | Record on: DN-GD-GP235 Shoulder Repair and hand in to supervisor
Concrete footpaths Vehicle crossings VC1, VC2, VC3 and VC4 Downer Activity #249 | Replacement |  | As per work procedure: HDC WMS CONCRETE FOOTPATH REPAIR | As programmed or reactive | F1 FOOTPATH REPAIR AND KERB & CHANNEL MAINTENANCE |  | V |  | V | W |  | Record on: HDC WMS CONCRETE FOOTPATH REPAIR and hand in to supervisor
Asphalt footpaths – Levelling / Rip and remakes Downer Activity #251 | Levelling pedestrian pavements Repair surfaces |  | As per work procedure: DN-GD-GP146 Construct or Repair an Asphaltic Concrete Footpath | As programmed or reactive | F1 FOOTPATH REPAIR AND KERB & CHANNEL MAINTENANCE |  |  |  | V | W |  | Record on: DN-GD-GP229 Repair a Asphalt Concrete Footpath and hand in to supervisor
Kerb and Channel / Stormwater outlets Downer Activity #143 | Replacement |  | As per work procedure: DN-GD-GP092 Repair Broken Kerb and Channel In Situ | As programmed | F1 FOOTPATH REPAIR AND KERB & CHANNEL MAINTENANCE |  | = |  | V | W |  | Record on: HDC WMS CONCRETE FOOTPATH REPAIR and hand in to supervisor
Sight rails Downer Activity #219 | Damaged/ Painting |  | As per work procedure: DN-GD-GP0130 Install a Timber Sight Rail | As programmed or reactive | G1 ERECTION & MAINTENANCE OF TRAFFIC SIGNS & SIGHT RAILS |  | = |  | V |  |  | RAMM entry Recording dimensions and location
LEGEND:  OPERATIONAL ACTIVITIES  VERIFICATION ACTIVITIES |  |  | V VERIFICATION W WITNESS H HOLD |  |  | DNZ Downer New Zealand S/C SUB-CONTRACTOR/SUPPLIER INITIAL & DATE IF APPROPRIATE