## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | DI-PM-TP022 Rev 3 | itp |  |  |  | Yes | DI-PM-TP022 Rev 3
checkpoint | Rip & Remake and Stabilising Repairs Downer Activity #39
label | VERIFICATION ACTIVITY - Visual - Levelling pavements
label | METHODS OR REFERENCE - As per work procedure: HDC WMS STABILISED REPAIR
label | FREQ. - As Programmed
label | ACCEPTANCE CRITERIA - C2 MINOR SURFACE LEVELLING
label | INSPECTORATE* V/W/H: DNZ - V
label | INSPECTORATE* V/W/H: CLIENT - W
label | RECORDS / REMARKS incl NCR ref - Record on: HDC Pavement Repairs QA Spreadsheet and hand in to supervisor
checkpoint | AC Levelling Downer Activity #52
label | VERIFICATION ACTIVITY - Surface Levelling
label | METHODS OR REFERENCE - As per work procedure: DN-GD-GP039 Repair Surface Depression – Hand Premix
label | FREQ. - As Programmed
label | ACCEPTANCE CRITERIA - C2 MINOR SURFACE LEVELLING
label | INSPECTORATE* V/W/H: DNZ - V
label | INSPECTORATE* V/W/H: CLIENT - W
label | RECORDS / REMARKS incl NCR ref - Record on: DN-GD-GP236 Surface Depression and hand in to supervisor
checkpoint | Edge breaks Downer Activity #108
label | VERIFICATION ACTIVITY - Size of repair
label | METHODS OR REFERENCE - As per work procedure: DN-GD-GP036 Edgebreak Repair - Formed Shoulder (Manual Premix Method)
label | FREQ. - As Programmed
label | ACCEPTANCE CRITERIA - C4 EDGE BREAK REPAIRS
label | INSPECTORATE* V/W/H: DNZ - V
label | INSPECTORATE* V/W/H: CLIENT - W
label | RECORDS / REMARKS incl NCR ref - Record on: DN-GD-GP207 Edgebreak Repair and hand in to supervisor
checkpoint | Dig outs Downer Activity #036
label | VERIFICATION ACTIVITY - Identify and method
label | METHODS OR REFERENCE - As per work procedure: HDC WMS DIGOUT REPAIR
label | FREQ. - As Programmed
label | ACCEPTANCE CRITERIA - C5 DIG-OUT REPAIRS IN SEALED PAVEMENTS
label | INSPECTORATE* V/W/H: DNZ - V
label | INSPECTORATE* V/W/H: CLIENT - W
label | RECORDS / REMARKS incl NCR ref - Record on: HDC Pavement Repairs QA Spreadsheet and hand in to supervisor
checkpoint | Shoulder Repairs: Low Shoulder / Shoulder Strengthening Downer Activity #110
label | VERIFICATION ACTIVITY - Size of repair
label | METHODS OR REFERENCE - As per work procedure: DN-GD-GP038 Repair Low Shoulder-Material Replacement
label | FREQ. - As Programmed
label | ACCEPTANCE CRITERIA - C6 RECONSTRUCTION & MAINTENANCE OF UNSEALED SHOULDERS
label | INSPECTORATE* V/W/H: DNZ - V
label | INSPECTORATE* V/W/H: CLIENT - W
label | RECORDS / REMARKS incl NCR ref - Record on: DN-GD-GP235 Shoulder Repair and hand in to supervisor
checkpoint | Culverts / Drop chambers / Flumes Downer Activity #134
label | VERIFICATION ACTIVITY - Repair and replacement
label | METHODS OR REFERENCE - As per work procedure: DN-GD-GP082 Install a Concrete Culvert Less Than 900mm in Diameter
label | FREQ. - As programmed or reactive
label | ACCEPTANCE CRITERIA - E3 CULVERT INSTALLATION
label | INSPECTORATE* V/W/H: DNZ - V
label | INSPECTORATE* V/W/H: CLIENT - W
label | RECORDS / REMARKS incl NCR ref - Record on: DN-GD-GP205 Culvert Cleaning.docx and hand in to supervisor
checkpoint | Headwall Repairs Downer Activity #134
label | VERIFICATION ACTIVITY - Repair and replacement
label | METHODS OR REFERENCE - As per work procedure: DN-GD-GP083 Install a Culvert Headwall Constructed of Dry Concrete Sand Bags
label | FREQ. - As programmed or reactive
label | ACCEPTANCE CRITERIA - E3 CULVERT INSTALLATION
label | INSPECTORATE* V/W/H: DNZ - V
label | INSPECTORATE* V/W/H: CLIENT - W
label | RECORDS / REMARKS incl NCR ref - Record on: DN-GP-GP202 Construct a Sandbag Headwall and hand in to supervisor
checkpoint | Drain Cleaning / Drain Re-Profiling Downer Activity #140
label | VERIFICATION ACTIVITY - Visual check for effectiveness of drainage
label | METHODS OR REFERENCE - As per work procedure: HDC WMS WATER CHANNEL RECONSTRUCTION
label | FREQ. - As programmed or reactive
label | ACCEPTANCE CRITERIA - E2 MAINTAIN ROADSDE SHOULDER PROFILES / RECONSTRUCTION & DRAIN INVERT CLEANING
label | INSPECTORATE* V/W/H: DNZ - V
label | INSPECTORATE* V/W/H: CLIENT - W
label | RECORDS / REMARKS incl NCR ref - Record on: HDC WMS WATER CHANNEL RECONSTRUCTION work procedure and hand in to supervisor
checkpoint | High Shoulder Downer Activity #109
label | VERIFICATION ACTIVITY - Removal of built up material
label | METHODS OR REFERENCE - As per work procedure: DN-GD-GP091 Removal of High Shoulders
label | FREQ. - As programmed
label | ACCEPTANCE CRITERIA - E2 MAINTAIN ROADSDE SHOULDER PROFILES / RECONSTRUCTION & DRAIN INVERT CLEANING
label | INSPECTORATE* V/W/H: DNZ - V
label | INSPECTORATE* V/W/H: CLIENT - W
label | RECORDS / REMARKS incl NCR ref - Record on: DN-GD-GP235 Shoulder Repair and hand in to supervisor
checkpoint | Concrete footpaths Vehicle crossings VC1, VC2, VC3 and VC4 Downer Activity #249
label | VERIFICATION ACTIVITY - Replacement
label | METHODS OR REFERENCE - As per work procedure: HDC WMS CONCRETE FOOTPATH REPAIR
label | FREQ. - As programmed or reactive
label | ACCEPTANCE CRITERIA - F1 FOOTPATH REPAIR AND KERB & CHANNEL MAINTENANCE
label | INSPECTORATE* V/W/H: S/C - V
label | INSPECTORATE* V/W/H: DNZ - V
label | INSPECTORATE* V/W/H: CLIENT - W
label | RECORDS / REMARKS incl NCR ref - Record on: HDC WMS CONCRETE FOOTPATH REPAIR and hand in to supervisor
checkpoint | Asphalt footpaths – Levelling / Rip and remakes Downer Activity #251
label | VERIFICATION ACTIVITY - Levelling pedestrian pavements Repair surfaces
label | METHODS OR REFERENCE - As per work procedure: DN-GD-GP146 Construct or Repair an Asphaltic Concrete Footpath
label | FREQ. - As programmed or reactive
label | ACCEPTANCE CRITERIA - F1 FOOTPATH REPAIR AND KERB & CHANNEL MAINTENANCE
label | INSPECTORATE* V/W/H: DNZ - V
label | INSPECTORATE* V/W/H: CLIENT - W
label | RECORDS / REMARKS incl NCR ref - Record on: DN-GD-GP229 Repair a Asphalt Concrete Footpath and hand in to supervisor
checkpoint | Kerb and Channel / Stormwater outlets Downer Activity #143
label | VERIFICATION ACTIVITY - Replacement
label | METHODS OR REFERENCE - As per work procedure: DN-GD-GP092 Repair Broken Kerb and Channel In Situ
label | FREQ. - As programmed
label | ACCEPTANCE CRITERIA - F1 FOOTPATH REPAIR AND KERB & CHANNEL MAINTENANCE
label | INSPECTORATE* V/W/H: DNZ - V
label | INSPECTORATE* V/W/H: CLIENT - W
label | RECORDS / REMARKS incl NCR ref - Record on: HDC WMS CONCRETE FOOTPATH REPAIR and hand in to supervisor
checkpoint | Sight rails Downer Activity #219
label | VERIFICATION ACTIVITY - Damaged/ Painting
label | METHODS OR REFERENCE - As per work procedure: DN-GD-GP0130 Install a Timber Sight Rail
label | FREQ. - As programmed or reactive
label | ACCEPTANCE CRITERIA - G1 ERECTION & MAINTENANCE OF TRAFFIC SIGNS & SIGHT RAILS
label | INSPECTORATE* V/W/H: DNZ - V
label | RECORDS / REMARKS incl NCR ref - RAMM entry Recording dimensions and location