## Mamaku Passing Lane
|  | Central Waikato NOC - Inspection & Test Plan - Catalogue Unbound Granular Overlay | [6 empty] | Document Number: | Pavement Renewals - Unbound Granular Overlay
|  | Site Name: | Mamaku Passing Lane | [5 empty] | Revision Number: | 0.02 | Number of Pages: |  | 7
|  | Location: | SH5 005-0008 10661 11996 | [5 empty] | Prepared: | T Quintal | Date: |  | 2022-11-11
[9 empty] | Approved: | M Owens | Date: |  | 2022-11-11
ITEM NUMBER | ACTIVITY DESCRIPTION |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | INSPECTORATE V/W/H |  |  |  | RESPONSIBLE PERSON | Sign & date if appropriate | RECORDS / REMARKS
[7 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | As per Quality Plan
[7 empty] | Type | Assessor signature | Description |  |  |  | incl NCR ref
1 | Preliminary and General
1.1 | Construction Programme Completion |  | Confirmation | Best Practice Contract Specific MMP | Before work commences | Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date | V |  |  |  | Renewals Manager
1.2 | Approved RQP |  | Confirmation | Contract Specification | At least 24hrs before establishment or work commences | Principal's Acceptance according to guidelines in Appendix 6.3 | H |  | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours before establishing on site. |  | Renewals Manager |  | NZTA to approve.
1.3 | Notification of Intention to Start Work |  | Notification |  | Before work commences | Letter drop to local residents | H |  | Hold point - No physical work is to be commenced on site until notification has been sent to residents - no later than 24 hours prior to establishing on site. |  | Renewals PM |  | NZTA to approve letter drop before distribution to residents.
1.4 | Traffic Management | TMP | Visual check | CoPTTM | Before work commences | TMP checked and approved Plans approved Current EED (if applicable) Size of site area to be checked to allow machinery to operate safely | H |  | Hold point - No traffic management is to be set up until TMP has been checked and approved |  | Renewals PM / TMC |  | CAR No.
1.5 | [12 empty] | TMP No.
1.5 | Design Report Approval |  | Confirmation | NZTA NOC Rehab Catalogue Design & Treatment Approach | Before work commences | Principal Acceptance's acceptance according to NZTA Catalogue Design Approach document | H |  | Hold point - Review meeting with NZTA National & Regional Leads and Downer NOC Managers & Pavement Designers/Reviewers |  | NZTA Network Manager & Accreditied Designer |  | NZTA Approval to Proceed NTC No.
1.6 | Seal Design Approval |  | Confirmation | Review and Sign off by Downer Regional Sealing Manager | Before work commences | Downer Regional Sealing Manager reviews and signs off on Seal Design proposed. | H |  | Hold point - Review and approval of seal design completed |  | Regional Sealing Manager
1.7 | Project Manager Handover |  | Confirmation | Review and Sign off by Downer Designer to PM | Before work commences | Downer Technical Services Team Designer reviews and signs off on Handover. | H |  | Hold point - Handover completed |  | Regional Engineering Team Designer
1.8 | Crew Pack |  |  | Items to be included: | Before work commences | Approved TMP | H |  |  |  | Renewals PM
1.9 | [5 empty] | Services location plans / Marked out
2 | [5 empty] | Approved RQP
2.1 | [5 empty] | Approved for Construction drawings & Pavement Design
2.2 | [5 empty] | Ramm data
2.3 | [5 empty] | Approved ITP
2.4 | [5 empty] | Crew Briefing Plan
2 | Setout / Site Preparation
2.1 | Setout |  | Survey | As per approved drawings | Per installation / Site | Design strings /design surface model loaded for machine control | V |  | Machine control requirement. Downer surveyor required for MC upload and verification of model operation |  | Renewals PM / Surveyor
2.2 | Services (includes Traffic Count Loops and Traffic Signal Detector Loops) |  | Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth) | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | H |  | Hold point - No excavation is to be commenced until services are located and accounted for |  | Renewals PM / Site Foreman
2.3 | Cultural/Heritage Risk Assessment |  | Notification | NZTA Cultural & Heritage Risk Model | Before work commences | Local iwi has been notified of intent to start work | H |  | Where risk of cultural discovery |  | Renewals PM / Communications Manager
2.4 | Archaeological Risk |  | Toolbox meeting | NZTA Cultural & Heritage Risk Model | Before work commences | Toolbox meeting held covering accidental discovery protocol | H |  | Hold point - No excavation is to be commenced until toolbox meeting is held |  | Site Foreman
2.5 | Traffic Management | Signs Setup | Visual check | Traffic Management Plan | Before work commences each day | Traffic management complies with TMP | H |  | Hold point - No physical works are to be commenced until necessary traffic management is in place |  | STMS |  | Daily site record sheet
2.6 | Pre-Construction walkover |  | Visual check | Approved Crew pack on site 2 weeks prior to work comencing | Before work commences | Principal / MS Civil / Downer Acceptance | H |  | Hold point - Walkover required ahead of MS Civil establishment |  | Renewals Manager / Construction PM / NZTA MCM |  | Invite for NZTA to carry out joint site visit to complete visual inspection
2.7 | [8 empty] | Hold point - No physical works are to be commenced until walkover completed
3 | Preliminary Works
3.1 | Shoulder Stripping / Vegetation clearing |  | Visual check | On site |  | Shoulder stripping as per drawings completed | V |  |  |  | Site Foreman |  | Invite for NZTA to carry out joint site visit to complete visual inspection
3.2 | Site pavement A/C digouts |  | Visual check | Check RAMM records for depths | Before Overlay work commences | Work completed prior to overlay contractor onsite | V |  | A/C Mill & Fills to be cut to waste & replaced with M/4 AP40 compacted & sealed |  | Construction Supervisor / Site Foreman
4 | Culvert extensions / Headwalls / Flumes
4.1 | Excavation Inlet / Outlet Gradients |  | Survey | NZTA F/3 | Once | Consistent gradient in and out | H |  | Hold Point – Visual check prior to pipe placement |  | Site Foreman |  | Required No
4.2 | Pipe materials / class |  | Visual Check | NZTA F/3 2.1 | Once | Meets appropriate AS/NZ standard reletive to specified type | V |  |  |  | Site Foreman |  | Required Yes / No
4.3 | Bedding contact |  | Visual Check | NZTA F/3 5.1 | continuous | uniform contact over full length of pipe | V |  |  |  | Site Foreman |  | Required Yes / No
5 | Subsoil drainage
5.1 | Trench |  | Visual |  | each site | Depth minimum 1.0m Width minimum 300mm, fall > 1:100, free from rocks etc. Position as per the design drawings +/- 100mm | H |  | Hold Point – Visual check prior to pipe placement |  | Site Foreman |  | Required Yes / No
5.2 | Drainage material |  | Visual | = | each site | 7-12mm clean filter material ( grade 2 - 4 Sealing chip | H |  | Hold Point – Visual check prior to pipe placement |  | Site Foreman |  | Required Yes / No
5.3 | Pipe type |  | Visual | Diameter as per the design drawings | Use outside traffic Lane | Docket to confirm | V |  | "Nova flow" |  | Site Foreman |  | Required Yes / No
|  |  | Visual |  | Under traffic lane | Docket to confirm | V |  | Nexus |  | Site Foreman |  | Required Yes / No
5.4 | Filter Fabric |  | Visual |  |  | 150mm lap, top of fabric minimum 150mm below FSL | H |  | Hold Point – Visual check prior to reinstatement |  | Site Foreman |  | Required Yes / No
5.5 | Outlet |  | Visual |  |  | Connect to sump barrel, culvert of construct Concrete Apron | H |  | Hold Point – Visual check prior to reinstatement |  | Site Foreman |  | Required Yes / No
5.6 | Flushing / Cleaning eyes |  | Visual | To be placed & constructed as per Approved Drawings | Each free end | [5 empty] | Site Foreman |  | Required Yes / No
5.7 | Reinstatement |  | Sealed Pavement |  |  | Pavement matches surrounding, surface with AC or 3/5 chip | V |  |  |  | Site Foreman |  | Required Yes / No
|  |  | Berms and shoulder |  |  | Top min 150mm impermiable backfill | V |  |  |  | Site Foreman |  | Required Yes / No
6 | Preteatment of Insitu Materials
6.1 | Cut to Waste Existing Seal |  | Visual Inspection |  | Prior to material import | No unsuitable material remaining | V |  |  |  | Site Foreman
6.2 | Undercut unsuitable areas |  | Visual Inspection/ measurements | Depth to be determined on site from investigations as per fig 15 Undercut & Reconstruct table | Where required | All unsuitable material removed. Excavated hole to be backfilled with M/4 AP40 & compacted to | H |  | Hold Point - Organise site walkover with NZTA MCM prior to dig outs commencing. Variation agreed. |  | Renewals Manager / Site Foreman / NZTA MCM |  | Invite for NZTA to carry out joint site visit to complete visual inspection
7 | Imported Basecourse Materials Testing
7.1 | Imported Basecourse Materials Source Property Testing | Crushing Resistance | NZTA M/4 Crushing Resistance (CR130) Test | NZS 4407 Test 3.10 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | V |  | Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old |  | Renewals PM |  | All source aggregate test results to be submitted to NZTA for review and verification
|  |  |  | NZTA M/4 |  |  | H
7.2 |  | Weathering Quality | Weathering Quality Index (WQI) Test | NZS 4407 Test 3.11 |  | Must have quality index of AA, AB, AC, BA, BB or CA | V
H
NZTA M/4
7.3 |  | Bearing Strength | Californian Bearing Ratio (CBR) | NZS 4407 T3.15 NZS 4402 T4.1.3 |  | Soaked CBR ≥ 80% when compacted/tested in accordance with both tests | V
|  |  |  | NZTA M/4 |  |  | H
7.4 | Imported Basecourse Materials Production Property Testing |  | Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF) | Refer project specification and NZTA M/4 | 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | Refer project specification | V |  | Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old |  | Renewals PM |  | All production aggregate test results to be submitted to NZTA for review and verification
H
7.5 | Imported Basecourse Materials Compaction Testing |  | Maximum Dry Density (MDD) at Optimum Water Content (OWC) | TNZ B/02 - 7.5 | 1 MDD per 5000m² or if aggregate source or processing method changes | Used to support results required in ITP section 8.4 - Compaction. | H |  | Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old |  | Renewals PM
7.6 | Nominal 150mm Make-up Metal |  | Quantity of material used | 150mm depth over high spots | Each Subsection | Correct amount of material used (M³Solid) as per geometric design / MC | V |  | Spot checks to be taken |  | Renewals PM / Surveyor
8 | Construction Quality Assurance (QA)
8.1 | Tie in taper |  | Visual Check and Stringlines/Lift Peg | NZTA B/2 | Per lane per tie in | Minimum layer thickness as per B/2 section 7.3a at tie ins. | V |  |  |  | Site Foreman / Renewals PM |  | Stringlines recorded and supplied, Photographs
8.2 | Uncompacted Layer Thickness |  | Stringline/Lift Pegs | NZTA B/2 | Per layer imported | No imported layer > 200mm no less than 2.5x particle size ie 100mm AP40 | V |  | = |  | Site Foreman |  | Stringlines recorded and supplied
8.3 | Field Compaction Target |  | NDM - Plateau | NZTA B/2 | 1 Every 3000m2 | Plateau testing done as required depending on the material variability throughout the site to determine compaction pattern. | H |  | Avg 98% plateau with min 95%. Plateau testing to be completed to determine Field Compaction Target |  | Site Foreman |  | Verified test results of plateau to be supplied
8.4 | Compaction |  | NDM T23 & Backscatter | NZTA B/2 - 7.5 (b) | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | Average ≥ 98% Laboratory MDD Minimum ≥ 95% Laboratory MDD | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Laboratory MDD) Compaction equipment shall be sufficent to achieve 98% MDD |  | Site Foreman / Renewals PM |  | Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
8.5 | [6 empty] | H
8.6
8.5 | Degree of Saturation |  | NDM | NZTA B/2 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | No tests higher than 80% | H |  | Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Plateau) Compaction equipment shall be sufficent to achieve 98% MDD |  | Site Foreman / Renewals PM |  | Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
8.6 | Surface Shape / Profile Layer Thickness |  | NZTA B/2 | Visual inspection Cut/fill tolerance check String records Straight edge | 1 test per 20m | ≤10mm variance from 3m straight edge | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved. MSCivil Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area |  | Site Foreman / Renewals PM / Surveyor |  | Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
Gradual deviations
Crossfall > 1%
[6 empty] | Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design | H
-5mm +15mm or ±5mm at lip of concrete channel where applicable
8.7 | Tolerances | Width Unconstrained | TNZ B/2 | Confirm offset from lift pegs | 2 at every lift peg or per 180 m2 | - 20mm + 100mm | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | Site Foreman / Renewals PM |  | 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
H
8.8 |  | Width Constrained | TNZ B/2 | Stringline/lift pegs | 3 at every lift peg or per 180 m2 | Zero | V
H
8.9 | Ride Quality |  | Owner acceptance test | As per Contract Documents OPM42 | 1 ride test for each lane following Basecourse completion prior to surfacing | Rolling 100m average NAASRA <75 counts/km | W |  | Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions |  | Road Science/ Renewals PM |  | NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
H
8.1 | Mosaic Surface |  | Visual inspection | A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ | Overview of site for tight mosaic surface | The large aggregate is held in place by a matrix of smaller aggregates The smaller aggregate is held firmly in place by fine material The matrix does not displace under normal trafficking or sweeping | W |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
H
8.11 | Preseal Check |  | Visual check | NZTA B/5 | Before sealing | All prior ITP checks have been completed and signed off | V |  | Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
[6 empty] | No caking layers present | H
8.12 | Pavement Surface As-Built |  | Survey | As per approved drawings | Per installation / Site | Accurate survey of all topograpgical features required | V |  |  |  | Renewals PM / Surveyor
9 | Sealing
9.1 | Sealing |  | See Sealing ITP |  |  |  | W |  | Hold Point – All hold points and checks in ITP to be completed before physical works continue |  | Sealing Manager
9.2 | Sealing TMP and Aftercare Process |  | See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site |  |  |  | W |  | Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed. |  | Renewals PM / Sealing Supervisor
H
9.3 | Sweeping of Sealing Works and Handover to Roadmarkers |  | Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor. |  |  |  | W |  | Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor. |  | Renewals PM / Sealing Supervisor
H
10 | Shoulders
10.1 | Slope |  | Visual check | Visual inspection with smart level |  | Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation | V |  | Hold Point – no surfacing layer is to be applied until all necessary results are achieved |  | Renewals PM / NZTA MCM |  | Invite NZTA to carry out joint site inspection to inspect site.
H
10.2 | Compaction |  | Visual check | Drive over 4 tonne, check wheeltracks | All shoulders | Vehicles can drive on shoulders without becoming stuck | V |  | Hold Point – physical works cannot be completed until all necessary results are achieved |  | Renewals PM / NZTA MCM
H
10.3 | Soiling |  | Visual check | Approved Design Drawings | All areas requiring grassing | Soiling has been done where required | W |  | As per the design drawings |  | Renewals PM
11 | Site Reinstatement / Clearance
11.1 | Traffic Services | Marker Pegs/ Signs/Markings/RRPMs Replaced | TNZ C/20: 2003 | Visual Inspection | All signs/markers | Replaced in same position, height etc | V |  | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced |  | Renewals PM / NZTA MCM |  | Invite NZTA to carry out joint site inspection to inspect site.
11.2 | [6 empty] | H
11.2 | Grassing |  | Visual check |  | All areas requiring grassing | Grassing has been done where required | W |  |  |  | Renewals PM
11.3 | Drains Cleared |  | Visual check |  | All drains, after all other works | Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated | W |  |  |  | Site Foreman
11.4 | Post Construction Design Verification |  | FWD/Beam | FWD or Beam at 20m Centres | On Works Completion | For information purposes only | V |  |  |  | Renewals PM |  | For Unbound Granular pavements <10year design life.
11.5 | Traffic Management Removed |  | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W |  | Hold Point – TMP cannot be removed until site Audited by Renewals PM |  | Site Foreman / STMS
11.6 | Site Left Clean and Tidy |  | Visual check | = | After vacating site | · Stockpiles removed | V |  |  |  | Renewals PM / NZTA MCM |  | Invite NZTA to carry out joint site inspection to inspect site.
11.7 | [5 empty] | · Plant removed
11.8 | [5 empty] | · Litter cleared from site
12 | As-built Records
12.1 | Collect Asset Data |  | SHDOM (SM050) |  | During construction | All relevant as built information collected | V |  |  |  | Renewals Project Manager
12.2 | Enter Asset Data into RAMM and/or Register(s) |  | SHDOM (SM050) | RAMM | At completion of work | All data entered into RAMM and/or register(s). Design report & drawings attached to RAMM site record as a media file. | H |  | Hold Point – project cannot be closed until data entered. |  | Renewals Project Manager/ WSP Information Manager |  | Submit all RAMM Data to Data Quality Manager for review and verification
12.3 | Construction Completion Report |  | Confirmation | Contract Specification | At completion of work | Checked and approved | V |  |  |  | Renewals Project Manager/ Renewals Manager |  | Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As-built Plans
| Quality Assurance Close Out By: | _________________________________________ |  |  | Date: ___________________ |  | _________________________________________________________
(signature)
_________________________________________________________
(name)
THIS RECORD TO CONTRACT FILE
Note on C36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Might pay to add a requird yes/no feild here to make it clear. Same for subsoils, dont want someone reviewing this to thik we didnt do it