## Sheet1
SECTION | DETAILS
Checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
SECTION | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
Checkpoint | FatraBond Adhesive
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor and Site Engineer/Foreman sign off
SECTION | PRE COMMENCEMENT- EACH LOCATION
Checkpoint | Samples Submitted
Label | Submit samples for approval as per Specific Material Requirements.
Label | Sample Approval Ref.
Checkpoint | First Of Type Inspection
Label | First of type of inspection conducted prior to commencment of works taking place.
Label | Document Ref.
HOLDPOINT | Sample Submission / First of type inspection - Site Engineer Sign Off
SECTION | APPLICATION - EACH LOCATION
Checkpoint | FatraBond Adhesive
Label | Apply adhesive consistently over required area using squeegee/rollers
Label | Adhesive is applied consistently and evenly across the surface to achieve correct adhesion
Label | Adhesive does not spill onto membrane, weldable laps or surrounding areas that can potentially contaminate welds
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Install Fatrafol PVC Membrane
Label | Install Fatrafol to coincide with the falls of the roof
Label | Ensure the membrane laps run with the fall of the roof to minimise negative laps on the roof
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor Inspection - Sign Off
Checkpoint | Builders Application Review
SIGNOFF | Site Engineer/ Foreman Inspection - Sign Off
SECTION | DETAILING - EACH LOCATION
Checkpoint | Hot Air Fusion Welding of PVC membrane.
Label | Hot air fusion weld overlaps.
Label | Achieve a minimum 40mm wide weld width on all hot air seam welds to achieve sufficient weld strength
Label | Records - Time Stamped Photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor Inspection - Sign Off
Checkpoint | Installation of PVC Coated Angles
Label | Fixing Fatranyl PVC coated termination angles using relevant fixings
Label | All termination metals are aligned correctly and are not disjointed or protruding
Label | Fixings centres do not exceed 200mm centres
Label | PVC coated termination angles are installed with a minimum 2mm gap between each angle to allow for structural movement and expansion
Label | Records - Time Stamped Photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Builders Detailing Review
SIGNOFF | Site Engineer/ Foreman Inspection - Sign Off
Section | QA TESTING - EACH LOCATION
Checkpoint | Inspection
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point