## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Enviro Clad V1.0 |  |  |  |  | Yes | Enviro Clad V1.0 | 164a11a9-4781-417c-99ef-775199a17e9a
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 4c1e4d8b-de70-5270-858f-732a6fd179f6 |  | textbox | ITP No.
text | ab35990d-2b9b-53ea-a9b9-67047bb36153 |  | textbox | Revision No. & Date
text | 52af26fe-b1f1-5ad9-9dd8-22230717089f |  | textbox | Prepared By
text | ee7de774-5091-593a-abaf-c589a1d45de6 |  | textbox | Reviewed By
text | fdbcb7ee-8507-561c-8eec-24e96e2b07ec |  | textbox | Approved By
text | 505da682-d432-57ea-a936-4f47a1115365 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro Shield
label | b6e54c33-3b4f-5435-8aac-ddd6593e57de |  | note | Records - Time stamped photograph
select | 871b57b3-3b80-50f2-9381-9e4ec468354a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex FC
label | 7438cd9f-b514-5cd3-83d1-0870dd51e994 |  | note | Records - Time stamped photograph
select | 58ebaf11-d035-53ad-b91d-e62e01d40d62 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro Clad
label | 2a81dabc-2f0e-50ff-91bd-269013cf5641 |  | note | Records - Time stamped photograph
select | 991ead6a-fe08-54a2-a8e7-6955caf1bd67 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | ce77453a-3c10-507a-8ebc-a4113d5928fb |  | note | Submit samples for approval as per Specific Material Requirements.
label | dbad506f-e491-5b51-b1dd-2d7ebccc227b |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | 8d924ed1-fd93-569f-a2d7-e6b335f95f2d |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | b70ae807-247b-550a-a52e-f5e2ea779425 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 0b478016-0ea7-59b2-aa56-a1cc766227c4 |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | 1157e6a2-2d2e-5beb-9892-08bfb6e2fbd2 |  | note | Records - Time stamped photograph
select | ac97ef68-a362-515c-82aa-e4dc637406b9 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | a0bce86f-41d3-5592-a9d2-256162d07ecd |  | note | Obtain clearance for work initiation.
label | 8a5ef42c-84f8-5135-bd95-486631d91462 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | e7816fc4-67d6-5e00-8f65-50a1c98707a7 |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | 7ea34972-a251-5898-a932-b7e2b6327dbf |  | note | Records - Time stamped photograph
select | f01e6527-ac1f-5214-bf3c-0b1679dd87b4 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | 1733c331-6aeb-50dc-a32b-8cb39cdc9676 |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | ce2f164b-f44d-5c44-959f-d808cf4180b1 |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | 6395825f-e79f-5f80-9b4b-2a2d8ad81075 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | aa573e73-e866-5356-86a5-bec2749b901a |  | note | Records - Time stamped photograph
select | 1abf3945-38d1-5d97-8644-65e22492ebc5 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | fa2d712c-91aa-5c3d-bcae-a5bf45c52180 |  | note | Ensure no substrate cracks greater than 1.6mm.
label | b4e26752-8765-52d7-853c-9fa52a87e2c8 |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 5d6f41d4-15d6-5daf-af61-3d6e8e91aece |  | note | Records - Time stamped photograph
select | 3a73333f-6646-5412-ad93-3559edc10285 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION - EACH LOCATION
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | af801355-6771-597d-9038-84f472011968 |  | note | Ensure Surface is prepared to receive primer application.
label | 05bba607-88f3-5266-b5e8-d8085ac58cf5 |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | f451aa0a-1f66-5bb8-ab34-3aa8b6fac161 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | b0ffe173-09dc-59a5-a516-5fe457ce82d9 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 127e4412-9aa5-5994-a1bb-90001044102b |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | 827fd484-e697-5ae5-a8fe-16be1773fd31 |  | note | Records - Time stamped photograph
select | 2f95cfc9-bcac-5ce9-a563-2760c8188279 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Shield Product TDS
label | ffff3856-0c23-5f43-a3be-3448f70ce246 |  | note | Check Moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | 691a45b4-5bb7-5364-ac5d-adc14e5ebdb5 |  | note | Records - Time stamped photograph
select | 7c8c9701-fa5e-5c13-b8e0-4ea8af2d9e7f |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Shield Product TDS
label | 206bb24b-60f7-5235-999e-74111d96324d |  | note | Apply within 10-35°C
label | 642ce0fc-d610-5cf7-b0ea-6418bbf69b73 |  | note | RH must be 0-85%
label | 7764faed-2fae-5a15-96a1-f018661ad73e |  | note | Screenshot - Temperature and weather forecast
select | bebd19fb-60fc-5026-a3a0-5c94a145aeb0 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - Enviro Shield Product TDS
label | 5c071bed-98e0-5eb7-bbd7-d175bc9e1184 |  | note | Add Enviro Shield Part B (grey liquid hardener) to the Enviro Shield Part A (base Thoroughly mix with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | a08c6a5e-1cc5-55bd-b653-fd873e4f34b8 |  | note | Mix for 5 minutes or until uniform.
label | 4c22b448-3a17-5f3d-8f08-63e43d76cb2f |  | note | Allow to stand 5 minutes after mixing and then mix again for a minute.
select | ede5bf9c-550c-57bd-a9ad-8b6b74570dd0 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Shield Product TDS
label | 1b0ed537-019a-5c75-ba71-98ddba7e7ca8 |  | note | Apply primer using a brush or roller.
label | 9751d78d-94e4-5344-9492-829f06d30432 |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface.
label | 8847f4ff-df09-5946-92b9-94fa7abd10fa |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 68112dfa-e454-5ea7-a693-0e3e4b586bb7 |  | note | Records - Time stamped photograph
select | 64e80e7d-453e-52d7-9387-6c62df4fcfcb |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER- EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | 68bb424c-0de9-57b6-8d19-d1e012be56e2 |  | note | Apply Enviro Flex FC/compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | cf0afdfe-9ffc-5420-a199-41d868694d56 |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | b9e1a8fb-078c-530e-b7c7-050d04edde65 |  | note | Allow to be tack free prior to over coating with membrane coats.
label | f3ffa249-10fd-5ea8-bfa4-6e62ee01b47a |  | note | Records - Time stamped photograph
select | 0c744db5-da69-5424-a411-0191fd8b7ee8 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman bond breaker inspection sign off
checkpoint-group |  |  | section | FIRST BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Clad Product TDS
label | 39984855-a3e8-50a3-a533-55778dd230b4 |  | note | Apply within 10-35°C
label | 7da2fa59-c4d3-594c-b6bd-3e59d1d57ecb |  | note | RH must be 0-85%
label | 3f5a8143-d112-5a4c-8843-4911ef887c61 |  | note | Screenshot - Temperature and weather forecast
select | 24a3397a-782f-5f54-9c8d-37351825a739 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - Enviro Clad Product TDS
label | a0a7fab7-e6e3-5a1c-8fc2-9fda54607c9f |  | note | • Enviro Clad should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | 5405e61f-5ee5-51c0-856f-55f1cf42238b |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Clad Product TDS
label | 296c81c6-966b-57d7-8e40-df9a1790646c |  | note | • Enviro Clad to be applied by roller on substrate and detailed with a brush
label | 275bdc0b-f963-5bf8-a8ae-9a8557868458 |  | note | Coating to achieve a wet film thickness of 600 micirons
label | 84fef2d4-0e7c-54c0-8b89-f77b007e1b6d |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | 065dd8ea-1942-5461-906e-28870a4d1052 |  | note | Records - time stamped photograph
label | bf4a5e7d-913a-5a93-b793-d0a439c5bc6b |  | note | Records - Wet film thickness reading
select | 799d9d79-a14a-5611-a312-8fca442e66ca |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman base coat inspection sign off
checkpoint-group |  |  | section | SECOND BASE COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 200P Ultra Product TDS
label | fd56a279-d1ba-51df-be12-27a86adff882 |  | note | Apply within 10-35°C
label | 8a5de68b-6919-542c-9d16-3fc27d437821 |  | note | RH must be 0-85%
label | b4dda4ce-6491-50b3-9c5f-ecd0dc6d9da9 |  | note | Screenshot - Temperature and weather forecast
select | 14810a78-d69b-56a7-94d2-d6f6306152b8 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - 200P Ultra Product TDS
label | 828f2831-a099-5b70-9363-849bf6bcf341 |  | note | 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | cdfb9248-bff9-5ec9-bcad-81d4a8761df8 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - 200P Ultra Product TDS
label | f56319fa-5afc-5c4d-b4d8-a3c3ec843fde |  | note | • Enviro Clad to be applied by roller on substrate and detailed with brush
label | b096599f-6c23-542b-97ec-a47d4da4dd00 |  | note | Records - time stamped photograph
label | bdf9ec66-f65b-5bd0-b4f7-766b7238f849 |  | note | Records - Wet film thickness reading
select | f1966b9f-18e4-5b51-ae78-36ca4d985543 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor second base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman second base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman base coat inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | ec31d57f-4bcc-5aa5-96d8-a4d4567d39e8 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | 15ac4d52-82f3-5319-9c12-88b4396a9a5c |  | note | Records - time stamped photograph
select | 9b3cc5c4-43fb-5df5-8cf2-0a59ce51120f |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | Site Engineer/foreman base coat inspection sign off
checklist-sectioned |  |  | checklist | Enviro BSM V1.0 |  |  |  |  | Yes | Enviro BSM V1.0 | 5614c9db-35da-4e38-a747-a1c9510c4231
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 68fe7e95-f059-5264-86a7-e41cd66e05ca |  | textbox | ITP No.
text | 22d2d90f-25db-5e4c-82e7-349a26282765 |  | textbox | Revision No. & Date
text | f0469602-b1f4-5efa-8c32-cfc4c53e0ccf |  | textbox | Prepared By
text | 35e45697-0d2c-52d1-9f6a-ba4eb50a02ad |  | textbox | Reviewed By
text | 937cca6c-68c5-5779-a5b6-460a11481716 |  | textbox | Approved By
text | 7ef022f5-5fb3-5071-bd20-9fe2674b3438 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro BSM
label | 4dda983e-76f7-51ef-ac6e-044873143abf |  | note | Records - Time stamped photograph
select | 6e682470-2c69-54b1-8ce2-e494b65cf238 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro Epoxy Grout 100
label | 43837305-55ca-556b-9cbc-69493bdbe9e0 |  | note | Records - Time stamped photograph
select | 406f4c83-24e9-5998-b510-2f66fbfe743a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 700X
label | 9298e06f-875f-5b39-8cad-a473d235982b |  | note | Records - Time stamped photograph
select | 823b7fc4-8035-520e-97aa-174646e6ee31 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Envro Flex FC/ Sika FC
label | 51c8542d-b0ee-5c89-a1ae-2f4240f9a38b |  | note | Records - Time stamped photograph
select | b9db5367-f444-5a10-869e-b05895fa6d30 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor and Site Engineer/Foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Material Management & Storage
label | 03ee53c8-40b1-5064-bc4c-9c1befd6d4a2 |  | note | Enviro BSM to be stored upright in dry, cool conditions out of direct UV and weather. Maximum storage temperature is 45°C.
label | 406e3541-5b3b-5469-a788-bfe8bd4f22e4 |  | note | Screenshot - Temperature and weather forecast
label | 0392ef1f-3db8-5341-8fac-e0306391905a |  | note | Records - Time stamped photograph
select | 306d18b7-1dbc-5a35-87e7-e5dca6a12da7 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection Sign Off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate
label | a10dc566-1da6-58a2-866c-ed24650feea7 |  | note | The substrate should be sound and even, thus preventing movement or subsidence during concrete placement. |  |  | `
label | 77a4edca-c87f-5787-91e5-3f3f5f897e6f |  | note | The substrate in which BSM is to be installed should have no protrusions, gaps or voids greater than 10mm. Penetrations such as plumbing and electrical pipes should be stabilized to prevent movement during membrane and concrete placement.
label | 0c67d8d0-6729-5019-a5e3-ef522062526d |  | note | For horizontal membrane placement, ensure that the substrate is sound, especially when installing over compacted fill so to avoid displacement from traffic or pouring of concrete.
label | 70429150-d883-5ec2-b037-7d4b17dd8527 |  | note | For vertical placement, ensure substrate is sound to provide required support for membrane during concrete placement.
label | c22345c7-1a27-5a2b-bb49-5c79852df830 |  | note | Records - Time stamped photograph
select | 7a080703-b2ac-555d-84bd-86b1fcc40c54 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection- Sign Off
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 6a8146ad-2607-5bee-ae1c-39cb3a178c92 |  | note | Submit samples for approval as per Specific Material Requirements.
label | 2b70c47d-9995-5ca2-805b-4d66ce69e44b |  | note | Sample Approval Ref.
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | dce40751-782d-5e7d-ba9b-0d0193f617cf |  | note | First of type of inspection conducted prior to commencment of works taking place.
label | db511336-681f-572f-8361-62251e98a7a0 |  | note | Document Ref.
holdpoint |  |  | signoff | Sample Submission / First of type inspection - Site Engineer Sign Off
checkpoint-group |  |  | section | APPLICATION - EACH LOCATION
checkpoint-status |  |  | checkpoint | Horizontal application
label | b3acb2bb-0dde-5411-976a-ae843eb1d3b4 |  | note | For horizontal applications, Enviro BSM should be placed with the coloured protective layer facing upwards and the white HDPE layer facing the substrate. Stagger end laps of each run to avoid a build-up of layers.
label | 1919977f-39ef-58b3-b8d1-f1a2a3df35da |  | note | Overlap each previous sheet by 75mm ensuring membranes overlap edge is positioned correctly. Ensure the back of each subsequent roll is clean prior to overlapping and once in place remove the plastic film (on the overlap section) to bond the sheets together.
label | cf7def19-fa00-56d2-aab8-79c7f676ff27 |  | note | Ensure a complete bond with no creases by using a heavy roller across overlap areas. Once overlap bond is complete the plastic film can be completely removed.
label | 4e47907d-d287-5f69-9c3b-979317092334 |  | note | Records - Time stamped photograph
select | 107b9246-dda3-519f-8892-db664400d0af |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection- Sign Off
checkpoint-status |  |  | checkpoint | Vertical application - Witness Point
label | f62f8c1b-1965-5bd4-9a9e-42122e4ae1a8 |  | note | Enviro BSM should be mechanically fixed to the substrate using (substrate dependent) fixings with the coloured protective layer facing the concrete pour.
label | f55af3a6-6382-54cb-9ef4-a0dfc30beb55 |  | note | These fixings should only be placed in the overlap section of the membrane and have a low-profile head so that the sheet overlaps can lay flat and rolled evenly for optimum adhesion.
label | 4b5e8d2a-6f99-572a-8e1b-a93d348fdb03 |  | note | Overlapping in vertical applications should be done in the same manner as horizontal applications ensuring subsequent sheet is overlapped by 75mm, adhered, and mechanically fixed correctly before proceeding with the next.
label | 669c98f6-3ff2-56fd-af4b-ad8f8142e93c |  | note | The plastic film can be removed immediately in vertical applications. All cut edges and roll ends should be overlapped by 75mm, be clean and dry and sealed with Enviro BSM SeamTape.
label | dd2def66-caf9-53c0-892a-5b4378ba69e4 |  | note | Records - Time stamped Photograph
select | 5788eff6-3c9d-5064-954e-d6149f1404c4 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection - Sign Off
checkpoint-status |  |  | checkpoint | Builders Application Review
holdpoint |  |  | signoff | Site Engineer/ Foreman Inspection - Sign Off
checkpoint-group |  |  | section | DETAILING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Reo Bars
label | 8770b17c-9d27-55aa-bd0f-ac5259938f74 |  | note | Ensure bars are chemset and fully cured prior to detailing.
label | e8e5b53c-6eaf-53ed-ac6f-4114cd0751de |  | note | Use Flex FC/ Sikaflex FC to caulk around reo bars and overcoat with Enviro 700X.
label | cd73380f-6c35-5517-b340-2124a86c46c7 |  | note | Membrane to return out minimum 50mm.
label | eea6c1df-d295-554e-bad0-11fd8343fa72 |  | note | Records - Time Stamped Photograph
select | 8c6c52ee-dd56-5ae8-b574-1d134a1fe64c |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection - Sign Off
checkpoint-status |  |  | checkpoint | Pile Caps
label | 6bd8bb3a-67da-5beb-ac61-2741684403f6 |  | note | Pile cap to be encapsulated with Enviro epoxy grout 100 achieving minimum 50mm finished height.
label | 7d890802-58d2-5e6a-ad42-42c2e0614224 |  | note | Records - Time Stamped Photograph
select | 12d214a0-57fb-5ec4-8cbe-46b4b11e26a3 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection - Sign Off
checkpoint-status |  |  | checkpoint | Sub columns
label | 72ee2c34-c0cc-5f9a-b078-c1194b591006 |  | note | Sub columns joints to be caulked and overcoated with Enviro 700X terminated minimum 100mm high and 100mm lapping on BSM sheet.
label | 6c3606bb-5a7d-53aa-ae49-b743b64fdadc |  | note | Records - Time Stamped Photograph
select | c4648a2e-bb0d-586c-95a6-37e12232bf12 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection - Sign Off
checkpoint-status |  |  | checkpoint | Service Penetrations
label | d5cc9510-5355-57e5-aba5-bd836303d38a |  | note | Service penetrations to be caulked around with Enviro flex FC/ SIka FC.
label | b2956fa8-d590-5a79-b450-9fa910e49af3 |  | note | Records - Time Stamped Photograph
select | efc985cd-4534-59ce-8645-417a173ca443 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection - Sign Off
checkpoint-status |  |  | checkpoint | Builders Detailing Review
holdpoint |  |  | signoff | Site Engineer/ Foreman Inspection - Sign Off
checklist-sectioned |  |  | checklist | 200P Ultra V01 |  |  |  |  | Yes | 200P Ultra V01 | 050c0976-f931-4e13-abdc-eb98f9232f89
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 8bf8049f-541c-5dec-a91a-e0076e222535 |  | textbox | ITP No.
text | 6bfd893c-8d8d-5ecc-ab89-7569a6830e80 |  | textbox | Revision No. & Date
text | eeb63688-9f05-5c73-a702-30ef7122e65b |  | textbox | Prepared By
text | c1c7332d-f454-546c-8560-c98b53871379 |  | textbox | Reviewed By
text | 48f012bc-8129-5126-b904-84b3ac897257 |  | textbox | Approved By
text | 5bb3b702-a603-5f36-bbc4-ec402dfa85ce |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro Shield
label | 53263a52-18c8-5f70-b582-b40870dd76e2 |  | note | Records - Time stamped photograph
select | 271a82c3-ba2c-59a8-88ad-13c49248ebe5 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex FC
label | 26ea71b6-15e8-598c-a5a2-8c3c08715d7b |  | note | Records - Time stamped photograph
select | e0a7173d-00c6-55bf-a7b1-adaf59259b49 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 200P Ultra
label | f9b49a28-d79e-5e12-bebf-1daa9d12ca59 |  | note | Records - Time stamped photograph
select | 4b86d52d-a854-5430-81b6-ca16c94c2e63 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 6fb8cb5c-35b8-5d2e-ba27-b05314b4d1ba |  | note | Submit samples for approval as per Specific Material Requirements.
label | c0c39b02-161d-5df7-a29a-cf57e07e24f2 |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | f37a3c24-5897-5221-a50c-8ee4816e43bb |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | b8446ec8-2453-5e57-825d-f40e1f682417 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 25367a9f-2d2d-57cc-851a-193cf265331f |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | c455e862-ac3a-53fc-9ee2-d2fcd06cce6f |  | note | Records - Time stamped photograph
select | ed88965e-ea13-5ccd-bdf2-adce640324a4 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | 71885b43-ccc4-58c3-9daa-87163637ed18 |  | note | Obtain clearance for work initiation.
label | ebf2494d-6d01-505e-8d20-877a93fbe849 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | 09615970-4504-5e54-95ec-806949bc7f7e |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | b1113e38-7052-5b6e-8b26-820bad48eeb1 |  | note | Records - Time stamped photograph
select | f82dcb2e-48ec-5892-b09d-c2bb69de848b |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
label | fc19b574-849d-5240-aaee-8298b6ee29e7 |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | bce6548f-0e0e-5f23-99b3-f28fec2e5cdd |  | note | Records - Time stamped photograph
select | 349a4787-e5d9-5b6c-9300-eaae5dbe4f4b |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | 1197488a-48a4-53f2-969b-c194e26cf5fd |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | ed763f59-8576-53fc-bd05-1a340f673c21 |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | d853df90-9e03-529a-a2a5-108497cd04c0 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | 86e9df03-c6da-5d21-bbf2-0061f60732ab |  | note | Records - Time stamped photograph
select | 52e348d9-83f7-51a4-854b-9e04da35b6a1 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | 44c83cb6-4e10-5d96-9588-94222c2456c2 |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | 927a9cfb-2daa-528c-8b76-c2861b792f61 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | cba16a60-1dbb-5e11-9ce6-11b4cddd4de4 |  | note | Ensure no substrate cracks greater than 1.6mm.
label | 9172796b-0d66-5ed1-992e-844438640298 |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 21ee1e19-aff3-5d87-8506-a0f41962c276 |  | note | Records - Time stamped photograph
select | 0eed3625-0c76-5038-9a64-4bb2a29ab81c |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION - EACH LOCATION
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | f225dce4-d5ec-5992-934c-a62ad612147a |  | note | Ensure Surface is prepared to receive primer application.
label | dc9d7dc8-4821-5168-89b4-b8adb6fc6f83 |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 41d5b9f5-d5b1-52ad-a206-62f2bc0ecaf5 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 9c24f3e0-cda1-5775-87d3-7dc563e2935b |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 8dc785fd-5849-56eb-8f32-dc6f99bf7a28 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | d993e4dc-ba77-5a44-aa47-a9d6fa944cb9 |  | note | Records - Time stamped photograph
select | 1ba7911e-adee-5126-bd5a-ecb62effc4af |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Shield Product TDS
label | 5128d1a0-b280-54d1-a6c4-153042df69ce |  | note | Check Moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | 80014ebe-8c44-52bd-9468-2678ee4dbe6d |  | note | Records - Time stamped photograph
select | 5f74b39e-e2ad-57bf-b651-a8b905f99e30 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Shield Product TDS
label | ff917656-8691-5a8a-8d1e-f25ec26e0c43 |  | note | Apply within 10-35°C
label | 23b195ec-a596-567d-ba6a-72ba1b45aae5 |  | note | RH must be 0-85%
label | e900bdd0-bffa-571b-bf95-dd1e7ade7b0e |  | note | Screenshot - Temperature and weather forecast
select | 1351a434-3e3c-5ac7-aa38-d500f4d0e295 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - Enviro Shield Product TDS
label | 99cbb6a2-d3be-5d99-839d-e381e2b59df5 |  | note | Add Enviro Shield Part B (grey liquid hardener) to the Enviro Shield Part A (base Thoroughly mix with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | 8ea85e55-9c4a-5e5b-afa6-9da24c2e0e7e |  | note | Mix for 5 minutes or until uniform.
label | 3d03b4a1-dbb2-5963-aafc-68db1e4b55e3 |  | note | Allow to stand 5 minutes after mixing and then mix again for a minute.
select | 4386869a-84f2-5119-8905-5527acf7977a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Shield Product TDS
label | ed461660-98b1-5c6e-b8a3-df83a69e6ed0 |  | note | Apply primer using a brush or roller.
label | dab92e41-45a2-5aca-bbb9-238693b3d0f8 |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface.
label | 01e324e7-4188-5adc-9d73-a1a4c58c8a4d |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | c71d6db1-6660-5517-a2eb-f18865ddb45c |  | note | Records - Time stamped photograph
select | 9fcbc418-29e7-51ad-bf9a-9489a4ad6c82 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER- EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | fa66b444-1ba3-511e-b588-5c24d6453241 |  | note | Apply Enviro Flex FC/compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | 2380358e-85c8-5810-ab0a-2b0f381aafc5 |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | 810c4307-958e-52d3-b0c2-92d3f66a7d5e |  | note | Allow to be tack free prior to over coating with membrane coats.
label | 2ae9b72f-707e-5508-af5c-abd23b025c78 |  | note | Records - Time stamped photograph
label | aee8fb86-4601-5107-9b2c-e9546ba5cc3b |  | note | Records - Thickness with fillet gauge
select | b2b8cfcc-f9c8-5533-b89b-a8ed256ad68e |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman bond breaker inspection sign off
checkpoint-group |  |  | section | FIRST BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 200P Ultra Product TDS
label | 494e7477-e8ed-58f3-8990-456e140db13b |  | note | Apply within 10-35°C
label | a206edf2-0156-5d45-bc18-29f85557f0c8 |  | note | RH must be 0-85%
label | f6dc4358-d526-56b7-adf0-b47910235ee6 |  | note | Screenshot - Temperature and weather forecast
select | e5ab4f1a-e383-5a35-9cb1-92fb8f15834c |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - 200P Ultra Product TDS
label | 095ae891-4185-5c4e-a005-97add4bacda7 |  | note | • 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | e139d0c5-7701-559d-8763-c6edc75950c3 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - 200P Ultra Product TDS
label | dd5e087a-1dc0-5a79-a7c8-bc6ab85b9b41 |  | note | • 200P Ultra to be applied by roller vertically on substrate and terminating min 150mm with brush.
label | 95dae775-74ac-5cc5-b2b8-829462a91be6 |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | 3c008728-fd12-5f50-b095-c9bbdff793d1 |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | f9336a01-1bb9-5bb7-8ba4-4d6cd2675d04 |  | note | Records - time stamped photograph
select | 59b0ab16-8223-59df-b888-4a2b7bd61af4 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman base coat inspection sign off
checkpoint-group |  |  | section | SECOND BASE COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 200P Ultra Product TDS
label | 5638c458-1e2e-55f0-a86a-92ab145f5a5c |  | note | Apply within 10-35°C
label | 06a3f156-d5c1-5f4c-b215-24c614e5b454 |  | note | RH must be 0-85%
label | 7e7799c6-4d43-5071-81f0-64294cca4daa |  | note | Screenshot - Temperature and weather forecast
select | 9ce59582-40b9-58ae-9074-226f61bb4aef |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - 200P Ultra Product TDS
label | 2dbef502-84af-572b-907b-3f541afa32de |  | note | 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | e90cdb40-7779-5bb5-ae99-75fb8023621b |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - 200P Ultra Product TDS
label | 84e0a3d4-96c4-547d-bc0f-e4cfd1945384 |  | note | 200P Ultra to be applied by roller Horizontally on substrate and terminating min 150mm with brush.
label | 43b05fac-03e8-5078-a9f7-afcd024c751c |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | d4f3fa87-8bfd-502e-a327-1c84d0d7fb04 |  | note | Allow membrane to cure for 3 days prior to testing.
label | c2867e4e-5cad-5b8d-afc7-005fcd203ca5 |  | note | Records - time stamped photograph
select | ab5a31b4-38e7-5c08-a25e-b6922227e6c7 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor second base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman second base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman base coat inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | 386ea325-c873-5cd9-9b24-07e9f7c16588 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | 033880c4-7081-5c47-a240-f814964b7437 |  | note | Records - time stamped photograph
select | 26178662-febd-5007-9cfa-a7e50e4c16f8 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Thickness Testing - Delfasco Positector
label | 532bd01c-8ec4-59cc-89ce-509fba7f7255 |  | note | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
label | 9b2db5b5-c147-5b51-a3a0-00e5218652ee |  | note | Records - time stamped photograph
select | 62a72c48-a560-5767-add3-39d7520ad8b8 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Flood Testing
label | ef4beef2-d953-5420-bffe-9a837e69e95b |  | note | Mark water level and conduct a 24 hour flood test for internal wet areas
label | faca497c-f9bd-506e-bf34-4d98088bbb08 |  | note | Records - time stamped photograph
select | a38ce732-b95e-53a9-829d-727e455d2b5f |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | Site Engineer/foreman base coat inspection sign off
checklist-sectioned |  |  | checklist | FATRA - V1.0 ITP |  |  |  |  | Yes | FATRA - V1.0 ITP | a107eebc-0352-4053-9bf6-b006a6b59831
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 266b0e68-81b1-53c5-9012-d39210f77446 |  | textbox | ITP No.
text | 7437d6c6-0c47-5af7-8313-043d36ec5be4 |  | textbox | Revision No. & Date
text | a74d8be7-700b-5f92-801a-25e1aab56017 |  | textbox | Prepared By
text | 8b927b52-1eb5-5d61-81bc-557d58780a71 |  | textbox | Reviewed By
text | 79d9552b-193c-55ef-8181-0c87fbc35812 |  | textbox | Approved By
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | FatraBond Adhesive
label | f4eb9c3e-0347-5757-8ef2-562bcd2b691a |  | note | Records - Time stamped photograph
select | 6c93fe70-3084-5110-9199-16336ca9b7f3 |  | dropdown | Inspection | Surveillance point,Witness point
holdpoint |  |  | signoff | Subcontractor and Site Engineer/Foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 81b5e898-c2da-588f-9e0c-a8c7893471bd |  | note | Submit samples for approval as per Specific Material Requirements.
label | 88dfd791-a17f-599a-b3d3-49713fcbeba2 |  | note | Sample Approval Ref.
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | a78e94e1-d5d3-5e45-860b-fbe7eb67960b |  | note | First of type of inspection conducted prior to commencment of works taking place.
label | b5132a29-c847-5019-bc7d-060534018eac |  | note | Document Ref.
holdpoint |  |  | signoff | Sample Submission / First of type inspection - Site Engineer Sign Off
checkpoint-group |  |  | section | APPLICATION - EACH LOCATION
checkpoint-status |  |  | checkpoint | FatraBond Adhesive
label | ac2208b3-2aa2-56d5-a1bb-0386c4866bc1 |  | note | Apply adhesive consistently over required area using squeegee/rollers
label | cc305264-0071-5789-8803-72ae8a497661 |  | note | Adhesive is applied consistently and evenly across the surface to achieve correct adhesion
label | cc6cbb15-639d-5513-85ce-c04beb472da6 |  | note | Adhesive does not spill onto membrane, weldable laps or surrounding areas that can potentially contaminate welds
label | 30c41b9c-bd9e-52c5-add5-5c6aeef902a2 |  | note | Records - Time stamped photograph
select | 1453c71b-0860-5d04-86c3-c0bf1809fb37 |  | dropdown | Inspection | Surveillance point,Witness point
checkpoint-status |  |  | checkpoint | Install Fatrafol PVC Membrane
label | f5314f82-9435-5226-ae22-4ae7f9149a8c |  | note | Install Fatrafol to coincide with the falls of the roof
label | afe50769-e6bf-590d-bbd0-00d5552f8ac4 |  | note | Ensure the membrane laps run with the fall of the roof to minimise negative laps on the roof
label | 27e04eca-8ff6-5940-b595-859e3cb8bbe1 |  | note | Records - Time stamped photograph
select | e5ebb07b-c368-5ae3-bf77-4b829c8ff45a |  | dropdown | Inspection | Surveillance point,Witness point
holdpoint |  |  | signoff | Subcontractor Inspection - Sign Off
checkpoint-status |  |  | checkpoint | Builders Application Review
holdpoint |  |  | signoff | Site Engineer/ Foreman Inspection - Sign Off
checkpoint-group |  |  | section | DETAILING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Hot Air Fusion Welding of PVC membrane.
label | b0ffc153-1957-5a98-82d0-0b13aa9b8685 |  | note | Hot air fusion weld overlaps.
label | 59dda9e2-5955-5bd7-8748-e621ef680d70 |  | note | Achieve a minimum 40mm wide weld width on all hot air seam welds to achieve sufficient weld strength
label | f17c2d28-d14f-5b6a-b684-8142bcec3681 |  | note | Records - Time Stamped Photograph
select | fa7dbb91-c681-59f2-bdc8-392eb302765d |  | dropdown | Inspection | Surveillance point,Witness point
holdpoint |  |  | signoff | Subcontractor Inspection - Sign Off
checkpoint-status |  |  | checkpoint | Installation of PVC Coated Angles
label | 9d80e734-218a-5dcc-966a-31f217d0be39 |  | note | Fixing Fatranyl PVC coated termination angles using relevant fixings
label | 1ee38694-9fa7-5d8f-8258-8f2baf53018f |  | note | All termination metals are aligned correctly and are not disjointed or protruding
label | d3ed1bdc-beb3-5347-8c78-53c4daccad02 |  | note | Fixings centres do not exceed 200mm centres
label | 5fcb45b5-0d6d-598b-9186-80d9e6272ca9 |  | note | PVC coated termination angles are installed with a minimum 2mm gap between each angle to allow for structural movement and expansion
label | f04af38e-402b-584f-9856-65f782da9ede |  | note | Records - Time Stamped Photograph
select | f29c6b4f-3b5a-53d9-b9e3-f5d4cafbacbe |  | dropdown | Inspection | Surveillance point,Witness point
checkpoint-status |  |  | checkpoint | Builders Detailing Review
holdpoint |  |  | signoff | Site Engineer/ Foreman Inspection - Sign Off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | 312cfd38-1fdb-59a2-a3bb-255ac75ab301 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | 82a2468b-448f-5c68-afbf-45e9d81f7981 |  | note | Records - time stamped photograph
select | ae8de0b5-83ac-5703-bfc4-9da619e43419 |  | dropdown | Inspection | Surveillance point,Witness point
checklist-sectioned |  |  | checklist | Pre Start Briefing Form V1.0 |  |  |  |  | Yes | Pre Start Briefing Form V1.0 | 7c086190-b1f9-4a22-83cb-dd5acabef41f
checkpoint-group |  |  | section | PRE-START DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
date | 240c5141-196d-5cb9-80cc-f32015af66ad |  | date | Date:
text | 7aa72205-e208-5066-9208-6bb617beeb98 |  | textbox | Time:
text | cebc36c3-4442-50fd-b749-91c0d1b9b1e5 |  | textbox | Location:
text | 6467baba-a79d-5ac4-b3f2-151c50d11da9 |  | textbox | Works Supervisor:
text | ad9b1fdb-f9ac-57f3-91f2-ccbbda17d1cd |  | textbox | Client:
text | fc21b8b7-aafd-55f7-aa27-796467119132 |  | textbox | Representative conducting meeting:
checkpoint-group |  |  | section | LAST WEEKS ISSUES
checkpoint-status |  |  | checkpoint | Issues arising from previous day?
text | 4b7c4efe-cf64-54a7-92cc-b080aac1e8ef |  | textbox | Issues from Previous day:
checkpoint-group |  |  | section | PLANNED WORK ACTIVITIES - DAILY
checkpoint-status |  |  | checkpoint | Work Activities
text | 24f32913-faa1-5e9e-a5e0-b473ef636fae |  | textbox | Activity 1
text | cc9c29d0-4891-5e02-9027-55231338209f |  | textbox | Activity 2
text | b8598ddf-9f53-5441-95c2-a542d80d4786 |  | textbox | Activity 3
text | f96fb439-859b-5067-961f-542fcfe9dbe6 |  | textbox | Activity 4
text | 8f192723-b827-5ab1-8c56-23a7c04803e8 |  | textbox | Activity 5
text | 96c63ec5-64ce-5657-b4f0-2b624b03a9e0 |  | textbox | Activity 6
text | a00932ad-8117-5a8a-b21c-9c5b9884eaf7 |  | textbox | Activity 7
text | beb1e468-192a-5eae-8ed0-01594b7c712c |  | textbox | Activity 8
text | 56b50cad-da18-56ca-9062-0fafde0beaaf |  | textbox | Activity 9
text | 9f7c61f3-02de-5266-84cd-fcc21b5af558 |  | textbox | Activity 10
button | eb1fcc6c-4d92-5fc9-84e9-8954ced6f593 |  | button | SWMS in place for all activities ? | Yes, No
checkpoint-group |  |  | section | SUBCONTRACTING
checkpoint-status |  |  | checkpoint | Subcontractors on Site
button | 72c3ea14-9dd1-563e-af6d-2d9e9ea8a5d9 |  | button | Are you subcontracting out any works today will you be interacting with other trades? | Yes, No
checkpoint-group |  |  | section | ENVIRONMENTAL AND HAZARD CONTROL
checkpoint-status |  |  | checkpoint | Environmental Control
text | 0679a8f7-e34b-52b4-96f3-1ee0263d981f |  | textbox | What controls are in place to manage envionmental risk on site, specific for today?
checkpoint-status |  |  | checkpoint | Hazardous Substances
text | c9e37a58-9ea7-59f5-961d-9ad069c92dee |  | textbox | Are any hazardous substances being used or will be brought to / or stored on site today?
checkpoint-group |  |  | section | ACTIVITY CHECKLISTS
checkpoint-status |  |  | checkpoint | Daily Risk Assesment
select | a879f08b-1a5b-55f4-a747-379d911e7418 |  | dropdown | Work area inspected and safe for staff to enter and work in today? | Yes, No
text | 76b3ea05-6b3a-5ffe-a221-7214f0d35aec |  | textbox | Indicate number of people in your work group
checkpoint-status |  |  | checkpoint | Qualifications/training of staff adequate for work activities
select | 49b75400-2e1b-5f6f-b65f-1ac166fc0659 |  | dropdown | Appropriate and adequate PPE supplied to work teams? | Yes, No
text | 45c68fca-b4c7-5022-8849-585113713a6e |  | textbox | Indicate number of workers allocated for todays clean up after works completed
checkpoint-status |  |  | checkpoint | Plant and equipment on/off site
select | b8612596-8972-5656-91b2-81f8111d9f31 |  | dropdown | Weather conditions for work to be conducted assessed | Yes,no
select | beccc4c4-151b-56c3-aeaa-c3f6e11fe520 |  | dropdown | Pre-start consulted to all work teams including subcontractors and Trade listed in section 4 | Yes,No
select | 372fcc76-3c5a-527e-8c25-bc6c9f4450eb |  | dropdown | Equipment safe to use | Yes,No
checkpoint-group |  |  | section | BUILDERS BRIEFING NOTES AND GENERAL NOTES
checkpoint-status |  |  | checkpoint | Builders Briefing notes
text | c1c53609-39bd-5d96-8501-e8350c299ed4 |  | textbox | List builders notes if applicable
checkpoint-status |  |  | checkpoint | General notes
text | ea79ff2c-c375-5e48-bb0c-99acd86c5163 |  | textbox | Today's general notes
checkpoint-group |  |  | section | ATTENDEES
checkpoint-status |  |  | checkpoint | Pre Start attendees
text | 7d8d51fd-350c-57fe-8022-daf535d9d7e0 |  | textbox | Attendees
holdpoint |  |  | signoff | Attendees sign off
checklist-sectioned |  |  | checklist | Sealer V1.0 |  |  |  |  | Yes | Sealer V1.0 | e090525f-618b-4ea6-98a1-d057baed003a
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 9a9f8d53-73c4-508b-8f2a-f1e8b281a41b |  | textbox | ITP No.
text | 054ed12e-91a0-5444-8081-c234431c6520 |  | textbox | Revision No. & Date
text | 817d8986-c5a4-58d7-8ac9-dcea522221d6 |  | textbox | Prepared By
text | fed66dab-f5fa-5738-af46-7321e8b9ce9d |  | textbox | Reviewed By
text | b5acea57-7930-5bde-9c65-b597eec7140a |  | textbox | Approved By
text | abc369d6-cada-5cf6-bb29-e5b5d6242f9c |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro Seal WB
label | 6a79fe94-0442-5750-a0be-5b8a8431582a |  | note | Records - Time stamped photograph
select | 0fbde961-9f60-558f-93c7-e863dacad104 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro CSH
label | 2e088cb7-bafe-51df-88ed-64406c97e400 |  | note | Records - Time stamped photograph
select | f63ee8a1-d291-58ab-8f40-d46c5ef13850 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 8a6edd7b-f5fa-529c-8403-0adbcfd78c35 |  | note | Submit samples for approval as per Specific Material Requirements.
label | b0c920f0-b09e-5b11-ad5b-ce6abe57c0d1 |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | e44b1cac-6615-55dc-8207-52574f2930db |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | c01460d5-5b1b-54d6-a494-2cb5854130a5 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 0fa92cbe-b9d0-5c5e-b739-2d014d243a2f |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | c659018f-7729-5ed5-9bf5-de086bca7a2d |  | note | Records - Time stamped photograph
select | fc0e316a-b4c0-552b-81f7-978116b343af |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | edcdb43f-e8e9-54c2-b0f4-903431ad0d46 |  | note | Obtain clearance for work initiation.
label | 6724bea6-480d-51ad-a91f-a333b00c1314 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | ab336e77-fc6d-514a-a4ed-9dce2d77f5bd |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | d9202f12-5876-5a2c-ad55-654a512a1a79 |  | note | Records - Time stamped photograph
select | e0d96745-b9bf-53a5-ab4a-0e688f933947 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | 47da9490-4b60-5fa4-9b7c-02e86994a1fe |  | note | Ensure no substrate cracks greater than 1.6mm.
label | 6a1bf96e-efff-534c-9728-60998836958c |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 75447aa9-da3d-5348-b05a-a01673029227 |  | note | Records - Time stamped photograph
select | f4020fb2-af60-5619-b537-22aad3d62a6e |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION - EACH LOCATION
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | df0e0dd8-4946-5b3b-8852-c6f4366cdbda |  | note | Ensure Surface is prepared to receive primer application.
label | 66f5e7b4-4b2f-5df1-8469-0d66751e2a51 |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 399876a6-f24e-5b49-9c3e-9f751c142e04 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 4d594018-8f55-56b4-b030-31407e7805df |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 6da8a6c1-b632-5518-a9a4-40423c426dae |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | 78339314-5df1-59f2-8d46-b331917f7aa6 |  | note | Records - Time stamped photograph
select | 351ee60f-8fc1-5bf9-90ef-93c281dc8ec5 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | FIRST SEALER COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Application
label | 98f0d9fa-05a9-5491-a3a2-b68338d7599d |  | note | Spray or roll concrete Sealer on substrate
label | acde0429-5f91-5b24-9956-fadd33bfc90e |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | b1d20ebc-83a4-51c7-9113-21f764ed400f |  | note | Records - time stamped photograph
select | adf80c57-1dd5-5c77-87dc-4da6be2e10a4 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first Sealer coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first sealer coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | SECOND SEALER COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Application
label | 54d77952-20bc-5927-914c-dc525854f80a |  | note | Spray or roll concrete Sealer on substrate
label | eef49155-c39a-588c-9ba1-eed2df43cdac |  | note | Records - time stamped photograph
select | a99bd96a-d2d2-5dc2-b908-2cba7621a15d |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor second Sealer coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman second sealer coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checklist-sectioned |  |  | checklist | Enviro HP1200+800TC V1.0 |  |  |  |  | Yes | Enviro HP1200+800TC V1.0 | 5ef7c5ad-1dde-4c02-97f4-1d9f1f76d994
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 3c694b2c-c959-5c77-ad7e-7c6c6b841f7a |  | textbox | ITP No.
text | 63bf2f0e-4033-50cf-af0b-86ef7e7d6fe3 |  | textbox | Revision No. & Date
text | 91bd5f27-98e1-5a39-9787-91fb5b4b2115 |  | textbox | Prepared By
text | f34f4d69-16f2-50d1-b7c4-fabe2c178bed |  | textbox | Reviewed By
text | 2c696b0e-ee75-5be7-b864-c495a245057b |  | textbox | Approved By
text | b293a4c3-8c8c-5292-b15a-0b0da323b732 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro B-LV
label | 979265b8-6bb9-5b02-ab45-9b49d90b989a |  | note | Records - Time stamped photograph
select | 7bd7e2d0-8bb7-5795-8c7a-c6e9af62d6ec |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Sika Flex FC/ Enviro Flex FC
label | 7c798ba4-643e-5562-9159-7ce1d6031baf |  | note | Records - Time stamped photograph
select | 7c6a71a0-deab-5822-b58b-f257db58bf8e |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro HP1200
label | cabd3104-5c34-5bc2-84e4-e28a4116fef3 |  | note | Records - Time stamped photograph
select | 10bc5688-f797-5169-b973-bdd9fcba6038 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 900 PUR
label | e094e936-3973-589d-a71a-054e8c9d1b11 |  | note | Records - Time stamped photograph
select | 791699a6-38aa-5b1f-9130-a402bf397dda |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 800TC
label | 88316839-3c6b-56d7-a15e-0a564c5668fd |  | note | Records - Time stamped photograph
select | dfb25ebe-0ebe-50e2-91fc-5cca8eead70a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 3e679d6c-8ea2-5ef8-84cc-795b7c95431a |  | note | Submit samples for approval as per Specific Material Requirements.
label | 02587a10-404e-5cf4-9db5-6f4fef8d151f |  | note | Records - Subcontractor Contracts Admin Confirmation
label | 1cd22931-678f-5894-a93c-6ee1d428445d |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | c4a42539-82ab-5f4b-bb18-5e4e4d1db80a |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | 36befb10-b92c-5a76-bc17-c0e7338d561e |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 8fa7b53a-b3e8-56d4-9f34-9afc0465e0c6 |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | b9904a1a-9226-5b11-9af0-c8e6417ff68b |  | note | Records - Time stamped photograph
select | 77408d11-5c6e-5894-8db8-5bc4906e994f |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | 895b2a9d-5d81-539e-90d8-8084a5037528 |  | note | Obtain clearance for work initiation.
label | 35ff15c1-dbed-52c2-ad2d-563dc1f2bc63 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | 69a956cd-0acf-5dfe-86fd-56dd13d73244 |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | 247afef4-6e5c-5529-b469-b1d8959f33a5 |  | note | Records - Time stamped photograph
select | ecee74d4-bdff-59ca-a260-3b84fc38830d |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
label | 5f12385b-1f9a-5a0a-912f-2a6d8986753c |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | 65f50955-c477-5cd7-a039-65cb774d1e81 |  | note | Records - Time stamped photograph
select | 8fb6fc3e-202e-54c1-bcd2-162ac9dd2d64 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | 98779d7c-7140-5822-9ae1-ab3e22a548be |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | c03cb8fd-3e2a-5890-928c-27a0eb64d55e |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | f23c40ee-2aa0-529f-8138-996b4f47b886 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | 5b1d15c3-2098-55a5-bf05-18daf85769f4 |  | note | Records - Time stamped photograph
select | 87b240fe-4218-50cf-ae53-5f6e0a1b693a |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | 1e2197ef-52a8-5472-a659-5cae50a04c92 |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | 8e7b5c22-e3ee-5d77-afe0-5fb70faa49b2 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | d8aed63f-c653-54e5-bf7b-e0deb61fec88 |  | note | Ensure no substrate cracks greater than 1.6mm.
label | e0251e0e-8798-5824-8a26-bd9202860e11 |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 0596d00c-f632-50f7-9510-d62a2571973c |  | note | Records - Time stamped photograph
select | 6652d8f2-6d6e-5b7e-aa9e-92b70059f1ae |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | 79895bec-2548-5b29-9c12-26942676e36e |  | note | Ensure Surface is prepared to receive primer application.
label | 62b1b9cf-461c-5e21-9ff3-9b0e914c5cef |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | bf10b33f-06e8-576e-bb34-280f591248dc |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | ab670afe-182a-593f-b09c-085442970523 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | e1a975f0-3050-534e-a7de-0d630057d8c4 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | c1abeb6f-13cf-53e2-9298-0886ba6c13ea |  | note | Records - Time stamped photograph
select | 0b7f56f0-6235-591a-b89f-4c8f6d4c67d9 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
label | 851e66dd-b1c8-5e8e-a740-1b10ba8c928d |  | note | Ensure Surface is prepared to receive primer application.
label | 9a5a1b36-1398-51c0-86e2-bb5092ffa8c9 |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 1c6edaa8-d09d-5dbb-be29-378b242f07a9 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | f303fd23-4375-5a7c-b13f-2a39ad07af56 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 30241c00-095d-5754-954d-fddb4214caf4 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | cd244bab-a2c6-5792-adbe-d2dd4176a67b |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | e0c45834-bfdd-5a54-bbd1-bd324be024ff |  | note | Records - Time stamped photograph
select | 35676b4c-26c4-5bb8-bce9-b6f9fcc65c83 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | 2978cf5c-7a56-50e1-bcf2-8309876bd543 |  | note | Apply within 5-35°C
label | 8664d6d0-6714-5574-bc22-f44acde7673c |  | note | RH must be 0-85%
label | 41ebc8e1-c630-5f96-beaf-cb99dfbd090d |  | note | Screenshot - Temperature and weather forecast
select | 459f9432-33b1-5bb9-a547-976e771dde7a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | a6169534-9918-5fdf-ae01-e3cafb574772 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | b7e906d9-8959-549c-9936-112197c3063e |  | note | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | 313da0d3-890a-50c7-96da-128f52fb4ba6 |  | note | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | f553c9ce-9c3e-5bf3-8b82-9b8ebd19b1d2 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | 414d99ef-9eeb-50d3-9d60-a3676b6d84bf |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | 412dab85-ad77-5b66-b009-b0e8537542ab |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | 9d6e812e-032f-5f16-8aad-d26c7fc208f0 |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 41f8dd1f-6811-5221-900a-334dc99a5c8f |  | note | Records - Time stamped photograph
select | b1328787-b592-5474-b199-1f5b510c6d56 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER- EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | 7906813a-0e9d-59b3-bae3-04d6a018f798 |  | note | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | 494f0425-503a-5305-9277-71484e2cfebe |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | 05a1d3b2-4283-5c6b-9d67-25d678bbdb9f |  | note | Bond breaker to be tack free prior to coating.
label | af582b73-ad72-58c5-9d18-82372f6761f1 |  | note | Records - Time stamped photograph
label | 9c54e1c2-e2c6-5629-8ef8-ffe33bdd8242 |  | note | Records - Thickness with fillet gauge
select | b6a98c49-e69a-54ea-a9dd-5a6754e98936 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
checkpoint-group |  |  | section | BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - HP!200 Product TDS
label | 2aa04793-0d0e-515c-93c1-a4be88c88c26 |  | note | Apply within 5-35°C
label | 4de94224-35e3-505d-92df-72f239704922 |  | note | RH must be 0-85%
label | 5fc813c4-4abc-5f6b-9b5c-65d747593538 |  | note | Screenshot - Temperature and weather forecast
select | 9e836fba-e2d5-5683-9c7f-002adf563bca |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - HP1200 Product TDS
label | c09b6c38-06bb-5d89-9782-448ea3104638 |  | note | Mixing by way of 1:1 mix ratio (by volume) in heated plural component.
label | f411dcd6-4b21-51ab-ae00-a10616baf1aa |  | note | Mix Part B thoroughly with a mechanical power mixer before use
select | 72a18d1c-77f1-540f-b256-2fbdb4ac8ee8 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- HP1200 Product TDS
label | c152500f-7936-5f26-a052-2de27acc16cb |  | note | HP1200 must be sprayed using high pressue plural component dispensing equipment - Drums of component must be pre-heated to at least 25C prior to mixing or dispensing
label | 56e2c7ba-3a99-5795-af21-d78fede5cb17 |  | note | Records - time stamped photograph
select | 66fdd4e4-1a43-56f6-b8e2-b793e554c3e1 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | 9ddd5169-fc74-5e6f-8426-c5d60e156d76 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | 7944f33c-b4f9-5ac0-adf2-d26c451fa4c0 |  | note | Records - time stamped photograph
select | 0823a64f-8912-5f8a-a257-f8bdc7973db7 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Thickness Testing - Delfasco Positector
label | c19a587f-f486-5d07-b501-59dd077a6c99 |  | note | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
label | 57dc1c7e-c8f7-58b4-9515-e7d453959e89 |  | note | Records - time stamped photograph
select | 31cdd15d-8897-553c-a41e-5c7a82700e75 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | ELT Testing - Delfasco Holiday Tester
label | 8b594d92-1317-5b07-95c7-08d4b03120db |  | note | Conduct Electronic Leak Testing ( ELT) on area membraned
label | cb663322-8651-5b10-bb87-fe03c26c12e7 |  | note | Records - time stamped photograph
select | 12f51491-5874-57cd-b1f4-ecaa14da47c0 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | HOLDPOINT - Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | HOLD POINT - Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | WEAR COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro 900 product TDS
label | fdab6e41-ba53-5f54-bb4d-e77b179fc49c |  | note | Apply within 5-35°C RH must be 0-85%
label | 3b55d11f-e46a-519b-a1ac-5d51c2cdedd7 |  | note | Screenshot - Temperature and weather forecast
select | c1606599-a8f9-58e9-a6bc-08590f245719 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing of Product - Enviro 900 product TDS
label | b2374e37-39af-5ba9-bc78-a120581a9ed8 |  | note | Mix Part A and Part B separately, before combining.
label | 5b8745cc-2daa-5e1d-8a14-bbd829e4be0b |  | note | Enviro 900 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for a minimum of thirty seconds prior to application.
select | d63c499f-f3d9-5a25-ae09-db878713d773 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro 900 product TDS
label | c523cd4a-7cdd-5b72-87c7-59fbd9a87bc5 |  | note | Enviro 900 to be applied by squeegee, roller or brush to finished membrane.
label | 6ae4ec7a-b9f4-595b-82e3-70026211554d |  | note | Aggregate should be uniformly broadcasted to the wet Enviro 900 within 10 minutes.
label | 0669022a-085f-522f-8a34-7552a69c0501 |  | note | Records - time stamped photograph
select | 30b61d0c-cae9-579e-97c9-323cae47f3e4 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor wear coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman wear coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | FIRST TOP COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro 800 product TDS
label | f9a9956f-e673-5c2c-b926-0ab8ae532b73 |  | note | Apply within 10-35°C
label | 0b12bb3c-3ee2-522b-9e5c-e3ca0a6e4c79 |  | note | RH must be 0-85%
label | 477e5b91-a44e-56b1-a93e-0a5a045bdc58 |  | note | Screenshot - Temperature and weather forecast
select | f36b68f0-9e84-5967-b1b7-4bed787ce042 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - Enviro 800 product TDS
label | 450f73c3-29cb-5d01-ab97-adb53ddafee6 |  | note | Mixing by way of 4:1 mix ratio (A:B) by volume.
label | 213013fd-601c-5d2f-ab82-8b67845c6837 |  | note | Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | d161a99f-28b3-58b4-b5dc-9ed68cdf3316 |  | note | Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
checkpoint-status |  |  | checkpoint | Application - Enviro 800 product TDS
label | ee3305de-cc9c-593d-9caf-99f1fc9333cb |  | note | Enviro 800TC to be applied by roller or brush to finished membrane.
label | 9ea24b53-12fc-514c-88a5-17f7a5b3efea |  | note | Allow coat to sufficiently dry ( 24H) before proceeding to the next coat.
label | d77fb3d7-2fcf-58b5-a1f0-3d4cf446941a |  | note | Records - time stamped photograph
select | 450c39b2-5c3e-5a2f-aa1c-8206bf3fcad6 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first top coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first top coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | SECOND TOP COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro 800 product TDS
label | 5d98f037-c9f8-52fb-bf56-111f42a9bd5d |  | note | Apply within 10-35°C
label | 4fa59f22-cd25-5dac-88c9-c4741c980aef |  | note | RH must be 0-85%
label | 9a114f63-356f-553e-845b-fb51a735178f |  | note | Screenshot - Temperature and weather forecast
select | c5395087-e661-5700-9056-836340d30410 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - Enviro 800 product TDS
label | 5c1c0e5d-ed3e-5c8e-81dc-1365333cf269 |  | note | Mixing by way of 4:1 mix ratio (A:B) by volume.
label | b485c9d9-3477-5830-a7d6-db4beed65d32 |  | note | Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | b4f3156d-3c99-56ea-9b79-b24bc3cf52b4 |  | note | Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
checkpoint-status |  |  | checkpoint | Application - Enviro 800 product TDS
label | 21ad6b73-7588-5e03-88c9-7d32273b4a8c |  | note | Enviro 800TC to be applied by roller or brush to finished membrane.
label | ab20ac86-0233-5cb3-a257-5a9e9cedfc99 |  | note | Allow coat to sufficiently dry (24H) before proceeding to the next coat.
label | ef2445ef-127d-5b3a-aab8-8a94bbbda3f1 |  | note | Records - time stamped photograph
select | 7c8e9001-89c3-573f-a776-6b1364df38ef |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor second top coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman second top coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | DETAILING- EACH LOCATION
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing - AS 4654.2
label | aed1cec1-1d7e-5a52-834e-6eb0e2224ba9 |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | e22c7f5d-c86e-5245-be51-f095c70f58e1 |  | note | Records - time stamped photograph
select | 555788a2-7196-5520-8d88-1b9c3adf88d5 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Detailing inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checklist-sectioned |  |  | checklist | Enviro HP1200 V1.0 |  |  |  |  | Yes | Enviro HP1200 V1.0 | 86f31228-a2bb-4b25-b1ba-b0ce562b638c
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 94725bd3-369e-56d2-a655-0db80384ff9a |  | textbox | ITP No.
text | fd6efd01-9b08-5356-8cdc-9c309d823ad4 |  | textbox | Revision No. & Date
text | e5edf8d5-4fd7-5de3-afe5-f85b4abffa2d |  | textbox | Prepared By
text | 9b204194-b7af-5415-9cfc-670875e1dc90 |  | textbox | Reviewed By
text | b0ef4712-0402-5dc1-bbbe-3b7824ede646 |  | textbox | Approved By
text | dee06efc-c32b-5a67-a253-dca05ada5846 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro B-LV
label | 0afb7336-56d8-5029-b900-6bd009129331 |  | note | Records - Time stamped photograph
select | 87cd7e2a-2d7b-5bcd-82c2-f5855219f247 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Sika Flex FC/ Enviro Flex FC
label | 917a4b14-8223-5d54-a673-6397f9cfca98 |  | note | Records - Time stamped photograph
select | 2d0d39a0-1b80-5a54-a37d-1270f303a3ad |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro HP1200
label | 42779e27-ff30-52af-b74b-144a3f7583c1 |  | note | Records - Time stamped photograph
select | d585e112-db0f-5fc8-a971-b281fe57ec01 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 900 PUR
label | 28e49637-e16a-5e8b-9852-924a652d5597 |  | note | Records - Time stamped photograph
select | e24eadbf-3d65-5aec-b0d4-366c78b3da8a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 800TC
label | 0ea196b8-2557-5308-bdec-3c9943dc6a75 |  | note | Records - Time stamped photograph
select | 16d1e4ed-1f36-55dc-bb54-005fbcceaa34 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | a46cf6dc-38a6-5549-90cc-1a75544b282a |  | note | Submit samples for approval as per Specific Material Requirements.
label | dcc9faf8-49ed-54fd-8648-8e1ccf82eef2 |  | note | Records - Subcontractor Contracts Admin Confirmation
label | 44ff0ae7-3ccf-5987-a652-38a225654a58 |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | 5853ab10-a279-51ee-8697-f4302d3c5029 |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | 334c234f-7033-5a22-bf22-c4e69a32d428 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 71af0db5-c98b-5d0c-bc4a-55c8f5505adc |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | 76616a99-a222-5ce4-85f9-d97709b565e4 |  | note | Records - Time stamped photograph
select | 9f98e673-3227-5416-a759-34d64054c135 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | 9bb31b46-d07a-559b-b63d-1b172c6c1c9c |  | note | Obtain clearance for work initiation.
label | acc33e65-5944-5d96-9b62-1ce2f63ffa61 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | dfe78e1e-ec9d-5c95-8d2b-fe49ca0406e1 |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | f60836ce-7416-5ff5-93cc-3f7e5de1e7cc |  | note | Records - Time stamped photograph
select | ceefd1a0-9d3e-57de-98e5-22a0d1b5772e |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
label | 0376d19d-9de3-566d-85c7-b76d54c06c10 |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | cebd0837-6ec3-5d39-a548-be035a119527 |  | note | Records - Time stamped photograph
select | eef99008-e794-557b-af54-349849ce403c |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | b27e267f-cd09-5b4e-99f0-4b538c35a9c1 |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | b7bed64d-4f0e-522e-bc04-7fe510d19377 |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | 0e825374-f8c1-50ca-a9cc-46bcf2702b77 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | 7667afdc-3a3c-5624-9855-f95c8d589f0d |  | note | Records - Time stamped photograph
select | 00db9bbe-8eb8-5161-8c90-e10a356e86f0 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | e2dc1914-8564-5e01-8721-704eb1613a32 |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | 5795b59e-50c4-5b63-bf9c-123be409ef90 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | f207650e-dd0f-5883-8a1f-d045d3a042ef |  | note | Ensure no substrate cracks greater than 1.6mm.
label | 924ee844-5a3e-5eae-8af5-748b2fc35898 |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 29b49db2-29fd-592b-afe2-48435e853bff |  | note | Records - Time stamped photograph
select | 755640c6-7aa6-5ff5-8114-0500eafda702 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | 80f39cd4-5ed2-5496-b170-3ba60f981d82 |  | note | Ensure Surface is prepared to receive primer application.
label | 033ad453-bd67-5fd3-8ae0-3f41c921f46a |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 127e9a07-cb29-5ef9-a68d-65aa3b67c1fc |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 2585d043-63e5-5ab5-a80b-b738bfabaeb2 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | d593f000-af97-5de4-a4ca-2aee1b902df5 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | d4899e80-9e04-5ba3-bb56-7db4c5bb54ee |  | note | Records - Time stamped photograph
select | 3943b6ed-5787-53bd-a914-2eb7aaaaafd3 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
label | 15135040-f945-5745-80ad-1559c69a03ce |  | note | Ensure Surface is prepared to receive primer application.
label | b0b00f51-3b21-542d-881f-9167ff463098 |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 95504290-8660-59db-a1e5-4490da16f423 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | e262b743-6b78-53c7-b9c6-87caa0886829 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 3171e538-439e-5fe0-aedd-270a07e05e09 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | 94a5d982-4f6d-525f-bd9c-92f5c5ecc73d |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | ee673852-d40a-5160-bc59-b7964ad19005 |  | note | Records - Time stamped photograph
select | 72800a1b-f492-5363-8e3a-53ab2289db76 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | 4c69fdaa-44e9-597b-8fa6-f839d93c13e2 |  | note | Apply within 5-35°C
label | 6de3f45f-75d1-5bff-a185-66d2d0d2646e |  | note | RH must be 0-85%
label | f2eabdc3-5266-5c95-87dc-19a7a4166c08 |  | note | Screenshot - Temperature and weather forecast
select | 04f22acb-0c9a-5db8-b4f9-b154653c176e |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | 49283950-4d44-540d-bae8-25b4265a7ac9 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | 74027b4e-abb5-5a1a-beea-8d9f151e1d18 |  | note | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | 5a9566fc-de86-508f-868d-d67d3553e26c |  | note | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | 57f21608-8daf-50aa-bacf-8caa12edc845 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | 7a08e99e-721d-574b-a185-1f92c5718fac |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | 308ad322-cac0-5cc8-b547-37d2b2cef779 |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | 661a5939-39a9-5c9c-8ecc-706170b92dc7 |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 5c91ca7e-48c3-508f-9dcc-c0c3a51e8a98 |  | note | Records - Time stamped photograph
select | 541e973f-4096-57e0-9d42-747637b07803 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER- EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | b8b49882-530b-5b34-a3a9-55a4b029df60 |  | note | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | 4463c036-4dd8-506c-830c-e2ee79760a3d |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | cf93cfe7-b847-50b9-b0f5-740d9f6ed773 |  | note | Bond breaker to be tack free prior to coating.
label | 3e0037a5-831c-5ecd-a90e-4989233cf90f |  | note | Records - Time stamped photograph
label | 24f0b347-56ec-5297-a2d0-3aa4015a71a6 |  | note | Records - Thickness with fillet gauge
select | 4aec454b-1acf-5fde-8aa7-676274623f68 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
checkpoint-group |  |  | section | BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - HP!200 Product TDS
label | a92f0824-a589-5106-9d22-a7dd1fd02af2 |  | note | Apply within 5-35°C
label | d70bc5f3-ab3f-5541-bb67-43a0dde264e5 |  | note | RH must be 0-85%
label | 322b4e23-2821-58b6-a3f0-e4643c960bff |  | note | Screenshot - Temperature and weather forecast
select | 11785fb1-ea1d-5208-aeca-350b52903325 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - HP1200 Product TDS
label | ec5f2416-38eb-5b35-abb3-a4efec0457c5 |  | note | Mixing by way of 1:1 mix ratio (by volume) in heated plural component.
label | e7301ae5-2382-537d-b880-c5a68741b02f |  | note | Mix Part B thoroughly with a mechanical power mixer before use
select | 84ed08f2-f654-5e31-942f-04203a2e08e1 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- HP1200 Product TDS
label | 34e6a669-93c1-5704-8ee2-46a06df4fea3 |  | note | HP1200 must be sprayed using high pressue plural component dispensing equipment - Drums of component must be pre-heated to at least 25C prior to mixing or dispensing
label | 400b8b66-0de9-51c9-9b82-49a5307d5785 |  | note | Records - time stamped photograph
select | 4faafbd1-68b8-5151-9993-ca67750eda11 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | 9190c1a3-e77e-5a81-ae82-133cec13736d |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | 57813cf6-9641-5698-a2a0-d8a103b02838 |  | note | Records - time stamped photograph
select | dbbebf5c-2d16-5de5-b4f4-2bb9fa2941f5 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Thickness Testing - Delfasco Positector
label | 5818f0c7-a865-55d2-90a3-63088a37cef8 |  | note | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
label | 9a3d0502-be4c-555d-a704-83c0c7c57d47 |  | note | Records - time stamped photograph
select | 070680fc-3ff4-52cf-9e30-66ff1510e8fe |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | ELT Testing - Delfasco Holiday Tester
label | dac36beb-17cc-55dd-b65e-138bad70f3bb |  | note | Conduct Electronic Leak Testing ( ELT) on area membraned
label | 04376728-1da2-5dae-92a2-392b63e75f41 |  | note | Records - time stamped photograph
select | e857169f-c29e-5eb9-872c-e6eb79433cfb |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | HOLDPOINT - Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | HOLD POINT - Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | DETAILING- EACH LOCATION
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing - AS 4654.2
label | 2a1c2edc-c432-5f1f-96c1-3a71bbaa3d48 |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | e72ee952-c071-51da-b27c-a39d4f7c5ecf |  | note | Records - time stamped photograph
select | b6659b6c-ccc1-54d2-88cd-ba0c18efdea3 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Detailing inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checklist-sectioned |  |  | checklist | Enviro Ultra Tuff V1.0 |  |  |  |  | Yes | Enviro Ultra Tuff V1.0 | ae0a0487-d6a5-4063-94cc-86d9345a56bb
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 0e432987-7a05-5b0e-b046-15244c90a7ba |  | textbox | ITP No.
text | 9db0406a-0288-5653-94af-ad9ce561d2b2 |  | textbox | Revision No. & Date
text | a3a1221c-4d3e-58cd-aaa7-7294a2920410 |  | textbox | Prepared By
text | c6427406-f084-5dc5-9521-a6dbd3ccbe91 |  | textbox | Reviewed By
text | 86d4b25f-3824-5fc3-9d65-c6c9f907e02e |  | textbox | Approved By
text | f4b4f363-0410-5ba7-99e0-317180f7e123 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro B-LV
label | e64cff10-5dc7-5585-959d-b9f9f442308b |  | note | Records - Time stamped photograph
select | bd15fe32-9d35-54ba-a234-8a3d0a083743 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro Ultra Tuff
label | bd283232-2937-54e3-94dc-aab211e49450 |  | note | Records - Time stamped photograph
select | c3cc8bb1-621e-5a42-9672-ac75aaebd972 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 188726b7-99ec-5a3d-a6b9-f8eea2107a30 |  | note | Submit samples for approval as per Specific Material Requirements.
label | 844519bd-0c59-55fb-8266-f66d4fe54a04 |  | note | Records - Subcontractor Contracts Admin Confirmation
label | 8d697f6c-c89e-5e93-8b3a-e18cb5be1f1b |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | 3b1ba64b-b947-5106-bec3-ba4890d0376e |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | 22326173-5120-5cff-961f-bf1c0d15514a |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 0d17c72a-f5be-5225-8ca7-24817729f059 |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | 657a9cd9-d30a-5d6e-9040-cdcb3740d3cb |  | note | Records - Time stamped photograph
select | f01dca8a-9538-5eb2-8116-dfd47197cd9b |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | fb7361f0-baf3-588f-92c3-8f76daddbfc3 |  | note | Obtain clearance for work initiation.
label | 14c976cb-7446-5703-abd5-cb654961c1d5 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | a3b3f574-c5d2-5850-b2d2-5a582a64ee4a |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | 22f35c1a-2dc3-5c44-92dd-0f1efc155ebb |  | note | Records - Time stamped photograph
select | 5ff16eef-799d-525c-916d-7dbc60560352 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | be04fd09-3ca5-5d7f-8b68-32cbf2787451 |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | 2cdd03a5-6645-5325-82bf-88111035eae0 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | 187c8105-dc38-5b86-9827-67f50b4e942e |  | note | Ensure no substrate cracks greater than 1.6mm.
label | face0b12-d38a-588f-9863-1ff20690187e |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 2f3d8fbe-2348-57fc-8f1d-4977f3b1d440 |  | note | Records - Time stamped photograph
select | 018dd6f7-fc78-574c-be3a-de4cfe1e582d |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | f73029b7-d7d9-52d4-b718-2080b7068adc |  | note | Ensure Surface is prepared to receive primer application.
label | 8155cb7b-1023-552b-9586-44c6050501e5 |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | a0554454-1068-5d6d-a41b-8d5d25d1b002 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 65830d99-860e-5c14-9cd9-8e15d42098f4 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | a667fa36-98e7-5a4b-a088-d3552389f205 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | cc42f9e4-53d0-5e48-bf59-6e5bf6cab88b |  | note | Records - Time stamped photograph
select | f2d86980-7b0f-5085-9adb-32c44d3079b7 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
label | bbd26e6e-4046-573a-af7e-c388529e373c |  | note | Ensure Surface is prepared to receive primer application.
label | e13b9b9a-3149-50be-9f3c-e35d33fa173b |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 9a7a99bc-7f65-5aff-ba27-f9b9231657f1 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | d5bddf98-5298-575a-8a0a-b11d1272186a |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 74ea621e-27d1-5499-a320-ab4a0a9bc81d |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | d979540a-ace6-566f-84d6-77230418c2ab |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | c4615d40-b6d2-5b65-9a1d-e040b15ad253 |  | note | Records - Time stamped photograph
select | 2b7ede86-3db5-56eb-b5ad-7c02763ba803 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | 6b92e4bb-e703-5a1d-a47c-358e664418d5 |  | note | Apply within 5-35°C
label | 3bea77be-5cac-541b-a15d-567839fd9950 |  | note | RH must be 0-85%
label | cd522ab2-d977-5bcd-bffd-ad72ebb6e702 |  | note | Screenshot - Temperature and weather forecast
select | ee755af7-7619-5483-87fb-d978f305a0f4 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | b4121da7-1488-5ea9-841a-b1eb133be2b9 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | 228060fa-d409-54ba-90e9-a6c9fd0cbf9d |  | note | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | e2b921f1-905f-5cf1-b3f9-d74b59251d86 |  | note | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | 7d903179-7589-5a42-9726-273e5a434f1f |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | a59821f9-948a-50ff-b02c-7675c665d8be |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | 51b1db2d-f556-52df-a14b-381de2912efc |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | 93443f4b-851d-5213-802e-476a35fcf8b2 |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 5677ff60-2b00-56d0-a2ab-af8fc062abc9 |  | note | Records - Time stamped photograph
select | ec86ed42-33a5-549a-9cf0-34520835833e |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | EPOXY COVING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Coving - Enviro Epoxy B product data sheet
label | aa80f82d-6ed8-5581-9efa-3136dbb429e3 |  | note | Mix Sand plus Epoxy B according to the works' design specifications to create minimum 75mm coving
label | 50912137-da2a-55ea-8e85-796d981ef31f |  | note | Records - Time stamped photograph
select | 2d3ff96b-7eaf-54e0-801d-4160b0c32d65 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Coving inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman inspection sign off
checkpoint-group |  |  | section | FIRST EPOXY COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Ultra Tuff Product TDS
label | 821356cc-878f-5950-b7e4-fcfb04e1acc8 |  | note | Apply within 5-35°C
label | 5323485f-7475-56dc-ba4c-068f86942a51 |  | note | RH must be 0-85%
label | de6cb11f-50e3-52e8-96e2-dfa4b8a4152d |  | note | Screenshot - Temperature and weather forecast
select | fbf4fb86-e352-5d22-8095-0aa5475d3a1b |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Ultra Tuff Product TDS
label | 4cdac9fa-bb63-5d8c-a017-574dd0dfbfd7 |  | note | When using a colour pack add to Part A and mechanically mix until uniform. Add Part B and re-mix until components are uniformly mixed. Colour Packs Rations: 1 pack to make a 8L kit and 2 for the 16L kit.
label | 0cadba3c-f70a-58cf-8e55-6ea1a466567d |  | note | Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for 3mins prior to application.
label | 7698d28c-9814-5ed7-a33a-484ca4fe63db |  | note | Records - Time stamped photograph
select | fa6a4d50-c2e4-51b7-bc46-4c72fa72de94 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- Enviro Ultra Tuff Product TDS
label | 470aa1aa-8af1-516b-af74-422b9055c9f6 |  | note | Enviro Ultra Tuff can be applied by brush or roller to minimum dry film thickness of 250 Microns
label | d9527122-f0be-55b0-9638-afedc6d15285 |  | note | Broadcast selected aggregate and allow to cure for 24 hours prior to second coat
label | b91a6b91-beec-5cf6-8f3b-48eba8a54135 |  | note | Records- wet film thickness reading
label | 7b5d8b21-e5e8-5ac2-9049-942c433c5675 |  | note | Records - time stamped photograph
select | 2ca52918-ce5e-56ff-baf4-807ea6598685 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first epoxy inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first epoxy inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | SECOND EPOXY COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Ultra Tuff Product TDS
label | 99d9566b-ac00-5ec4-be35-37211d68eed0 |  | note | Apply within 5-35°C
label | ea601ac8-ce61-5884-abfd-c032c36f1a8d |  | note | RH must be 0-85%
label | 49fb3e26-8375-5b57-804d-d2e8b52cb1ff |  | note | Screenshot - Temperature and weather forecast
select | ace1fe7c-dde7-57c6-863c-70d12789e780 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Ultra Tuff Product TDS
label | add9c94f-848b-57f8-8b4f-aabd091f118a |  | note | When using a colour pack add to Part A and mechanically mix until uniform. Add Part B and re-mix until components are uniformly mixed. Colour Packs Rations: 1 pack to make a 8L kit and 2 for the 16L kit.
label | 231f6974-1382-523e-bbbf-2a615a4ae780 |  | note | Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for 3mins prior to application.
label | 04185d97-aa5b-5a63-a84b-1e95e0ad50a6 |  | note | Records - Time stamped photograph
select | 46abf0c7-f49c-51a7-bd97-4db6e8cc315b |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- Enviro Ultra Tuff Product TDS
label | d3c16b7a-2f41-5273-abdc-5b8d36da1e81 |  | note | Enviro Ultra Tuff can be applied by brush or roller to minimum dry film thickness of 250 Microns
label | cfae4e12-2dbb-57a0-b7b1-e0f0147c9f25 |  | note | Records- wet film thickness reading
label | 03414d9d-1918-5709-918b-ede4647cdc24 |  | note | Records - time stamped photograph
select | a4c4a3eb-3049-5e47-991e-3dbceaec275d |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor second epoxy inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman second epoxy coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | 197191bd-f1c3-5d54-af32-8d7622df8fdd |  | note | Inspect after installation of reinforcement/finishes to check for any damage to coating and rectify as required.
label | f6565312-0f2a-502a-bf10-32acd7ccb05f |  | note | Records - time stamped photograph
select | d96eb5ca-3638-5bd5-b98f-9796b41ed059 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checklist-sectioned |  |  | checklist | Toolbox Talk V1.0 |  |  |  |  | Yes | Toolbox Talk V1.0 | ce98f959-53a9-4f30-942c-e5e8158ce739
checkpoint-group |  |  | section | TOOLBOX DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 0a7a5ad8-9880-5404-9982-a3685f646102 |  | textbox | Date:
text | 00da87d9-930d-597f-9390-1c1195a982aa |  | textbox | Time:
text | 2ae1483a-915f-59ea-bc1e-a3670e33e545 |  | textbox | Location:
text | 282e5874-1f86-5745-90b8-a531a9edfece |  | textbox | Works Supervisor:
text | 5940e661-e107-5e13-84f2-44a6848a07ee |  | textbox | Client:
text | 753cb08e-a9bc-5aa5-9bf4-3eec5bd35108 |  | textbox | Representative conducting meeting:
checkpoint-group |  |  | section | LAST WEEK INCIDENTS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 3a6d8083-4be4-5d70-93a5-347e0f61058c |  | textbox | Injuries last week
text | 728d23de-a5fd-507b-899f-ca64e6be1efa |  | textbox | Near misses last week
text | efe9a9ea-e171-58ed-b27f-4bf616e75c8e |  | textbox | Hazards last week
text | 61f6626b-4c75-5b04-ab12-a592f3bada71 |  | textbox | Environmental damages and personal injury last week
checkpoint-group |  |  | section | FEEDBACK ON LAST WEEK AND NEW ISSUES
checkpoint-status |  |  | checkpoint | Feedback on issues raised by Work Crews on Previous Day/shift
text | 217b514d-4bff-5426-b345-82539e694af0 |  | textbox | Issues
text | f02ae579-403b-51ef-a836-88461f418c40 |  | textbox | Action
checkpoint-status |  |  | checkpoint | New Issues Raised
text | 2fc77fdf-70f6-5ef6-b45c-87259aeb158e |  | textbox | Issues
text | 18a4bd29-d0a9-5bdb-ad6d-3c0417285517 |  | textbox | Actions
checkpoint-group |  |  | section | ATTENDANCE RECORD
checkpoint-status |  |  | checkpoint | Toolbox talk attendees
text | cb7a17d9-e48c-5477-b242-d77d77c2ecbe |  | textbox | Attendees
holdpoint |  |  | signoff | Attendees sign off
checkpoint-group |  |  | section | DIARY
checkpoint-status |  |  | checkpoint | Diary Report
text | b29ee070-27e0-532e-bbba-f87cad53eb3a |  | textbox | Diary report database
checklist-sectioned |  |  | checklist | Enviro 700X V1.0 |  |  |  |  | Yes | Enviro 700X V1.0 | 14eb502d-3f68-4f61-a6ce-55640a8f055f
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 87e65c91-7b68-5310-af73-b26fbee25f6a |  | textbox | ITP No.
text | 34b9e350-ee60-58dc-b215-b59fdfb02ade |  | textbox | Revision No. & Date
text | e2ce1d94-f00a-5e0e-8819-b5d5427b949e |  | textbox | Prepared By
text | b43cea91-2f2a-5eb1-a61c-6a38d17cc87b |  | textbox | Reviewed By
text | ecbdef1b-a5c2-501a-9fa4-4ed7c6e6b59b |  | textbox | Approved By
text | e1a0f824-2969-5c83-a852-b28da724e188 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex Pro
label | b852c9d7-9487-526d-aecf-67923841253f |  | note | Records - Time stamped photograph
select | 92a04eb9-c17b-5bdf-8022-2deb6de2228f |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro B-LV
label | 4e04ddd2-ca14-5b8f-8ba9-db3533e68f6d |  | note | Records - Time stamped photograph
select | 568eb1be-aef9-51e5-9883-18973b2aad2a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 700X
label | 48a8f90b-1e8a-542c-b510-a46aae08c829 |  | note | Records - Time stamped photograph
select | f3455359-ef68-559d-b27d-98adf7d63832 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | d3c6bdec-f061-5750-b0e8-1d3d94a95ca6 |  | note | Submit samples for approval as per Specific Material Requirements.
label | 5171d4c8-87d7-5f94-a9f9-8bcc766d5133 |  | note | Records - Subcontractor Contracts Admin Confirmation
label | a80a15fb-fc9e-5770-8bbe-63eb3e4f682a |  | note | Sample Approval Ref
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | 5d69d16f-5e6a-52dc-94d2-d709e77d58ca |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | f58c83de-8fee-53bf-9d6c-139c27606883 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 7c6ad560-b277-5fb7-b884-a089f5607446 |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | 7a804f34-ea05-56b2-9a71-fd77740fe9cd |  | note | Records - Time stamped photograph
select | d4485d89-6953-5ca9-a7aa-274a0b24ed05 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | 7cce6fc1-23e3-524a-ad7d-80448c2cdd56 |  | note | Obtain clearance for work initiation.
label | 4c493887-9b9d-5f69-8e33-d512c5b987ad |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | 5f5deb02-a087-5a76-89af-04c154266e35 |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | ec338a3f-68f5-5aff-b082-8f09ba47ed6a |  | note | Records - Time stamped photograph
select | d4a10c0c-8892-59a7-82e4-d4815a932a94 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
label | 79e20cd7-5a28-51a0-9770-eb7a9b7f02c1 |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | 9ae84ce0-a1bd-50dc-847d-88143b1fdb6b |  | note | Records - Time stamped photograph
select | 96cc545f-e2ab-5f98-bd6b-a4e6e6d34e5e |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | 21af6f3b-2bd4-52ef-b255-b0287eddd939 |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | 18e10f81-adf7-55b7-9ffb-a8f07594cf7f |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | e146befd-01f4-5925-b8ba-7903a094af85 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | 5c4f1565-8d02-5e3d-bd81-7433f18b2ed0 |  | note | Records - Time stamped photograph
select | 4bbbae17-bdb9-5a53-93ff-7472e37fb506 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | c96ebdce-02fb-57a6-936c-ec91012ccfa6 |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | dc7ad5a2-a3e0-5726-9343-d092c1044d45 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | e3ae8f7b-68e1-58b4-a6fa-f0c34ad2a092 |  | note | Ensure no substrate cracks greater than 1.6mm.
label | 47f440d9-d7c9-563d-bc6b-fd9b97cf6a73 |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | d36f7f88-98e3-58a3-84bf-e55400817330 |  | note | Records - Time stamped photograph
select | 1dbbc85f-79fa-58e5-9565-24f3c923fd34 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | 5102c300-d540-524e-bd61-aebacbfee632 |  | note | Ensure Surface is prepared to receive primer application.
label | 93c40def-de53-5b8c-9e41-a4125a1866bf |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | b4d47da4-c744-54ec-804f-8a28b92f6c7a |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | bb031dd4-c371-588a-af4d-166530646ed8 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 7f1523a8-6b85-565e-a4f9-c154f0278539 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | 9136c5de-abfa-5a95-9c93-b1b4ba87875c |  | note | Records - Time stamped photograph
select | c3bbaf25-a36b-598f-b8f1-8b63b2dd497a |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
label | 54ad968b-bce5-5d45-84c6-398fd8a1a6d6 |  | note | Ensure Surface is prepared to receive primer application.
label | 599a0280-fc44-5e64-8e83-d41ec2efa70f |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | a596ecca-6cef-5627-b62d-7b553ad5c5b9 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | a7300891-d03f-5cf2-a8f3-9d9ee6647ec2 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 2153e184-5202-5fe2-ad06-ec246527f124 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | 02b17268-37a0-5920-aada-e9460f3e21de |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | b0696ea1-5627-5ab1-a312-32e3823195b0 |  | note | Records - Time stamped photograph
select | 06ca84e6-5f55-5050-9bdf-e9b2c2fd8d60 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | 9c329917-4192-5080-8258-90f87fc94b73 |  | note | Apply within 5-35°C
label | c5589271-3ac2-58d2-9bf4-21c7c435a2bd |  | note | RH must be 0-85%
label | 17743667-da6b-5517-8368-41b3700f20d0 |  | note | Screenshot - Temperature and weather forecast
select | 3aeba620-dec3-51d6-ba49-d421679710eb |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | 0d8d7b4b-bac8-5bd5-82b6-f66334bedb54 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | b62f959a-cfbb-5d44-af3f-313d5eabc0bd |  | note | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | b7ef0bfd-ecef-5a10-b581-f248a308e11d |  | note | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | f8399b05-a981-5a11-977a-478085550f96 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | 076fa037-58c9-503b-a6a9-cf7f9dde4a7e |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | 422a6828-7211-57e8-93db-a4511b48afb4 |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | 571d3483-b400-553e-b611-24cad8d1f1e4 |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 722e7bd3-eeaa-5503-838a-9d402d110502 |  | note | Records - Time stamped photograph
select | 556ef9d9-1792-5586-9ae4-1129a54416ef |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER- EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | 52fe28ed-202e-520b-aad7-b296e64e7504 |  | note | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | b4181ade-57cd-543c-8ea0-190e3fdc2173 |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | cafdc463-59bf-5caa-8da9-f3454a28a414 |  | note | Bond breaker to be tack free prior to coating.
label | c6f58f24-0123-5395-ab94-02c225524ba2 |  | note | Records - Time stamped photograph
label | ebde83f2-510d-56b5-84d2-bcc35714aa11 |  | note | Records - Thickness with fillet gauge
select | 1e0a49ce-e9f8-5dd5-b39d-982adb762968 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman inspection sign off
checkpoint-group |  |  | section | FIRST BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 700X Product TDS
label | a425ea8a-e459-518e-9ddd-1cda5263d42c |  | note | Apply within 5-35°C
label | b0e748f5-1629-550d-ad0a-f4d696b50d78 |  | note | RH must be 0-85%
label | ca815c69-225c-5512-8707-09b651012206 |  | note | Screenshot - Temperature and weather forecast
select | 52ebba3a-af27-5851-b05d-6ac9bf6fbf00 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - 700X Product TDS
label | 187fbbdc-337a-5805-8196-c39fbc229db4 |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | 25e7e202-50fa-522c-81d3-6caf97ee899d |  | note | Records - Time stamped photograph
select | c6cc35cf-594f-529a-8f0b-b50bafa52979 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- 700X Product TDS
label | eea4052d-b7b5-5f98-8fa4-9b6cdc2cd2cd |  | note | • 700X to be applied by roller vertically on substrate and terminating min 150mm with brush.
label | fa94b9ae-a6d5-53a1-ba79-7973769df2d2 |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | a2a0a41d-c52c-5937-b3d6-67c29e81062e |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | 1597cbfd-3b5d-596a-8d8f-f3de66dc65a2 |  | note | Records - time stamped photograph
select | eb3ab580-3a00-52fd-a1bb-4b86a30ce6ea |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | ENVIRO 700X - SECOND COAT
checkpoint-status |  |  | checkpoint | Weather/RH - 700X Product TDS
label | 45e0fcfb-1e5e-50a8-aa58-4b1f7618db3f |  | note | Apply within 5-35°C
label | da63e75e-a552-5278-9194-b4d6b883156f |  | note | RH must be 0-85%
label | 49065873-126e-5dc1-9158-3d0d77247b72 |  | note | Screenshot - Temperature and weather forecast
select | 76bca100-0613-5cd5-837a-0dd7ef23411c |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - 700X Product TDS
label | 77ab2295-45b6-58b1-8cb0-1bb6df7aaa3a |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | 040a1850-061f-5a3f-b995-f9ea5e627b33 |  | note | Records - Time stamped photograph
select | c8819489-e187-590a-b6ec-29cb984dad54 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- 700X Product TDS
label | dacc2263-eae4-5db3-9125-5d1cb63282f0 |  | note | • 700X to be applied by roller Horizontally on substrate and terminating min 150mm with brush.
label | 618eb451-7925-5fc7-80a7-36c0674d718e |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | c96d8958-7847-5d71-8635-d2479405db6c |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | 177a6365-7667-5960-8473-0224c670fd6f |  | note | Records - time stamped photograph
select | 8adaf006-2f99-5581-87f2-dddd10f67060 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor Second base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Second base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | ff3cc332-b87e-5299-a6b9-77d28d9e0eac |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | a00e0f51-11a1-5483-aa76-81affdde62c1 |  | note | Records - time stamped photograph
select | 42aca190-5a7c-56dd-a057-a30fb5c8d426 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Thickness Testing - Delfasco Positector
label | c7a3f27f-5e63-590a-990a-b2aa5a78a841 |  | note | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
label | 83f7ddbf-5f36-53dc-a1a4-42632a2e3a38 |  | note | Records - time stamped photograph
select | f1d0c4cb-3262-5f0b-89e0-07e47c4ec6c4 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | ELT Testing - Delfasco Holiday Tester
label | 2cf31767-04d9-52ed-b72e-e6d460845a48 |  | note | Conduct Electronic Leak Testing ( ELT) on area membraned
label | ed1c133f-502c-57f3-ad23-ea83aec6f13e |  | note | Records - time stamped photograph
select | 834f6bfe-2e0d-5cd5-a471-acad53bc0191 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | DETAILING- EACH LOCATION
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing - AS 4654.2
label | 15043794-2d96-580a-bb34-39667afceaa3 |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | cd03f1e1-61b3-5c46-9551-7db8d9501c27 |  | note | Records - time stamped photograph
select | f3d52266-e334-5b0b-8e47-b2aedf97c7e1 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Detailing inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checklist-sectioned |  |  | checklist | Enviro 700X + 250NS 1.0 |  |  |  |  | Yes | Enviro 700X + 250NS 1.0 | de4bd4da-f648-4309-a289-65b9de4104dd
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | e3007d7f-101f-545c-9277-366c5d14b44a |  | textbox | ITP No.
text | 060595e3-f92d-518c-8ceb-994ea7f24d38 |  | textbox | Revision No. & Date
text | a47c53c1-28fc-559c-ba94-c157ff73a35f |  | textbox | Prepared By
text | 5f059ab4-9a09-5541-b103-3aec04ea7677 |  | textbox | Reviewed By
text | 60866230-8659-59d7-b2f5-72d0daf81a95 |  | textbox | Approved By
text | e6902c0c-6694-5bcb-bf39-85320fc371a0 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex Pro
label | e293524a-089b-5cb6-817f-089ee05f1320 |  | note | Records - Time stamped photograph
select | 70bbcaa5-5620-5a70-b58c-6aa083b6b18a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro B-LV
label | eee8bf13-701c-55f7-bf37-1c2cb3d1ccba |  | note | Records - Time stamped photograph
select | 6b798daa-2b41-5e4b-a446-95ad76b32e9f |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 700X
label | 0d99b989-2829-53c9-8e4f-42f51c9e5064 |  | note | Records - Time stamped photograph
select | a34fab65-fb38-50d0-a261-752765736af7 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 250NS
label | ba6a458a-d50a-542e-8f67-2f38bf60859b |  | note | Records - Time stamped photograph
select | 95870546-913e-5b5d-aa6e-9247d684c4a9 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 3ddabded-427b-5c94-b938-7a6fd80872f4 |  | note | Submit samples for approval as per Specific Material Requirements.
label | 55cf6181-1300-513a-94ed-3fe311c1c756 |  | note | Records - Subcontractor Contracts Admin Confirmation
label | 286a86db-bebe-529b-84e1-d52d87e85b99 |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | 5c652d13-80f2-52ec-9527-db0b1e6b666d |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | 8cc6ae76-8412-5c80-b62c-0c78669ce45f |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 229b1f2a-7e9f-50c4-98bc-32defdfebb04 |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | 843fb8ed-e209-5542-9d5c-214eea9726a0 |  | note | Records - Time stamped photograph
select | b3d561dc-479c-53fa-a7e5-8798f2c63393 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | 8ef9e2de-5f75-554e-a4e2-fd54cbcab08e |  | note | Obtain clearance for work initiation.
label | eb5bfb73-ce69-5a02-904d-62c89ac6aa5f |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | 5e9d9ab2-2e96-598e-af55-f9bb10a516ac |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | 78b963da-415d-5fdd-b313-9ec312a5d570 |  | note | Records - Time stamped photograph
select | dbdbd997-0f52-5c28-8aa6-b5f8b76544d7 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
label | 7c9760f3-ab0a-572d-bf07-d9d3606c1a8f |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | 60bd819c-2396-5a92-bde4-bb05c8632c9f |  | note | Records - Time stamped photograph
select | 68e814e0-3b56-54c2-a26b-ff7a6872212f |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | b8eb1206-3533-5fd9-823d-d387dbf5ab01 |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | 078b7911-7727-5865-bb5e-d22d9c77621a |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | 2a75098e-e595-5f2c-8753-d9343f9b98e3 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | cb7152c8-df6d-59df-a30e-8ff0b0117266 |  | note | Records - Time stamped photograph
select | 41352753-d749-598a-995f-a9e5960376bf |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | 58e323be-f347-57e1-b720-97c1bb0b9dd6 |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | b8571748-1e48-5ea0-a3fc-134a15035869 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | a0909787-4878-50a9-86f5-82a28c0a13ad |  | note | Ensure no substrate cracks greater than 1.6mm.
label | 86f60568-c137-57fa-a802-42c000b2461b |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | a7e95e82-af76-563e-9445-6f82932bd5d4 |  | note | Records - Time stamped photograph
select | d75559fd-e073-51a5-a96e-96c6b7103aaf |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | f5cfa46d-cc2d-580c-8375-fae63eaeb587 |  | note | Ensure Surface is prepared to receive primer application.
label | 35d684e8-d9fb-5cb1-99a0-e50ff3927166 |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 2ab97271-3960-5472-a55f-83c2d312af84 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 6959092b-cc90-5749-a2e8-d9792e5f9c75 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 2cc7ed35-a83b-5396-956a-1d8420d05a9c |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | 5e9a5f4e-d205-5517-b6fd-f5404e24b55f |  | note | Records - Time stamped photograph
select | d7b6f59f-55fc-5ea7-92aa-8cda671913ba |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
label | db170fc3-351e-5d51-9099-2739e096cafe |  | note | Ensure Surface is prepared to receive primer application.
label | 2bac230f-2f02-52be-8162-f3c63852ca82 |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | a1b6f6cf-2b27-5eb4-ac9a-ba5436293567 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | fb7042c0-3374-57a0-a918-61066a97be08 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | af5f7399-e2f4-53e0-a360-b7d81301b66a |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | 954119a9-9aa3-5f5d-8d85-a02b19715eba |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | 00413e37-39d4-59c8-a40a-4cdb1da384f9 |  | note | Records - Time stamped photograph
select | 6baceca7-2336-5407-93f3-ee6c7f0b83f4 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | 85c55890-e792-5de0-bd69-847ab0ca0cfa |  | note | Apply within 5-35°C
label | 5c276fed-ed32-574a-a847-bcd07ecf3d15 |  | note | RH must be 0-85%
label | 8b9a88a2-077a-5dd6-9d6f-afcaddc0f355 |  | note | Screenshot - Temperature and weather forecast
select | 01f7ea4a-5bcb-522d-a5c1-e080b6ae0947 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | 59d245d9-f9d3-5683-b764-02f5083aaed7 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | c46fe92f-9ca8-5685-94ec-46186e80d929 |  | note | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | ab7949d5-ee6a-5366-a069-dd9cfa65267e |  | note | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | ea7b9c52-36cb-5b5f-b75f-bb48e8373aef |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | ea883414-c549-55ba-96e3-415d1fe66a83 |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | 143aaf61-9d1e-5ce6-8daf-0fad40b6ae89 |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | 6e2636df-16a7-5d53-8b1c-a40f8be20af7 |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 0bc94d28-6178-5f61-ab53-2a4f4577d054 |  | note | Records - Time stamped photograph
select | 8f244b20-e137-5fa3-88e4-f2e4b597bd63 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER- EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | d7239a6f-144a-5d06-afb2-14669b3972e3 |  | note | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | 2bfa7dd9-8750-59d9-b784-eab92bc70453 |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | 5b2806d7-2986-5fed-b2dd-fc1d3cdcf422 |  | note | Bond breaker to be tack free prior to coating.
label | 6f291ebe-87d2-5861-9d50-a57d7e0d6fd2 |  | note | Records - Time stamped photograph
label | 0ed24b45-eb3b-5cff-b7b6-734de74ff02d |  | note | Records - Thickness with fillet gauge
select | 933219fc-e461-5d26-80e0-75ae75447ed0 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman inspection sign off
checkpoint-group |  |  | section | FIRST BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 700X Product TDS
label | 4fce58a4-85bb-55ab-9168-deb449994032 |  | note | Apply within 5-35°C
label | 2094bc88-7675-5cd7-ac12-368d278fbebd |  | note | RH must be 0-85%
label | 3a10c03b-0e26-50de-a8af-eddbd912cb61 |  | note | Screenshot - Temperature and weather forecast
select | 9551c6c7-c1a3-5373-b753-56c8b145a179 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - 700X Product TDS
label | 5e5d1c6b-9c4c-52a0-8152-b14a3e1f5d8e |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | a36a2a76-614d-5705-9550-2ee482c4092c |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- 700X Product TDS
label | ae598013-766c-5de3-bbe3-bf661019f486 |  | note | • 700X to be applied by roller vertically on substrate and terminating min 150mm with brush.
label | d398fe3b-3210-5e38-8b0c-f317dab5a3d7 |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | d267e1a8-33e1-59ad-930a-f088cce4fb2a |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | 3d3bc4dc-0c43-5a35-9bbd-d9c8afe08076 |  | note | Records - time stamped photograph
select | 6d5f98a6-5419-5288-8ecc-d94e0ea3cf13 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | ENVIRO 700X - SECOND COAT
checkpoint-status |  |  | checkpoint | Weather/RH - 700X Product TDS
label | 0ff77458-408c-5d8e-8b8d-44f96162ec47 |  | note | Apply within 5-35°C
label | a9b6a5ab-a129-5b69-b2b3-fc93f218d66a |  | note | RH must be 0-85%
label | 28fbaa2a-f0ce-56a9-9782-a34948912587 |  | note | Screenshot - Temperature and weather forecast
select | 1c220c83-9554-5a7b-8535-4cc62d159400 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - 700X Product TDS
label | 1a58fd5f-f488-5165-ba27-14f762140383 |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | 1b5663f4-1074-56ca-ac00-772bb6867dff |  | note | Records - Time stamped photograph
select | 8815edaf-45ec-5ee9-96a4-fb654fca26b5 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- 700X Product TDS
label | 2f7f13f2-d568-5786-9054-effcc27be7e3 |  | note | • 700X to be applied by roller Horizontally on substrate and terminating min 150mm with brush.
label | 545cf603-8532-55ab-abea-a7f00fe69976 |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | ff27f98e-f374-59f5-b1b4-3eab124991a9 |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | d62036bb-bff5-5fea-8cfa-64a32885d947 |  | note | Records - time stamped photograph
select | 307712fb-4669-5e8b-b26c-c1543fa93e5b |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor Second base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Second base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | 664a8917-342d-5501-ae83-c57187f4f003 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | f21eaf99-4adf-5880-aeba-be5b4ac7ee68 |  | note | Records - time stamped photograph
select | ab4b0373-a005-528b-87bd-afca87bf23b9 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Thickness Testing - Delfasco Positector
label | c07944d1-c073-52b0-ae44-45975dec2d94 |  | note | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
label | 1a62b0c5-d482-5f51-828c-630497d1bb4c |  | note | Records - time stamped photograph
select | cffd0697-d0f4-5050-9bc2-220cc488e034 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | ELT Testing - Delfasco Holiday Tester
label | f8489c09-1293-5d5a-8d3a-8da42b3eac82 |  | note | Conduct Electronic Leak Testing (ELT) on area membraned
label | cab29b5e-e7ca-5688-80ff-b67c87bbb122 |  | note | Records - time stamped photograph
select | eec87432-bf68-5f7a-a4a0-ee7658981c5c |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | DETAILING- EACH LOCATION
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing - AS 4654.2
label | a03d6d1e-cedf-5986-9563-bf69968ab52d |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | c327a573-fe73-5f60-b47d-604e8e267ce3 |  | note | Records - time stamped photograph
select | 4bd15d9b-106e-5a5b-b070-850b5bb4f168 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Detailing inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | FIRST TOP COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 250NS PRODUCT TDS
label | 22a0444f-aa62-5578-969a-fabc66ecc614 |  | note | Apply within 5-35°C
label | 90361f81-7e08-50fb-9428-11e5332267a3 |  | note | RH must be 35-85%
label | 92ad9857-6bc4-555c-935c-0340b05a751e |  | note | Screenshot - Temperature and weather forecast
select | f3f989b4-e2c7-5570-a82f-c5c39215dfd7 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing- 250NS PRODUCT TDS
label | c4269b44-5730-5fbb-abe6-d5e7258cc015 |  | note | • Enviro 250NS should be thoroughly mixed with a mechanical mixer at low speed (less that 400 RPM) prior to application.
select | 15b3db66-61b5-56cb-a6e6-af2ab581f955 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | APPLICATION - 250NS PRODUCT TDS
label | cb220963-5c6a-5eba-be5f-3daebbeb39ff |  | note | • 250NS to be applied using roller and brush.
label | 6f357246-b4b2-5aeb-93fd-2aae623698ca |  | note | • Ensure Product is cured for 24 hours prior to second coat.
label | 5a5857e1-d69c-562e-9b28-07d824c48b55 |  | note | Records - time stamped photograph
select | 5c5175d0-48e6-592a-995e-e12f3e8d1d08 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first top coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first top coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | SECOND TOP COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 250NS PRODUCT TDS
label | 64653848-a28f-5f7c-a7e2-2515e551f102 |  | note | Apply within 5-35°C
label | 9603e68c-9d4e-5b5b-9b3e-9fdfe8137d90 |  | note | RH must be 35-85%
label | 599aeeda-90ad-5043-af4f-bfb2faac0179 |  | note | Screenshot - Temperature and weather forecast
select | 90745838-7e1b-542f-a156-eb54bbc4745f |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing- 250NS PRODUCT TDS
label | 57d0ce18-9c74-5ddf-a065-e462424d0b2e |  | note | • Enviro 250NS should be thoroughly mixed with a mechanical mixer at low speed (less that 400 RPM) prior to application.
select | 083c06f0-8a36-533e-9c38-e031af2b0ceb |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | APPLICATION - 250NS PRODUCT TDS
label | 63daab2b-d288-578d-9f05-66ccef517e31 |  | note | • 250NS to be applied using roller and brush.
label | 48e3904c-5716-5c0e-b993-8b878beb355e |  | note | • Ensure Product is cured for 24 hours prior to second coat.
label | 24c3f504-5445-5523-9ea4-6806f6514a20 |  | note | Records - time stamped photograph
select | 7d2e196b-2fbc-5053-bd36-3236f8b17ad0 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor second coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman second top coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off