## Folder Structure
10 Kaimata Cladding
Elevation | Level | Gridline | Checklist
North
| 2 | A-D | Cladding Checklist
| 3 | B-D | Cladding Checklist
| 4 | B-D | Cladding Checklist
South
| 1 | W-Z | Cladding Checklist
| 2 | W-Z | Cladding Checklist
| 3 | W-Z | Cladding Checklist
| 4 | W-Z | Cladding Checklist
| 1 to 4 | X-Y | Baguette Checklist
East
| 1 | 1-4 | Cladding Checklist
|  | 4-5 | Cladding Checklist
|  | 5-9 | Cladding Checklist
| 2 | 1-4 | Cladding Checklist
|  | 4-5 | Cladding Checklist
|  | 5-9 | Cladding Checklist
| 3 | 1-4 | Cladding Checklist
|  | 4-5 | Cladding Checklist
|  | 5-9 | Cladding Checklist
| 4 | 1-4 | Cladding Checklist
|  | 4-5 | Cladding Checklist
|  | 5-9 | Cladding Checklist
| 1-4 | 4-5 | Baguette Checklist
| 1 | 3-4 | Baguette Checklist
West
| 1 | 1-4 | Cladding Checklist
|  | 4-5 | Cladding Checklist
|  | 5-9 | Cladding Checklist
| 2 | 1-4 | Cladding Checklist
|  | 4-5 | Cladding Checklist
|  | 5-9 | Cladding Checklist
| 3 | 1-4 | Cladding Checklist
|  | 4-5 | Cladding Checklist
|  | 5-9 | Cladding Checklist
| 4 | 1-4 | Cladding Checklist
|  | 4-5 | Cladding Checklist
|  | 5-9 | Cladding Checklist

## Cladding Checklists
Checklist
Section | Substrate Inspection
All prior works done
Substrate has no damages and sound
Waterproofing has no damages
All wall penetrations done and waterproofing around penetrations done
Wall Square and Plumb, not exceeding 7mm tolerance
Nogs and Studs in correct positions
Hold Point | Substrate Sign Off
Section | Setting Out
RL provided by main contractor
Control of horizontal and vertical lines
Control of Plumb Line
Setting out follows shop drawings
Section | Sub-structure Installation
Subsection | Fixing rail to concrete with M6 Stainless Steel Concrete Screw
Min Embedment 55mm
Min Edge Distance 35mm
Max Spacing 1200mm
Subsection | Fixing rail to timber with 8G Tek Screw
Min Embedment 50mm
Min Edge Distance 21mm
Max Spacing 1200mm
Vaporshims applied for every fixing to substrate
Interstorey Flashings installed
Interstorey Flashings Corners Installed
Cavity Closure Installed
Hold Point | Sub Structure Sign Off
Section | Tempio Tiles Installation
Setting out according to shop drawing
No chipping / damage / crack
External Corners Check
Internal Corners Check
Tile Penetration Checks
Ventilation Cowl Installed
2mm vertical tile joint
Windows Head having end dam both sides before tile install
Tiles installed are fix properly and not moving or rattling
Section | Final Clean
Clean all debris and stain
Clean all visible marks
Section | Sign Off
Sign Off and Handover

## Baguette Checklists
Checklist
Section | Substrate Inspection
All prior works done
Substrate has no damages and sound
Waterproofing has no damages
All wall penetrations done and waterproofing around penetrations done
Wall Square and Plumb, not exceeding 7mm tolerance
Nogs and Studs in correct positions
Hold Point | Substrate Sign Off
Section | Setting Out
RL provided by main contractor
Control of horizontal and vertical lines
Control of Plumb Line
Setting out follows shop drawings
Section | Sub-structure Installation
Subsection | Fixing Bracket to concrete with M8 Stainless Steel Concrete Screw
Min Embedment 55mm
Min Edge Distance 10mm
Max Spacing 600mm
Subsection | Fixing bracket to timber with 8G Tek Screw
Min Embedment 50mm
Min Edge Distance 21mm
Max Spacing 600mm
Vaporshims applied for every fixing to substrate
Hold Point | Sub Structure Sign Off
Section | Tempio Baguette Installation
Setting out according to shop drawing
No chipping / damage / crack
Rubber Washer Insert between 2 Baguette
Square Tube Reinforcement insert into Baguette
Flat plate installed to top and bottom of Baguette using M6 Counter Sunk Bolt
Install Baguette onto Bracket using M6 Bolts and Nuts
Baguette Spacing Check
Tiles installed are fix properly and not moving or rattling
Section | Final Clean
Clean all debris and stain
Clean all visible marks
Section | Sign Off
Sign Off and Handover