## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | SVR: |  |  |  |  | Yes | Engineer Site Visit Report | 02963c06-15b7-4667-a33c-9941bd9ea40e
checkpoint-group |  |  | section | Site Visit Report
checkpoint-status |  |  | checkpoint | SVR Attached
text | 2bf6224d-212d-4c05-8d20-702627eeda57 |  | textbox | SVR No.
folder-normal |  | Not allowed as a child of checklist-sectioned. | folder-normal | Follow-Up Action(s)
checkpoint-group |  |  | section | Close-Out
checkpoint-status |  |  | checkpoint | SVR Closed-Out
checklist-flat |  |  | checklist | Internal Gutter |  |  |  |  | Yes | Internal Gutter | 096cf461-335f-42e0-98b6-428bf7ee67c3
checkpoint-status |  |  | checkpoint | Timber framing installed as per drawing
checkpoint-status |  |  | checkpoint | Outlet opening done as per drawing
checkpoint-status |  |  | checkpoint | ILD mesh installed
checkpoint-status |  |  | checkpoint | Torch on membrane installed (bottom and side)
checkpoint-status |  |  | checkpoint | ILD test result collected
checkpoint-status |  |  | checkpoint | PIR 50mm glue down + outlet installed
checkpoint-status |  |  | checkpoint | ILD mesh installed
checkpoint-status |  |  | checkpoint | Sarnafil welded correctly
checkpoint-status |  |  | checkpoint | ILD test result collected
checkpoint-status |  |  | checkpoint | Hand over to roof work
checklist-sectioned |  |  | checklist | Ceiling Preline incl High Level Services |  |  |  |  | Yes | Ceiling Preline incl High Level Services | 1397430a-c250-4975-b408-6d3672401e83
checkpoint-group |  |  | section | QA - Plumbing First Fix
checkpoint-status |  |  | checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Consultants Inspection sign off
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council inspection and testing complete and signed off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Witness testing of pipework by Hawkins
checkpoint-group |  |  | section | Fire Protection (Sprinklers & Alarms) First Fix
checkpoint-status |  |  | checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Consultant inspection sign off
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Witness testing of pipework by Hawkins
checkpoint-group |  |  | section | Mechanical Services First Fix
checkpoint-status |  |  | checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Consultant sign off
checkpoint-status |  |  | checkpoint | All ends covered/protected to reduce debris
checkpoint-status |  |  | checkpoint | Witness testing of compliance check by Hawkins
checkpoint-group |  |  | section | Electrical First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Consultant sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Witness testing of compliance check by Hawkins
checkpoint-group |  |  | section | Data First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Consultant sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Witness testing of compliance check by Hawkins
checkpoint-group |  |  | section | Security First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Consultant sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Witness testing of compliance check by Hawkins
checkpoint-group |  |  | section | Rondo Ceiling Grid Installation
checkpoint-status |  |  | checkpoint | Service penetrations mark out completed, checked and acceptable (clashes considered)
checkpoint-status |  |  | checkpoint | Ceiling Grid ( pass when all below ticked)
boolean | 68e7cef0-de8a-5c29-8460-fc52fad1daa9 |  | tickbox | Ceiling height correct
boolean | 74b9a255-4e27-5a78-8ecd-f370ccb73e3a |  | tickbox | Appropriate fixings used and installed as per required specification
boolean | 98f383af-0990-5f7b-8a95-6e5e275ead5c |  | tickbox | Appropriate spacings for respective grid elements
boolean | 70642190-88ae-5cef-aa35-b8f91b909586 |  | tickbox | Perimeter channel/angle installed correctly
boolean | ba858e08-ae3b-51aa-9d03-c4d16db0180e |  | tickbox | All strong backs installed where required to meet specification
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Insulation Prior to Lining
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Insulation pre lining works completed, checked & approved
boolean | 0e8a6528-73d9-5e03-87e2-32322c4873f4 |  | tickbox | Correct product & R value as per specification
boolean | 34066410-3f3f-5290-b2ec-9cf9ed662c9d |  | tickbox | Fitting Snug
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Council Sign Off
checkpoint-status |  |  | checkpoint | Council preline inspection passed
checklist-flat |  |  | checklist | Base Isolator |  |  |  |  | Yes | Base Isolator | 161037e5-9cdf-4639-a81f-373b64ced9cf
checkpoint-status |  |  | checkpoint | Base Isolator
text | 567df56e-5eb8-598a-9772-d8f4ecf553a7 |  | textbox | Zone / Level / Grid(s) recorded
checkpoint-status |  |  | checkpoint | RL base isolator checked
button | c940c22f-ea8a-5aca-b7db-1ea3416a4105 |  | button | Isolator type | LRB,NRB,PS-A,PS-B,PS-C
checklist-sectioned |  |  | checklist | ISN Report: |  |  |  |  | Yes | ISN Report | 368f0a2d-e9ae-46ac-b6a5-d673601baf08
checkpoint-group |  |  | section | Site Visit Report
checkpoint-status |  |  | checkpoint | SVR Attached
text | 2bf6224d-212d-4c05-8d20-702627eeda57 |  | textbox | SVR No.
folder-normal |  | Not allowed as a child of checklist-sectioned. | folder-normal | Follow-Up Action(s)
checkpoint-group |  |  | section | Close-Out
checkpoint-status |  |  | checkpoint | SVR Closed-Out
checklist-flat |  |  | checklist | Site Concrete Checklist |  |  |  |  | Yes | Site Concrete Checklist | 3e65946a-d9f9-4b20-bb2b-6e917280ca60
checkpoint-status |  |  | checkpoint | Excavation depth and location checked and correct
checkpoint-status |  |  | checkpoint | Ground conditions acceptable
checkpoint-status |  |  | checkpoint | Concrete specifications checked, correct and delivery docket photographed
checkpoint-status |  |  | checkpoint | Site concrete placed
text | 4d63a2e5-37bf-5496-b4fa-b5b68f82dc43 |  | textbox | Placed by:
checkpoint-status |  |  | checkpoint | Concrete placed to the correct height
checkpoint-status |  |  | checkpoint | Site concrete pour completed and finish acceptable
checklist-sectioned |  |  | checklist | Eye Brow |  |  |  |  | Yes | Eye Brow | 473405f6-f59b-4e34-be1c-900673d31778
checkpoint-group |  |  | section | QC Summary
checkpoint-no-status |  |  | checkpoint | QC Summary
text | 98f0f1e2-bc57-5e47-b447-9ee2d851bac0 |  | textbox | Subcontractor/Supplier
text | 803ae822-c5ee-5c27-8dd9-a550be84f9e1 |  | textbox | Works area
text | 356c968d-c8dc-5126-9a63-a9acdd0a62ad |  | textbox | Drawings reference
text | 441ee782-5edd-5718-a829-1901f613fc02 |  | textbox | Project specification reference
checkpoint-group |  |  | section | Precladding
checkpoint-status |  |  | checkpoint | RAB and timber is dry prior to apply revalshield
label | 6e9ab6ea-ba9c-5f32-8535-749c5c8b0ca4 |  | note | Photos
checkpoint-status |  |  | checkpoint | Revealshield is applied correctly (80mm overlap) and as per drawing
label | 8f10462a-72ea-5c9f-9a9c-c4b270645021 |  | note | Photos
checkpoint-status |  |  | checkpoint | Liquidflash is apply around the window opening andany other location required
label | 6363da32-354a-5aeb-b146-2d214d140777 |  | note | Photos
checkpoint-status |  |  | checkpoint | Sealant and flashing tape is applied ( brackets fixed on RAB/ over the top of pressure bar...)
label | 7ad2ebc6-75ab-5fbb-8f55-5abb016ddc53 |  | note | Photos
checkpoint-group |  |  | section | Eyes brow Cladding
checkpoint-status |  |  | checkpoint | Cleats surveyed and checked
label | 0979ea91-4454-5246-b1ef-203c5abdb1ce |  | note | Photos
checkpoint-status |  |  | checkpoint | Aluminium frame as per shopdrawings
label | 605a589a-675c-5dc8-a720-c5db2168a5ba |  | note | Photos
checkpoint-status |  |  | checkpoint | Aluminium frame plumb and levelled
label | a6bd3307-259b-5ab6-8705-f1057133df86 |  | note | Photos
checkpoint-status |  |  | checkpoint | Induraplate flashing as per drawings
label | 6eef6120-6300-51ca-9122-6889f2acf976 |  | note | Photos
checkpoint-group |  |  | section | Final approvals and holdpoints
checkpoint-status |  |  | checkpoint | Hold point - Sub contractor QA
label | 4078bd1a-9dab-5eb2-981a-0ee4e24370dd |  | note | QA REPORT
holdpoint |  |  | signoff | Company QA Check
checkpoint-status |  |  | checkpoint | Engineer Inspections
label | 95a329b3-bcc0-5f8f-8123-5448f02f0fdd |  | note | SITE REPORTS
checkpoint-status |  |  | checkpoint | Council Inspections
label | 257595df-030d-5a4d-9eeb-b9d9e2452c33 |  | note | INSPECTION REPORT
checklist-flat |  |  | checklist | Civil - Sanitary Sewer |  |  |  |  | Yes | Civil - Sanitary Sewer | 4db08abb-c08b-4125-baed-699b2c45e719
checkpoint-status |  |  | checkpoint | Location details and relevant mark ups attached
checkpoint-status |  |  | checkpoint | Consultant inspection completed as required
checkpoint-status |  |  | checkpoint | Council Inspection completed as required
checkpoint-status |  |  | checkpoint | Invert levels recorded
checkpoint-status |  |  | checkpoint | Invert levels as per design
checkpoint-status |  |  | checkpoint | Received QA from Subcontractor?
checkpoint-status |  |  | checkpoint | As Built drawings received
checkpoint-status |  |  | checkpoint | CCTV Survey
checkpoint-status |  |  | checkpoint | Certificates provided
checkpoint-status |  |  | checkpoint | Installation record photos
checkpoint-status |  |  | checkpoint | Foul Installation completed
checkpoint-status |  |  | checkpoint | Any onsite changes documented (Attach marked up drawings, etc)
checklist-flat |  |  | checklist | Description/Number: |  |  |  |  | Yes | ISN Follow Up Action | 4ecac9a3-994c-4f28-b83b-5ae35da7bced
checkpoint-status |  |  | checkpoint | Follow-Up Action completed
text | ddf14301-8239-5b3b-951b-d5fa379a59cd |  | textbox | Specific Location:
text | 91c806c7-c985-559e-94d6-00a2b29bd0fd |  | textbox | Detail:
text | f17daeb2-6b36-59f2-add1-159d86b7a239 |  | textbox | Action Required:
holdpoint |  |  | signoff | Request Review
checklist-flat |  |  | checklist | Ceiling Postline |  |  |  |  | Yes | Ceiling Postline | 5231d811-39b5-4a95-b5b8-91f3f6ab9b91
checkpoint-status |  |  | checkpoint | Correct linings installed as per linings plan
checkpoint-status |  |  | checkpoint | Fixings as per specification including if glue required
checkpoint-status |  |  | checkpoint | Service penetrations cut out as per architecture RCP
checkpoint-status |  |  | checkpoint | Any ceiling hatches installed & fixed correctly
checkpoint-status |  |  | checkpoint | Ceiling approved for stopping
checkpoint-status |  |  | checkpoint | Stopping light check complete ready for paint
checklist-flat |  |  | checklist | Backfill Checklist |  |  |  |  | Yes | Backfill Checklist | 5b9f438f-c1de-4e63-a188-742908209859
checkpoint-status |  |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status |  |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status |  |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status |  |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status |  |  | checkpoint | General photos and observations during backfill
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-sectioned |  |  | checklist | Concrete Pour Checklist (Self Perform) |  |  |  |  | Yes | Concrete Pour Checklist (Self Perform) | 612e926c-bce9-4f0f-8faa-fb3e43064a34
checkpoint-group |  |  | section | Pour Details
checkpoint-no-status |  |  | checkpoint | Pour Details:
text | 56535b3e-d0a7-5921-adfc-f8c02e5c2a96 |  | textbox | Area to be poured:
text | a13f129e-ab15-58c3-b2ea-f102f4655927 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request trades QA / Sign Off
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Any relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-no-status |  |  | checkpoint | Concrete Supplier Specifics:
text | 4f39b43a-f59b-591f-a22e-def2e43c795f |  | textbox | Supplier Name:
text | 74ff00be-21af-5944-858e-8b549bbcb90c |  | textbox | Specified concrete strength:
text | e99293c8-715e-5ecb-ab91-81453b575302 |  | textbox | Concrete strength ordered:
text | 0d971149-5263-5e2a-b3ee-90464604b481 |  | textbox | Concrete quantity ordered:
checkpoint-status |  |  | checkpoint | Test blocks booked
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Concrete Distribution
checkpoint-status |  |  | checkpoint | General distribution photos, documents and observations attached
checkpoint-status |  |  | checkpoint | All concrete distributed correctly (area left clean and tidy)
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 1cf85b65-9ecb-5aec-863e-753b0f2266f5 |  | button | Is the cover correct to specification | Yes, No
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | Description/Number: |  |  |  |  | Yes | Engineer Follow Up Action | 66bf98fc-2aca-4032-a7f9-6f5ab8a7f23c
checkpoint-status |  |  | checkpoint | Follow-Up Action completed
text | ddf14301-8239-5b3b-951b-d5fa379a59cd |  | textbox | Specific Location:
text | 91c806c7-c985-559e-94d6-00a2b29bd0fd |  | textbox | Detail:
text | f17daeb2-6b36-59f2-add1-159d86b7a239 |  | textbox | Action Required:
holdpoint |  |  | signoff | Request Review
checklist-flat |  |  | checklist | Bulk Excavation Checklist |  |  |  |  | Yes | Bulk Excavation Checklist | 78c10b4e-549c-419f-a24c-2baece743a91
checkpoint-status |  |  | checkpoint | Excavation depth determined using appropriate RL's
checkpoint-status |  |  | checkpoint | Confirm location and isolation of relevant services
checkpoint-status |  |  | checkpoint | General excavation documentation and photos attached
checkpoint-status |  |  | checkpoint | Any batters formed correctly
checkpoint-status |  |  | checkpoint | Any trenches/ pits / hazardous areas appropriately isolated
checkpoint-status |  |  | checkpoint | Any soft spots identified and appropriate remedial completed
checkpoint-status |  |  | checkpoint | Any hardfill/ blinding installed correctly to required specification
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-sectioned |  |  | checklist | Nu Wall Cladding |  |  |  |  | Yes | Nu Wall Cladding | 7c895ed4-f1a1-4649-97b6-de9f78ef24e3
checkpoint-group |  |  | section | QC Summary
checkpoint-no-status |  |  | checkpoint | QC Summary
text | b788dc77-8f2e-56e7-ba1a-5c2779e36611 |  | textbox | Subcontractor/Supplier
text | e0f364de-b553-56cd-838e-4376a3c888a2 |  | textbox | Works area
text | 5a6bbcb7-08d1-5d04-8cdf-9f781f243cf6 |  | textbox | Drawings reference
text | 0ec5cd9f-d79d-5eb6-9030-0cfd4f90fe6e |  | textbox | Project specification reference
checkpoint-group |  |  | section | Precladding
checkpoint-status |  |  | checkpoint | RAB and timber is dry prior to apply revealshield
label | d428cdad-4895-5648-a3f4-b332175d6819 |  | note | Photos
checkpoint-status |  |  | checkpoint | Revealshield is applied correctly (80mm overlap) and as per drawing
label | a23f1fe9-795c-59c0-964e-b4f7889eb032 |  | note | Photos
checkpoint-status |  |  | checkpoint | Liquidflash is apply around the window opening andany other location required
label | 12f16471-76bb-53c5-929d-85bf18234763 |  | note | Photos
checkpoint-status |  |  | checkpoint | Sealant and flashing tape is applied ( brackets fixed on RAB/ over the top of pressure bar...)
label | c4dc960c-6c9a-5484-af17-5cffed30c4b4 |  | note | Photos
checkpoint-group |  |  | section | Cladding - Nu Wall
checkpoint-status |  |  | checkpoint | Façade bottom flashing detail installed (equal angle/ steel angle/ vermin/J flashing..)
label | f4a984fa-7527-57fe-93a2-9b91d926fec6 |  | note | Photos
checkpoint-status |  |  | checkpoint | Aluminum batten installed as per spec (600mm/enough fixing/location on windows sides)
label | 4ac384b7-a950-5902-b560-dce0eb0c47c5 |  | note | Photos
checkpoint-status |  |  | checkpoint | Fixings installed as per product installation guide
label | 134a3e91-3894-55d0-9a92-2f9a29853994 |  | note | Photos
button | 0dc1a7b3-6e37-5213-ad33-deeb49604dd6 |  | button | Flashing tapes installed as per installation guide | Timber,Concrete,Steel
label | b3170e02-a2d7-59ad-a4ab-fd708124cf1f |  | note | Photos
checkpoint-status |  |  | checkpoint | Seismic movement join in correctly
label | ebed63aa-9efb-5e1e-bf1e-331c9a5b3fc8 |  | note | Photos
checkpoint-status |  |  | checkpoint | Check colour and type of Nu wall
label | af2a4e6e-6b1f-5a3c-a27c-9bfa6f860f58 |  | note | Photos
checkpoint-status |  |  | checkpoint | Vertical sheet flashings installed
label | b9c61898-8679-51b2-8829-523ff3876ad5 |  | note | Photos
checkpoint-status |  |  | checkpoint | Interstorey flashing/ head flashing/ sill flashing installed correctly - with soaker and sealant
label | 59b11c5b-c721-51e9-a103-0f33837a12b0 |  | note | Photos
checkpoint-status |  |  | checkpoint | Corners flashing if required on
checkpoint-status |  |  | checkpoint | Windows jamb cap align with vertical jointer cap -detail 5-A330
checkpoint-status |  |  | checkpoint | Flashing tape over flashing (head flashing, interstorey flashing)
label | 153a33f1-60e5-58d8-a7d8-a7187b0d6d87 |  | note | Photos
checkpoint-status |  |  | checkpoint | Top flashing detail complete with flashing tape over it
checkpoint-status |  |  | checkpoint | Is it complete and tightly fitted
label | 2560df36-3e6b-5fd7-bda1-39a80880603c |  | note | Photos
checkpoint-group |  |  | section | Services
checkpoint-status |  |  | checkpoint | Check if services penetrating the RAB are required in this location
label | d7e52687-954f-5735-856f-a4d3b93772a0 |  | note | Photos
checkpoint-status |  |  | checkpoint | Security services installed to correct locations
label | 1183022c-c75c-566a-af9f-4386d191d1a5 |  | note | Photos
checkpoint-status |  |  | checkpoint | Plumbing services installed to correct locations
label | a6bf809b-1f3c-5e33-9fdb-d0e9ec6f7d2c |  | note | Photos
checkpoint-status |  |  | checkpoint | Fire services installed to correct loctions
label | 0deb001d-8e9d-5f01-b39b-7a7c07ea168d |  | note | Photos
checkpoint-status |  |  | checkpoint | Lighting and power services installed to correct locations
label | 71e8717b-0930-5c87-8aae-88f367cfe51c |  | note | Photos
checkpoint-status |  |  | checkpoint | Mechanical services installed to correct locations
checkpoint-group |  |  | section | Final approvals and holdpoints
checkpoint-status |  |  | checkpoint | Hold point - Sub contractor QA
label | 5324250e-4be7-5675-b916-5b35624d3fa1 |  | note | QA REPORT
holdpoint |  |  | signoff | Company QA Check
checkpoint-status |  |  | checkpoint | Engineer Inspections
label | d1010b87-f397-5ff8-950f-26fb2c0a8146 |  | note | SITE REPORTS
checkpoint-status |  |  | checkpoint | Council Inspections
label | 692c7767-d92e-5079-b1c2-a17f1f4cbbb6 |  | note | INSPECTION REPORT
checklist-sectioned |  |  | checklist | Shroud & Finns |  |  |  |  | Yes | Shroud & Finns | 84756185-a6f0-4b7d-8d4f-167485e06b84
checkpoint-group |  |  | section | QC Summary
checkpoint-no-status |  |  | checkpoint | QC Summary
text | be104312-4d2a-51a0-8c7d-1ad0579fedee |  | textbox | Subcontractor/Supplier
text | b6af4c2d-eba7-5b36-8877-e37351b5ff3b |  | textbox | Works area
text | 5e7f15d0-df69-5613-a9be-c9d03a93af1e |  | textbox | Drawings reference
text | 18c041d2-d8a1-5cc7-8944-fcd1ddca78e8 |  | textbox | Project specification reference
checkpoint-group |  |  | section | Precladding
checkpoint-status |  |  | checkpoint | RAB and timber is dry prior to apply revalshield
label | b297b1c9-30ea-5a9c-996e-e54823979439 |  | note | Photos
checkpoint-status |  |  | checkpoint | Revealshield is applied correctly (80mm overlap) and as per drawing
label | 24c2e58b-209d-5d2f-b202-6c5e575cc83c |  | note | Photos
checkpoint-status |  |  | checkpoint | Liquidflash is apply around the window opening andany other location required
label | 95b055ef-ae39-5db6-a80e-8883a437d1da |  | note | Photos
checkpoint-status |  |  | checkpoint | Sealant and flashing tape is applied ( brackets fixed on RAB/ over the top of pressure bar...)
label | cd9ef285-d527-5c5e-b1e5-60193b2a9003 |  | note | Photos
checkpoint-group |  |  | section | Shroud
checkpoint-status |  |  | checkpoint | Brackets in and leveled
label | 1f9c9cb1-da79-5819-a0cb-f0d356ec756d |  | note | Photos
checkpoint-status |  |  | checkpoint | Brackets setout correct
label | c8a6878f-8039-584b-9129-a4253f4b7493 |  | note | Photos
checkpoint-status |  |  | checkpoint | Anodised Frost Ultra black check
label | a1b27ded-062f-51ac-9eb3-7e4802e85d55 |  | note | Photos
checkpoint-status |  |  | checkpoint | Bottom and top shroud leveled
label | 82827932-7e41-5520-bc61-50beec232d34 |  | note | Photos
checkpoint-status |  |  | checkpoint | Side shroud plumb
label | 254ea561-b604-5243-ba5c-65ef5af80bc4 |  | note | Photos
checkpoint-status |  |  | checkpoint | Fixing as per drawings
label | c0248300-5186-54e8-b60e-46852ed3e6b0 |  | note | Photos
checkpoint-status |  |  | checkpoint | Join, gap, notch, all detail as per drawings
label | 11224243-61f8-58c0-a2b7-eada85f714fc |  | note | Photos
checkpoint-group |  |  | section | Finns
checkpoint-status |  |  | checkpoint | Brackets in
label | 32a03a7e-af9f-52c0-9b5c-de899ff0099f |  | note | Photos
checkpoint-status |  |  | checkpoint | Anodised Frost Ultra black check
label | 99654c42-a4d9-51a3-bede-6fc476eb0b38 |  | note | Photos
checkpoint-status |  |  | checkpoint | Fines installed as per drawings (lengh, gap, fixing detail )
label | 62afadae-5f35-508c-b9a5-a4e7cb9fea4a |  | note | Photos
checkpoint-status |  |  | checkpoint | Fixing as per drawings
label | ebfda595-e827-5af3-8d19-4847a32bc66c |  | note | Photos
checkpoint-group |  |  | section | Final approvals and holdpoints
checkpoint-status |  |  | checkpoint | Hold point - Sub contractor QA
label | e1eefd4d-4216-5240-a9a2-0fc3c55837aa |  | note | QA REPORT
holdpoint |  |  | signoff | Company QA Check
checkpoint-status |  |  | checkpoint | Engineer Inspections
label | 60a8c94f-1dec-5cf5-bd4a-1d6a6da442c7 |  | note | SITE REPORTS
checkpoint-status |  |  | checkpoint | Council Inspections
label | 8e2de418-acd0-57e8-ac3e-bdb5ae259190 |  | note | INSPECTION REPORT
checklist-flat |  |  | checklist | Flooring |  |  |  |  | Yes | Flooring | 88d090ae-0b7c-4c6c-ac5b-e46cb473bff6
checkpoint-status |  |  | checkpoint | Floor substrate clean, dry, ready for finishes
checkpoint-status |  |  | checkpoint | Finishes as per architectural plans
checkpoint-status |  |  | checkpoint | Trim thresholds junction as per detail
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checklist-flat |  |  | checklist | Shotcrete Fill Works Checklist |  |  |  |  | Yes | Shotcrete Fill Works Checklist | 9a209efb-31eb-4d67-864d-38849fd15c70
checkpoint-status |  |  | checkpoint | Specified the cut upper or lower cut and position (grid lines)
checkpoint-status |  |  | checkpoint | Imported fill material checked either GAP65 hardfill-HOROKIWI or RM65 hardfill-Winstones belmont
checkpoint-status |  |  | checkpoint | Every 500mm layer plateform checked
checkpoint-status |  |  | checkpoint | Compaction test with Mats check and passed
checkpoint-status |  |  | checkpoint | As built location of the cut confirmed
checkpoint-status |  |  | checkpoint | As built the slope either 40deg or 60deg
checkpoint-status |  |  | checkpoint | Progress photos
checklist-flat |  |  | checklist | Bore Drain Checklist |  |  |  |  | Yes | Bore Drain Checklist | 9baf8235-8c5a-48a6-8670-3b7e4a48268d
checkpoint-status |  |  | checkpoint | Set out confirmed
checkpoint-status |  |  | checkpoint | Coordinate with pile locations
checkpoint-status |  |  | checkpoint | General photos, comments and observations during drilling
checklist-flat |  |  | checklist | Ground Anchor Checklist |  |  |  |  | Yes | Ground Anchor Checklist | 9ecbef25-39ec-42d9-8101-eda57339d4ac
checkpoint-status |  |  | checkpoint | Set out confirmed
checkpoint-status |  |  | checkpoint | Drilling angle confirmed
checkpoint-status |  |  | checkpoint | Coordinate with pile locations
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Load testing complete
checkpoint-status |  |  | checkpoint | General photos, comments and observations during drilling
checklist-flat |  |  | checklist | Roof Decks |  |  |  |  | Yes | Roof Decks | a4cb475c-0923-48bb-bef2-31d38d5a125d
checkpoint-status |  |  | checkpoint | Safety mesh and cavity batten installed correctly
checkpoint-status |  |  | checkpoint | Outside box gutter with eave flashing installed - if required
checkpoint-status |  |  | checkpoint | Covertek 407 on safety mesh installed as per drawing
checkpoint-status |  |  | checkpoint | Revealshield/ flashing tape dressed over covertek as per drawing
checkpoint-status |  |  | checkpoint | Eco foam closure strip installed
checkpoint-status |  |  | checkpoint | Roof metal decking sheet installed and screwed correctly & colorcote – Off white checked
checkpoint-status |  |  | checkpoint | Side flashing 0.55BMT coil coated steel installed & colorcote - off white
checkpoint-status |  |  | checkpoint | Flashing tape over Apron flashing - Installed
checkpoint-status |  |  | checkpoint | No damage, scratches - hand over to next trade approved
checklist-sectioned |  |  | checklist | Sumner Schist Stone Cladding |  |  |  |  | Yes | Sumner Schist Stone Cladding | ac5a1afd-4a3a-416c-953c-cf97f02e9788
checkpoint-group |  |  | section | QC Summary
checkpoint-no-status |  |  | checkpoint | QC Summary
text | 82b1d8e1-a124-5fa3-af99-c39da9e4b998 |  | textbox | Subcontractor/Supplier
text | a18d1c32-200e-58f0-b024-fce23ef020a3 |  | textbox | Works area
text | 99f32d87-d469-58a0-839e-af7901638a6f |  | textbox | Drawings reference
text | d1deadd2-7ebc-5562-9e7b-79f395c23f86 |  | textbox | Project specification reference
checkpoint-group |  |  | section | Precladding
checkpoint-status |  |  | checkpoint | RAB and timber is dry prior to apply revalshield
label | d7809b79-4225-52b4-bc9b-c02385554aef |  | note | Photos
checkpoint-status |  |  | checkpoint | Revealshield is applied correctly (80mm overlap) and as per drawing
label | 35575107-3f69-5513-b1de-48f359c610fb |  | note | Photos
checkpoint-status |  |  | checkpoint | Liquidflash is apply around the window opening andany other location required
label | ed08d027-f9d1-5c23-8c29-45c8aca4b512 |  | note | Photos
checkpoint-status |  |  | checkpoint | Sealant and flashing tape is applied ( brackets fixed on RAB/ over the top of pressure bar...)
label | f53749aa-3a8e-53f8-9e82-f28a19a8fccc |  | note | Photos
checkpoint-group |  |  | section | Sumner Schist - Stone Cladding
checkpoint-status |  |  | checkpoint | Installation of Cavity Batten as per drawing
label | d039d756-1603-574a-9535-a293dc187a17 |  | note | Photos
checkpoint-status |  |  | checkpoint | Movement join as per drawing and set out
label | 3d9e790e-d130-5534-81d7-0b9aa050234a |  | note | Photos
checkpoint-status |  |  | checkpoint | Sumner schist 9mm board installed as per manual
label | fdddc186-4d25-5987-bdcc-27f3ae6a068f |  | note | Photos
checkpoint-status |  |  | checkpoint | Sumner stone primer and stone installed as per specification
label | c7234151-4561-5c13-8aa9-8f3b1d8ce474 |  | note | Photos
checkpoint-status |  |  | checkpoint | Backing rod/ sealant applied
label | 3c840c97-fa2f-5a98-9f33-6de82e801f0d |  | note | Photos
checkpoint-status |  |  | checkpoint | Windows sill checked
label | 6a7a0b74-87f6-5b40-8fa8-567e0fe2bd11 |  | note | Photos
checkpoint-status |  |  | checkpoint | Connection to ground checked
label | b1d3c83d-243d-5265-9652-43193ad0200d |  | note | Photos
checkpoint-group |  |  | section | Services
checkpoint-status |  |  | checkpoint | Check if services penetrating the RAB are required in this location
label | 689ef172-7833-58fe-87d9-21463820f731 |  | note | Photos
checkpoint-status |  |  | checkpoint | Security services installed to correct locations
label | 7677586a-7404-5963-af95-68e8ab732a98 |  | note | Photos
checkpoint-status |  |  | checkpoint | Plumbing services installed to correct locations
label | 92729d83-25ef-5507-b69f-51390bf7be01 |  | note | Photos
checkpoint-status |  |  | checkpoint | Fire services installed to correct loctions
label | ce3cb479-40db-59b9-a5c4-c95f0c1a7606 |  | note | Photos
checkpoint-status |  |  | checkpoint | Lighting and power services installed to correct locations
label | 2529d919-4c0e-59cd-b631-c64bfbefcda6 |  | note | Photos
checkpoint-status |  |  | checkpoint | Mechanical services installed to correct locations
label | 82a1c704-3a75-5207-9775-755c062bc714 |  | note | Photos
checkpoint-group |  |  | section | Final approvals and holdpoints
checkpoint-status |  |  | checkpoint | Hold point - Sub contractor QA
label | a89ab464-9871-572c-80c8-6782340a5875 |  | note | QA REPORT
holdpoint |  |  | signoff | Company QA Check
checkpoint-status |  |  | checkpoint | Engineer Inspections
label | d59f0d2d-88b0-55fb-8331-7107df8cb175 |  | note | SITE REPORTS
checkpoint-status |  |  | checkpoint | Council Inspections
label | 3652b802-6089-5e9d-859b-d12738fb7c26 |  | note | INSPECTION REPORT
checklist-flat |  |  | checklist | Grouting Checklist |  |  |  |  | Yes | Grouting Checklist | b0179418-bc04-4424-bfff-68d97253f7ea
checkpoint-status |  |  | checkpoint | Dry pack completed?
checkpoint-status |  |  | checkpoint | Pumped used?
checkpoint-status |  |  | checkpoint | Grout Used: Mapei SP (If different add in comments)
text | 93cdd564-7873-50ad-a6ea-b748040d5270 |  | textbox | Number of bags of grout used
checkpoint-status |  |  | checkpoint | Is the grout mixed properly? (3.0 to 3.4 Litres of Water per bag)
text | ecd64d6e-531d-5263-9781-a4b1eb8c8644 |  | textbox | Number of grout tubes in panel
text | 399d2858-213f-5223-92f5-3e5aff18d5db |  | textbox | Duration of pumping the whole panel
checkpoint-status |  |  | checkpoint | Did grout came out of top of dross tube?
checkpoint-status |  |  | checkpoint | No blow outs
checklist-flat |  |  | checklist | Final Sign Off |  |  |  |  | Yes | Final Sign Off | b4ac42ea-5913-401c-8068-7ef79c4b6af7
checkpoint-status |  |  | checkpoint | Doors Installed including drop down seals if applicable
checkpoint-status |  |  | checkpoint | Hardware as per approved schedule
checkpoint-status |  |  | checkpoint | Architraves and skirtings installed
checkpoint-status |  |  | checkpoint | Electrical Power/Lighting second fix installed
checkpoint-status |  |  | checkpoint | Sprinkler/Alarm second fix installed
checkpoint-status |  |  | checkpoint | Security second fix installed
checkpoint-status |  |  | checkpoint | Data second fix installed
checkpoint-status |  |  | checkpoint | HVAC second fix installed
checkpoint-status |  |  | checkpoint | Floor finishes installed as per architectural plan
checkpoint-status |  |  | checkpoint | Paint correct colour
checkpoint-status |  |  | checkpoint | Door signage installed
checkpoint-status |  |  | checkpoint | Manifestations on glazing
checkpoint-status |  |  | checkpoint | Joinery installed correctly
checklist-sectioned |  |  | checklist | Wall Preline |  |  |  |  | Yes | Wall Preline | c562b382-c53a-47b1-93fd-b0eea059984f
checkpoint-group |  |  | section | Interior Framing
checkpoint-status |  |  | checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All framing setout correctly & surveyed in respective area
boolean | c5461e37-9dd3-5471-9ca6-290d56001b84 |  | tickbox | Spot checks on frames for square
boolean | 77546d39-aa58-5b0d-bd28-c7ff65566f29 |  | tickbox | Spot checks on frame level
boolean | aabbc6a5-b4ba-5559-87e0-08bb26e4882e |  | tickbox | Fixings are correct including seismic requirements
boolean | dffceefc-1ab2-5a28-89ac-70d17825a1e7 |  | tickbox | Service Nogs installed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Plumbing Walls First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Plumbing install First fix complete - checks done based on elevations of current drawings
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council inspection and testing complete and signed off
checkpoint-group |  |  | section | Fire Protection Walls (Alarms) First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor (alarms)
checkpoint-status |  |  | checkpoint | All required 1st fix testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Mechanical Services Wall First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with subcontractor
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Electrical Wall First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor
checkpoint-status |  |  | checkpoint | All required first fix testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Data Wall First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required first fix completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Security Wall First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required first fix completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | AV Wall First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required first fix completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Insulation/Acoustic
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Spot checks on correct product
checkpoint-status |  |  | checkpoint | Spot checks on correct R value
checkpoint-status |  |  | checkpoint | Fitting Snug
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Council Sign Off
checkpoint-status |  |  | checkpoint | Council preline inspection passed
checklist-sectioned |  |  | checklist | Blockwork Checklist |  |  |  |  | Yes | Blockwork Checklist | d0ad75e6-94a7-4aa1-9a1a-2cc41c1c7e41
checkpoint-group |  |  | section | Blockwork Setout/Pre Start QA
checkpoint-status |  |  | checkpoint | Grids available for reference and base of wall marked accurately
checkpoint-status |  |  | checkpoint | RL reference/TOW confirmed
checkpoint-status |  |  | checkpoint | Starter bars correct (location, length and strength)
checkpoint-status |  |  | checkpoint | Concrete/footing clean, tidy and level (ready for first course)
checkpoint-status |  |  | checkpoint | Blockwork reinforcing steel delivered correct and accessible (Attach photos of respective reinforcing docket)
checkpoint-status |  |  | checkpoint | Any additional pre start observations
checkpoint-status |  |  | checkpoint | Correct blocks delivered, checked & accessible
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
text | 9aedf9df-f3d9-565a-8c91-170ce02767bf |  | textbox | Relevant drawings & revisions for reference:
checkpoint-status |  |  | checkpoint | Approval given to start laying blockwork
checkpoint-group |  |  | section | Blockwall Prepour
checkpoint-status |  |  | checkpoint | Base of wall in correct location
checkpoint-status |  |  | checkpoint | Horizontal reinforcing installed correctly (centres/ size / splicing etc)
checkpoint-status |  |  | checkpoint | Ties / Control joints installed as required
checkpoint-status |  |  | checkpoint | Vertical reinforcing installed as required with appropriate splice laps & secure
checkpoint-status |  |  | checkpoint | Openings checked and correct - location, height and width
checkpoint-status |  |  | checkpoint | Washouts correct/openings covered correctly and wall braced adequately (if required)
checkpoint-status |  |  | checkpoint | Any additional observations/ inspections attached
checkpoint-status |  |  | checkpoint | Wall built within tolerance - straight, level and to the correct height (Approval to pour)
checkpoint-group |  |  | section | Blockwall Pour
checkpoint-status |  |  | checkpoint | Any remedial work completed/observations closed out and approval given to pour
checkpoint-status |  |  | checkpoint | Concrete specifications checked and correct - delivery docket(s) photographed
checkpoint-status |  |  | checkpoint | General photos and any additional observations
checkpoint-status |  |  | checkpoint | All blocks filled to correct height
checkpoint-status |  |  | checkpoint | Starter bars in centre of block if applicable
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Any concrete spillage/splatter cleaned up
checkpoint-status |  |  | checkpoint | Blockwork wall(s) complete to required specification
checklist-flat |  |  | checklist | Civil - Storm Checklist |  |  |  |  | Yes | Civil - Storm Checklist | d210e3cd-e249-46d1-9239-5f19665a62a9
checkpoint-status |  |  | checkpoint | Location details and relevant mark ups attached
text | a9663646-22e9-5ab0-9117-3cae71fd1015 |  | textbox | Location
checkpoint-status |  |  | checkpoint | Consultant inspection completed as required
checkpoint-status |  |  | checkpoint | Council Inspection completed as required
checkpoint-status |  |  | checkpoint | Invert levels recorded
checkpoint-status |  |  | checkpoint | Invert levels as per design
text | 8e93c404-a12c-589c-be44-16a75a010538 |  | textbox | Invert Levels
checkpoint-status |  |  | checkpoint | Received QA from Subcontractor?
checkpoint-status |  |  | checkpoint | As Built drawings received
checkpoint-status |  |  | checkpoint | CCTV Survey
checkpoint-status |  |  | checkpoint | Certificates provided
checkpoint-status |  |  | checkpoint | Installation record photos
checkpoint-status |  |  | checkpoint | Storm Installation completed
checklist-flat |  |  | checklist | Screw Piling Checklist |  |  |  |  | Yes | Screw Piling Checklist | d718ba31-adcc-4c6c-86e5-6ef77e629807
checkpoint-status |  |  | checkpoint | As-Built location confirmed (allowable tolerance 75mm)
checkpoint-status |  |  | checkpoint | Verticality checked
checkpoint-status |  |  | checkpoint | Concrete specification checked (concrete docket supplied)
checkpoint-status |  |  | checkpoint | Rebar installed (if required)
checkpoint-status |  |  | checkpoint | Lattey QA Received (As per requirements of Section 1.23 Piling Specification)
checkpoint-status |  |  | checkpoint | Cut off RL checked
checkpoint-status |  |  | checkpoint | Excess pile removed and disposed off
checkpoint-status |  |  | checkpoint | Progress photos
checklist-flat |  |  | checklist | Walls Postline |  |  |  |  | Yes | Walls Postline | f21a05d6-e610-459e-b5c9-903642eeeb38
checkpoint-status |  |  | checkpoint | Correct linings installed as per linings plan
checkpoint-status |  |  | checkpoint | Bracing fixings installed correctly as per requirements
checkpoint-status |  |  | checkpoint | Linings cut out for flush boxes neat and tidy
checkpoint-status |  |  | checkpoint | All screws installed flush
checkpoint-status |  |  | checkpoint | Wall approved for stopping
checkpoint-status |  |  | checkpoint | Stopping light check complete ready for paint
checklist-sectioned |  |  | checklist | Spanlok Cladding |  |  |  |  | Yes | Spanlok Cladding | f28fd8a2-e4a3-4a96-8fe5-523091602d1f
checkpoint-group |  |  | section | QC Summary
checkpoint-no-status |  |  | checkpoint | QC Summary
text | 217a0ac7-32e7-5823-9f50-08b5cde24042 |  | textbox | Subcontractor/Supplier
text | 2c375605-e35d-51ed-a449-a5f84fae8d50 |  | textbox | Works area
text | caac1df2-74fb-57aa-b189-9f584b109712 |  | textbox | Drawings reference
text | 05caea43-9de6-5180-a20c-652e4861cbe4 |  | textbox | Project specification reference
checkpoint-group |  |  | section | Precladding
checkpoint-status |  |  | checkpoint | RAB and timber is dry prior to apply revalshield
checkpoint-status |  |  | checkpoint | Revealshield is applied correctly (80mm overlap) and as per drawing
checkpoint-status |  |  | checkpoint | Liquidflash is apply around the window opening andany other location required
checkpoint-status |  |  | checkpoint | Sealant and flashing tape is applied ( brackets fixed on RAB/ over the top of pressure bar...)
checkpoint-group |  |  | section | Spanlok
checkpoint-status |  |  | checkpoint | Façade bottom flashing detail installed (equal angle/ steel angle/ vermin..)
label | 7b131631-515c-5181-ab50-0d20712ed1f6 |  | note | Photos
checkpoint-status |  |  | checkpoint | Timber batten + castellated cavity batten (James hardie)
label | 36f3bd62-b0bd-56a6-844c-21d15868eb1e |  | note | Photos
checkpoint-status |  |  | checkpoint | PVC stripes over timber batten
label | 68c4b63c-8136-5b5a-8898-d84b7abbaa84 |  | note | Photos
checkpoint-status |  |  | checkpoint | Shroud brackets on if required
label | 3d49858e-055d-571d-ab4c-59c578ba97c2 |  | note | Photos
checkpoint-status |  |  | checkpoint | Horizontal fixing plate on
label | 6209ed1f-57d0-5ca1-9abb-576230ebc373 |  | note | Photos
checkpoint-status |  |  | checkpoint | Spanlok sheet plumb and leveled (10mm gap over the head flashing))
label | b170e69c-8832-558c-b81b-d5baeca39610 |  | note | Photos
checkpoint-status |  |  | checkpoint | Sill flashing installed correctly
label | c174aae9-62f9-5d22-94d6-4534ed08a831 |  | note | Photos
checkpoint-status |  |  | checkpoint | Is it complete and tightly fitted
label | 943fcb18-f0b6-56ba-8824-4f2b5b0fb044 |  | note | Photos
checkpoint-group |  |  | section | Services
checkpoint-status |  |  | checkpoint | Check if services penetrating the RAB are required in this location
label | d96c25af-dac3-5d3e-82d6-bd5023b42de4 |  | note | Photos
checkpoint-status |  |  | checkpoint | Security services installed to correct locations
label | e510a0fe-17fe-57e6-ba1e-df4fd213bdd7 |  | note | Photos
checkpoint-status |  |  | checkpoint | Plumbing services installed to correct locations
label | f19be9ce-e142-5d79-ab86-7e78057e7236 |  | note | Photos
checkpoint-status |  |  | checkpoint | Fire services installed to correct loctions
label | dc123978-6318-57f2-8780-bcfa014e5e2b |  | note | Photos
checkpoint-status |  |  | checkpoint | Lighting and power services installed to correct locations
label | 9adf994e-5a98-50fb-ae60-ad6a2d576ef1 |  | note | Photos
checkpoint-status |  |  | checkpoint | Mechanical services installed to correct locations
label | 1a7fa40e-f2d2-514d-bfd9-9cbcbd388851 |  | note | Photos
checkpoint-group |  |  | section | Final approvals and holdpoints
checkpoint-status |  |  | checkpoint | Hold point - Sub contractor QA
label | 2c1d1940-c9df-5950-90f5-d55db202c580 |  | note | QA REPORT
holdpoint |  |  | signoff | Company QA Check
checkpoint-status |  |  | checkpoint | Engineer Inspections
label | 64f6674e-1e53-50b0-ab6c-6f7ccd59bd74 |  | note | SITE REPORTS
checkpoint-status |  |  | checkpoint | Council Inspections
label | a7dcefb6-fd05-56b1-8f87-10d4c6599be5 |  | note | INSPECTION REPORT
checklist-flat |  |  | checklist | Retaining Wall Checklist |  |  |  |  | Yes | Retaining Wall Checklist | f4a8dded-3356-4ea2-aa22-c8841ed67b2c
checkpoint-status |  |  | checkpoint | Retaining wall(s) setout/heights confirmed
checkpoint-status |  |  | checkpoint | Area prepared - Excavation depths and location of wall checked and correct
checkpoint-status |  |  | checkpoint | General install photos and observations attached
checkpoint-status |  |  | checkpoint | Correct materials used and installed using appropriate methodology
checkpoint-status |  |  | checkpoint | All relevant services / waterproofing elements completed, checked and approved prior to backfill
checkpoint-status |  |  | checkpoint | Backfill completed - correct materials and compaction methodology used - specified compaction achieved
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Additional observations/ inspections attached and all remedial items closed out
checkpoint-status |  |  | checkpoint | Retaining wall completed to required specifications
checklist-flat |  |  | checklist | Framing |  |  |  |  | Yes | Framing | f6ca7bd9-7c48-43e1-9e71-6e5dc8b19e90
checkpoint-status |  |  | checkpoint | Timber complies with spec for type and grade
checkpoint-status |  |  | checkpoint | Timber gauge sizing correct
checkpoint-status |  |  | checkpoint | Timber to steel fixings
checkpoint-status |  |  | checkpoint | Setting out as per architectural drawings
checkpoint-status |  |  | checkpoint | Dampcourse installed
checkpoint-status |  |  | checkpoint | Top plate hardware install (every 600mm/80mm from slab edge)
checkpoint-status |  |  | checkpoint | Special and service nogs complete
checkpoint-status |  |  | checkpoint | Stud centres
checkpoint-status |  |  | checkpoint | Nog centres, level and ridged
checkpoint-status |  |  | checkpoint | Floor fixings - Holding down bolts
checkpoint-status |  |  | checkpoint | Seismic joint frame correct
checkpoint-status |  |  | checkpoint | Additional blocking Nuwall
checkpoint-status |  |  | checkpoint | Additional blocking spanlok
checkpoint-status |  |  | checkpoint | Additional blocking INSOL (shrouds/fine)