## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Church Valley Road Area Wide Treatment ITP | itp | Church Valley Road Area Wide Treatment ITP | ef3ad7b3-1705-4981-b0a6-196898596678
| section | Details
| checkpoint | 1 - AP40 Material Quality
7d952b8d-e111-537d-a6f0-4123400d12ba | note | Inspection Point: Quality Control Activity - Record TNZ/M4 Test Document
1b8ad650-a0bc-5a93-bc29-433113139b7c | note | Acceptance Criteria - Confirm material meets M4 Crushing resistance test
a94b5c82-be7f-5ec4-a064-6e942eb06615 | note | Verifying Document - Report
9192c2da-f9cf-5ddf-b2e7-6a278a2586ec | note | Frequency - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
bf313c13-9eb8-53d6-8407-fb59e054d8fb | note | Inspection Type (Visual, other) - Verification
2f87fbef-9984-5263-8510-bdad95ed0b55 | note | Inspection: Key - PE
eb78b367-e38c-54b4-98a6-96fc811ab126 | note | Inspection: By (Role Key) - Supplier
| checkpoint | 2 - Stabi Agent (Cement)
de7325eb-9c8f-5eca-844b-f4dc6661b385 | note | Inspection Point: Quality Control Activity - Record NZS 3122
20de6dee-8bfc-5a4f-8ac7-497689da9816 | note | Acceptance Criteria - Confirm material as per NZS 3122
84477d05-a8c3-57c9-a98f-c6f19c0ea2fa | note | Verifying Document - Report
7f46089d-cb18-5c39-ab10-d55d7628d1c4 | note | Frequency - per Batch
0ae4ca1f-d453-5fa9-abd2-707910442d49 | note | Inspection Type (Visual, other) - Verification
2bdc0722-3232-557d-a345-5385dae7bb9a | note | Inspection: Key - PE
24bcbb73-5da7-56ea-8885-a657fa212bcd | note | Inspection: By (Role Key) - Supplier
| checkpoint | 3 - Weather Limitation
51f7cfc6-e766-5e28-96d3-e2107c92c2cf | note | Inspection Point: Quality Control Activity - Measure temperature
a5e9953a-943e-5ced-bad6-caaa5ca552fe | note | Acceptance Criteria - Minimum ambient air temp.
c6f501de-bd81-5239-b18d-d4c8b15cc0d0 | note | ○ Cement 5°C
bcf15b5e-8e2a-5a28-905c-56325f00ec5e | note | ○ Lime 10°C" & Maximum windspeed of 25km/hr
ac725d4e-b07b-5a1b-8f34-8868797d2def | note | Verifying Document - Site notes
6d1d7da8-95e6-58d8-8ec2-6b3bff7ff8d0 | note | Frequency - Daily
b89d62f5-0b5c-500f-8bfc-1f66b441050b | note | Inspection Type (Visual, other) - Witness
ea100e3f-c6b7-5522-8505-69671347c430 | note | Inspection: Key - PS
211893fc-8dbe-59ac-8ebc-7ea87a55c334 | note | Inspection: By (Role Key) - Alliance
| checkpoint | 4 - Spreading rate
2fc7ba82-fcea-53b3-bcf4-cfdf8e133ba7 | note | Inspection Point: Quality Control Activity - Average usage test
cc8e7c08-cd5f-5eaa-b470-b88dd355e692 | note | Acceptance Criteria - Target = 2.4kg/m2,Within ±0.5km/m² of the specified rate
37bd0d42-003c-5ece-ae3a-c9d556a06e81 | note | Verifying Document - Site notes
3cc9abbb-965d-5330-8f36-986ee421cabc | note | Frequency - Daily
2508a3a3-02fd-5361-b098-9a11759e0ea3 | note | Inspection Type (Visual, other) - Verification
c9ce6700-3c0a-5d67-a90b-e654b3139784 | note | Inspection: Key - PS
9da0c026-d960-551f-bc68-3c4351598fc6 | note | Inspection: By (Role Key) - Alliance
| checkpoint | 5 - Time limitation
3db66e95-fa02-5c4e-a522-cd2c95fc6592 | note | Inspection Point: Quality Control Activity - Maximum time period from mixing to primary compaction
5553c53e-0c96-5449-b200-d25fb582f4be | note | Acceptance Criteria - 2 hours, TNZB/5
2424a7d4-962c-5836-b8ed-0d749b275139 | note | Verifying Document - Site notes
68537152-db45-54cc-8ec4-737dddb35b47 | note | Frequency - Post stabilisation
f8b8c2cc-4ade-5ae0-9e65-741e2ad5c5d6 | note | Inspection Type (Visual, other) - Holdpoint
3b2e25ef-6428-5926-9cc1-623e64dbbb5f | note | Inspection: Key - PS
cad365f6-3835-5713-854d-55dd972cd22b | note | Inspection: By (Role Key) - Alliance
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - In-situ Mixing
9cc4dc59-ab97-5e26-86ee-6918354d311a | note | Inspection Point: Quality Control Activity - Cut depth
a9b3fd15-e30a-5968-93f6-54f51833f3d3 | note | Acceptance Criteria - -5mm +15mm of design depth
b4dc1759-c6f2-59b2-ac7a-3058daeabace | note | Verifying Document - Site notes
88942ce7-3a26-52d0-ab8f-30f5026e5a72 | note | Frequency - At both ends of cut & every 200m
6b566007-5010-5ff6-be78-d9ec62eb8452 | note | Inspection Type (Visual, other) - Witness
93c6f30c-60a1-52a8-a22d-411589a019c4 | note | Inspection: Key - PS
0474c12f-1b3e-532b-af68-a6fa591d50d0 | note | Inspection: By (Role Key) - Alliance
| checkpoint | 7 - In-situ Mixing
0a2c81cc-bfac-5a30-8127-ab6785e236eb | note | Inspection Point: Quality Control Activity - Join Overlap
ebf8e744-835d-5116-b16a-2e323c96cbc8 | note | Acceptance Criteria - 100mm overlap
4c7104a7-a972-5f6b-b792-082a9e2c9d0e | note | Verifying Document - Site notes
649800b7-a082-5a1f-b64d-123cfcef8be2 | note | Frequency - Continuous
c1c2ba78-7258-571f-a6d2-9b0a91d8131f | note | Inspection Type (Visual, other) - Witness
a8c0a167-2a4b-558b-b756-993c94e6cc63 | note | Inspection: Key - PS
67288611-ea04-5d4e-b540-231627edc79a | note | Inspection: By (Role Key) - Alliance
| checkpoint | 8 - In-situ Mixing
b04d94da-1198-546f-94f6-deb2ff1e43db | note | Inspection Point: Quality Control Activity - Particle Breakdown
149411d1-dd4d-5bb8-b547-13353bc4523c | note | Acceptance Criteria - Well mixed material with acceptable particle size distribution
a0fda8b2-a435-5de5-bad3-aca4cb3ac842 | note | Verifying Document - Site notes
ab044f71-2dd5-57c3-b24f-7da026321351 | note | Frequency - within the first 20m of each run, and where ever material changes
d6f6f03b-9f0f-5381-8816-d8678434094e | note | Inspection Type (Visual, other) - Witness
91cafca5-6e2c-5a7c-a26d-dc4690e99c27 | note | Inspection: Key - PS
229bc9be-3f4b-5544-835d-36f4b229d673 | note | Inspection: By (Role Key) - Alliance
| checkpoint | 9 - Construction (Site Extent)
62210e59-d61c-533b-82ee-b76561e6e8bc | note | Inspection Point: Quality Control Activity - String line & survey
48baf99c-850a-5467-a1ba-6544039a4b6e | note | Acceptance Criteria - As per the design
fbae896a-c513-532e-81bd-4c9dad753e75 | note | Verifying Document - Image
e7067718-cd09-59c8-be7d-4529ba53ee91 | note | Frequency - One for whole site
7a6580b4-40a3-5d57-9074-cff09086f072 | note | Inspection Type (Visual, other) - Witness
37964e6d-0165-5b4a-967d-0c642495137d | note | Inspection: Key - PE
c4c3b629-9afc-54e1-af0b-3a6e0c4abb8d | note | Inspection: By (Role Key) - Alliance
| checkpoint | 10 - Construction (Compaction & Degree of Saturation)
282c65a3-cb60-585b-b37b-5cd4ab44a2d6 | note | Inspection Point: Quality Control Activity - NDM - Maximum Dry Density & Degree of Saturation (DOS)
1bdc7466-e8b8-5875-b97d-b905c157b48c | note | Acceptance Criteria - Base:Average ≥ 98% MDD,
44fdafaf-8e2a-5d01-8fd5-d0ce56fa7d7a | note | ○ Minimum ≥ 95% MDD")
c60a6352-a05c-5a77-a1c8-faafc3334c62 | note | Verifying Document - Report
a2714eb1-dffa-5c0e-9de1-762821d863e1 | note | Frequency - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
9ff8cfb9-7e2c-583f-a35d-6c6d33a031dc | note | Inspection Type (Visual, other) - Holdpoint
b80f4546-9cef-5f1e-8aa3-b9e994ab8711 | note | Inspection: Key - PE
6bc2fdb9-1db0-565d-8ffd-9028f204661a | note | Inspection: By (Role Key) - LAB
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Construction (Surface, Profile & layer thickness)
18855a3e-d2fc-5e79-b0f7-50b742a5479b | note | Inspection Point: Quality Control Activity - Visual inspection, Check string records, straight edge
ac69fefd-6810-52c2-b6a3-63a00d16d2f1 | note | Acceptance Criteria - No ponding if crossfall > 1% , Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
090757f3-19b7-53d0-a888-b5362f5b7be5 | note | Verifying Document - Site notes
e2486380-c7c2-5522-ac87-4def4680069e | note | Frequency - 1 test per 20m
9eab0027-3326-58a7-88c9-629276b162c6 | note | Inspection Type (Visual, other) - Holdpoint
026ce32f-1379-5e0d-ad17-5681a09eda9b | note | Inspection: Key - PE
e5be83fd-59db-5b20-a925-62e0ecd65817 | note | Inspection: By (Role Key) - Alliance
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Pavement finished surface
de22a6bc-7313-5efe-9873-70eb357bd535 | note | Inspection Point: Quality Control Activity - Ride quality & Mosaic surface
38f2949c-3a5e-515d-a868-2f5c75af1849 | note | Acceptance Criteria - As per LDM
0ecd558e-aa4d-5145-a3a7-e15678ae5503 | note | Verifying Document - Site notes
a3683bc7-1a8b-5b9b-adc3-5dba11ded178 | note | Frequency - 1 ride test for each lane following Basecourse completion prior to surfacing
6d4650b4-aeb2-5dd3-bd7c-15ab3ce47f25 | note | Inspection Type (Visual, other) - Holdpoint
1917089a-24a6-5e13-b17f-8888384ce1d6 | note | Inspection: Key - PE
a339c87f-aedc-5fc4-a817-db1f7cdfcb36 | note | Inspection: By (Role Key) - Alliance
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Shoulders
386579dc-a7a3-52a2-8dcb-4a79002524db | note | Inspection Point: Quality Control Activity - Slope, Compaction & Soil support
9378da75-0c6e-58b6-ac4c-bcc650e4b9a9 | note | Acceptance Criteria - Consistent slope, Vehicles can drive on shoulders without becoming stuck
c06ffedf-bba7-5c42-b9c2-02a3bb4dcd3d | note | Verifying Document - Visual Inspection
0257e624-a8d6-59f5-9d8f-e09c2b848445 | note | Frequency - All shoulders
5c5f0afa-a76e-56a5-b2be-ec8cfd439437 | note | Inspection Type (Visual, other) - Holdpoint
3e058e4c-445d-50b8-93f8-c67d8024dff6 | note | Inspection: Key - PS
b9019b98-b091-5d29-bfce-592ca4dce4ea | note | Inspection: By (Role Key) - Alliance
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Ready for sealing (Strength)
94dcc8e5-e0ee-5e78-85ee-390e0d929416 | note | Inspection Point: Quality Control Activity - B Beam
7c33aac5-f4cf-5b10-a609-adb99b6cc965 | note | Acceptance Criteria - Maximum deflection = 1.3mm
524ef796-3766-5c13-9c54-592d7c886cfd | note | Verifying Document - Report
d760ce82-d149-54ba-9b09-b9e095140d6f | note | Frequency - Staggered every 10m
55570f23-8847-5a67-a912-bb0f3c598eab | note | Inspection Type (Visual, other) - Holdpoint
f6ac253d-13b3-50dc-b3fe-989ac490b44f | note | Inspection: Key - PE
b773f5f8-e03c-5625-b65b-218e92c3d0e3 | note | Inspection: By (Role Key) - LAB
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Ready for sealing (Slope)
2ee2bea9-1f29-5527-815b-a3a51286be8c | note | Inspection Point: Quality Control Activity - Levelling
ca4e2ecc-162b-5a76-9b40-9e29d8ec80fd | note | Acceptance Criteria - 3m Straight edge deviation 10mm deviation
5bc4c8b6-36c3-57a5-a995-48308b569938 | note | Verifying Document - Image
4cbe46af-e0ac-54f5-83ad-04d74f1f931b | note | Frequency - Entire site
7ca7d4bb-623c-5e1d-94a6-4f41b862f742 | note | Inspection Type (Visual, other) - Verification
89a02266-bb57-5c21-8edb-5a7828e67078 | note | Inspection: Key - PS
b08f560f-64a9-5304-a91d-40f8ef0d84af | note | Inspection: By (Role Key) - Alliance
| checkpoint | 16 - Ready for sealing (Surface to seal texture)
5513e876-3764-52e3-86f4-38f9e968b012 | note | Inspection Point: Quality Control Activity - Mosaic surface
cb26a910-f066-54a4-8edf-5ab15c98ef2d | note | Acceptance Criteria - NTLDM 4.17.5.2
618534d0-05a7-5392-8431-5bda564ac8bd | note | Verifying Document - photos
684deb9e-3f0c-5852-a3f7-8b92640ff3c2 | note | Frequency - Entire site
bc30a152-7857-5215-b2f3-6452f8696193 | note | Inspection Type (Visual, other) - Witness
806f77c9-4418-531d-a922-ad68a030044d | note | Inspection: Key - PS
f3442672-8b5c-56a4-b616-8f981e345c82 | note | Inspection: By (Role Key) - Alliance
| checkpoint | 17 - Binder application
71e75d5c-e529-5dd2-bdee-b7931ac9a873 | note | Inspection Point: Quality Control Activity - Verify m2 treated vs litres used
8e6154e7-5151-5864-9ea5-4645d94d78c2 | note | Acceptance Criteria - -0.05
4b700aaa-c51f-5fe0-8640-bdc06c809060 | note | Verifying Document - QA operator
ff45d2ef-d315-5f65-86a7-68bc9f343667 | note | Frequency - Entire site
1d43299e-6382-545e-b1d6-ac841f2ad276 | note | Inspection Type (Visual, other) - Verification
1d20471f-48ba-5d65-9953-f74aa730cb52 | note | Inspection: Key - PS
98ef0bd3-fba7-5201-b764-7599c7872331 | note | Inspection: By (Role Key) - Alliance
| checkpoint | 18 - Traffic services
e5a63dd8-0759-59df-8fbd-2cba0c737543 | note | Inspection Point: Quality Control Activity - Marker pegs, sign & marking
2063f62d-88e9-55da-b910-1f3b625b791a | note | Acceptance Criteria - Replaced in same position/height unless specified otherwise
1bd4d9b2-a9c0-5fb9-ad2e-9a29799de450 | note | Verifying Document - Site notes
168cbf91-6d28-52c8-bc2c-7a2f23ab9eb3 | note | Frequency - Entire site
ae086561-0c06-5ad7-ae9b-308ca450f9e8 | note | Inspection Type (Visual, other) - Verification
8566788b-34e1-58ca-9c45-d7802d84bd2a | note | Inspection: Key - PS
ca5e421a-2648-5b02-a2e9-6cc524b49a6e | note | Inspection: By (Role Key) - Alliance
| checkpoint | 19 - Asset As built Data
ef45a5ff-7105-55cd-8e9a-acb90b05ee7c | note | Inspection Point: Quality Control Activity -
104a471e-c395-57bc-b8b0-4fab3b21933f | note | Acceptance Criteria - All relevant as built information collected
774ce5e3-3809-506a-862d-7b041e18ad35 | note | Verifying Document - RAMM forms
112f3211-672a-5a83-ba6b-8f41bcd49392 | note | Frequency - During Construction
236d2187-46b3-59cf-9f75-84072ced5013 | note | Inspection Type (Visual, other) - Verification
9ae81a3d-b9e8-5cd2-a1d8-8c0f0a18dc02 | note | Inspection: Key - PS
2b727b67-e699-50bb-9a49-f27ca64df2de | note | Inspection: By (Role Key) - Alliance
| checklist | DG-QA-TP018 Inspection and Test Plan (ITP) | itp | DG-QA-TP018 Inspection and Test Plan (ITP) | 45f2bc5c-246a-49b0-923f-48e53609874b
| section | 1. Receiving Inspection
| checkpoint | 1.1 - Service Locates
6045ad6a-b573-5325-b704-71fa8eeb436e | note | Acceptance Criteria - Services located by Chorus and Delta prior to wokrs commencing
b3525edd-839b-55b4-a9b6-0e5ab7fc7b9e | note | Verifying Document - Photos
0fad300b-f57a-537b-a09c-b28c1536e21d | note | Frequency - Once for each work location
78b6f9a8-3424-5033-90d1-dea405906776 | note | Inspection Type (Visual, other) - Verification
f66a400a-bf2e-5752-900d-00543df0b5f1 | note | Inspection: By (Role Key) - Downer
| checkpoint | 1.2 - Temporary Traffic Management
e68c8162-3887-5256-8efa-586e6f634e3a | note | Inspection Point: Quality Control Activity - Temporary Traffic Management to be set up on site prior to any works commencing
fbf3213b-ecb3-52c6-b5db-305eebafb5dc | note | Acceptance Criteria - Temporary Traffic Management set up by qualified STMS according to approved plans
13ff03fd-c3b4-5ed7-a425-8b094e2a542d | note | Verifying Document - Approved TM Plan
2722667a-66ea-53ca-825c-3a5b286576d0 | note | Frequency - Daily
57134c83-66af-5bed-8ac0-379b65484adb | note | Inspection Type (Visual, other) - Verification
c38cd082-f883-539d-b7be-f87c4105ece7 | note | Inspection: By (Role Key) - Downer
| checkpoint | 1.3 - Culvert Bedding
54ac98e7-e2ea-540b-9412-95948af6592a | note | Inspection Point: Quality Control Activity - Scalas to be done on subgrade
49988d8d-955b-52fc-9144-58b8a6d6aa37 | note | Acceptance Criteria - If scala test results lower than 3, add 100mm of compacted AP65
fd9f4b41-51b0-5e9e-96dc-eec787d62825 | note | Verifying Document - Photos, Field testing document
f09540a0-bde4-5fb1-a51d-a2502e066ac2 | note | Frequency - One lot of tests for each work location
3a797265-f1ee-5f2b-b87a-a2f7df9f0fe6 | note | Inspection Type (Visual, other) - Hold Point
0e8e5a55-50e8-5672-a3b9-42ef3ffeefb5 | note | Inspection: By (Role Key) - Downer
| checkpoint | 1.4 - AP65 Backfill
65d4c908-52f4-538b-81dc-d944f18261b1 | note | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
baae139e-6ef1-5605-afd6-b061b8f5f0fc | note | Acceptance Criteria - Clegg Impact Value to be greater than 25
6f3ee88b-e357-51a0-8dfc-d3fda5f58fac | note | Verifying Document - Photos, Field testing document
8834281f-396c-518a-aa81-0d40edb36a22 | note | Frequency - Every 150mm lift
e43b16b3-ff51-5a91-a8e3-05229798d2c9 | note | Inspection Type (Visual, other) - Hold Point
a0e6e6a7-136d-5c1b-8589-6bce74d4b463 | note | Inspection: By (Role Key) - Downer
| checkpoint | 1.5 - AP40 Backfill
2967c5b8-595d-5abd-8fe5-a0251daa99c1 | note | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
28a7fd18-656c-5419-8f4e-8cb41a4d815f | note | Acceptance Criteria - Clegg Impact Value to be greater than 35
de3c786f-5f82-5301-b1fc-1867a0627307 | note | Verifying Document - Photos, Field testing document
0e77f767-1dd7-55ee-8d83-60f84c907d4d | note | Frequency - Every 150mm lift
97948f30-dd5f-58ea-bfb3-2ab30f0e03dc | note | Inspection Type (Visual, other) - Hold Point
1cd7386a-021f-5157-83b5-da8c70136d32 | note | Inspection: By (Role Key) - Downer
| checkpoint | 1.6 - Pavement Strength
e33835f6-2856-5d1a-8f17-62660e0b629e | note | Inspection Point: Quality Control Activity - Clegg testing to be done on Pavement
06834782-f401-5e2d-bddf-59e9eade8dae | note | Acceptance Criteria - Clegg Impact Value to be greater than 35
0b376344-9917-5c4a-bc46-fc7132990bf7 | note | Verifying Document - Photos, Field testing document
07c982ed-2556-5943-a48d-5026ad09e2af | note | Frequency - One lot of tests for each work location
2699fe34-8793-5ba1-88a8-21bbc98953a1 | note | Inspection Type (Visual, other) - Hold Point
73f9effc-830e-5ace-a902-483bcf9d145c | note | Inspection: By (Role Key) - Downer
| checkpoint | 1.7 - Alignment
e784c8cf-0e23-5199-9483-78af6e9c3346 | note | Inspection Point: Quality Control Activity - 3 metre straight edge
5a689631-2d88-5cce-bdc5-00abd06d0515 | note | Acceptance Criteria - Maximum 10mm
debb4dd8-7b33-5a3a-8ff3-bfa2bb578038 | note | Verifying Document - Visual
28d4823c-efe9-58f9-917f-11f05c436355 | note | Frequency - One lot of tests for each work location
22726955-649b-5b97-a45d-80e0a2e5fb0c | note | Inspection Type (Visual, other) - Verification
204b270c-7136-5b27-8b22-4f72166e7db1 | note | Inspection: By (Role Key) - Downer
| section | 2. Culvert Grade
| checkpoint | Culvert Grade
| section | 3. Photos
| checkpoint | Photos
| checklist | Sealed Pavement Maintenance - Digouts all depths | itp | Sealed Pavement Maintenance - Digouts all depths | 9c31a82c-cd59-4293-9e29-d9ab6d8d66c9
| section | Details
| checkpoint | 1 - Service Locates
4c96b043-3feb-5548-b942-849a016470a1 | note | Acceptance Criteria - Services located by Chorus and Delta prior to works commencing.
116f87c4-9f2e-56e9-9631-0f8dbf398220 | note | Verifying Document - Photos
827dbe59-5676-5df6-8e73-97a95d7d9d4d | note | Frequency - Once for each work location
696a3052-01b5-54ad-a94a-e04e3c0a2ea6 | note | Inspection Type (Visual, other) - Hold Point
d4aba7df-94f7-5e1b-a166-44c49e5e3288 | note | Inspection: By - Alliance
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - AP40 Material Quality
1e255379-435c-56b4-b931-07d55c9e83fc | note | Inspection Point: Quality Control Activity - Record M4 Test Document
6d0bda3a-2023-56d3-b6a2-e433b89f0db5 | note | Acceptance Criteria - Confirm material meets M4 Spec
0f728b64-58d2-5ac2-b1df-3446a1a031e9 | note | Verifying Document - Photos
40ba5e05-7795-571d-bad2-ad083499fd98 | note | Frequency - Once for each work location
731fb0b7-b894-5e73-aa46-f4f68ccf2526 | note | Inspection Type (Visual, other) - Verification
776f4219-c2df-5842-8696-f6d7addc57af | note | Inspection: By - Alliance
| checkpoint | 3 - Scala Penetrometer
efe121ea-4473-5697-8e18-aade60e2218f | note | Inspection Point: Quality Control Activity - Scala on fault to determine digout depth
605449b0-647a-5c1a-88ff-0063d734359b | note | Verifying Document - Photos, Field testing document
85adf26b-860d-5644-844b-510cc240bf1c | note | Frequency - One set of tests for each patch
c0fe0925-8195-516b-bba2-2023d1a31cc8 | note | Inspection Type (Visual, other) - Hold Point
d4f3f492-d99d-5dd9-a7b5-05f346df007b | note | Inspection: By - Alliance
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Digout
22a3bd7e-122c-5b49-9576-b4654ed45ded | note | Inspection Point: Quality Control Activity - Digout complete to required depth. Stability of subgrade assessed
b75c115c-fd5e-5b32-ad33-fa5d601655cb | note | Acceptance Criteria - No soft spots, uneven areas or potential issues affecting roads foundations
312e675a-7542-5249-b581-f695c1dafb22 | note | Verifying Document - Visual, Photo
fa0d763e-f4bd-54c5-928d-8ebaa6bc724f | note | Inspection Type (Visual, other) - Verification
002aa14c-1f7e-55c4-8b5f-d23a9d811bab | note | Inspection: By - Alliance
| checkpoint | 5 - AP65 Backfill
f72b0414-bdd0-50ec-ab28-de31ea942b20 | note | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
ec1e3598-9111-513e-b9b9-a02517639587 | note | Acceptance Criteria - Clegg Impact Value to be greater than 25
e2b7f596-3f79-53d0-a875-c22a0ac3f22a | note | Verifying Document - Photos, Field testing document
f60bf15b-76d0-5ad3-b134-7dc40bc1c0a4 | note | Frequency - Every 150mm lift, Minimum 1 per 20m2
24a17d91-e027-59fb-a43c-b388cafac3d5 | note | Inspection Type (Visual, other) - Hold Point
617cbc89-d712-582b-8bfc-a79ad2ff29ce | note | Inspection: By - Alliance
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - AP40 Backfill
d7f154ed-d758-57c9-bc9a-0add660f57d8 | note | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
79ed613e-6038-566b-b940-4ad553a34663 | note | Acceptance Criteria - Clegg Impact Value to be greater than 35
bbbc6467-e852-562d-ae00-8992d224dc1a | note | Verifying Document - Photos, Field testing document
c9d6e1e5-cbcc-54e2-826d-c1b96807e8ad | note | Frequency - Every 150mm lift, Minimum 1 per 20m2
f67c2871-96ed-54f8-8b78-e6de7034a80f | note | Inspection Type (Visual, other) - Hold Point
1e6fb061-1113-553b-9f01-6519d0e0b8ca | note | Inspection: By - Alliance
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Ready for sealing
6d2f8eab-36c1-5378-9b86-60304c1ecaac | note | Verifying Document - Photo
2700deaf-17e8-5503-b0e7-7e54d277f1c4 | note | Inspection Type (Visual, other) - Verification
ef91bce4-04d2-5c8f-b1ac-41d45e026974 | note | Inspection: By - Alliance
| checklist | Sealed Pavement Maintenance - Stabilise (emulsion) | itp | Sealed Pavement Maintenance - Stabilise (emulsion) | 888e572a-ceca-405d-976f-4d138ff663c8
| section | Details
| checkpoint | 1 - Cement
782e8cc6-223f-5f0c-a326-b517c34c6fe4 | note | Inspection Point: Quality Control Activity - Cement added and raked evenly
c2762e4c-950d-511c-8536-5d66919de1da | note | Acceptance Criteria - 1 Bag per 10 m2, raked evenly
8050c2e1-54a2-5512-9697-73531f646519 | note | Verifying Document - Visual, photo
a33ddb76-a6c5-59a7-915e-4f054642dcbb | note | Frequency - Once per patch
4a5b6b29-ecca-566a-aabb-21576edf3967 | note | Inspection Type (Visual, other) - Verification
1b1c3c71-fdc0-5c9d-b4db-9f459f1e00af | note | Inspection: By - Alliance
| checkpoint | 2 - Emulsion Mill
57162398-98cc-51f6-97c2-5d5f13a89881 | note | Inspection Point: Quality Control Activity - Litres of Emulsion used per m2
c95b2406-96e9-59b4-abc6-e478ea910e42 | note | Acceptance Criteria - Aim 8L per m2
904c6666-6de4-5259-b151-b3847bef497a | note | Verifying Document - Add comment of Litres used
ba09601d-c037-5179-9949-a29f7ae1f989 | note | Frequency - Once per patch
e7f5cffa-bb17-5cce-9d75-dbe0d1b996d8 | note | Inspection Type (Visual, other) - Verification
626c67cb-aaac-5613-84e5-650da8bd4a7d | note | Inspection: By - Alliance
| checkpoint | 3 - Pavement Stength
9e5e8089-823d-564e-af97-2554d6cda2c3 | note | Inspection Point: Quality Control Activity - Clegg testing to be done
564d4603-dea2-5684-8556-1f3d10dcb3f6 | note | Acceptance Criteria - Clegg Impact Value to be greater than 35
28584bc6-caa3-56fe-99af-8874d14b4bd5 | note | Verifying Document - Photos, Field testing document
2fdadd6f-1bfd-5c83-9b36-efc55fbf7e3d | note | Frequency - Minimum 1 per 20m2
584bf8c6-a203-5398-ab06-95e11c09caee | note | Inspection Type (Visual, other) - Hold Point
cd53178d-4707-569d-95d1-bc7441bf00cb | note | Inspection: By - Alliance
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Ready for Sealing
62239452-8a36-5db7-bf42-1fca3a663fc7 | note | Verifying Document - Photo
ee60067d-773b-5d09-9cb0-e3b0cbf7a85e | note | Inspection Type (Visual, other) - Verification
6635e920-67a9-5bf4-98ef-47f426ebf684 | note | Inspection: By - Alliance