## SAC Treatment
| PAVEMENT RENEWALS INSPECTION AND TEST PLAN – Structural AC Treatment | [6 empty] | Doc No: Pavement Renewals
| Wensley road Site 1 | [6 empty] | Rev: 1 Pages: 2
| RP 397 - 639 | [6 empty] | Prepared: | TP & BC | Date: | 2025-01-31
[8 empty] | Approved: |  | Date:
ACTIVITY DESCRIPTION |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQ. | ACCEPTANCE CRITERIA | INSPECTORATE V/W/H |  |  |  | Responsible Person | RECORDS / REMARKS
[6 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | (print name) | incl NCR ref
[6 empty] | Type | Assessor | Description |  |  | Sign & date if appropriate
Preliminary and General
Set-out / Site preparation
Setout |  | Survey | Best Practice | Per installation | As presented on the construction drawings set | V | Site Engineer/Supervisor
Services (includes Traffic Count Loops and Traffic Signal Detector Loops) |  | Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth) | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | H | Site Engineer/Supervisor | Hold point - No excavation is to be commenced until services are located and accounted for
Cultural/Heritage Risk Assessment |  | Notification | NZTA Cultural & Heritage Risk Model | Before work commences | Local iwi has been notified of intent to start work | H | Renewals Engineer | Check and confirm if an Iwi representative need to be on site
Notification of intention to start work |  | Notification |  | Before work commences | Letter drop to local residents | H | Site Engineer/ Comms Manager | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
Archaeological Risk |  | Toolbox meeting | NZTA Cultural & Heritage Risk Model. Tasman DC ADP. | Before work commences | Toolbox meeting held covering accidental discovery protocol | H | Site Supervisor | Hold point - No excavation is to be commenced until toolbox meeting is held
Traffic Management | TMP | Visual check | CoPTTM/ Risk Based Assesment | Before traffic management set up | TMP checked and approved - Plans approved - Current EED | H | TTM Planner | Hold point - No traffic management is to be set up until TMP has been checked and approved
| Setup | Visual check | Traffic Management Plan | Before work commences | Traffic management complies with TMP | H | STMS | Hold point - No physical works are to be commenced until necessary traffic management is in place
Preliminary Works
Shoulder & driveway stripping |  | Visual check | On site |  | Shoulder & driveway stripping completed | H | Site Engineer/Supervisor | Hold point - Communicate with affected residents
Plants & Equipmens are suitable to be on site/road. | Compaction | Inspection | RQP | Prior to commencement | Legal REGO, WOF & suitable to use | H | Operation Manager | Required by appendix 6.3
Pavement
Imported Basecourse Materials Testing
Material source & production properties Note: Running course to be produced from the same type and source of material as the basecourse. | PSD (Particle Size Distribution) | Wet Sieving Test | TNZ M/4:2006 NZS 4407 :1991 Test 3.8.1 | 1-400m3 – 1 test | TNZ M/4: Cl.4.2.3 | H | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road
| Broken Faces | Broken Face Test | TNZ M/4: 2006 NZS 4407 :1991 Test 3.14 | 1500-4000m3 – 3 tests | Aggregate broken face content in each of the 3 aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces | V | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road
|  |  |  | >4000m3 – 1 test per 1000m3 |  | H
| Plasticity Index | Plasticity Index Test | NZS 4407 :1991 Test 3.6 |  | PI ≤ 5 | V | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road
|  |  | TNZ M/4: 2006 |  |  | H
| Lab tests: |  | NZS 4402: 1986 MDD and W/C Test 4.1.3 | The lesser of: | MDD as the higher of the two results from lab and field | V | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road
| Optimum water content (OWC) | -NZ vibrating hammer compaction test at OWC | NZS 4407:1991 Solid Density Test 3.7 | a) 1 test per stockpile or new seam | OWC as determined in the lab
| Solid Density | -Solid density | NZS 4407:1991 W/C Test 3.1 | b) 1 test every 5000m2 (in place) | When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples)
TNZ B/2: 2005
| Maximum Dry Density (MDD) | MDD at OWC – in lab | NZS 4402: 1986 MDD and W/C Test 4.1.3 | The lesser of: | MDD as the higher of the two results from lab and field | H | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road
|  |  | TNZ B/2: 2005 | a) 1 test per stockpile or new seam | Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset
b) 1 test every 5000m2 (in place)
| Crushing Resistance | TNZ M/4 Crushing Resistance Test | TNZ M/4: 2006 NZS 4407 :1991 Test 3.10 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | V | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road for a source <2 years old
H
| Californian Bearing Ratio (CBR) | TNZ M/4 | NZS 4402: 1986 Test 4.13 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock. | Soaked CBR ≥ 80% when compacted/tested in accordance with either test | V | Site Engineer/Supervisor | Hold Point – All production and source testing results to be provided prior to placement of material on road for a source <2 years old
|  | NZ vibrating hammer compaction test at OMC | NZS 4407: 1991 Test CBR 3.15 |  |  | H
|  | Determination of CBR. | TNZ M/4: 2006
| Weathering | Weathering quality index test | NZS 4407:1991 Test 3.11 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Must have quality index of AA, AB, AC, BA, BB or CA | V | Site Engineer/Supervisor | Hold Point – All production and source testing results to be provided prior to placement of material on road for a source <2 years old
|  |  | TNZ M/4:2006 |  |  | H
Construction QA
Construction | AP40 Compaction | NDM – maximum dry density | NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | Base: N/A | V | Site Engineer/Supervisor | Hold Point – SAC layer not to be laid until passing results are achieved (ie average & minimum MDD)
[5 empty] | SubBase: Average ≥ 95% MDD Minimum ≥ 92% MDD | H
| Layer thickness | TNZ B/2 | Site Survey during contruction | 1 test per 50m | Overlay Thickness meets design | V | Site Engineer/Supervisor | Verification Point
| Management of coal tar | Safe Handling & Dumping | PPE & recoding volume | Daily during stage | Coal tar to be loaded & dumped safely with appropriate PPE & record manifest upto date. | V | Site Engineer/Supervisor | Verification Point
| Verify Subgrade strength | Designer's recommendation | Scala Penetrometer test | Every 20m, alternating lanes, except where D/Os completed previouslty | CBR > 4. Each 1 less CBR equivilent to an extra 100mm of pavement required | H | Site Engineer/Supervisor | Hold point - no basecourse layer to be added until CBR is greater than 4
| Placement of Geotextile | As per the spec | Visual inspection | every 50m, each lane | Well covered & pressed onto the subgrade | V
| Work around Protected tree | Involving an arborist while working near the tree | Stand over on site | Around 2 Protected trees | As agreed by An arborist | W | Renewals Engineer | Witness point
| Subcontractor involvement (Ezi sweep, Independent Kerb & channel, Safe Hire, Dwyer & Bird) | Downer's supervisor to guide subcontractors for quality work | Reports, Photos | As required | As agreed by the site supervisor | H | Site Engineer/Supervisor | Hold point
| Footpath base | Clegg Hammer test | Report | Every 50m | Reading greater than 25 | V | Site Engineer/Supervisor
| Reconstruct existing accessway | Grade & Tie in levels onto footpath | Checking grade | Each accessway | Constrcut as per the design & check levels regularly | H | Site Engineer/Supervisor | Holdpoint
| Subsoil drainage | Adequate length & grade for pipes | Visual inspection | Along the site | Connect subsoil drainge to existing sump with adequate fall | V | Site Engineer/Supervisor
| Subcontractor involvement for other utility operators (DELTA, Downer Telco, Powertech) | Renewal Engineer to get paperwork to respective utility operators | Reports, Photos | Each designated site where subcontractors work | CBR greater than 4 | H | Site Engineer/Supervisor | Hold point - no basecourse layer to be added until CBR is greater than 4
| Visual appearance | TNZ B/2 | Visual inspection after sweeping | Immediately prior to sealing | Well compacted & graded | V | Site Engineer/Supervisor | Hold Point – no surfacing layer is to be applied until passing results are achieved
H
Pavement finished surface
SAC
Structural AC compaction |  | NDM | NDM acceptance against mix designs based on M10: 2020. Photos and paving records for each layer. | 20m intervals for each compacted layer, alternating lanes in accordance with rolling patterns. | In accordance with M10 and Mix Design. Target air voids 4% | H | Sealing Manager | Hold point
Structural AC layering |  | Survey |  | Survey check of finished Structural and Top Surface Layers to confim layer thickness. | Meets design thickness +/- 10mm | H | Site Enginner / Sealing Manager | Hold point
Finished surface crossfall |  | Survey |  | Survey check of Top Surface and Smart level | Finshed surface crossfall target 3% Min 2% - Max 4% | H | Site Enginner / Sealing Manager | Hold point
Site Reinstatement / Clearance
Traffic Services | Marker pegs/ Signs/Markings/RRPMs Replaced | TNZ C/20: 2003 | Visual inspection | All signs/markers | Replaced in same position, height etc | V | Site Engineer/Supervisor | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
H
Grassing |  | Visual check |  | All areas requiring grassing | Grassing has been done where required | W | Site Engineer/Supervisor
Drains cleared |  | Visual check |  | All drains, after all other works | Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated | W
Traffic Management Removed |  | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W | Site Engineer/Supervisor
Site left clean & tidy |  | Visual check |  | After vacating site | · Stockpiles removed | V | Site Engineer/Supervisor
· Plant removed
· Litter cleared from site
As Built Records
Collect asset data |  | SHDOM (SM050) |  | During construction | All relevant as built information collected. | V | Renewals Engineer
Enter asset data into RAMM and/or register(s) |  | SHDOM (SM050) | RAMM | At completion of work. | All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file. | H | Asset Engineer | Hold Point – project cannot be closed until data entered.
Quality Assurance Close Out by: | _______________________________________________ |  | Date: _____________
(signature)
________________________________________________
(name)
This record to contract file.