## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Wensley Road Site 1 ITP | itp |  |  |  |  | Wensley Road Site 1 ITP
section | Set-out / Site preparation
checkpoint | Setout
label | VERIFICATION ACTIVITY - Survey
label | METHODS OR REFERENCE - Best Practice
label | FREQ. - Per installation
label | ACCEPTANCE CRITERIA - As presented on the construction drawings set
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
checkpoint | Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Zero service strikes
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold point - No excavation is to be commenced until services are located and accounted for
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Cultural/Heritage Risk Assessment
label | VERIFICATION ACTIVITY - Notification
label | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Local iwi has been notified of intent to start work
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Renewals Engineer
label | INSPECTORATE: Description - Check and confirm if an Iwi representative need to be on site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Notification of intention to start work
label | VERIFICATION ACTIVITY - Notification
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Letter drop to local residents
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Engineer/ Comms Manager
label | INSPECTORATE: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Archaeological Risk
label | VERIFICATION ACTIVITY - Toolbox meeting
label | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model. Tasman DC ADP.
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Toolbox meeting held covering accidental discovery protocol
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Supervisor
label | INSPECTORATE: Description - Hold point - No excavation is to be commenced until toolbox meeting is held
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Traffic Management - TMP
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - CoPTTM/ Risk Based Assesment
label | FREQ. - Before traffic management set up
label | ACCEPTANCE CRITERIA - TMP checked and approved
label | ○ Plans approved
label | ○ Current EED
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - TTM Planner
label | INSPECTORATE: Description - Hold point - No traffic management is to be set up until TMP has been checked and approved
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Traffic Management - Setup
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - Traffic Management Plan
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - STMS
label | INSPECTORATE: Description - Hold point - No physical works are to be commenced until necessary traffic management is in place
holdpoint | AUTHORITY HOLDPOINT
section | Preliminary Works
checkpoint | Shoulder & driveway stripping
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - On site
label | ACCEPTANCE CRITERIA - Shoulder & driveway stripping completed
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold point - Communicate with affected residents
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Plants & Equipmens are suitable to be on site/road. - Compaction
label | VERIFICATION ACTIVITY - Inspection
label | METHODS OR REFERENCE - RQP
label | FREQ. - Prior to commencement
label | ACCEPTANCE CRITERIA - Legal REGO, WOF & suitable to use
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Operation Manager
label | INSPECTORATE: Description - Required by appendix 6.3
holdpoint | AUTHORITY HOLDPOINT
section | Pavement
checkpoint | Material source & production properties
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - Wet Sieving Test
label | METHODS OR REFERENCE - TNZ M/4:2006, NZS 4407 :1991 Test 3.8.1
label | FREQ. - 1-400m3 – 1 test
label | ACCEPTANCE CRITERIA - TNZ M/4: Cl.4.2.3
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Renewals Engineer
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Material source & production properties - Broken Faces (1)
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - Broken Face Test
label | METHODS OR REFERENCE - TNZ M/4: 2006, NZS 4407 :1991 Test 3.14
label | FREQ. - 1500-4000m3 – 3 tests
label | ACCEPTANCE CRITERIA - Aggregate broken face content in each of the 3 aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Renewals Engineer
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
checkpoint | Material source & production properties - Broken Faces (2)
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - Broken Face Test
label | METHODS OR REFERENCE - TNZ M/4: 2006, NZS 4407 :1991 Test 3.14
label | FREQ. - >4000m3 – 1 test per 1000m3
label | ACCEPTANCE CRITERIA - Aggregate broken face content in each of the 3 aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Renewals Engineer
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Material source & production properties - Plasticity Index (1)
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - Plasticity Index Test
label | METHODS OR REFERENCE - NZS 4407 :1991 Test 3.6
label | ACCEPTANCE CRITERIA - PI ≤ 5
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Renewals Engineer
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
checkpoint | Material source & production properties - Plasticity Index (2)
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - Plasticity Index Test
label | METHODS OR REFERENCE - TNZ M/4: 2006
label | ACCEPTANCE CRITERIA - PI ≤ 5
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Renewals Engineer
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Material source & production properties - Lab tests: Optimum water content (OWC), Solid Density
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - NZ vibrating hammer compaction test at OWC
label | ○ Solid density
label | METHODS OR REFERENCE - NZS 4402: 1986 MDD and W/C Test 4.1.3
label | ○ NZS 4407:1991 Solid Density Test 3.7
label | ○ NZS 4407:1991 W/C Test 3.1
label | ○ TNZ B/2: 2005
label | FREQ. - The lesser of:
label | a) 1 test per stockpile or new seam
label | b) 1 test every 5000m2 (in place)
label | ACCEPTANCE CRITERIA - MDD as the higher of the two results from lab and field
label | ○ OWC as determined in the lab
label | ○ When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples)
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Renewals Engineer
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
checkpoint | Material source & production properties - Maximum Dry Density (MDD)
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - MDD at OWC – in lab
label | METHODS OR REFERENCE - NZS 4402: 1986 MDD and W/C Test 4.1.3, TNZ B/2: 2005
label | FREQ. - The lesser of:
label | a) 1 test per stockpile or new seam
label | b) 1 test every 5000m2 (in place)
label | ACCEPTANCE CRITERIA - MDD as the higher of the two results from lab and field
label | ○ Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Renewals Engineer
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Material source & production properties - Crushing Resistance (1)
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - TNZ M/4 Crushing Resistance Test
label | METHODS OR REFERENCE - TNZ M/4: 2006, NZS 4407 :1991 Test 3.10
label | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Renewals Engineer
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source <2 years old
checkpoint | Material source & production properties - Crushing Resistance (2)
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - TNZ M/4 Crushing Resistance Test
label | METHODS OR REFERENCE - TNZ M/4: 2006, NZS 4407 :1991 Test 3.10
label | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Renewals Engineer
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source <2 years old
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Material source & production properties - Californian Bearing Ratio (CBR) (1)
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - TNZ M/4
label | METHODS OR REFERENCE - NZS 4402: 1986 Test 4.13
label | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock.
label | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with either test
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source <2 years old
checkpoint | Material source & production properties - Californian Bearing Ratio (CBR) (2)
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - NZ vibrating hammer compaction test at OMC
label | ○ Determination of CBR.
label | METHODS OR REFERENCE - NZS 4407: 1991 Test CBR 3.15, TNZ M/4: 2006
label | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock.
label | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with either test
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source <2 years old
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Material source & production properties - Weathering (1)
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - Weathering quality index test
label | METHODS OR REFERENCE - NZS 4407:1991 Test 3.11
label | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source <2 years old
checkpoint | Material source & production properties - Weathering (2)
label | Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - Weathering quality index test
label | METHODS OR REFERENCE - TNZ M/4:2006
label | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source <2 years old
holdpoint | AUTHORITY HOLDPOINT
section | Construction QA
checkpoint | AP40 Compaction (1)
label | VERIFICATION ACTIVITY - NDM – maximum dry density
label | METHODS OR REFERENCE - NZS 4407: 1991, Test 4.2.2. TNZ B/2: 2005
label | FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | ACCEPTANCE CRITERIA - Base: N/A
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold Point – SAC layer not to be laid until passing results are achieved (ie average & minimum MDD)
checkpoint | AP40 Compaction (2)
label | VERIFICATION ACTIVITY - NDM – maximum dry density
label | METHODS OR REFERENCE - NZS 4407: 1991, Test 4.2.2. TNZ B/2: 2005
label | FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | ACCEPTANCE CRITERIA - SubBase: Average ≥ 95% MDD
label | ○ Minimum ≥ 92% MDD
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold Point – SAC layer not to be laid until passing results are achieved (ie average & minimum MDD)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Layer thickness
label | VERIFICATION ACTIVITY - TNZ B/2
label | METHODS OR REFERENCE - Site Survey during contruction
label | FREQ. - 1 test per 50m
label | ACCEPTANCE CRITERIA - Overlay Thickness meets design
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Verification Point
checkpoint | Management of coal tar
label | VERIFICATION ACTIVITY - Safe Handling & Dumping
label | METHODS OR REFERENCE - PPE & recoding volume
label | FREQ. - Daily during stage
label | ACCEPTANCE CRITERIA - Coal tar to be loaded & dumped safely with appropriate PPE & record manifest upto date.
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Verification Point
checkpoint | Verify Subgrade strength
label | VERIFICATION ACTIVITY - Designer's recommendation
label | METHODS OR REFERENCE - Scala Penetrometer test
label | FREQ. - Every 20m, alternating lanes, except where D/Os completed previouslty
label | ACCEPTANCE CRITERIA - CBR > 4. Each 1 less CBR equivilent to an extra 100mm of pavement required
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold point - no basecourse layer to be added until CBR is greater than 4
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Placement of Geotextile
label | VERIFICATION ACTIVITY - As per the spec
label | METHODS OR REFERENCE - Visual inspection
label | FREQ. - every 50m, each lane
label | ACCEPTANCE CRITERIA - Well covered & pressed onto the subgrade
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
checkpoint | Work around Protected tree
label | VERIFICATION ACTIVITY - Involving an arborist while working near the tree
label | METHODS OR REFERENCE - Stand over on site
label | FREQ. - Around 2 Protected trees
label | ACCEPTANCE CRITERIA - As agreed by An arborist
label | INSPECTORATE: Type - W
label | INSPECTORATE: Assessor - Renewals Engineer
label | INSPECTORATE: Description - Witness point
checkpoint | Subcontractor involvement (Ezi sweep, Independent Kerb & channel, Safe Hire, Dwyer & Bird)
label | VERIFICATION ACTIVITY - Downer's supervisor to guide subcontractors for quality work
label | METHODS OR REFERENCE - Reports, Photos
label | FREQ. - As required
label | ACCEPTANCE CRITERIA - As agreed by the site supervisor
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold point
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Footpath base
label | VERIFICATION ACTIVITY - Clegg Hammer test
label | METHODS OR REFERENCE - Report
label | FREQ. - Every 50m
label | ACCEPTANCE CRITERIA - Reading greater than 25
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
checkpoint | Reconstruct existing accessway
label | VERIFICATION ACTIVITY - Grade & Tie in levels onto footpath
label | METHODS OR REFERENCE - Checking grade
label | FREQ. - Each accessway
label | ACCEPTANCE CRITERIA - Constrcut as per the design & check levels regularly
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Holdpoint
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Subsoil drainage
label | VERIFICATION ACTIVITY - Adequate length & grade for pipes
label | METHODS OR REFERENCE - Visual inspection
label | FREQ. - Along the site
label | ACCEPTANCE CRITERIA - Connect subsoil drainge to existing sump with adequate fall
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
checkpoint | Subcontractor involvement for other utility operators (DELTA, Downer Telco, Powertech)
label | VERIFICATION ACTIVITY - Renewal Engineer to get paperwork to respective utility operators
label | METHODS OR REFERENCE - Reports, Photos
label | FREQ. - Each designated site where subcontractors work
label | ACCEPTANCE CRITERIA - CBR greater than 4
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold point - no basecourse layer to be added until CBR is greater than 4
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Visual appearance (1)
label | VERIFICATION ACTIVITY - TNZ B/2
label | METHODS OR REFERENCE - Visual inspection after sweeping
label | FREQ. - Immediately prior to sealing
label | ACCEPTANCE CRITERIA - Well compacted & graded
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold Point – no surfacing layer is to be applied until passing results are achieved
checkpoint | Visual appearance (2)
label | VERIFICATION ACTIVITY - TNZ B/2
label | METHODS OR REFERENCE - Visual inspection after sweeping
label | FREQ. - Immediately prior to sealing
label | ACCEPTANCE CRITERIA - Well compacted & graded
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold Point – no surfacing layer is to be applied until passing results are achieved
holdpoint | AUTHORITY HOLDPOINT
section | SAC
checkpoint | Structural AC Compaction
label | VERIFICATION ACTIVITY - NDM
label | METHODS OR REFERENCE - NDM acceptance against mix designs based on M10: 2020. Photos and paving records for each layer.
label | FREQ. - 20m intervals for each compacted layer, alternating lanes in accordance with rolling patterns.
label | ACCEPTANCE CRITERIA - In accordance with M10 and Mix Design. Target air voids 4%
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Sealing Manager
label | INSPECTORATE: Description - Hold point
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Structural AC layering
label | VERIFICATION ACTIVITY - Survey
label | FREQ. - Survey check of finished Structural and Top Surface Layers to confim layer thickness.
label | ACCEPTANCE CRITERIA - Meets design thickness +/- 10mm
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Enginner / Sealing Manager
label | INSPECTORATE: Description - Hold point
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Finished surface crossfall
label | VERIFICATION ACTIVITY - Survey
label | FREQ. - Survey check of Top Surface and Smart level
label | ACCEPTANCE CRITERIA - Finshed surface crossfall target 3%
label | ○ Min 2% - Max 4%
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Enginner / Sealing Manager
label | INSPECTORATE: Description - Hold point
holdpoint | AUTHORITY HOLDPOINT
section | Site Reinstatement / Clearance
checkpoint | Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced (1)
label | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | METHODS OR REFERENCE - Visual inspection
label | FREQ. - All signs/markers
label | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
checkpoint | Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced (2)
label | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | METHODS OR REFERENCE - Visual inspection
label | FREQ. - All signs/markers
label | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
label | INSPECTORATE: Description - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Grassing
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - All areas requiring grassing
label | ACCEPTANCE CRITERIA - Grassing has been done where required
label | INSPECTORATE: Type - W
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
checkpoint | Drains cleared
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - All drains, after all other works
label | ACCEPTANCE CRITERIA - Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated
label | INSPECTORATE: Type - W
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
checkpoint | Traffic Management Removed
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - When safe, after all physical works completed
label | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | INSPECTORATE: Type - W
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
checkpoint | Site left clean & tidy
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - After vacating site
label | ACCEPTANCE CRITERIA - Stockpiles removed
label | ○ Plant removed
label | ○ Litter cleared from site
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Site Engineer/Supervisor
section | As Built Records
checkpoint | Collect asset data
label | VERIFICATION ACTIVITY - SHDOM (SM050)
label | FREQ. - During construction
label | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | INSPECTORATE: Type - V
label | INSPECTORATE: Assessor - Renewals Engineer
checkpoint | Enter asset data into RAMM and/or register(s)
label | VERIFICATION ACTIVITY - SHDOM (SM050)
label | METHODS OR REFERENCE - RAMM
label | FREQ. - At completion of work.
label | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | INSPECTORATE: Type - H
label | INSPECTORATE: Assessor - Asset Engineer
label | INSPECTORATE: Description - Hold Point – project cannot be closed until data entered.
holdpoint | AUTHORITY HOLDPOINT