## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - SP1 Pump Station Structural Works | itp |  |  |  |  | ITP - SP1 Pump Station Structural Works
section | Details
checkpoint | 1 - Footings (1)
label | ACTIVITY TASK - Excavation
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Upon completion of excavated footings. Confirm dimensions on IFC drawings
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey confirmation
checkpoint | 1 - Footings (2)
label | ACTIVITY TASK - Subgrade
label | ACCEPTANCE CRITERIA - Geotech inspection minimum 100Kpa bearing capacity
label | FREQUENCY - Upon completion of excavated footings
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Geotech inspection
holdpoint | HOLD POINT
checkpoint | 2 - Footings
label | ACTIVITY TASK - Concrete
label | ACCEPTANCE CRITERIA - 10 MPa
label | FREQUENCY - Check dispatch docket prior to pouring
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Dispatch docket
holdpoint | HOLD POINT
checkpoint | 3 - Foundation Slab (1)
label | ACTIVITY TASK - Hardfill
label | ACCEPTANCE CRITERIA - 95% MDD
label | FREQUENCY - At finished level
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Geotechnical engineers report
holdpoint | HOLD POINT
checkpoint | 3 - Foundation Slab (2)
label | ACTIVITY TASK - Geogrid and Bidum
label | ACCEPTANCE CRITERIA - Triaxial Geogrid Tensar TX170
label | ○ Bidum A19
label | FREQUENCY - Each EQ layer
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per manufacturers specifications
checkpoint | 3 - Foundation Slab (3)
label | ACTIVITY TASK - Formwork
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Throughout construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Formwork check sheet
checkpoint | 4 - Foundation Slab
label | ACTIVITY TASK - Reinforcing
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Throughout construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Mill Certs, Reinforcing check sheet
checkpoint | 5 - Foundation Slab
label | ACTIVITY TASK - Concrete
label | ACCEPTANCE CRITERIA - 50.0MPa
label | ○ Visual Inspection
label | ○ Crush test reports
label | FREQUENCY - Check dispatch docket prior to pouring
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Concrete Pre-Pour Check sheet
label | ○ Mix from certified plant
holdpoint | HOLD POINT
checkpoint | 6 - Sloped Floor Slab
label | ACTIVITY TASK - Formwork
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Throughout construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Formwork check sheet
checkpoint | 7 - Sloped Floor Slab
label | ACTIVITY TASK - Reinforcing
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Throughout construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Mill Certs Reinforcing check sheet
checkpoint | 8 - Sloped Floor Slab
label | ACTIVITY TASK - Concrete
label | ACCEPTANCE CRITERIA - 50.0 MPa
label | ○ Visual Inspection
label | ○ Crush test reports
label | FREQUENCY - Check dispatch docket prior to pouring
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Concrete Pre-Pour Check sheet
label | ○ Mix from certified plant
holdpoint | HOLD POINT
checkpoint | 9 - Install precast panels
label | ACTIVITY TASK - Lifting/Rigging
label | ACCEPTANCE CRITERIA - Approved lift plan
label | FREQUENCY - Communicated/signed prior to any lifting
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Implemented Lift Plan
holdpoint | HOLD POINT
checkpoint | 10 - Cast insitu stitch joints (1)
label | ACTIVITY TASK - Formwork
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Throughout construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Formwork check sheet
checkpoint | 10 - Cast insitu stitch joints (2)
label | ACTIVITY TASK - Reinforcing
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Throughout construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Mill certs, Reinforcing check sheet
checkpoint | 10 - Cast insitu stitch joints (3)
label | ACTIVITY TASK - Joint seal
label | ACCEPTANCE CRITERIA - Visual inspection
label | FREQUENCY - Upon installation
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Sikaswell S2 installed in accordance with manufacturers guidelines
checkpoint | 10 - Cast insitu stitch joints (4)
label | ACTIVITY TASK - Concrete
label | ACCEPTANCE CRITERIA - 50.0MPa
label | ○ Visual Inspection
label | ○ Crush test reports
label | FREQUENCY - Check dispatch docket prior to pouring
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Concrete Pre-Pour Check sheet
label | ○ Mix from certified plant
holdpoint | HOLD POINT
checkpoint | 11 - Cast insitu walls in Discharge basin (1)
label | ACTIVITY TASK - Formwork
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Throughout construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Formwork check sheet
checkpoint | 11 - Cast insitu walls in Discharge basin (2)
label | ACTIVITY TASK - Reinforcing
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Throughout construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Mill Certs Reinforcing check sheet
checkpoint | 11 - Cast insitu walls in Discharge basin (3)
label | ACTIVITY TASK - Joint seal
label | ACCEPTANCE CRITERIA - Visual inspection
label | FREQUENCY - Upon installation
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Sikaswell S2 installed in accordance with manufacturers guidelines
checkpoint | 11 - Cast insitu walls in Discharge basin (4)
label | ACTIVITY TASK - Concrete Fixings
label | ACCEPTANCE CRITERIA - Visual inspection
label | FREQUENCY - Each Fixing/drill hole
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Drill holes cleaned with compressed air
label | ○ Anchors installed in accordance with manufacturers guidelines
label | ○ 8.8 galvanized threaded rod fixed with Hilti HY200 epoxy
checkpoint | 11 - Cast insitu walls in Discharge basin (5)
label | ACTIVITY TASK - Concrete
label | ACCEPTANCE CRITERIA - 50.0MPa
label | ○ Visual Inspection
label | ○ Crush test reports
label | FREQUENCY - Check dispatch docket prior to pouring
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Concrete Pre-Pour Check sheet
label | ○ Mix from certified plant
holdpoint | HOLD POINT
checkpoint | 12 - Cast insitu retention walls (1)
label | ACTIVITY TASK - Formwork
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Throughout construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Formwork check sheet
checkpoint | 12 - Cast insitu retention walls (2)
label | ACTIVITY TASK - Reinforcing
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Throughout construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Mill Certs Reinforcing check sheet
checkpoint | 12 - Cast insitu retention walls (3)
label | ACTIVITY TASK - Concrete Fixings
label | ACCEPTANCE CRITERIA - Visual inspection
label | FREQUENCY - Each Fixing/drill hole
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Drill holes cleaned with compressed air
label | ○ Anchors installed in accordance with manufacturers guidelines
label | ○ 8.8 galvanized threaded rod fixed with Hilti HY200 epoxy
checkpoint | 12 - Cast insitu retention walls (4)
label | ACTIVITY TASK - Concrete
label | ACCEPTANCE CRITERIA - 50.0MPa
label | ○ Visual Inspection
label | ○ Crush test reports
label | FREQUENCY - Check dispatch docket prior to pouring
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Concrete Pre-Pour Check sheet
label | ○ Mix from certified plant
holdpoint | HOLD POINT
checkpoint | 13 - Cast insitu roof slab (1)
label | ACTIVITY TASK - Formwork
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Throughout construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Formwork check sheet
checkpoint | 13 - Cast insitu roof slab (2)
label | ACTIVITY TASK - Reinforcing
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Throughout construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Mill Certs Reinforcing check sheet
checkpoint | 13 - Cast insitu roof slab (3)
label | ACTIVITY TASK - Concrete
label | ACCEPTANCE CRITERIA - 50.0MPa
label | ○ Visual Inspection
label | ○ Crush test reports
label | FREQUENCY - Check dispatch docket prior to pouring
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Concrete Pre-Pour Check sheet
label | ○ Mix from certified plant
holdpoint | HOLD POINT