## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Laydowns | itp |  |  |  |  | ITP - Laydowns
section | Preconstruction
checkpoint | Design Drawings
label | Issued for Construction Drawings available
holdpoint | United Civil Hold Point
checkpoint | Survey & Setout
label | Verification of road alignment and layout
label | Alignment with approved IFC Drawings
holdpoint | United Civil Hold Point
checkpoint | Site Clearing
label | Visual inspection of cleared area
label | Free from vegetation, debris, and obstructions
holdpoint | United Civil Hold Point
section | Material Procurement
checkpoint | Material Approval
label | Approval of road materials (e.g., aggregates, subbase, basecourses
label | Compliance with KDC EES2011 specifications and standards and IFC Drawings
label | Material Test Certificates - Gradings, CBR, Crushing Resistance
holdpoint | CHINT / United Civil Hold Point
section | Construction - Subgrade
checkpoint | Excavation/Grading
label | Inspect grading and levelling of subgrade
label | Uniform surface with proper slope and drainage
label | Visual Inspection and Measurements
label | Every Internal Road
holdpoint | United Civil Hold Point
checkpoint | Compaction
label | Field density test
label | Achieves required compaction (Scalar Penetrometer with min of 2 blows per 100mm) Tests every 100m
label | Scalar Penetrometer test check sheet
label | For each section
label | Hold Point for United Civil
holdpoint | United Civil Hold Point
section | Subgrade Improvements (Where Required)
checkpoint | Identify areas of Undercut
label | Identify areas of undercut and liaise with Client
checkpoint | Excavate Undercut
label | Excavate a minimum of 200mm in depth full width of the road
label | Any free water has a path off the road in a controlled manor
label | Visual inspection of subgrade with Client
label | Undercut ITC completed
checkpoint | Geotextile Installation
label | Visual inspection of geotextile placement for each section
label | Correctly installed with proper overlap and anchorage
label | Delivery Dockets
checkpoint | Backfill Undercut
label | Visual inspection of backfilled material
label | Compaction to be static compaction only
label | Proof rolled with no obvious weaving or areas of instability
section | Construction - Base and Subbase
checkpoint | Material Placement
label | Inspection of base and subbase layers
label | Compliance with IFC Drawings and Material Specifications
label | 100mm thickness of Gap40 and 50mm of Gap20
label | ITC Completed for Laydowns
checkpoint | Compaction
label | Proof Roll
label | Visual Inspection of Compacted Base and Basecourse
label | Each Laydown
holdpoint | United Civil Hold Point
checkpoint | Level and Alignment
label | Visual Inspection of Alignment
label | Compliance with design tolerances
label | Each Laydown
holdpoint | United Civil Hold Point
section | Construction - Surface Layer As Required
checkpoint | Aggregate Placement
label | Inspect placement of aggregate layer
label | Even distribution; meets design thickness of 50mm
label | ITC Completed for Laydowns
label | Each Laydown
checkpoint | Surface Compaction
label | Proof Roll
label | Visual Inspection of compacted surface layer
label | Each Laydown
holdpoint | United Civil Hold Point
checkpoint | Final Grading
label | Visual Inspection of final grading and surface finish
label | Smooth surface with proper slope for drainage
label | Each Laydown
holdpoint | United Civil Hold Point
section | Drainage - If Applicable
checkpoint | Culverts and Drains
label | Visual Inspection of installation of culverts and drainage channels
label | Installed as per design; no blockages
label | Water will flow without deviation
section | Post Construction and Handover
checkpoint | Final Walkthrough & Inspection
label | Comprehensive Visual Inspection of laydownsn & ensure laydowns are ready for use
label | Compliance with IFC drawings and specifications
label | No defects
holdpoint | CHINT / United Civil Hold Point
checkpoint | Non-Conformance-Reports
label | Each Non-Conformance Reported, Rectified & Closed Out
checkpoint | Punch List
label | Development of Punchlist with Client and Contractor Representative Punch List closed out in a timely manor
checkpoint | Documentation
label | On completion of the laydowns
label | Submission of all test results, ITC's and any as-built drawings
label | Drone Survey as-built for alignment and levels
holdpoint | CHINT / United Civil Hold Point
checklist | ITP - Internal Roads | itp |  |  |  |  | ITP - Internal Roads
section | Preconstruction
checkpoint | Design Drawings
label | Issued for Construction Drawings available
holdpoint | United Civil Hold Point
checkpoint | Survey & Setout
label | Verification of road alignment and layout
label | Alignment with approved IFC Drawings
holdpoint | United Civil Hold Point
checkpoint | Site Clearing
label | Visual inspection of cleared area
label | Free from vegetation, debris, and obstructions
holdpoint | United Civil Hold Point
section | Material Procurement
checkpoint | Material Approval
label | Approval of road materials (e.g., aggregates, subbase, basecourses
label | Compliance with KDC EES2011 specifications and standards and IFC Drawings
label | Material Test Certificates - Gradings, CBR, Crushing Resistance
holdpoint | CHINT / United Civil Hold Point
section | Construction - Subgrade
checkpoint | Excavation/Grading
label | Inspect grading and levelling of subgrade
label | Uniform surface with proper slope and drainage
label | Visual Inspection and Measurements
label | Every Internal Road
holdpoint | United Civil Hold Point
checkpoint | Compaction
label | Field density test
label | Achieves required compaction (Scalar Penetrometer with min of 2 blows per 100mm) Tests every 100m
label | Scalar Penetrometer test check sheet
label | For each section
label | Hold Point for United Civil
holdpoint | United Civil Hold Point
section | Subgrade Improvements (Where Required)
checkpoint | Identify areas of Undercut
label | Identify areas of undercut and liaise with Client
checkpoint | Excavate Undercut
label | Excavate a minimum of 200mm in depth full width of the road
label | Any free water has a path off the road in a controlled manor
label | Visual inspection of subgrade with Client
label | Undercut ITC completed
checkpoint | Geotextile & Geogrid Installation
label | Visual inspection of geotextile & Geogrids placement for each section
label | Correctly installed with proper overlap and anchorage
label | Product Data Sheets
checkpoint | Backfill Undercut
label | Visual inspection of backfilled material
label | Compaction to be static compaction only
label | Proof rolled with no obvious weaving or areas of instability
section | Construction - Base and Subbase
checkpoint | Material Placement
label | Inspection of base and subbase layers
label | Compliance with IFC Drawings and Product Data Sheets with Material Specifications
label | 100mm thickness of Gap40 and 50mm of Gap20
label | ITC Completed for Internal Roads
checkpoint | Compaction
label | Proof Roll
label | Visual Inspection of Compacted Base and Basecourse
label | Each Road
holdpoint | United Civil Hold Point
checkpoint | Level and Alignment
label | Visual Inspection of Alignment
label | Compliance with design tolerances
label | Each Road
holdpoint | United Civil Hold Point
section | Construction - Surface Layer
checkpoint | Aggregate Placement
label | Inspect placement of aggregate layer
label | Even distribution; meets design thickness of 50mm
label | ITC Completed for Internal Roads
label | Every section
checkpoint | Surface Compaction
label | Proof Roll
label | Visual Inspection of compacted surface layer
label | Each Road
holdpoint | United Civil Hold Point
checkpoint | Final Grading
label | Visual Inspection of final grading and surface finish
label | Smooth surface with proper slope for drainage
label | Each Road
holdpoint | United Civil Hold Point
section | Drainage
checkpoint | Culverts and Drains
label | Visual Inspection of installation of culverts and drainage channels
label | Installed as per design; no blockages
label | Water will flow without deviation
label | Reference Drainage ITP for Culverts
section | Post Construction and Handover
checkpoint | Final Walkthrough & Inspection
label | Comprehensive Visual Inspection of road construction & ensure roads are ready for use
label | Compliance with IFC drawings and specifications
label | No defects
holdpoint | CHINT / United Civil Hold Point
checkpoint | Non-Conformance-Reports
label | Each Non-Conformance Reported, Rectified & Closed Out
checkpoint | Punch List
label | Development of Punchlist with Client and Contractor Representative Punch List closed out in a timely manor
checkpoint | Documentation
label | On completion of the Internal Roads
label | Submission of all test results, ITC's and any as-built drawings
label | Drone Survey as-built for alignment and levels
holdpoint | CHINT / United Civil Hold Point
checklist | ITP - Drainage | itp |  |  |  |  | ITP - Drainage
section | Location
checkpoint-no-status | Drainage Location
textbox | Location of Installed drainage line
textbox | Project drainage line reference (if applicable)
section | Preconstruction
checkpoint | Design Drawings
label | Issued for Construction Drawings available
holdpoint | United Civil Hold Point
checkpoint | Site Preparation
label | Visual inspection of cleared and levelled area
label | Site free from debris, vegetation, and unevenness
checkpoint | Survey and Marking
label | Verification of layout and drain alignment & grades
label | Alignment with approved IFC drawings
checkpoint | Material Approval
label | Review and approval of pipes, culverts, and other materials
label | Compliance with IFC drawings, specifications, KDC EES - S06 for accessways, and standards
label | Material Test Certificates / Delivery Dockets attached
holdpoint | United Civil Hold Point
section | Construction - Excavation
checkpoint | Excavation
label | Visual inspection and measurement
label | Depth, dimensions, and cleanliness
label | Compliance with design drawings
checkpoint | Soil Stability
label | Inspection of trench stability and shoring where necessary
label | Stable and safe for pipe laying
section | Construction - Installation
checkpoint | Pipe Placement
label | Visual Inspection of pipe placement, alignment, and bedding
label | Compliance with approved IFC Drawings
checkpoint | Joint Sealing
label | Inspection of joint sealing materials and application
label | No leakage; proper sealing per specifications
checkpoint | Backfilling
label | Inspection of backfill material and compaction
label | Proper compaction as per specification
label | ITC for compaction
holdpoint | United Civil Hold Point
section | Construction - Testing
checkpoint | Hydrostatic Test
label | Pressure testing of pipes for leakage
label | Meets pressure standards for type of line being tested
label | Test Report Completed
holdpoint | CHINT / United Civil Hold Point
checkpoint | Flow Test
label | Visual Inspection to verify water flow through drains
label | Smooth flow; no blockages
section | Post Construction and Handover
checkpoint | Final Walkthrough & Inspection
label | Comprehensive Visual Inspection of Stormwater and that it is ready for use
label | Comply with IFC Drawings / Specifications / KDC EES
label | No misalignment, defects, or debris
holdpoint | CHINT / United Civil Hold Point
checkpoint | Non-Conformance-Reports
label | Each Non-Conformance Reported, Rectified & Closed Out
checkpoint | Punch List
label | Development of Punchlist with Client and Contractor Representative Punch List closed out in a timely manor
checkpoint | Documentation
label | On completion of the Mechanical works for this Block
label | Submission of all test results, ITC's and any as-built drawings
label | Complete and approved by client
holdpoint | CHINT / United Civil Hold Point
checklist | ITP - Inverter Foundations | itp |  |  |  |  | ITP - Inverter Foundations
section | Preconstruction
checkpoint | Design Drawings
label | Issued for Construction Drawings available
holdpoint | United Civil Hold Point
checkpoint | Survey & Setout
label | Visual Inspection of Inverter Foundation layout
label | Alignment with approved drawings and site plan
holdpoint | United Civil Hold Point
checkpoint | Site Clearing
label | Visual inspection of cleared area
label | Free from vegetation, debris, and obstructions
holdpoint | CHINT / United Civil Hold Point
section | Material Procurement
checkpoint | Review of Concrete, and Reinforcement steel
label | Compliance with IFC Drawings, Specifications and Standards
label | All reinforcing bars shall be Grade 300E or 500E to AS/NZS 4671
label | All concrete construction shall be in accordance with NZS3109 and IFC Drawings
label | Concrete shall be 40MPa Minimum Strength for precast elements or 30MPa for concrete poured insitu
label | Material Test Certificates / Dockets supplied for each delivery/Pour
holdpoint | CHINT / United Civil Hold Point
section | Construction - Excavation
checkpoint | Excavation & Footing Construction
label | Visual Inspection of each footing location
label | Check that depth & dimensions comply with IFC Drawings
label | Compacted hardfill pad under footing locations
label | Results Recorded on Clegg Hammer Checksheet for compaction of each footing
holdpoint | United Civil Hold Point
section | Construction - Concrete
checkpoint | Formwork Installation
label | Visual inspection of formwork alignment and cleanliness
label | Compliance with IFC drawings; no gaps or damage
label | Prepour Inspection completed for each pour
checkpoint | Reinforcement Installation
label | Visual Inspection of steel bar placement, cover, and tying
label | Compliance with bar bending schedule and specifications
label | Prepour Inspection / Inspection Report for each Pour
checkpoint | Embedments
label | Positioning of anchor bolts or inserts
label | As per approved IFC drawings
label | Dimensional check
label | Prepour Inspection / Inspection Report
checkpoint | Concrete Mixing
label | Verify Certified Batching Plant is used
label | Concrete Mix Delivery Records
label | Prepour Inspection / Inspection Report for each Pour
checkpoint | Concrete Placement
label | Visual Inspection during pouring
label | Proper compaction of poured concrete, no segregation
label | Each Pour
checkpoint | Slump Test
label | Tests Taken in accordance with NZS3112.2
label | Slump Test Report
label | Per Pour
holdpoint | United Civil Hold Point
checkpoint | Concrete Strength
label | Compression test on cylinders taken in accordance with NZS3112.2
label | Meets required strength of 40MPa for precast element or 30MPa for concrete poured insitu
label | Test Report
holdpoint | United Civil Hold Point
section | Post Construction
checkpoint | Curing
label | Visual Inspection of curing of concrete
checkpoint | Foundation Alignment
label | Check position and alignment of foundation
label | Dimensional checks & compliance with tolerance in drawings
label | Larger Block dimensions should be 3338mm x 600mm x 770mm
label | Small block dimensions should be 3338mm x 500mm x 725mm
checkpoint | Surface Finish
label | Visual Inspection of surface for cracks, voids, and finish quality
label | No visible defects or honeycombing
label | Every foundation
section | Inverter Container Installation
checkpoint | Anchor Bracket Installation
label | Compliance with IFC Drawings, Specifications and Standards
label | Material Test Certificates / Dockets supplied for steel and galvanising
label | Hold down bolts as per IFC Drawings and specifications
label | Epoxy to be as per IFC Drawings and specifications
label | Grout to be a minimum of 20mm thick under Anchor bracket plate
holdpoint | CHINT / United Civil Hold Point
section | Post Construction and Handover
checkpoint | Final Walkthrough & Inspection
label | Comprehensive inspection of all elements relating to the Inverter Foundations
label | Compliance with IFC drawings and specifications
label | Verify all Inverter Foundations meet design and functional requirements
label | Inverter Foundations ready for subsequent construction activities
holdpoint | CHINT / United Civil Hold Point
checkpoint | Non-Conformance-Reports
label | Each Non-Conformance Reported, Rectified & Closed Out
checkpoint | Punch List
label | Development of Punchlist with Client and Contractor Representative Punch List closed out in a timely mannor
checkpoint | Documentation
label | On completion of the Inverter Foundations
label | Submission of all test results, ITC's and any as-built drawings
label | Complete and approved by client
holdpoint | CHINT / United Civil Hold Point