## Sheet1
| Setout | Survey | Best Practice | Per installation | As presented on the construction drawings set | V | Site Engineer/Supervisor |  | - Setout | VERIFICATION ACTIVITY - Survey | METHODS OR REFERENCE - Best Practice | FREQ. - Per installation | ACCEPTANCE CRITERIA - As presented on the construction drawings set | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - | - Setout
| Services (includes Traffic Count Loops and Traffic Signal Detector Loops) | Visual plan BeforeUDig Cable locate (electronic or pothole for line CHAR(AMP) depth) | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | H | Site Engineer/Supervisor | Hold point - No excavation is to be commenced until services are located and accounted for | - Services (includes Traffic Count Loops and Traffic Signal Detector Loops) | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line CHAR(AMP) depth) | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road | FREQ. - Before work commences | ACCEPTANCE CRITERIA - Zero service strikes | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold point - No excavation is to be commenced until services are located and accounted for | VERIFICATION ACTIVITY - Survey
| Cultural/Heritage Risk Assessment | Notification | NZTA Cultural CHAR(AMP) Heritage Risk Model | Before work commences | Local iwi has been notified of intent to start work | H | Renewals Engineer | Check and confirm if an Iwi representative need to be on site | - Cultural/Heritage Risk Assessment | VERIFICATION ACTIVITY - Notification | METHODS OR REFERENCE - NZTA Cultural CHAR(AMP) Heritage Risk Model | FREQ. - Before work commences | ACCEPTANCE CRITERIA - Local iwi has been notified of intent to start work | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Renewals Engineer | INSPECTORATE: Description - Check and confirm if an Iwi representative need to be on site | METHODS OR REFERENCE - Best Practice
| Notification of intention to start work | Notification |  | Before work commences | Letter drop to local residents | H | Site Engineer/ Comms Manager | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. | - Notification of intention to start work | VERIFICATION ACTIVITY - Notification | METHODS OR REFERENCE - | FREQ. - Before work commences | ACCEPTANCE CRITERIA - Letter drop to local residents | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Engineer/ Comms Manager | INSPECTORATE: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. | FREQ. - Per installation
| Archaeological Risk | Toolbox meeting | NZTA Cultural CHAR(AMP) Heritage Risk Model. Tasman DC ADP. | Before work commences | Toolbox meeting held covering accidental discovery protocol | H | Site Supervisor | Hold point - No excavation is to be commenced until toolbox meeting is held | - Archaeological Risk | VERIFICATION ACTIVITY - Toolbox meeting | METHODS OR REFERENCE - NZTA Cultural CHAR(AMP) Heritage Risk Model. Tasman DC ADP. | FREQ. - Before work commences | ACCEPTANCE CRITERIA - Toolbox meeting held covering accidental discovery protocol | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Supervisor | INSPECTORATE: Description - Hold point - No excavation is to be commenced until toolbox meeting is held | ACCEPTANCE CRITERIA - As presented on the construction drawings set
| Traffic Management - TMP | Visual check | CoPTTM/ Risk Based Assesment | Before traffic management set up | TMP checked and approved - Plans approved - Current EED | H | TTM Planner | Hold point - No traffic management is to be set up until TMP has been checked and approved | - Traffic Management - TMP | VERIFICATION ACTIVITY - Visual check | METHODS OR REFERENCE - CoPTTM/ Risk Based Assesment | FREQ. - Before traffic management set up | ACCEPTANCE CRITERIA - TMP checked and approved - Plans approved - Current EED | INSPECTORATE: Type - H | INSPECTORATE: Assessor - TTM Planner | INSPECTORATE: Description - Hold point - No traffic management is to be set up until TMP has been checked and approved | INSPECTORATE: Type - V
| Traffic Management - Setup | Visual check | Traffic Management Plan | Before work commences | Traffic management complies with TMP | H | STMS | Hold point - No physical works are to be commenced until necessary traffic management is in place | - Traffic Management - Setup | VERIFICATION ACTIVITY - Visual check | METHODS OR REFERENCE - Traffic Management Plan | FREQ. - Before work commences | ACCEPTANCE CRITERIA - Traffic management complies with TMP | INSPECTORATE: Type - H | INSPECTORATE: Assessor - STMS | INSPECTORATE: Description - Hold point - No physical works are to be commenced until necessary traffic management is in place | INSPECTORATE: Assessor - Site Engineer/Supervisor
| Shoulder CHAR(AMP) driveway stripping | Visual check | On site |  | Shoulder CHAR(AMP) driveway stripping completed | H | Site Engineer/Supervisor | Hold point - Communicate with affected residents | - Shoulder CHAR(AMP) driveway stripping | VERIFICATION ACTIVITY - Visual check | METHODS OR REFERENCE - On site | FREQ. - | ACCEPTANCE CRITERIA - Shoulder CHAR(AMP) driveway stripping completed | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold point - Communicate with affected residents | INSPECTORATE: Description -
Plants CHAR(AMP) Equipmens are suitable to be on site/road. | Compaction | Inspection | RQP | Prior to commencement | Legal REGO, WOF CHAR(AMP) suitable to use | H | Operation Manager | Required by appendix 6.3 | Plants CHAR(AMP) Equipmens are suitable to be on site/road. - Compaction | VERIFICATION ACTIVITY - Inspection | METHODS OR REFERENCE - RQP | FREQ. - Prior to commencement | ACCEPTANCE CRITERIA - Legal REGO, WOF CHAR(AMP) suitable to use | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Operation Manager | INSPECTORATE: Description - Required by appendix 6.3 | - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
Material source CHAR(AMP) production properties Note: Running course to be produced from the same type and source of material as the basecourse. | PSD (Particle Size Distribution) | Wet Sieving Test | TNZ M/4:2006 NZS 4407 :1991 Test 3.8.1 | 1-400m3 – 1 test | TNZ M/4: Cl.4.2.3 | H | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road | Material source CHAR(AMP) production properties Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution) | VERIFICATION ACTIVITY - Wet Sieving Test | METHODS OR REFERENCE - TNZ M/4:2006 NZS 4407 :1991 Test 3.8.1 | FREQ. - 1-400m3 – 1 test | ACCEPTANCE CRITERIA - TNZ M/4: Cl.4.2.3 | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Renewals Engineer | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line CHAR(AMP) depth)
Material source CHAR(AMP) production properties | Broken Faces (1) | Broken Face Test | TNZ M/4: 2006 NZS 4407 :1991 Test 3.14 | 1500-4000m3 – 3 tests | Aggregate broken face content in each of the 3 aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces | V | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road | Material source CHAR(AMP) production properties - Broken Faces (1) | VERIFICATION ACTIVITY - Broken Face Test | METHODS OR REFERENCE - TNZ M/4: 2006 NZS 4407 :1991 Test 3.14 | FREQ. - 1500-4000m3 – 3 tests | ACCEPTANCE CRITERIA - Aggregate broken face content in each of the 3 aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Renewals Engineer | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
Material source CHAR(AMP) production properties | Broken Faces (2) | Broken Face Test | TNZ M/4: 2006 NZS 4407 :1991 Test 3.14 | >4000m3 – 1 test per 1000m3 | Aggregate broken face content in each of the 3 aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces | H | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road | Material source CHAR(AMP) production properties - Broken Faces (2) | VERIFICATION ACTIVITY - Broken Face Test | METHODS OR REFERENCE - TNZ M/4: 2006 NZS 4407 :1991 Test 3.14 | FREQ. - >4000m3 – 1 test per 1000m3 | ACCEPTANCE CRITERIA - Aggregate broken face content in each of the 3 aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Renewals Engineer | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road | FREQ. - Before work commences
Material source CHAR(AMP) production properties | Plasticity Index (1) | Plasticity Index Test | NZS 4407 :1991 Test 3.6 |  | PI ≤ 5 | V | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road | Material source CHAR(AMP) production properties - Plasticity Index (1) | VERIFICATION ACTIVITY - Plasticity Index Test | METHODS OR REFERENCE - NZS 4407 :1991 Test 3.6 | FREQ. - | ACCEPTANCE CRITERIA - PI ≤ 5 | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Renewals Engineer | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road | ACCEPTANCE CRITERIA - Zero service strikes
Material source CHAR(AMP) production properties | Plasticity Index (2) | Plasticity Index Test | TNZ M/4: 2006 |  | PI ≤ 5 | H | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road | Material source CHAR(AMP) production properties - Plasticity Index (2) | VERIFICATION ACTIVITY - Plasticity Index Test | METHODS OR REFERENCE - TNZ M/4: 2006 | FREQ. - | ACCEPTANCE CRITERIA - PI ≤ 5 | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Renewals Engineer | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road | INSPECTORATE: Type - H
Material source CHAR(AMP) production properties | Lab tests: Optimum water content (OWC) Solid Density | NZ vibrating hammer compaction test at OWC ○ Solid density | NZS 4402: 1986 MDD and W/C Test 4.1.3 NZS 4407:1991 Solid Density Test 3.7 NZS 4407:1991 W/C Test 3.1 TNZ B/2: 2005 | The lesser of: a) 1 test per stockpile or new seam b) 1 test every 5000m2 (in place) | MDD as the higher of the two results from lab and field OWC as determined in the lab When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples) | V | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road | Material source CHAR(AMP) production properties - Lab tests: Optimum water content (OWC) Solid Density | VERIFICATION ACTIVITY - NZ vibrating hammer compaction test at OWC ○ Solid density | METHODS OR REFERENCE - NZS 4402: 1986 MDD and W/C Test 4.1.3 NZS 4407:1991 Solid Density Test 3.7 NZS 4407:1991 W/C Test 3.1 TNZ B/2: 2005 | FREQ. - The lesser of: a) 1 test per stockpile or new seam b) 1 test every 5000m2 (in place) | ACCEPTANCE CRITERIA - MDD as the higher of the two results from lab and field OWC as determined in the lab When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples) | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Renewals Engineer | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road | INSPECTORATE: Assessor - Site Engineer/Supervisor
Material source CHAR(AMP) production properties | Maximum Dry Density (MDD) | MDD at OWC – in lab | NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005 | The lesser of: a) 1 test per stockpile or new seam b) 1 test every 5000m2 (in place) | MDD as the higher of the two results from lab and field Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset | H | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road | Material source CHAR(AMP) production properties - Maximum Dry Density (MDD) | VERIFICATION ACTIVITY - MDD at OWC – in lab | METHODS OR REFERENCE - NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005 | FREQ. - The lesser of: a) 1 test per stockpile or new seam b) 1 test every 5000m2 (in place) | ACCEPTANCE CRITERIA - MDD as the higher of the two results from lab and field Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Renewals Engineer | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road | INSPECTORATE: Description - Hold point - No excavation is to be commenced until services are located and accounted for
Material source CHAR(AMP) production properties | Crushing Resistance (1) | TNZ M/4 Crushing Resistance Test | TNZ M/4: 2006 NZS 4407 :1991 Test 3.10 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | V | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old | Material source CHAR(AMP) production properties - Crushing Resistance (1) | VERIFICATION ACTIVITY - TNZ M/4 Crushing Resistance Test | METHODS OR REFERENCE - TNZ M/4: 2006 NZS 4407 :1991 Test 3.10 | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Renewals Engineer | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old | - Cultural/Heritage Risk Assessment
Material source CHAR(AMP) production properties | Crushing Resistance (2) | TNZ M/4 Crushing Resistance Test | TNZ M/4: 2006 NZS 4407 :1991 Test 3.10 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | H | Renewals Engineer | Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old | Material source CHAR(AMP) production properties - Crushing Resistance (2) | VERIFICATION ACTIVITY - TNZ M/4 Crushing Resistance Test | METHODS OR REFERENCE - TNZ M/4: 2006 NZS 4407 :1991 Test 3.10 | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Renewals Engineer | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old | VERIFICATION ACTIVITY - Notification
Material source CHAR(AMP) production properties | Californian Bearing Ratio (CBR) (1) | TNZ M/4 | NZS 4402: 1986 Test 4.13 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock. | Soaked CBR ≥ 80% when compacted/tested in accordance with either test | V | Site Engineer/Supervisor | Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old | Material source CHAR(AMP) production properties - Californian Bearing Ratio (CBR) (1) | VERIFICATION ACTIVITY - TNZ M/4 | METHODS OR REFERENCE - NZS 4402: 1986 Test 4.13 | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock. | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with either test | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old | METHODS OR REFERENCE - NZTA Cultural CHAR(AMP) Heritage Risk Model
Material source CHAR(AMP) production properties | Californian Bearing Ratio (CBR) (2) | NZ vibrating hammer compaction test at OMC Determination of CBR. | NZS 4407: 1991 Test CBR 3.15 TNZ M/4: 2006 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock. | Soaked CBR ≥ 80% when compacted/tested in accordance with either test | H | Site Engineer/Supervisor | Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old | Material source CHAR(AMP) production properties - Californian Bearing Ratio (CBR) (2) | VERIFICATION ACTIVITY - NZ vibrating hammer compaction test at OMC Determination of CBR. | METHODS OR REFERENCE - NZS 4407: 1991 Test CBR 3.15 TNZ M/4: 2006 | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock. | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with either test | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old | FREQ. - Before work commences
Material source CHAR(AMP) production properties | Weathering (1) | Weathering quality index test | NZS 4407:1991 Test 3.11 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Must have quality index of AA, AB, AC, BA, BB or CA | V | Site Engineer/Supervisor | Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old | Material source CHAR(AMP) production properties - Weathering (1) | VERIFICATION ACTIVITY - Weathering quality index test | METHODS OR REFERENCE - NZS 4407:1991 Test 3.11 | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old | ACCEPTANCE CRITERIA - Local iwi has been notified of intent to start work
Material source CHAR(AMP) production properties | Weathering (2) | Weathering quality index test | TNZ M/4:2006 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Must have quality index of AA, AB, AC, BA, BB or CA | H | Site Engineer/Supervisor | Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old | Material source CHAR(AMP) production properties - Weathering (2) | VERIFICATION ACTIVITY - Weathering quality index test | METHODS OR REFERENCE - TNZ M/4:2006 | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old | INSPECTORATE: Type - H
| AP40 Compaction (1) | NDM – maximum dry density | NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | Base: N/A | V | Site Engineer/Supervisor | Hold Point – SAC layer not to be laid until passing results are achieved (ie average CHAR(AMP) minimum MDD) | - AP40 Compaction (1) | VERIFICATION ACTIVITY - NDM – maximum dry density | METHODS OR REFERENCE - NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement | ACCEPTANCE CRITERIA - Base: N/A | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold Point – SAC layer not to be laid until passing results are achieved (ie average CHAR(AMP) minimum MDD) | INSPECTORATE: Assessor - Renewals Engineer
| AP40 Compaction (2) | NDM – maximum dry density | NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | SubBase: Average ≥ 95% MDD Minimum ≥ 92% MDD | H | Site Engineer/Supervisor | Hold Point – SAC layer not to be laid until passing results are achieved (ie average CHAR(AMP) minimum MDD) | - AP40 Compaction (2) | VERIFICATION ACTIVITY - NDM – maximum dry density | METHODS OR REFERENCE - NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement | ACCEPTANCE CRITERIA - SubBase: Average ≥ 95% MDD Minimum ≥ 92% MDD | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold Point – SAC layer not to be laid until passing results are achieved (ie average CHAR(AMP) minimum MDD) | INSPECTORATE: Description - Check and confirm if an Iwi representative need to be on site
| Layer thickness | TNZ B/2 | Site Survey during contruction | 1 test per 50m | Overlay Thickness meets design | V | Site Engineer/Supervisor | Verification Point | - Layer thickness | VERIFICATION ACTIVITY - TNZ B/2 | METHODS OR REFERENCE - Site Survey during contruction | FREQ. - 1 test per 50m | ACCEPTANCE CRITERIA - Overlay Thickness meets design | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Verification Point | - Notification of intention to start work
| Management of coal tar | Safe Handling CHAR(AMP) Dumping | PPE CHAR(AMP) recoding volume | Daily during stage | Coal tar to be loaded CHAR(AMP) dumped safely with appropriate PPE CHAR(AMP) record manifest upto date. | V | Site Engineer/Supervisor | Verification Point | - Management of coal tar | VERIFICATION ACTIVITY - Safe Handling CHAR(AMP) Dumping | METHODS OR REFERENCE - PPE CHAR(AMP) recoding volume | FREQ. - Daily during stage | ACCEPTANCE CRITERIA - Coal tar to be loaded CHAR(AMP) dumped safely with appropriate PPE CHAR(AMP) record manifest upto date. | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Verification Point | VERIFICATION ACTIVITY - Notification
| Verify Subgrade strength | Designer's recommendation | Scala Penetrometer test | Every 20m, alternating lanes, except where D/Os completed previouslty | CBR > 4. Each 1 less CBR equivilent to an extra 100mm of pavement required | H | Site Engineer/Supervisor | Hold point - no basecourse layer to be added until CBR is greater than 4 | - Verify Subgrade strength | VERIFICATION ACTIVITY - Designer's recommendation | METHODS OR REFERENCE - Scala Penetrometer test | FREQ. - Every 20m, alternating lanes, except where D/Os completed previouslty | ACCEPTANCE CRITERIA - CBR > 4. Each 1 less CBR equivilent to an extra 100mm of pavement required | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold point - no basecourse layer to be added until CBR is greater than 4 | METHODS OR REFERENCE -
| Placement of Geotextile | As per the spec | Visual inspection | every 50m, each lane | Well covered CHAR(AMP) pressed onto the subgrade | V | Site Engineer/Supervisor |  | - Placement of Geotextile | VERIFICATION ACTIVITY - As per the spec | METHODS OR REFERENCE - Visual inspection | FREQ. - every 50m, each lane | ACCEPTANCE CRITERIA - Well covered CHAR(AMP) pressed onto the subgrade | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - | FREQ. - Before work commences
| Work around Protected tree | Involving an arborist while working near the tree | Stand over on site | Around 2 Protected trees | As agreed by An arborist | W | Renewals Engineer | Witness point | - Work around Protected tree | VERIFICATION ACTIVITY - Involving an arborist while working near the tree | METHODS OR REFERENCE - Stand over on site | FREQ. - Around 2 Protected trees | ACCEPTANCE CRITERIA - As agreed by An arborist | INSPECTORATE: Type - W | INSPECTORATE: Assessor - Renewals Engineer | INSPECTORATE: Description - Witness point | ACCEPTANCE CRITERIA - Letter drop to local residents
| Subcontractor involvement (Ezi sweep, Independent Kerb CHAR(AMP) channel, Safe Hire, Dwyer CHAR(AMP) Bird) | Downer's supervisor to guide subcontractors for quality work | Reports, Photos | As required | As agreed by the site supervisor | H | Site Engineer/Supervisor | Hold point | - Subcontractor involvement (Ezi sweep, Independent Kerb CHAR(AMP) channel, Safe Hire, Dwyer CHAR(AMP) Bird) | VERIFICATION ACTIVITY - Downer's supervisor to guide subcontractors for quality work | METHODS OR REFERENCE - Reports, Photos | FREQ. - As required | ACCEPTANCE CRITERIA - As agreed by the site supervisor | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold point | INSPECTORATE: Type - H
| Footpath base | Clegg Hammer test | Report | Every 50m | Reading greater than 25 | V | Site Engineer/Supervisor |  | - Footpath base | VERIFICATION ACTIVITY - Clegg Hammer test | METHODS OR REFERENCE - Report | FREQ. - Every 50m | ACCEPTANCE CRITERIA - Reading greater than 25 | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - | INSPECTORATE: Assessor - Site Engineer/ Comms Manager
| Reconstruct existing accessway | Grade CHAR(AMP) Tie in levels onto footpath | Checking grade | Each accessway | Constrcut as per the design CHAR(AMP) check levels regularly | H | Site Engineer/Supervisor | Holdpoint | - Reconstruct existing accessway | VERIFICATION ACTIVITY - Grade CHAR(AMP) Tie in levels onto footpath | METHODS OR REFERENCE - Checking grade | FREQ. - Each accessway | ACCEPTANCE CRITERIA - Constrcut as per the design CHAR(AMP) check levels regularly | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Holdpoint | INSPECTORATE: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
| Subsoil drainage | Adequate length CHAR(AMP) grade for pipes | Visual inspection | Along the site | Connect subsoil drainge to existing sump with adequate fall | V | Site Engineer/Supervisor |  | - Subsoil drainage | VERIFICATION ACTIVITY - Adequate length CHAR(AMP) grade for pipes | METHODS OR REFERENCE - Visual inspection | FREQ. - Along the site | ACCEPTANCE CRITERIA - Connect subsoil drainge to existing sump with adequate fall | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - | - Archaeological Risk
| Subcontractor involvement for other utility operators (DELTA, Downer Telco, Powertech) | Renewal Engineer to get paperwork to respective utility operators | Reports, Photos | Each designated site where subcontractors work | CBR greater than 4 | H | Site Engineer/Supervisor | Hold point - no basecourse layer to be added until CBR is greater than 4 | - Subcontractor involvement for other utility operators (DELTA, Downer Telco, Powertech) | VERIFICATION ACTIVITY - Renewal Engineer to get paperwork to respective utility operators | METHODS OR REFERENCE - Reports, Photos | FREQ. - Each designated site where subcontractors work | ACCEPTANCE CRITERIA - CBR greater than 4 | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold point - no basecourse layer to be added until CBR is greater than 4 | VERIFICATION ACTIVITY - Toolbox meeting
| Visual appearance (1) | TNZ B/2 | Visual inspection after sweeping | Immediately prior to sealing | Well compacted CHAR(AMP) graded | V | Site Engineer/Supervisor | Hold Point – no surfacing layer is to be applied until passing results are achieved | - Visual appearance (1) | VERIFICATION ACTIVITY - TNZ B/2 | METHODS OR REFERENCE - Visual inspection after sweeping | FREQ. - Immediately prior to sealing | ACCEPTANCE CRITERIA - Well compacted CHAR(AMP) graded | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold Point – no surfacing layer is to be applied until passing results are achieved | METHODS OR REFERENCE - NZTA Cultural CHAR(AMP) Heritage Risk Model. Tasman DC ADP.
| Visual appearance (2) | TNZ B/2 | Visual inspection after sweeping | Immediately prior to sealing | Well compacted CHAR(AMP) graded | H | Site Engineer/Supervisor | Hold Point – no surfacing layer is to be applied until passing results are achieved | - Visual appearance (2) | VERIFICATION ACTIVITY - TNZ B/2 | METHODS OR REFERENCE - Visual inspection after sweeping | FREQ. - Immediately prior to sealing | ACCEPTANCE CRITERIA - Well compacted CHAR(AMP) graded | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold Point – no surfacing layer is to be applied until passing results are achieved | FREQ. - Before work commences
| Structural AC compaction | NDM | NDM acceptance against mix designs based on M10: 2020. Photos and paving records for each layer. | 20m intervals for each compacted layer, alternating lanes in accordance with rolling patterns. | In accordance with M10 and Mix Design. Target air voids 4% | H | Sealing Manager | Hold point | - Structural AC compaction | VERIFICATION ACTIVITY - NDM | METHODS OR REFERENCE - NDM acceptance against mix designs based on M10: 2020. Photos and paving records for each layer. | FREQ. - 20m intervals for each compacted layer, alternating lanes in accordance with rolling patterns. | ACCEPTANCE CRITERIA - In accordance with M10 and Mix Design. Target air voids 4% | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Sealing Manager | INSPECTORATE: Description - Hold point | ACCEPTANCE CRITERIA - Toolbox meeting held covering accidental discovery protocol
| Structural AC layering | Survey |  | Survey check of finished Structural and Top Surface Layers to confim layer thickness. | Meets design thickness +/- 10mm | H | Site Enginner / Sealing Manager | Hold point | - Structural AC layering | VERIFICATION ACTIVITY - Survey | METHODS OR REFERENCE - | FREQ. - Survey check of finished Structural and Top Surface Layers to confim layer thickness. | ACCEPTANCE CRITERIA - Meets design thickness +/- 10mm | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Enginner / Sealing Manager | INSPECTORATE: Description - Hold point | INSPECTORATE: Type - H
| Finished surface crossfall | Survey |  | Survey check of Top Surface and Smart level | Finshed surface crossfall target 3% Min 2% - Max 4% | H | Site Enginner / Sealing Manager | Hold point | - Finished surface crossfall | VERIFICATION ACTIVITY - Survey | METHODS OR REFERENCE - | FREQ. - Survey check of Top Surface and Smart level | ACCEPTANCE CRITERIA - Finshed surface crossfall target 3% Min 2% - Max 4% | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Enginner / Sealing Manager | INSPECTORATE: Description - Hold point | INSPECTORATE: Assessor - Site Supervisor
Traffic Services | Marker pegs/ Signs/Markings/RRPMs Replaced (1) | TNZ C/20: 2003 | Visual inspection | All signs/markers | Replaced in same position, height etc | V | Site Engineer/Supervisor | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced | Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced (1) | VERIFICATION ACTIVITY - TNZ C/20: 2003 | METHODS OR REFERENCE - Visual inspection | FREQ. - All signs/markers | ACCEPTANCE CRITERIA - Replaced in same position, height etc | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced | INSPECTORATE: Description - Hold point - No excavation is to be commenced until toolbox meeting is held
Traffic Services | Marker pegs/ Signs/Markings/RRPMs Replaced (2) | TNZ C/20: 2003 | Visual inspection | All signs/markers | Replaced in same position, height etc | H | Site Engineer/Supervisor | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced | Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced (2) | VERIFICATION ACTIVITY - TNZ C/20: 2003 | METHODS OR REFERENCE - Visual inspection | FREQ. - All signs/markers | ACCEPTANCE CRITERIA - Replaced in same position, height etc | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced | - Traffic Management - TMP
| Grassing | Visual check |  | All areas requiring grassing | Grassing has been done where required | W | Site Engineer/Supervisor |  | - Grassing | VERIFICATION ACTIVITY - Visual check | METHODS OR REFERENCE - | FREQ. - All areas requiring grassing | ACCEPTANCE CRITERIA - Grassing has been done where required | INSPECTORATE: Type - W | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - | VERIFICATION ACTIVITY - Visual check
| Drains cleared | Visual check |  | All drains, after all other works | Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated | W | Site Engineer/Supervisor |  | - Drains cleared | VERIFICATION ACTIVITY - Visual check | METHODS OR REFERENCE - | FREQ. - All drains, after all other works | ACCEPTANCE CRITERIA - Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated | INSPECTORATE: Type - W | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - | METHODS OR REFERENCE - CoPTTM/ Risk Based Assesment
| Traffic Management Removed | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W | Site Engineer/Supervisor |  | - Traffic Management Removed | VERIFICATION ACTIVITY - Visual check | METHODS OR REFERENCE - | FREQ. - When safe, after all physical works completed | ACCEPTANCE CRITERIA - All traffic management removed from site safely | INSPECTORATE: Type - W | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - | FREQ. - Before traffic management set up
| Site left clean CHAR(AMP) tidy | Visual check |  | After vacating site | · Stockpiles removed · Plant removed · Litter cleared from site | V | Site Engineer/Supervisor |  | - Site left clean CHAR(AMP) tidy | VERIFICATION ACTIVITY - Visual check | METHODS OR REFERENCE - | FREQ. - After vacating site | ACCEPTANCE CRITERIA - · Stockpiles removed · Plant removed · Litter cleared from site | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Site Engineer/Supervisor | INSPECTORATE: Description - | ACCEPTANCE CRITERIA - TMP checked and approved - Plans approved - Current EED
| Collect asset data | SHDOM (SM050) |  | During construction | All relevant as built information collected. | V | Renewals Engineer |  | - Collect asset data | VERIFICATION ACTIVITY - SHDOM (SM050) | METHODS OR REFERENCE - | FREQ. - During construction | ACCEPTANCE CRITERIA - All relevant as built information collected. | INSPECTORATE: Type - V | INSPECTORATE: Assessor - Renewals Engineer | INSPECTORATE: Description - | INSPECTORATE: Type - H
| Enter asset data into RAMM and/or register(s) | SHDOM (SM050) | RAMM | At completion of work. | All data entered into RAMM and/or register(s). Design Report CHAR(AMP) Drawings attached to RAMM site record as a media file. | H | Asset Engineer | Hold Point – project cannot be closed until data entered. | - Enter asset data into RAMM and/or register(s) | VERIFICATION ACTIVITY - SHDOM (SM050) | METHODS OR REFERENCE - RAMM | FREQ. - At completion of work. | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report CHAR(AMP) Drawings attached to RAMM site record as a media file. | INSPECTORATE: Type - H | INSPECTORATE: Assessor - Asset Engineer | INSPECTORATE: Description - Hold Point – project cannot be closed until data entered. | INSPECTORATE: Assessor - TTM Planner
INSPECTORATE: Description - Hold point - No traffic management is to be set up until TMP has been checked and approved
- Traffic Management - Setup
VERIFICATION ACTIVITY - Visual check
METHODS OR REFERENCE - Traffic Management Plan
FREQ. - Before work commences
ACCEPTANCE CRITERIA - Traffic management complies with TMP
INSPECTORATE: Type - H
INSPECTORATE: Assessor - STMS
INSPECTORATE: Description - Hold point - No physical works are to be commenced until necessary traffic management is in place
- Shoulder CHAR(AMP) driveway stripping
VERIFICATION ACTIVITY - Visual check
METHODS OR REFERENCE - On site
FREQ. -
ACCEPTANCE CRITERIA - Shoulder CHAR(AMP) driveway stripping completed
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold point - Communicate with affected residents
Plants CHAR(AMP) Equipmens are suitable to be on site/road. - Compaction
VERIFICATION ACTIVITY - Inspection
METHODS OR REFERENCE - RQP
FREQ. - Prior to commencement
ACCEPTANCE CRITERIA - Legal REGO, WOF CHAR(AMP) suitable to use
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Operation Manager
INSPECTORATE: Description - Required by appendix 6.3
Material source CHAR(AMP) production properties Note: Running course to be produced from the same type and source of material as the basecourse. - PSD (Particle Size Distribution)
VERIFICATION ACTIVITY - Wet Sieving Test
METHODS OR REFERENCE - TNZ M/4:2006 NZS 4407 :1991 Test 3.8.1
FREQ. - 1-400m3 – 1 test
ACCEPTANCE CRITERIA - TNZ M/4: Cl.4.2.3
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Renewals Engineer
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
Material source CHAR(AMP) production properties - Broken Faces (1)
VERIFICATION ACTIVITY - Broken Face Test
METHODS OR REFERENCE - TNZ M/4: 2006 NZS 4407 :1991 Test 3.14
FREQ. - 1500-4000m3 – 3 tests
ACCEPTANCE CRITERIA - Aggregate broken face content in each of the 3 aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Renewals Engineer
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
Material source CHAR(AMP) production properties - Broken Faces (2)
VERIFICATION ACTIVITY - Broken Face Test
METHODS OR REFERENCE - TNZ M/4: 2006 NZS 4407 :1991 Test 3.14
FREQ. - >4000m3 – 1 test per 1000m3
ACCEPTANCE CRITERIA - Aggregate broken face content in each of the 3 aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Renewals Engineer
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
Material source CHAR(AMP) production properties - Plasticity Index (1)
VERIFICATION ACTIVITY - Plasticity Index Test
METHODS OR REFERENCE - NZS 4407 :1991 Test 3.6
FREQ. -
ACCEPTANCE CRITERIA - PI ≤ 5
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Renewals Engineer
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
Material source CHAR(AMP) production properties - Plasticity Index (2)
VERIFICATION ACTIVITY - Plasticity Index Test
METHODS OR REFERENCE - TNZ M/4: 2006
FREQ. -
ACCEPTANCE CRITERIA - PI ≤ 5
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Renewals Engineer
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
Material source CHAR(AMP) production properties - Lab tests: Optimum water content (OWC) Solid Density
VERIFICATION ACTIVITY - NZ vibrating hammer compaction test at OWC ○ Solid density
METHODS OR REFERENCE - NZS 4402: 1986 MDD and W/C Test 4.1.3 NZS 4407:1991 Solid Density Test 3.7 NZS 4407:1991 W/C Test 3.1 TNZ B/2: 2005
FREQ. - The lesser of: a) 1 test per stockpile or new seam b) 1 test every 5000m2 (in place)
ACCEPTANCE CRITERIA - MDD as the higher of the two results from lab and field OWC as determined in the lab When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples)
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Renewals Engineer
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
Material source CHAR(AMP) production properties - Maximum Dry Density (MDD)
VERIFICATION ACTIVITY - MDD at OWC – in lab
METHODS OR REFERENCE - NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005
FREQ. - The lesser of: a) 1 test per stockpile or new seam b) 1 test every 5000m2 (in place)
ACCEPTANCE CRITERIA - MDD as the higher of the two results from lab and field Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Renewals Engineer
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road
Material source CHAR(AMP) production properties - Crushing Resistance (1)
VERIFICATION ACTIVITY - TNZ M/4 Crushing Resistance Test
METHODS OR REFERENCE - TNZ M/4: 2006 NZS 4407 :1991 Test 3.10
FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Renewals Engineer
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old
Material source CHAR(AMP) production properties - Crushing Resistance (2)
VERIFICATION ACTIVITY - TNZ M/4 Crushing Resistance Test
METHODS OR REFERENCE - TNZ M/4: 2006 NZS 4407 :1991 Test 3.10
FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Renewals Engineer
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old
Material source CHAR(AMP) production properties - Californian Bearing Ratio (CBR) (1)
VERIFICATION ACTIVITY - TNZ M/4
METHODS OR REFERENCE - NZS 4402: 1986 Test 4.13
FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock.
ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with either test
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old
Material source CHAR(AMP) production properties - Californian Bearing Ratio (CBR) (2)
VERIFICATION ACTIVITY - NZ vibrating hammer compaction test at OMC Determination of CBR.
METHODS OR REFERENCE - NZS 4407: 1991 Test CBR 3.15 TNZ M/4: 2006
FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock.
ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with either test
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old
Material source CHAR(AMP) production properties - Weathering (1)
VERIFICATION ACTIVITY - Weathering quality index test
METHODS OR REFERENCE - NZS 4407:1991 Test 3.11
FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old
Material source CHAR(AMP) production properties - Weathering (2)
VERIFICATION ACTIVITY - Weathering quality index test
METHODS OR REFERENCE - TNZ M/4:2006
FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old
- AP40 Compaction (1)
VERIFICATION ACTIVITY - NDM – maximum dry density
METHODS OR REFERENCE - NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005
FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
ACCEPTANCE CRITERIA - Base: N/A
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold Point – SAC layer not to be laid until passing results are achieved (ie average CHAR(AMP) minimum MDD)
- AP40 Compaction (2)
VERIFICATION ACTIVITY - NDM – maximum dry density
METHODS OR REFERENCE - NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005
FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
ACCEPTANCE CRITERIA - SubBase: Average ≥ 95% MDD Minimum ≥ 92% MDD
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold Point – SAC layer not to be laid until passing results are achieved (ie average CHAR(AMP) minimum MDD)
- Layer thickness
VERIFICATION ACTIVITY - TNZ B/2
METHODS OR REFERENCE - Site Survey during contruction
FREQ. - 1 test per 50m
ACCEPTANCE CRITERIA - Overlay Thickness meets design
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Verification Point
- Management of coal tar
VERIFICATION ACTIVITY - Safe Handling CHAR(AMP) Dumping
METHODS OR REFERENCE - PPE CHAR(AMP) recoding volume
FREQ. - Daily during stage
ACCEPTANCE CRITERIA - Coal tar to be loaded CHAR(AMP) dumped safely with appropriate PPE CHAR(AMP) record manifest upto date.
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Verification Point
- Verify Subgrade strength
VERIFICATION ACTIVITY - Designer's recommendation
METHODS OR REFERENCE - Scala Penetrometer test
FREQ. - Every 20m, alternating lanes, except where D/Os completed previouslty
ACCEPTANCE CRITERIA - CBR > 4. Each 1 less CBR equivilent to an extra 100mm of pavement required
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold point - no basecourse layer to be added until CBR is greater than 4
- Placement of Geotextile
VERIFICATION ACTIVITY - As per the spec
METHODS OR REFERENCE - Visual inspection
FREQ. - every 50m, each lane
ACCEPTANCE CRITERIA - Well covered CHAR(AMP) pressed onto the subgrade
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description -
- Work around Protected tree
VERIFICATION ACTIVITY - Involving an arborist while working near the tree
METHODS OR REFERENCE - Stand over on site
FREQ. - Around 2 Protected trees
ACCEPTANCE CRITERIA - As agreed by An arborist
INSPECTORATE: Type - W
INSPECTORATE: Assessor - Renewals Engineer
INSPECTORATE: Description - Witness point
- Subcontractor involvement (Ezi sweep, Independent Kerb CHAR(AMP) channel, Safe Hire, Dwyer CHAR(AMP) Bird)
VERIFICATION ACTIVITY - Downer's supervisor to guide subcontractors for quality work
METHODS OR REFERENCE - Reports, Photos
FREQ. - As required
ACCEPTANCE CRITERIA - As agreed by the site supervisor
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold point
- Footpath base
VERIFICATION ACTIVITY - Clegg Hammer test
METHODS OR REFERENCE - Report
FREQ. - Every 50m
ACCEPTANCE CRITERIA - Reading greater than 25
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description -
- Reconstruct existing accessway
VERIFICATION ACTIVITY - Grade CHAR(AMP) Tie in levels onto footpath
METHODS OR REFERENCE - Checking grade
FREQ. - Each accessway
ACCEPTANCE CRITERIA - Constrcut as per the design CHAR(AMP) check levels regularly
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Holdpoint
- Subsoil drainage
VERIFICATION ACTIVITY - Adequate length CHAR(AMP) grade for pipes
METHODS OR REFERENCE - Visual inspection
FREQ. - Along the site
ACCEPTANCE CRITERIA - Connect subsoil drainge to existing sump with adequate fall
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description -
- Subcontractor involvement for other utility operators (DELTA, Downer Telco, Powertech)
VERIFICATION ACTIVITY - Renewal Engineer to get paperwork to respective utility operators
METHODS OR REFERENCE - Reports, Photos
FREQ. - Each designated site where subcontractors work
ACCEPTANCE CRITERIA - CBR greater than 4
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold point - no basecourse layer to be added until CBR is greater than 4
- Visual appearance (1)
VERIFICATION ACTIVITY - TNZ B/2
METHODS OR REFERENCE - Visual inspection after sweeping
FREQ. - Immediately prior to sealing
ACCEPTANCE CRITERIA - Well compacted CHAR(AMP) graded
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold Point – no surfacing layer is to be applied until passing results are achieved
- Visual appearance (2)
VERIFICATION ACTIVITY - TNZ B/2
METHODS OR REFERENCE - Visual inspection after sweeping
FREQ. - Immediately prior to sealing
ACCEPTANCE CRITERIA - Well compacted CHAR(AMP) graded
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold Point – no surfacing layer is to be applied until passing results are achieved
- Structural AC compaction
VERIFICATION ACTIVITY - NDM
METHODS OR REFERENCE - NDM acceptance against mix designs based on M10: 2020. Photos and paving records for each layer.
FREQ. - 20m intervals for each compacted layer, alternating lanes in accordance with rolling patterns.
ACCEPTANCE CRITERIA - In accordance with M10 and Mix Design. Target air voids 4%
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Sealing Manager
INSPECTORATE: Description - Hold point
- Structural AC layering
VERIFICATION ACTIVITY - Survey
METHODS OR REFERENCE -
FREQ. - Survey check of finished Structural and Top Surface Layers to confim layer thickness.
ACCEPTANCE CRITERIA - Meets design thickness +/- 10mm
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Site Enginner / Sealing Manager
INSPECTORATE: Description - Hold point
- Finished surface crossfall
VERIFICATION ACTIVITY - Survey
METHODS OR REFERENCE -
FREQ. - Survey check of Top Surface and Smart level
ACCEPTANCE CRITERIA - Finshed surface crossfall target 3% Min 2% - Max 4%
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Site Enginner / Sealing Manager
INSPECTORATE: Description - Hold point
Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced (1)
VERIFICATION ACTIVITY - TNZ C/20: 2003
METHODS OR REFERENCE - Visual inspection
FREQ. - All signs/markers
ACCEPTANCE CRITERIA - Replaced in same position, height etc
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced (2)
VERIFICATION ACTIVITY - TNZ C/20: 2003
METHODS OR REFERENCE - Visual inspection
FREQ. - All signs/markers
ACCEPTANCE CRITERIA - Replaced in same position, height etc
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
- Grassing
VERIFICATION ACTIVITY - Visual check
METHODS OR REFERENCE -
FREQ. - All areas requiring grassing
ACCEPTANCE CRITERIA - Grassing has been done where required
INSPECTORATE: Type - W
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description -
- Drains cleared
VERIFICATION ACTIVITY - Visual check
METHODS OR REFERENCE -
FREQ. - All drains, after all other works
ACCEPTANCE CRITERIA - Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated
INSPECTORATE: Type - W
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description -
- Traffic Management Removed
VERIFICATION ACTIVITY - Visual check
METHODS OR REFERENCE -
FREQ. - When safe, after all physical works completed
ACCEPTANCE CRITERIA - All traffic management removed from site safely
INSPECTORATE: Type - W
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description -
- Site left clean CHAR(AMP) tidy
VERIFICATION ACTIVITY - Visual check
METHODS OR REFERENCE -
FREQ. - After vacating site
ACCEPTANCE CRITERIA - · Stockpiles removed · Plant removed · Litter cleared from site
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Site Engineer/Supervisor
INSPECTORATE: Description -
- Collect asset data
VERIFICATION ACTIVITY - SHDOM (SM050)
METHODS OR REFERENCE -
FREQ. - During construction
ACCEPTANCE CRITERIA - All relevant as built information collected.
INSPECTORATE: Type - V
INSPECTORATE: Assessor - Renewals Engineer
INSPECTORATE: Description -
- Enter asset data into RAMM and/or register(s)
VERIFICATION ACTIVITY - SHDOM (SM050)
METHODS OR REFERENCE - RAMM
FREQ. - At completion of work.
ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report CHAR(AMP) Drawings attached to RAMM site record as a media file.
INSPECTORATE: Type - H
INSPECTORATE: Assessor - Asset Engineer
INSPECTORATE: Description - Hold Point – project cannot be closed until data entered.