## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Compliance Documents |  |  |  |  | Yes | Compliance Documents | 2889fd2a-c834-466a-b282-da6fd8e093b8
checkpoint-status |  |  | checkpoint | PS3 (Two-Storey brick veneer Cladding System)
checkpoint-status |  |  | checkpoint | Product Warranty
checkpoint-status |  |  | checkpoint | Brick Tie Galv Thickness Test
checkpoint-status |  |  | checkpoint | Records of Building work
checklist-flat |  |  | checklist | Pre-commencement checks |  |  |  |  | Yes | Pre-commencement checks | 42a8cbb5-3c86-45e4-9c29-eda75f244234
checkpoint-status |  |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
checkpoint-status |  |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status |  |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status |  |  | checkpoint | Matrix/insights Setup (if required)
checklist-flat |  |  | checklist | Compliance Documents |  |  |  |  | Yes | Compliance Documents | 7529b920-7660-4cf6-b653-0313df16d6a0
checkpoint-status |  |  | checkpoint | PS3 (Two-Storey brick veneer Cladding System)
checkpoint-status |  |  | checkpoint | Product Warranty
checkpoint-status |  |  | checkpoint | Brick Tie Galv Thickness Test
checkpoint-status |  |  | checkpoint | Records of Building work
checklist-sectioned |  |  | checklist | Brick Checklist |  |  |  |  | Yes | Brick Checklist | 7561ba27-a865-44eb-95cf-7fa27065e7b2
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Approval from Ryman foreman to begin bricking
checkpoint-status |  |  | checkpoint | Set up accurate stringline for entire face
checkpoint-group |  |  | section | Bricking Installation
checkpoint-status |  |  | checkpoint | Check bricks and any broken ones discarded
checkpoint-status |  |  | checkpoint | Mortar mixed correctly & colour consistent
checkpoint-status |  |  | checkpoint | Mortar joints are in alignment
checkpoint-status |  |  | checkpoint | Cavity width correct - as specified on drawing
checkpoint-status |  |  | checkpoint | Brick ties used are as per the specifications, correct length & installed correctly - 5 degree fall
checkpoint-status |  |  | checkpoint | Cavity and brick ties free of mortar and debris
checkpoint-status |  |  | checkpoint | Weep-holes checked and accurate (required every 3 bricks at base & sills)
checkpoint-status |  |  | checkpoint | Brick sill installed and checked - 15 degree consistent fall
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Brick installation completed to specified standard & finish
checklist-sectioned |  |  | checklist | Brick Checklist |  |  |  |  | Yes | Brick Checklist | 7f1478bc-b671-40c7-b013-198e9f020d30
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Approval from Ryman foreman to begin bricking
checkpoint-status |  |  | checkpoint | Set up accurate stringline for entire face
checkpoint-group |  |  | section | Bricking Installation
checkpoint-status |  |  | checkpoint | Check bricks and any broken ones discarded
checkpoint-status |  |  | checkpoint | Mortar mixed correctly & colour consistent
checkpoint-status |  |  | checkpoint | Mortar joints are in alignment
checkpoint-status |  |  | checkpoint | Cavity width correct - as specified on drawing
checkpoint-status |  |  | checkpoint | Brick ties used are as per the specifications, correct length & installed correctly - 5 degree fall
checkpoint-status |  |  | checkpoint | Cavity and brick ties free of mortar and debris
checkpoint-status |  |  | checkpoint | Weep-holes checked and accurate (required every 3 bricks at base & sills)
checkpoint-status |  |  | checkpoint | Brick sill installed and checked - 15 degree consistent fall
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Brick installation completed to specified standard & finish
checklist-sectioned |  |  | checklist | FC - S - Brick Works |  |  |  |  | Yes | FC - S - Brick Works | 8384760f-f907-4e3c-b840-37fe0dec0318
checkpoint-group |  |  | section | Preinstall checks
checkpoint-status |  |  | checkpoint | Area accessible, substrate acceptable & approval to start works - Consider services, cavity & waterproofing requirements prior to install
checkpoint-status |  |  | checkpoint | Ground clearance correct to specification
checkpoint-status |  |  | checkpoint | Grids/Wall marked for reference. RL reference/TOW confirmed. Base/Concrete/footing clean, tidy and level ready for first coarse.
checkpoint-group |  |  | section | Brick installation
checkpoint-status |  |  | checkpoint | Base of wall starting correct location - Brick base overhang within tolerances (no more than 20mm)
checkpoint-status |  |  | checkpoint | Control joints installed correctly
checkpoint-status |  |  | checkpoint | Weep holes installed correctly - Consider setout & size
checkpoint-status |  |  | checkpoint | Mortar Joints installed within tolerances (7-13mm)
checkpoint-status |  |  | checkpoint | Wall ties installed and aligning with specification (spacing, spans, length etc)
checkpoint-status |  |  | checkpoint | Horizontal shelf angles & lintel bars installed and correctly fixed where required - Consider horizontal and vertical alignment
checkpoint-status |  |  | checkpoint | All relevant flashings and waterproofing/taping completed as required - If Applicable
checkpoint-status |  |  | checkpoint | Caulking completed (correct colour) and satisfactory finish achieved
checkpoint-status |  |  | checkpoint | Brick cavity is correctly formed and free of obstructions
checkpoint-status |  |  | checkpoint | Brickwork completed to required specification. All brickwork washed/clean & area left clean & tidy - Wall built within tolerance - straight, level and to the correct height and colour
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | f5f39938-17b3-4da0-bc1b-3e01aa90df91
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | a7e2dcf5-2dd2-5015-b8f8-05725f317fb1 |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | c48f1fbd-eb35-53e0-9a7c-b816be0ed28b |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS