## Breakdown
Miriam Corban(AU brick)
B06
Façade
|  |  | North Elevation | Prepopulate | FC - S - Brick Works
|  |  | South Elevation | Prepopulate | FC - S - Brick Works
|  |  | West Elevation | Prepopulate | FC - S - Brick Works
|  |  | East Elevation | Prepopulate | FC - S - Brick Works

## Checklist
Type | Name | Value
checklist | FC - S - Brick Works
section | Preinstall checks
checkpoint | Area accessible, substrate acceptable & approval to start works - Consider services, cavity & waterproofing requirements prior to install
checkpoint | Ground clearance correct to specification
checkpoint | Grids/Wall marked for reference. RL reference/TOW confirmed. Base/Concrete/footing clean, tidy and level ready for first coarse.
section | Brick installation
checkpoint | Base of wall starting correct location - Brick base overhang within tolerances (no more than 20mm)
checkpoint | Control joints installed correctly
checkpoint | Weep holes installed correctly - Consider setout & size
checkpoint | Mortar Joints installed within tolerances (7-13mm)
checkpoint | Wall ties installed and aligning with specification (spacing, spans, length etc)
checkpoint | Horizontal shelf angles & lintel bars installed and correctly fixed where required - Consider horizontal and vertical alignment
checkpoint | All relevant flashings and waterproofing/taping completed as required - If Applicable
checkpoint | Caulking completed (correct colour) and satisfactory finish achieved
checkpoint | Brick cavity is correctly formed and free of obstructions
checkpoint | Brickwork completed to required specification. All brickwork washed/clean & area left clean & tidy - Wall built within tolerance - straight, level and to the correct height and colour
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS