## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DG-QA-TP018 Inspection and Test Plan (ITP) | itp |  |  |  |  | DG-QA-TP018 Inspection and Test Plan (ITP) | 970f6a1d-5474-4bfc-89c1-99f4afc5306d
section | Consent Conditions 1.0
checkpoint | 1.1 - Appoint contact person for Councils monitoring officer.
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Prior to works
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CH
label | Inspection: By (Role Key) - Consent Holder
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Appoint ecologist
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Prior to works
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CH
label | Inspection: By (Role Key) - Consent Holder
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Advise council montoring officer of contact people (Rep, Principal Contractor, Ecologist)
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Prior to works. (ongoing, and within one day of changes
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CH
label | Inspection: By (Role Key) - Consent Holder
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Advise monitoring officer of works commencing
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - 10 working days prior to works. (and when sediment control measures placed and 24hrs prior to measures being removed
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CH + C
label | Inspection: By (Role Key) - Consent Holder + Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Site meeting between principal contractor, ecologist, monotoring officer, iwi officer
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Prior to works
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CH + C
label | Inspection: By (Role Key) - Consent Holder + Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Iwi monitor to be appointed, and forward evidence of this to monitoring officer
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - 10 working days prior to works.
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CH
label | Inspection: By (Role Key) - Consent Holder
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Prepare construction management plan, traffic management plan and spill management plan - see conditions for requirements
label | Inspection Point: Quality Control Activity - Engineer to inspect plans
label | Acceptance Criteria - 15 working days prior to works
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CH + C
label | Inspection: By (Role Key) - Consent Holder + Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Penguin management plan submitted to council
label | Inspection Point: Quality Control Activity - Engineer to inspect plans
label | Acceptance Criteria - 15 working days prior to works
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CH
label | Inspection: By (Role Key) - Consent Holder
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.9 - Lizard management by Ecologist 2-10 days prior to vegetation removal in specific areas
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - 2-10 days prior to vegetation clearance in specific areas
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CH + C
label | Inspection: By (Role Key) - Consent Holder + Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.10 - Clean machinery prior to arrival on site
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Prior to arrival on site
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - C
label | Inspection: By (Role Key) - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.11 - Access routes (on foot) identified to works areas to avoid vegetation
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Identified on-site prior to works impacting estuary vegetation
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - C
label | Inspection: By (Role Key) - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.12 - Erect notices at each end of works site prior to works commencing
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - 2 working days prior to works (minimum)
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CH + C
label | Inspection: By (Role Key) - Consent Holder + Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.13 - Provide written notice to neighbours prior to works commencing
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - 2 working days prior to works (minimum)
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CH + C
label | Inspection: By (Role Key) - Consent Holder + Contractor
holdpoint | AUTHORITY HOLDPOINT
section | Safety 2.0
checkpoint | 2.1 - Traffic Management
label | Inspection Point: Quality Control Activity - Traffic Management to be set up daily before work can commence.
label | Acceptance Criteria - Traffic Management set up by qualified STMS according to approved plan
label | Verifying Document - Approved TMP
label | Frequency - Daily
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - C
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Locate services
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Services located by Delta, Chorus and TDC prior to commencing works.
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Verification
label | Inspection: Key - C
label | Inspection: By (Role Key) - Contractor
section | Pavement Construction Road Widening 4.0
checkpoint | 4.4 - Compaction of basecoursde (Field Dry Density)
label | Inspection Point: Quality Control Activity - NDM as per TNZ B/02 clause 7.6
label | Acceptance Criteria - ≥ 98% ave at MDD. ≥ 95% min
label | Verifying Document - Inspection
label | Frequency - 1 lot ( 5 tests)
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - SC
label | Inspection: By (Role Key) - Sels Civil
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Saturation
label | Inspection Point: Quality Control Activity - NDM as per TNZ B/02 clause 12
label | Acceptance Criteria - Less than 80%
label | Verifying Document - Inspection
label | Frequency - 1 per 110m²
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - SC
label | Inspection: By (Role Key) - Sels Civil
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Pre Seal Inspection
holdpoint | AUTHORITY HOLDPOINT
section | Pavement Construction Estuary Side 4.0
checkpoint | 4.4 - Compaction of basecoursde (Field Dry Density)
label | Inspection Point: Quality Control Activity - NDM as per TNZ B/02 clause 7.6
label | Acceptance Criteria - ≥ 98% ave at MDD. ≥ 95% min
label | Verifying Document - Inspection
label | Frequency - 1 lot ( 5 tests)
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - SC
label | Inspection: By (Role Key) - Sels Civil
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Saturation
label | Inspection Point: Quality Control Activity - NDM as per TNZ B/02 clause 12
label | Acceptance Criteria - Less than 80%
label | Verifying Document - Inspection
label | Frequency - 1 per 110m²
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - SC
label | Inspection: By (Role Key) - Sels Civil
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Pre Seal Inspection
holdpoint | AUTHORITY HOLDPOINT
section | Basecourse 4.1
checkpoint | 4.1.1 - Sand Equivalent
label | Inspection Point: Quality Control Activity - As per NZS 4407:2015
label | Acceptance Criteria - ≥ 40
label | Verifying Document - Council / Engineer to approve materials
label | Frequency - 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - WSP / TDC
label | Inspection: By (Role Key) - WSP / TDC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - Clay Index
label | Inspection Point: Quality Control Activity - As per NZS 4407:2015
label | Acceptance Criteria - ≤ 3 passing 75um
label | Verifying Document - Council / Engineer to approve materials
label | Frequency - 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1
label | Inspection: Key - WSP / TDC
label | Inspection: By (Role Key) - WSP / TDC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.4 - Broken Face Content
label | Inspection Point: Quality Control Activity - As per NZS 4407:2015
label | Acceptance Criteria - 70% with 2 broken faces
label | Verifying Document - Council / Engineer to approve materials
label | Frequency - 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1
label | Inspection: Key - WSP / TDC
label | Inspection: By (Role Key) - WSP / TDC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.5 - Particle Size Distribution
label | Inspection Point: Quality Control Activity - As per NZS 4407:2015
label | Acceptance Criteria - To be within envelope limits
label | Verifying Document - Council / Engineer to approve materials
label | Frequency - 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1
label | Inspection: Key - WSP / TDC
label | Inspection: By (Role Key) - WSP / TDC
holdpoint | AUTHORITY HOLDPOINT
section | Footpath
checkpoint | Riwaka Gold material being used for the footpath
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - WSP / TDC
label | Inspection: By (Role Key) - WSP / TDC
holdpoint | AUTHORITY HOLDPOINT
section | Asphaltic Concrete 8.0
checkpoint | 8.1 - Surface shape on completion
label | Inspection Point: Quality Control Activity - 3 metre straight edge
label | Acceptance Criteria - Maximum 5mm
label | Verifying Document - Visual
label | Frequency - /
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CS
label | Inspection: By (Role Key) - Construction Supervisor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.2 - Depth
label | Inspection Point: Quality Control Activity - Ruler measurement
label | Acceptance Criteria - -0mm +5mm
label | Verifying Document - Visual
label | Frequency - /
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - CS
label | Inspection: By (Role Key) - Construction Supervisor
holdpoint | AUTHORITY HOLDPOINT
section | Boardwalk 9.0
checkpoint | 9.1 - Refer to DRG 5-G3445.40
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Built to plan
label | Verifying Document - Inspection
label | Frequency - When Required
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - WSP / TDC
label | Inspection: By (Role Key) - WSP / TDC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.2 - Post set out
label | Inspection Point: Quality Control Activity - Ruler measurement / and stringline
label | Acceptance Criteria - Spacing and alignment
label | Verifying Document - inspection
label | Frequency - prior to comencement of driving piles
label | Inspection Type (Visual, other) - Hold point
label | Inspection: Key - WSP
label | Inspection: By (Role Key) - WSP / C
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.3 - Depth of piles
label | Inspection Point: Quality Control Activity - Pre marked on Piles
label | Acceptance Criteria - Minimum 2.5m
label | Verifying Document - measuremnt on piles
label | Frequency - all
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - WSP
label | Inspection: By (Role Key) - WSP / C
checkpoint | 9.4 - Resistance
label | Acceptance Criteria - 60kN
label | Verifying Document - Blows of driver record
label | Frequency - all
label | Inspection Type (Visual, other) - visual
label | Inspection: Key - WSP
label | Inspection: By (Role Key) - construction Supervisor