## CON
|  | ROBINSON CONTRACTORS Ltd and EVERGREEN LANDSCAPING |  | INSPECTION AND TEST PLAN |  |  |  |  | Project Number - DN1203
|  |  |  | Project: NZTA 5363 CIP SH30 Te Ngae Road Corridor-Iles Rd to Coulter Rd |  |  |  |  | Date submitted: September 2023
|  |  |  | Construction Process: Landscaping |  |  |  |  | Prepared By: Downer New Zealand
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: Apendix 5 |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
Setout, Materials and Preparation
.1 | Survey Set Out | GPS Setout of the gardens and treepits as per the construction drawings. | W | All gardens | Visual Inspection | N/A | Contractor's site diary and/or photos | Contractor | Setout location prior to commencing works.
.2 | Underground services | Identify and positively locate services | H | All proposed treepits | Hydro excavation | N/A | Drawings | Contractor
Construction and Finshing
.3 | Gardens for shrubs | Remove existing soil to a depth of 400mm | W | Whole garden | Visual Inspection | 400mm from TOK. Tolerance: - 30mm / +0mm | QC Sheets | Contractor | Drawing 310204560-01-100-C709 Rev 2
.4 |  | Backfill with topsoil 300m | M | Whole garden | Visual Inspection | 100mm from TOK | QC Sheets | Contractor | Plant pit to be dug to twice the width of the rootball
.5 |  | Finish when planting is complete | W | Whole garden | Visual Inspection | 100mm Bark Mulch, Forest floor or Fine nuggets | QC Sheets | Contractor
.6 | Tree pits | Excavate treepits as per layout on drawing | W | All tree pits | Visual Inspection | 750mm from TOK | QC Sheets | Contractor | Check for multiple services within the construction area.
.7 |  | Break up base of tree pit to minimum depth of 300mm | M | All tree pits | Visual Inspection |  | QC Sheets | Contractor
.8 |  | Fill soil to tree pit minimum 750 mm depth: Site won top soil or imported topsoil as per specification, lightly compacted by body weight | M | All tree pits | Visual Inspection |  | QC Sheets | Contractor | Clean topsoil to be used
.9 |  | 150mm Layer of free drainage gravel | M | All tree pits | Visual Inspection |  | Stringsheet | Contractor | At base of tree pits
.10 |  | Install 1.5m x 2m Heavy duty Hope tree root barrier membrane if adjacent to surfaces or utility trenches | M | All tree pits | Visual Inspection |  | QC Sheets | Contractor | Only required where trees are near existing ducts, manholes or footpaths
.11 |  | Import topsoil and plant trees to same level as grown in nursery | M | All tree pits | Visual Inspection |  | Concrete Dockets | Contractor
.12 |  | 75mm layer bark mulch in Amenity area as specified by the Drawing / Specification | M | All tree pits | Visual Inspection |  | QC Sheets | Contractor
.13 |  | Timber stakes driven to 600mm in ground to even height, 3 stakes per tree paced evenly around tree | M | All tree pits | Visual Inspection |  | QC Sheets | Contractor
Close Out
.14 | Collate above documentation | Document review | H | Each ITP | Review | All above documentation is shown as attached to this work pack. | Review | Contractor
.15 | As-built drawings | Survey | H | At completion of construction | Asbuilts to be submitted at the completion of construction, information to be captured | Asbuilts reviewed and submitted | In Eight record | Contractor
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.