## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Landscaping | itp |  |  |  | Yes | ITP - Landscaping
section | Setout, Materials and Preparation
checkpoint | 1 - Survey Set Out
label | Detail of Activity - GPS Setout of the gardens and treepits as per the construction drawings.
label | W
label | Minimum Test Frequency - All gardens
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - N/A
label | Record documents - Contractor's site diary and/or photos
label | Responsibility - Contractor
label | Comments - Setout location prior to commencing works.
checkpoint | 2 - Underground services
label | Detail of Activity - Identify and positively locate services
label | H
label | Minimum Test Frequency - All proposed treepits
label | Inspection / Test method - Hydro excavation
label | Acceptance Criteria - N/A
label | Record documents - Drawings
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
section | Construction and Finshing
checkpoint | 3 - Gardens for shrubs
label | Detail of Activity - Remove existing soil to a depth of 400mm
label | W
label | Minimum Test Frequency - Whole garden
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - 400mm from TOK.
label | Tolerance: - 30mm / +0mm
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Drawing 310204560-01-100-C709 Rev 2
checkpoint | 4 - Gardens for shrubs
label | Detail of Activity - Backfill with topsoil 300m
label | M
label | Minimum Test Frequency - Whole garden
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - 100mm from TOK
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Plant pit to be dug to twice the width of the rootball
checkpoint | 5 - Gardens for shrubs
label | Detail of Activity - Finish when planting is complete
label | W
label | Minimum Test Frequency - Whole garden
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - 100mm Bark Mulch, Forest floor or Fine nuggets
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | 6 - Tree pits
label | Detail of Activity - Excavate treepits as per layout on drawing
label | W
label | Minimum Test Frequency - All tree pits
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - 750mm from TOK
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Check for multiple services within the construction area.
checkpoint | 7 - Tree pits
label | Detail of Activity - Break up base of tree pit to minimum depth of 300mm
label | M
label | Minimum Test Frequency - All tree pits
label | Inspection / Test method - Visual Inspection
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | 8 - Tree pits
label | Detail of Activity - Fill soil to tree pit minimum 750 mm depth: Site won top soil or imported topsoil as per specification, lightly compacted by body weight
label | M
label | Minimum Test Frequency - All tree pits
label | Inspection / Test method - Visual Inspection
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Clean topsoil to be used
checkpoint | 9 - Tree pits
label | Detail of Activity - 150mm Layer of free drainage gravel
label | M
label | Minimum Test Frequency - All tree pits
label | Inspection / Test method - Visual Inspection
label | Record documents - Stringsheet
label | Responsibility - Contractor
label | Comments - At base of tree pits
checkpoint | 10 - Tree pits
label | Detail of Activity - Install 1.5m x 2m Heavy duty Hope tree root barrier membrane if adjacent to surfaces or utility trenches
label | M
label | Minimum Test Frequency - All tree pits
label | Inspection / Test method - Visual Inspection
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Only required where trees are near existing ducts, manholes or footpaths
checkpoint | 11 - Tree pits
label | Detail of Activity - Import topsoil and plant trees to same level as grown in nursery
label | M
label | Minimum Test Frequency - All tree pits
label | Inspection / Test method - Visual Inspection
label | Record documents - Concrete Dockets
label | Responsibility - Contractor
checkpoint | 12 - Tree pits
label | Detail of Activity - 75mm layer bark mulch in Amenity area as specified by the Drawing / Specification
label | M
label | Minimum Test Frequency - All tree pits
label | Inspection / Test method - Visual Inspection
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | 13 - Tree pits
label | Detail of Activity - Timber stakes driven to 600mm in ground to even height, 3 stakes per tree paced evenly around tree
label | M
label | Minimum Test Frequency - All tree pits
label | Inspection / Test method - Visual Inspection
label | Record documents - QC Sheets
label | Responsibility - Contractor
section | Close Out
checkpoint | 14 - Collate above documentation
label | Detail of Activity - Document review
label | H
label | Minimum Test Frequency - Each ITP
label | Inspection / Test method - Review
label | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | Record documents - Review
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - As-built drawings
label | Detail of Activity - Survey
label | H
label | Minimum Test Frequency - At completion of construction
label | Inspection / Test method - Asbuilts to be submitted at the completion of construction, information to be captured
label | Acceptance Criteria - Asbuilts reviewed and submitted
label | Record documents - In Eight record
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - Contractor
label | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | Contractor's Rep Name:
holdpoint | Add Signature
checkpoint | Client Final Inspection - BBO Engineer
label | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | BBO Engineers Rep Name:
holdpoint | Add Signature