## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CTN-ITP-020 - Rock Fill Construction | itp |  |  |  |  | CTN-ITP-020 - Rock Fill Construction
checkpoint | 1.1 - Rock size and strength
label | Specification Requirement - CL 205.03
label | Acceptance Criteria - 205.03(a) Sound rock fragments with at least 2 x broken or angular faces each Test 10 pieces > 100mm for point Load Strength Is(50) of 2.0MPA or better.
label | Inspection Type - TP
label | Inspection Frequency - Prior to delivery
label | Records to attach - Test Results
date | Date Completed:
checkpoint | 1.2 - Post-Compaction Grading
label | Specification Requirement - CL 205.03 – Table 205.031
label | Acceptance Criteria - Post compaction grading complies with the Limits of Grading ion Table 205.031.
label | Inspection Type - HP
label | Inspection Frequency - Prior and/or During Works
label | Records to attach - Grading report
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Geotextiles
label | Specification Requirement - CL 205.03(b)
label | Acceptance Criteria - Geotextiles used in rock fill shall have G robustness rating greater than 3000.
label | Inspection Type - Check / inspect
label | Inspection Frequency - Prior to placing initial rock layer
label | Records to attach - Specification sheet, roll label and manufacturers test report.
date | Date Completed:
checkpoint | 1.4 - Fill Construction
label | Specification Requirement - CL 205.05 )a), CL 204.10 (b)
label | Acceptance Criteria - The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
label | Inspection Type - HP
label | Inspection Frequency - Prior to Fill Placement
label | Records to attach - HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Trial placement and compaction
label | Specification Requirement - CL 205.06
label | Acceptance Criteria - For each material type and grading, the first and second layer shall be trialled:
label | – An area > 1000m2
label | – Rolled for the greater of - until no further consolidation, or 15 passes.
label | – Be surveyed after each roller pass, measure minimum of 20 points.
label | – Engineer / Supervisor / QAV review survey results to determine the number of passes before refusal occurs.
label | Inspection Type - HP
label | Inspection Frequency - Prior to Fill Placement
label | Records to attach - HP Release, consolidation record
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1 - Placement & Compaction
label | Specification Requirement - CL 205.06
label | Acceptance Criteria - Proceed with placement and compaction in accordance with the approved procedure. Maintain layer thicknesses and material size in accordance with 2.2, 2.3 and 2.4 above.
label | Inspection Type - HP
label | Inspection Frequency - Every Lot
label | Records to attach - Placement and compaction record
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Level Control
label | Specification Requirement - CL 205.05(d)
label | Acceptance Criteria - Survey each layer for conformance with tolerance. +/- 100mm Intermediate layers
label | Inspection Type - WP
label | Inspection Frequency - Every layer
date | Date Completed:
checkpoint | 3.3 - Test Rolling
label | Specification Requirement - CL 205.07
label | Acceptance Criteria - Undertake test roll for each layer as per Section 173. Rectify any identified failed areas.
label | Inspection Type - WP
label | Inspection Frequency - Each layer
date | Date Completed:
checkpoint | 3.4 - Cover layers
label | Specification Requirement - Table 205.051
label | Acceptance Criteria - Material size and layer thickness per Table 205.051, Test Roll each layer
label | Inspection Type - WP
label | Inspection Frequency - Each Layer
label | Records to attach - Test roll record
date | Date Completed:
checkpoint | 3.5 - Level Control
label | Specification Requirement - CL 205.05(d)
label | Acceptance Criteria - Survey final layer for conformance with tolerance. +0mm / - 100mm
label | Inspection Type - WP
label | Inspection Frequency - Every layer
date | Date Completed:
checkpoint | 3.6 - Geotextile separation
label | Specification Requirement - CL 205.05 (b)
label | Acceptance Criteria - Geotextiles used in rock fill shall have G robustness rating greater than 3000.
label | Inspection Type - Check / inspect
label | Inspection Frequency - Prior to placing initial rock layer
label | Records to attach - Specification sheet, roll label and manufacturers test report.
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with Gradco’s Quality System Procedures and verifies lot compliance with specifications
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: