## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP 005 - Fixtures & Fittings (NFH) |  |  |  |  | Yes | ITP 005 - Fixtures & Fittings (NFH) | 197f2322-6476-49a8-be58-79a54986b4f4
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Spec. Ref: HY-SP-002
text | 73369c00-965d-5548-b2fe-80c432c4ceb0 |  | textbox | Drawing Ref & Revision #
text | 574cf04e-4e75-59f9-8459-e83865920b49 |  | textbox | Service & Fitting Types:
checkpoint-status |  |  | checkpoint | Correct Items Installed
label | f33c7173-0c52-5a8d-bafa-6bdaa5854708 |  | note | Acceptance Criteria / Reference: As per approved shop drawings
label | f9243d35-5113-5974-8f47-014ef383e8ba |  | note | Inspection Type: Hold Point
checkpoint-status |  |  | checkpoint | Items are of High Quality
label | 96ac0ecb-9734-53f1-b3a6-30b6d72155f7 |  | note | Acceptance Criteria / Reference: No apparent damage - free of cracks, chips, crazing or other defects
label | 58473d74-660e-5b05-bd9b-b78c77bb3c4e |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Sealant
label | 0a10dc28-a9bb-5767-9889-b0675f1f603b |  | note | Acceptance Criteria / Reference: Sealant is neat, correct type, colour and volume
label | 6c942ee1-efd8-5c49-a69a-dfce3f473d78 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Fittings Installed Straight
label | 01829d9c-2d5b-5bda-adde-2fd56747ae98 |  | note | Acceptance Criteria / Reference: Visual inspection
label | 89ee9666-ad8e-58e9-ba90-b227648b1d68 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Access Panels are Installed
label | f1757726-9206-5826-8fde-e27e8d7d137d |  | note | Acceptance Criteria / Reference: As per approved installation drawings
label | f6cceae8-b66f-5944-92c5-39bda0ec83c4 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | WC's
label | f90e749f-f504-512c-885d-110f773f06ea |  | note | Acceptance Criteria / Reference: Fixed with levelling brackets after floor installation, seat lid is secure
label | 5f5dca03-267d-507c-9d12-5e8c6ea6c00d |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Items all Operate Correctly
label | 552558fe-b3d4-5b02-b12a-6a525319b89f |  | note | Acceptance Criteria / Reference: Check each item for operation – hot and cold if applicable and have no leaks
label | 3c17e1b6-0189-56a3-a4b1-173967a91d03 |  | note | Inspection Type: Testing
label | daa1fa8e-3594-5c84-9618-55c4d79c32c8 |  | note | Refer commissioning plan for disinfection and flushing of mains, TMV commissioning and cross connections potable & recycled water
checkpoint-status |  |  | checkpoint | Sign-Off Completed
label | 60300e98-8ade-5452-becf-5c1a0eff13d4 |  | note | Inspections carried out by
text | 345b1d60-8cdb-5f45-bb48-7a88813b811a |  | textbox | Name
text | 2396407c-b18d-5355-9c9e-2474f962ddcf |  | textbox | Organisation
label | 7a939dd6-934a-5e31-b0d5-789f1d04d665 |  | note | Signature(s) attached below
checklist-flat |  |  | checklist | Commissioning (V.061221) |  |  |  |  | Yes | Commissioning (V.061221) | 2d44d1a7-cecc-4512-a591-5aafd7663e3c
checkpoint-status |  |  | checkpoint | Check products for imperfections
checkpoint-status |  |  | checkpoint | Fixtures location & fixings all correct (as per drawings & samples)
checkpoint-status |  |  | checkpoint | Clean out all strainers / aerators
checkpoint-status |  |  | checkpoint | Check for no cross connections / leaks / access to isolation valves
checkpoint-status |  |  | checkpoint | Floor wastes (clear of debris & draining correctly)
checkpoint-status |  |  | checkpoint | Quality of silicone seals to fixtures acceptable
checkpoint-status |  |  | checkpoint | Hot water tempering valve set to 50c (+/- 5c) & DDA thermostatic mixing valve set to 42 degrees.
checkpoint-status |  |  | checkpoint | Water pressure acceptable 350Kpa to 500 Kpa
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | e91f7631-63b2-54a7-a141-4a27bd0b4a59 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 32f6ad6b-71aa-5f3c-b440-d97e637fbe92 |  | note | Click to Attach Signature(s) below
button | 3b8b927b-9a56-5c58-99b7-033b210c6d6c |  | button | Signature by Builders Site Coordinator | Yes, No
button | 894fb203-d84b-508c-ae1e-b2dca7dfb925 |  | button | Planet Plumbing Signature Sign-Off added below | Yes, No
checklist-flat |  |  | checklist | Document Attachment Checklist (V.081021) |  |  |  |  | Yes | Document Attachment Checklist (V.081021) | 50fe9f58-b988-4fa4-940e-2df6ca87d132
checkpoint-status |  |  | checkpoint | Documents attached for reference - Pass once attached
checklist-sectioned |  |  | checklist | ITP 003 - Drainage Above Ground (NFH) |  |  |  |  | Yes | ITP 003 - Drainage Above Ground (NFH) | 5e8c65c4-d689-47ed-a011-136f8848cd4f
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Spec. Ref: HY-SP-002
text | b2250e7a-651c-5aa8-9ba9-96840cd00ee8 |  | textbox | Drawing Ref & Revision #
text | ce9fae50-c934-5b18-b6a5-06e1f461b4c3 |  | textbox | Service Type
boolean | ba9003fe-465e-505a-839b-9f66f6e7e06b |  | tickbox | Stormwater/Syfonic
boolean | 8c0a0f47-a36a-51c7-8d10-4c64ed612988 |  | tickbox | Sanitary Drainage
boolean | 3d90e593-3819-5617-ac3d-d21df4c86ed9 |  | tickbox | Trade Waste
text | aa119712-8119-51d5-9946-9d4bc6ef7392 |  | textbox | Other:
checkpoint-status |  |  | checkpoint | Set Out and Alignment
label | 2df43df2-3e29-5c93-a569-33b4f322afea |  | note | Acceptance Criteria / Reference: Approved shop drawings
label | ad7cd08e-c6d2-5e5d-b4fd-7a5698d0ee20 |  | note | Inspection Type: Hold Point
checkpoint-status |  |  | checkpoint | Inverts and Grades
label | 4b9f52e8-2d9f-59a2-b175-efe0dadef622 |  | note | Acceptance Criteria / Reference: Approved shop drawings
label | f6d56e09-2141-562b-841a-520b4025a5d6 |  | note | Inspection Type: Hold Point
checkpoint-status |  |  | checkpoint | Brackets Installed Correctly
label | 9d0ea752-d41d-5d4b-8e3f-6b8df8c54188 |  | note | Acceptance Criteria / Reference: Bracket spacing as per AS3500
label | f6af9b7d-ce54-58b1-b47b-4c0500a4c7a4 |  | note | Inspection Type: Normal Inspection
label | 6040ecfb-374b-5ac6-bf33-814862b54462 |  | note | Refer to seismic drawings for restraints
checkpoint-status |  |  | checkpoint | Pipe Material Correct
label | 3f66aa29-0431-536f-9492-9db66cb87b2e |  | note | Acceptance Criteria / Reference: As per approved shop drawings
boolean | 27ccecc4-6e5b-5585-b9a3-00c9d1b7f050 |  | tickbox | PVC
boolean | 4e2d720e-02dc-5646-a343-1fbce12cc277 |  | tickbox | HDPE
text | 363a4667-7974-525d-8576-96c038d13350 |  | textbox | Other
label | d2b6ce9a-38f9-50b7-9bdd-a675612f6f0e |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Inspection & Testing Prior to Concealing
label | 7ba193b3-b38e-508d-b4bf-d4f697d1b094 |  | note | Acceptance Criteria / Reference: AS3500.2
label | 955ea715-6efa-54fb-aee5-78fea54b5fbf |  | note | Test Type:
boolean | 29797063-9f39-5808-90f5-3727e621d3f4 |  | tickbox | Hydrostatic Test as per AS3500.2,15.2
boolean | 721a3b03-27ed-56b4-b231-0be08825b4f2 |  | tickbox | Air Test as per AS3500.2,15.3.2
label | 5d4fb31e-39b5-593e-aa70-0770433ecac8 |  | note | Inspection Type: Hold Point, Test, Witness
label | 68d0978c-15e2-5d84-b476-c534cf1bb6e3 |  | note | REF TEST CRITERIA; Hydrostatic Test - Fill with water and must show no leaks Air Test - To hold at 30kPa for a minimum of 3 minutes
checkpoint-status |  |  | checkpoint | Pipework Labelling
label | 20aaef5a-c86b-5a7f-a125-4c47e1a10b99 |  | note | Acceptance Criteria / Reference: As per AS1345
label | 351d4fa2-597a-58a1-b5b4-9b970e6051a8 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Floor Waste Riser Length
label | 2a80a8ab-6c4b-527d-b90d-0d5df6afa838 |  | note | Acceptance Criteria / Reference: Check not to be greater than 600mm from water level to FFL
label | 2bbe93f5-bb92-5f2d-8388-9300559b6362 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Acoustic Lagging
label | 24e5e6c0-aab4-5cbf-897f-c4fc038b2215 |  | note | Acceptance Criteria / Reference: Secure and full coverage
label | 5bbac98b-85b3-507f-bf61-074f89daa83b |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | As Built Information Recorded
label | 3f29e896-2c5b-535c-9ef9-546345877896 |  | note | Recorded on shop drawings as required prior to concealment
label | 6cd37909-8912-5fb3-b146-892b8a1ac3a7 |  | note | Inspection Type: Shop Drawings
checkpoint-status |  |  | checkpoint | Sign-Off Completed
label | a97b7065-4364-5b74-a6de-e52fc0694c00 |  | note | Inspections carried out by
text | 7165a2eb-02f7-54a8-a1c7-a15f946243cb |  | textbox | Name
text | 7e5a85c6-85c0-5622-a4c5-f195e1685d65 |  | textbox | Organisation
label | b395d81f-0242-59cf-9939-2a8eb8595f37 |  | note | Signature(s) attached below
checklist-flat |  |  | checklist | Drawing Upload - Checklist (V.101221) |  |  |  |  | Yes | Drawing Upload - Checklist (V.101221) | 7d52a5c2-7fb9-402a-8bde-a8be52699a31
checkpoint-status |  |  | checkpoint | Drawings/comments/signatures - attached below
checklist-sectioned |  |  | checklist | ITP 004 - Reticulated Above Ground (NFH) |  |  |  |  | Yes | ITP 004 - Reticulated Above Ground (NFH) | 81eda1b1-40e9-4662-939d-6b5d96f522cb
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Spec. Ref: HY-SP-002
text | 893390b6-1f1d-59b2-9235-ca1d35174eaf |  | textbox | Drawing Ref & Revision #
text | 971cedb6-31b4-53c1-b65e-9196abeecd9a |  | textbox | Service Type:
boolean | 61e9cf5d-0e69-50e0-9939-e4b5ef47d7b0 |  | tickbox | Cold Water
boolean | 58331637-ab8f-5760-aa12-44336d5827e8 |  | tickbox | Hot Water
boolean | a9e6b0ee-9ec8-5923-bf1a-524466810dc8 |  | tickbox | Recycled Water
boolean | e1bc2591-ff40-576e-af1e-a932d75866c0 |  | tickbox | RO Water
boolean | 891623b1-73a1-523a-88ca-40b63dc1915a |  | tickbox | Gas
text | bd30ce6e-95f7-57c3-a02d-2a4d9b140756 |  | textbox | Other:
checkpoint-status |  |  | checkpoint | Set Out and Alignment
label | ee86b21a-caaf-5e42-808e-41cfa7e5c5d3 |  | note | Acceptance Criteria / Reference: Approved installation drawings
label | e19567ff-de20-5c4f-b72c-350e1702efd9 |  | note | Inspection Type: Hold Point
checkpoint-status |  |  | checkpoint | Inverts and Grades
label | 3a0fac22-bfe3-531b-895f-fb84c4ee90c9 |  | note | Acceptance Criteria / Reference: Approved installation drawings
label | f22eafb3-cc65-52bf-950e-9f06ab07166e |  | note | Inspection Type: Hold Point
checkpoint-status |  |  | checkpoint | Brackets Installed Correctly
label | 202c4582-39f4-5b1d-b960-f3ae6967eccf |  | note | Acceptance Criteria / Reference: Bracket spacing as per AS3500
text | ad40a2ee-a2dc-51ef-bd34-467be9298049 |  | textbox | Bracket Types
label | 437bf8c3-e9b4-543f-a661-d8ee3033def8 |  | note | Inspection Type: Normal Inspection
label | 6c2e4992-a1f9-5134-8041-bf025a0ea2a6 |  | note | Refer to seismic drawings for restraints
checkpoint-status |  |  | checkpoint | Pipe Material Correct
label | f12b3891-25a6-5668-8ce4-9a79d6204e3c |  | note | Acceptance Criteria / Reference: As per approved installation drawings
label | 24bdff79-b921-53d2-b259-2ea8e129e4d9 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Inspection & Testing Prior to Concealing
label | 306d29e6-0eb7-5aed-8b7b-52c400eee159 |  | note | Acceptance Criteria / Reference: Pressure Test completed per AS3500
label | acaf30c2-7fb3-5dc3-a947-f56d88187c4d |  | note | Test Type:
boolean | 79673e4b-f5be-5e65-9c5f-1012d926e8f1 |  | tickbox | Water as per 3500.4, 9.3
boolean | 9ccf7f9d-b75c-5382-abba-cb870c26258c |  | tickbox | Air as per AS5601:2013, Appendix E4
text | a79d7108-7ff7-52e4-bbb9-d7761a99a234 |  | textbox | Pressure (kPa)
text | 8d4a024a-6f95-5517-809d-1135214ee35c |  | textbox | Duration
text | 20480891-b0b0-523b-8071-06265d555a39 |  | textbox | Gauge/Serial Number:
label | 5125b94f-a9f9-567c-b0bf-fbee01ad7a94 |  | note | Inspection Type: Hold Point, Test, Witness
label | 48e257e2-ae9d-56e6-8f08-98d720e55db1 |  | note | REF TEST CRITERIA; Water: 1 ½ times the working pressure or 1500kPa for a period of not less than 30 minutes. Air: 1 ½ times operating pressure or minimum of 7kPa. Time depends on pipe volume.
checkpoint-status |  |  | checkpoint | Pipework Labelling
label | 3b6bf6cd-07b9-5094-8910-85e7dc59cd10 |  | note | Acceptance Criteria / Reference: As per AS:1345
label | 9da23dae-6140-52cd-b730-e42c93d2a56e |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Thermal Lagging
label | ca0362b2-4f45-5726-b433-84455ad62c27 |  | note | Acceptance Criteria / Reference: Secure and full coverage
label | a72466ad-168b-538a-95f2-a5cd58682067 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | As Built Information Recorded
label | 0b5a8d8b-abf9-5af2-8d43-d1d97a103e09 |  | note | Recorded on shop drawings as required prior to concealment
label | d0b2f21d-ed8b-50ee-a5a2-0aec37fb88f8 |  | note | Inspection Type: Shop Drawings
checkpoint-status |  |  | checkpoint | Sign-Off Completed
label | 56354379-f00a-5a5c-b9d5-40e7a86c506a |  | note | Inspections carried out by
text | 78e159c6-1b25-519f-8137-28c15404fe0d |  | textbox | Name
text | 7648859d-f96e-5302-9ab3-968dd8312151 |  | textbox | Organisation
label | 03caecb6-e997-5711-a6cd-8c9493d9eaf3 |  | note | Signature(s) attached below
checklist-sectioned |  |  | checklist | ITP 001 - Drainage In Ground |  |  |  |  | Yes | ITP 001 - Drainage In Ground | 963a473a-c846-4555-adce-e9ee019caba2
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Spec. Ref: HY-SP-002 / MA Civil Specification
text | 08e2659f-fef0-5e4f-982b-267218d87902 |  | textbox | Drawing Ref & Revision #
text | 7b28dce1-6a93-55a0-9a4e-901f5df210d0 |  | textbox | Service Type
boolean | 1a15bdb9-2225-5c4f-96f4-9c8d9ca5f653 |  | tickbox | Stormwater
boolean | 574bac30-254a-5bfb-ab66-21cee42e63f7 |  | tickbox | Sanitary Drainage
boolean | 94ae9ea1-dc25-5aaf-affd-942855d69940 |  | tickbox | Trade Waste
text | 834082e7-9446-56df-be4f-189ea06ae147 |  | textbox | Other (Specify Here)
checkpoint-status |  |  | checkpoint | Set Out and Alignment
label | 81369400-b035-5a57-88b7-ea32e3c9c19b |  | note | Acceptance Criteria / Reference: Approved installation drawings
label | aa691395-be8c-5f7f-a2f1-b07201133dcb |  | note | Inspection Type: Hold Point
checkpoint-status |  |  | checkpoint | Inverts and Grades
label | 3eceb31e-3384-50db-8f0f-928af7f5885a |  | note | Acceptance Criteria / Reference: Approved installation drawings
label | 9c65fbea-d323-5237-a319-8d0d03b44be1 |  | note | Inspection Type: Hold Point
checkpoint-status |  |  | checkpoint | Pipe Bedding Material
label | 081c379b-4a0a-5aba-8654-bc80cfe65e0d |  | note | Acceptance Criteria / Reference: As per specification
text | ca0b78fb-7676-5623-a4c6-7abf017d081a |  | textbox | Specification
label | 1d0d2fec-6ee5-5cf6-b8ac-5f46c6205f7c |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Pipe Material Correct
label | f89f8bfa-5f79-5e1f-8ac0-edeb471fffbb |  | note | Acceptance Criteria / Reference: As per approved installation drawings
boolean | 2495c3ea-9d2c-58a5-8e2b-e50a38688089 |  | tickbox | PVC
boolean | eac73e66-8942-52cb-b81d-9f15878f78d9 |  | tickbox | HDPE
boolean | cd8cf1cf-08ab-504d-ba8a-de4139678ded |  | tickbox | STORMPRO
boolean | d1e88cb2-44a1-5994-bd93-7895694a6199 |  | tickbox | RCP
text | 954bf3c5-989a-5490-ac33-abaa9774629b |  | textbox | Other
label | 3839d707-e8b7-565a-b8f5-28d6bff1fc28 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Inspection & Testing Prior to Concealing
label | 09a4cb0d-a97d-5869-8afd-d699928506be |  | note | Acceptance Criteria / Reference: AS3500.2
label | c4f77297-8979-5650-bcb6-c0ac67a720bc |  | note | Test Type:
boolean | 287580e6-cf78-5c50-b810-5d0a24650bb0 |  | tickbox | Hydrostatic Test as per AS3500.2,15.2
boolean | 67d73e15-bbe1-5da7-aa84-8c181e3cfa25 |  | tickbox | Air Test as per AS3500.2,15.3.2
label | 7e044513-602e-54bf-b7f7-4053515bc14e |  | note | Inspection Type: Hold Point, Test, Witness
label | 90014c09-0310-5bab-ad1b-bd5113015f81 |  | note | REF TEST CRITERIA; Hydrostatic Test - Fill with water and must show no leaks Air Test - To hold at 30kPa for a minimum of 3 minutes
checkpoint-status |  |  | checkpoint | Seal Open Drainage Points
label | 794914ac-bedd-550d-97d9-1e790eaa7b3e |  | note | Acceptance Criteria / Reference: Sealed
label | ac123000-35d1-5b42-a0c2-a8faf25bdadd |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Backfill Trenches & ID Tape
label | 7d98068b-f464-5ae7-b2f5-5492aa27d7c0 |  | note | Acceptance Criteria / Reference: Existing material used for backfill or approved alternative (details in comments) . ID Tape laid 300mm OVER SERVICE
label | 9f9aeaca-f517-56a7-b21c-f94fe9437ef9 |  | note | Inspection Type: Normal Inspection
label | 191bc5f9-fd10-5fc0-95e1-a74566d05a6c |  | note | Comment: Detail as per Planet Plumbing shop drawing
checkpoint-status |  |  | checkpoint | As Built Records
label | 73caf0e4-7fdc-5857-97f8-8b17d055ebcb |  | note | Survey as installed works and update As-Built
checkpoint-status |  |  | checkpoint | Compaction and Compaction Testing
label | 28a68dd9-2559-5bd9-bff4-3a3afc21fc4e |  | note | Acceptance Criteria / Reference: Stabilised sand backfill, N/A, Landscaped areas N/A
label | 8f21b44e-bfb7-5022-a511-4a12ea229c56 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | CCTV & Photo Records
label | d82b8771-5d25-573c-80e5-a53245abf189 |  | note | Acceptance Criteria / Reference: Photo records during installation works and CCTV after backfilling. Attach reference drawing
label | ba71aa85-7e3c-5805-befd-3802647c328d |  | note | Refer Independent CCTV records prior to Practical Completion
label | 9a72ee48-dcfb-58e2-8f8c-c196f6d3cb81 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Sign-Off Completed
label | 47bca4be-a97a-59b7-af90-f3a6c7e53ec3 |  | note | Inspections carried out by
text | 3206ae2f-6e51-5658-94ab-93c25290c6b6 |  | textbox | Name
text | b9c54dff-aa43-5700-a13c-7005e34d60e6 |  | textbox | Organisation
label | aa3b8492-daa7-597d-bf95-b8d843dd2f59 |  | note | Signature(s) attached below
checklist-sectioned |  |  | checklist | ITP 002 - Reticulated Systems In-Ground |  |  |  |  | Yes | ITP 002 - Reticulated Systems In-Ground | edc293b6-695d-4c42-b328-e5038a7592eb
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Spec. Ref: HY-SP-002
text | ba1f9383-3ac6-5623-a4e1-f050fc20a7ca |  | textbox | Drawing Ref & Revision #
text | 86ba0723-8deb-59da-b58a-dacd7da4badb |  | textbox | Service Type
boolean | 2d58483b-0eb1-57bf-9b9e-512c58e74d34 |  | tickbox | Cold Water
boolean | 95441638-5e5d-59a7-843c-63b33f5231b2 |  | tickbox | Recycled Water
boolean | 45a1e5a0-1a08-5277-be31-a2edb7c9cd09 |  | tickbox | Gas
text | 2a61b76f-e220-549e-a1d4-25dbcbaef265 |  | textbox | Other:
checkpoint-status |  |  | checkpoint | Set Out and Alignment
label | 55c467e3-32b1-57fc-88c7-153106f367d3 |  | note | Acceptance Criteria / Reference: Approved shop drawings
label | 67a87fdc-042e-5f31-9af8-f5007f7c87f5 |  | note | Inspection Type: Hold Point
checkpoint-status |  |  | checkpoint | Inverts and Grades
label | 32e2ffc6-d2fa-5834-9933-43a2baa01b8c |  | note | Acceptance Criteria / Reference: Approved shop drawings
label | 60a0bee1-c1a0-5e69-96c4-12b4eb22ef52 |  | note | Inspection Type: Hold Point
checkpoint-status |  |  | checkpoint | Pipe Bedding Material
label | 0e227125-0001-5e6e-9973-e7145b4bd688 |  | note | Acceptance Criteria / Reference: As per specification
text | c8808698-314d-5757-98f4-d5bf63edf008 |  | textbox | Specification
label | 22e60ef4-75d3-537f-96e2-55a6dbf907df |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Pipe Material Correct
label | ba08bfe2-3a4a-5757-af93-2f6a3e3fd8be |  | note | Acceptance Criteria / Reference: As per approved installation drawings
label | 3b5256ba-9f10-506d-8e4a-5d4dc97c6f37 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Electrofusion/Flange Joints
label | 24a339f4-0abd-59bc-8707-f2fe36d2f5e4 |  | note | Acceptance Criteria / Reference: Visual check on joints
label | c9e09e4d-1a8b-5bf7-8c56-86cc40333479 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Inspection & Testing Prior to Concealing
label | bb52353a-fa11-5c0f-8fd5-340ffe24e198 |  | note | Acceptance Criteria / Reference: Pressure Test completed per AS3500 or AS5601:2013
label | 7547a849-1c37-5e1d-a9b3-de092053a16a |  | note | Test Type:
boolean | daed0ed7-5b2f-56b5-9643-166144c57b3c |  | tickbox | Water as per 3500.4, 9.3
boolean | 58ddb1e5-fc14-517a-b572-b8d848087d00 |  | tickbox | Air as per AS5601:2013, Appendix E4
text | 8378f505-b458-5d4f-bbc8-ad2ce1e84070 |  | textbox | Pressure (kPa)
text | a71e8101-99a8-5ef1-bbc1-bf1d55471021 |  | textbox | Duration
text | d84ad389-cdbb-574a-9c94-a5ae15aeaeaa |  | textbox | Gauge Number
label | df9169bd-c8b0-59e1-8ae3-a7761559b131 |  | note | Inspection Type: Hold Point, Test, Witness
label | 052c0aea-1b4c-5ddf-bf3e-85ab927613ef |  | note | REF TEST CRITERIA; Water: 1 ½ times the working pressure or 1500kPa for a period of not less than 30 minutes. Air: 1 ½ times operating pressure or minimum of 7kPa. Time depends on pipe volume.
checkpoint-status |  |  | checkpoint | As Built Records
label | 72ab149b-ea08-5b1a-8db1-1734e4bd2f02 |  | note | Survey as installed works and update As-Built
checkpoint-status |  |  | checkpoint | Backfill trenches
label | 9e4d76fb-a2c6-5db9-82d2-a8cc8b025540 |  | note | Acceptance Criteria / Reference: Existing material used for backfill or approved alternative (details in comments)
label | 2ce3d405-cb4e-58cb-a0ae-c17612586e36 |  | note | Inspection Type: Normal Inspection
checkpoint-status |  |  | checkpoint | Compaction and Compaction Testing
label | 4c3562bd-4240-5d51-95a1-704c39655bdb |  | note | Acceptance Criteria / Reference: To AS1289
label | 0d665d18-eb02-53d2-a02f-8b6e31ecd832 |  | note | Inspection Type: Test
checkpoint-status |  |  | checkpoint | Sign-Off Completed
label | b49f3afa-e828-5f03-bc7d-a2ece18b27a9 |  | note | Inspections carried out by
text | dc065df3-d0f0-57b6-96f8-02e241fdd2f6 |  | textbox | Name
text | aa657bcf-b973-5362-be50-0710462a7a62 |  | textbox | Organisation
label | 90bae70d-07fa-5e18-90d4-dba1d7c040f1 |  | note | Signature(s) attached below