## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
078399e2-962f-4f71-8310-e59835e982f7 | checklist | ITP - Traffic Services - 809 - Rev 1 | itp | ITP - Traffic Services - 809 - Rev 1
5c26fa3c-c8d8-4b72-8004-2af52ec96e99 | section | 3.01 - General
a4cb808b-65b1-4175-a4d1-66c4149f2acc | checkpoint | 3.01.01 - Precondition Surveys
2a282d77-07d7-583e-b770-6cfbf6013471 | note | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
33c82791-aed6-59e6-b7b9-e5e1d8f3dd07 | note | Standard / Specification - PS 2.13
345098f4-1ddd-553b-a95c-eefb75fce1d3 | note | Verifying Document - Precondition Survey
d5eb6930-5de5-5d02-93fe-15c9f8bf39f7 | note | Frequency - Prior to the Contractor taking possession of the Site.
5fb3d95a-5df2-5b74-8a74-f17ddb6ca862 | note | Verification Activity: Activity - H
1633d4da-f7bd-51a5-a343-9d7818a9d201 | note | Verification Activity: By - PM
91dc205e-67dd-44d3-83c5-5c99c026b870 | section | 4.34 - Traffic Service Materials
51f6be55-069c-441a-9f7f-1241236d5cb1 | checkpoint | 4.34.01 - Safe Lane Delineator and Guard Rail Concrete
12218cce-9571-5ccc-91a9-f44751d35da4 | note | Acceptance / Conformance Criteria - Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days.
5eb42641-14de-57bc-aad7-43c862fdb48b | note | Standard / Specification - PS 23.7, PS 23.6, M23
3f2e4fcb-bc20-54b3-aacb-f60c0c95f5b7 | note | Verifying Document - Delivery Dockets/Test Cube Results from Supplier
f741a807-9e14-54f4-ae4d-da09188b8720 | note | Frequency - Prior to use
14b5aeb8-8f46-5e0e-b386-ec972e9fdc9e | note | Verification Activity: Activity - R
322c5154-0320-5dc9-a6e4-741ee8d04e9c | note | Verification Activity: By - SE
3b421434-6c8f-48af-b283-e97bf459d14e | checkpoint | 4.34.02 - Proposed Guard Rails (including Wire Rope Barriers)
6cc58598-f842-58c0-a666-ed2744d22a84 | note | Acceptance / Conformance Criteria - The Contractor shall submit details of proposed proprietary materials and systems. Submission to include checklists, post spacing, footing type and barrier deflection for both wire rope and w beam barrier in accordance with M23
674d86d5-f155-5d12-a50c-8c1acc91a208 | note | Standard / Specification - PS 23.6, M23
db6d801e-ef17-5320-8fd4-835e87e7963b | note | Verifying Document - Datasheets
932da17e-dec7-5790-ab2a-e3678d920e90 | note | Frequency - Prior to material order (4 weeks prior to installation)
d728715c-5617-5bc0-aa5e-436f5ef76637 | note | Verification Activity: Activity - HP
92f04e96-45b9-56c8-82b8-54ee2dfb5f69 | note | Verification Activity: By - ENG
5c7fe200-8c40-4805-8ad0-8daada82381c | signoff | AUTHORITY HOLDPOINT
a81a5211-5c80-478a-b90f-0653ecd94977 | checkpoint | 4.34.03 - Guard Rail Maintenance Instructions
573dedf2-944b-525a-8b58-b83a7e18abda | note | Acceptance / Conformance Criteria - The Contractor shall submit details of the manufacturers maintenance instructions for the type of barrier installed.
0c51e013-d3b5-5b67-a61e-77c47587c1e5 | note | Standard / Specification - PS 23.6, M23
9e157d03-aa2e-5c33-b3cb-e37ce8f593c4 | note | Verifying Document - Maintenance Instructions
7172b5b5-8b67-5fbc-a655-015c66195183 | note | Frequency - Upon completion of the Guardrail Construction
dca0b275-bb69-508d-88da-1b47f0dcec16 | note | Verification Activity: Activity - HP
2c377e67-2cca-5163-b015-973b3447f816 | note | Verification Activity: By - ENG
c1475a85-ea4c-4aaf-ae0d-2ec3c078bb4c | signoff | AUTHORITY HOLDPOINT
5f436252-d900-43ea-8cde-7c5ac7558077 | checkpoint | 4.34.04 - Coloured Surfacing
95b8adf1-c98f-5ff3-a281-60f71bfacd56 | note | Acceptance / Conformance Criteria - The contractor shall provide evidence to the Engineer before preparation and marking of the surfacing, that the material conforms in its entirety to the requirements of NZTA P33.
db5a0221-6338-5548-b228-6ba58b973a5b | note | Standard / Specification - PS 23.4
e80c4edf-9c61-5104-a3af-75827d4418fc | note | Verifying Document - Datasheets
0cb0987d-a7c4-50c3-894d-494e2dc9ff9f | note | Frequency - Prior to use
909cd1f8-7fe4-5623-b117-dc13ea618889 | note | Verification Activity: Activity - R
4bef5a00-9bff-5a1b-9bfa-d72c98dac370 | note | Verification Activity: By - SE
16c1f2b5-818d-4943-ad31-f087d24e0f1f | section | 4.35 - Sign Materials
0fdddb75-3063-4936-9fe0-7f3000f1cdea | checkpoint | 4.35.01 - Retro-reflective sheeting
1c2abc8d-623b-5e32-81c9-2974577cdbb5 | note | Acceptance / Conformance Criteria - All retro-reflective sheeting must be approved for use in New Zealand and comply with the following requirements of NZTA P24 Specification for Permanent Traffic Signs and AS/NZS 1906.1: 1993 Retro-reflective Materials and Devices for Road Traffic Control Purposes, Part 1 Retroreflective Sheeting.
7142a9b0-e2e8-5759-9ee2-be798a537cf5 | note | Standard / Specification - PS 23.2.6
7fb75964-b2e1-5001-b6a2-1395a1d81d2a | note | Verifying Document - Datasheet
c45fe06d-2128-5c2d-bc5a-3cbad6a85e93 | note | Frequency - Prior to use
f37e0bc6-c92c-5888-8e0b-e18087590157 | note | Verification Activity: Activity - R
c4af15d4-13b4-5c3d-ad31-f331ae4eacff | note | Verification Activity: By - PE
5364b394-dada-4840-b2d9-7dc3cd3dcaff | checkpoint | 4.35.02 - Anti-Graffiti Coating
9f7ddf07-3e7d-5344-9851-9b4a6b389cc8 | note | Acceptance / Conformance Criteria - Graffiti protective coating shall be applied to all ground mounted sign and shall be approved for such use by the reflective sheeting manufacturer and shall maintain all guarantees for the sign.
4b65ac20-280a-5a13-8df6-3138d2a6ca5a | note | Standard / Specification - PS 23.2.14
aaa1b925-a999-543c-9b51-10d6837f5bac | note | Verifying Document - Datasheet
76ee4a23-5bcc-52b7-bc98-2806d01b46c3 | note | Frequency - Prior to use
ac2513c3-3c87-5cc3-9712-b7e929ea349a | note | Verification Activity: Activity - R
fe62e98a-3ed6-5679-a6fa-3d76495911e8 | note | Verification Activity: By - PE
383a5b00-91c8-4058-ab47-689deca77eec | checkpoint | 4.35.03 - Dew Effect Coating
0ebc8646-e378-5662-a4e9-8790a37e11e4 | note | Acceptance / Conformance Criteria - All overhead mounted signs, except for bridge name plates, shall be manufactured with an overlay that is designed to prevent dew droplets forming to overcome the phenomenon known as ‘dew effect’. Conractor shall submit special handling and washing methodology for installation of dew effect coated signs
12d37e2b-e584-5e70-b055-5d98bdc9f3c8 | note | Standard / Specification - PS 23.2.15
8425d970-4e50-56f3-b674-7b72f627f21e | note | Verifying Document - Datasheet
34641d00-0afe-5f93-995e-6eecb4586ace | note | Frequency - Prior to use
1dcaeb9d-6744-581b-b9b2-6fde525ac12b | note | Verification Activity: Activity - R
7b803d43-42b9-54f5-8fd2-598756813511 | note | Verification Activity: By - PE
48970554-840b-47a5-8e4e-2b21c9f05f0d | checkpoint | 4.35.04 - Stickers
3144e02c-0301-5401-a403-bc5749e170a6 | note | Acceptance / Conformance Criteria - Installation of manufacturer and installer stcikers accroding to P24 specification
2fef1926-20d0-5adf-b10b-53637298c2a3 | note | Standard / Specification - NZTA P24: 2020
e171bbdb-11c8-5ce0-bc9f-277e3790e354 | note | Verifying Document - Site Record
84a13ce6-6c93-5ee0-8b3b-aff6985412aa | note | Frequency - Installation
b203f8a8-cefe-522d-849d-b6b1686727a9 | note | Verification Activity: Activity - S
cca2d514-fee8-5889-922f-0e4e8c0c8fc8 | note | Verification Activity: By - PE
396d6e22-e344-41ee-8d0e-e721b2fc3f4a | checkpoint | 4.35.05 - Sign Shop Drawings
b23bc80f-ff86-5e20-96c3-d710d0c80938 | note | Acceptance / Conformance Criteria - The supplier shall prepare shop drawings detailing the panel layout, positions of channel framing, reflective sheeting classes used, footing and post designs for larger signs and assembly systems prior to the manufacture of any sign. The shop drawings shall be submitted for review and comment at least ten working days prior to manufacture of the sign.
83764d54-e62a-596e-9959-4be8fc74b91d | note | Standard / Specification - PS 23.2.6
23250ded-8c9d-553f-81e4-39b42fb3775a | note | Verifying Document - Shop Drawings
27ec1539-9d96-5496-ab19-5c5114a17e51 | note | Frequency - At least ten working days prior to manufacture of the sign.
f77e0a9c-c6c9-53dd-b56a-7ba30f4820d9 | note | Verification Activity: Activity - R
ce193b5d-f2b2-5642-88d5-2a0eef66bde7 | note | Verification Activity: By - PE
55af1a3b-0aff-4f95-a287-89fd1272fc53 | checkpoint | 4.35.06 - Post Embedment
33c41562-98fa-5558-9b88-b470e910aa82 | note | Acceptance / Conformance Criteria - All post foundation shall comply with the requirements of NZTA P24 specification of permanent traffic signs. All posts shall be encased in a concrete foundation 300mm minimum diameter and have a 100mm cover to the base of the post, unless specified otherwise.
4f15d7ef-4be7-59b4-b748-f08d6247abb7 | note | Standard / Specification - PS 23.2.18
c36b11b0-fea3-54ed-8991-47d5dfd80645 | note | Verifying Document - Site Record
115f802e-b493-5953-9966-86f879f92bfa | note | Frequency - Every foundation
42981262-5995-5090-8662-72c72a79d5ee | note | Verification Activity: Activity - I
aff59ac0-9dbd-53df-be3f-6d45bc699c5a | note | Verification Activity: By - PE
36dd10ee-f411-4718-ad85-f1b45319a9e7 | checkpoint | 4.35.07 - Timber Posts
26095001-19b5-5146-9f84-214a8f32b438 | note | Acceptance / Conformance Criteria - Timber posts shall not exceed 100mm x 100mm section size. They shall be Number 1 Framing grade timber as specified in NZS 3631, dried to 20-24% moisture content, and treated in accordance with the New Zealand Timber Preservation Council’s requirements as specified in NZS 3640 for Hazard Class H4. The timber finish may be gauged or dressed. The timber posts shall be primed and finished with white high gloss paint over the length above ground level.
afbead56-a50c-5d3f-ae29-ee128e357a45 | note | Standard / Specification - PS 23.2.19
93a100d5-7bd9-5b98-ab63-2fca5a88c957 | note | Verifying Document - Datasheet
319ebbd9-01bc-520e-83e2-464d083a65e0 | note | Frequency - Prior to use
d4300e55-6a25-5410-96b1-8159bd5ed34c | note | Verification Activity: Activity - R
1d66ffaf-dc92-5fca-950d-0794c2a033f9 | note | Verification Activity: By - PE
e81f317c-04a2-4d67-860f-507a45bced3a | checkpoint | 4.35.08 - Steel Posts
12e8a193-c02b-5770-a8b7-d78da766b13c | note | Acceptance / Conformance Criteria - Steel posts shall be of an approved frangible design. They shall be hot-dip galvanised and finished with white high gloss paint. The paint system shall be specified and applied in accordance with AS/NZS 2312.1. All poles shall be fitted with white PVC caps.
e55d8977-f6b9-585b-8639-d2916cd4f71e | note | Standard / Specification - PS 23.2.20
63867518-b4be-5eb5-a2b5-2d145b5113c2 | note | Verifying Document - Datasheet
166c4eaf-d150-5577-9afb-8aa17ccb72a6 | note | Frequency - Prior to use
dd25312d-95d2-5acf-913c-329eb4e05acb | note | Verification Activity: Activity - R
b8bc8e9c-f23c-5107-bf8f-428f97d12d3f | note | Verification Activity: By - PE
b91d8b62-6665-4b91-8650-392209656f31 | checkpoint | 4.35.09 - Aluminium Poles
240e9e70-6dd5-5bc1-89e2-dee3f56aa290 | note | Acceptance / Conformance Criteria - Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps.
a593cd5d-f671-5422-a76d-e5ec0f814fe9 | note | Standard / Specification - PS 23.2.21
8e66f08e-e5bc-57df-bcdb-685bdd7ded1a | note | Verifying Document - Datasheet
10c9d351-956a-59aa-82bc-77b6f4f5cae4 | note | Frequency - Prior to use
913f21d3-ff1a-56dd-8428-b2af540f58ed | note | Verification Activity: Activity - R
3c2fa7f7-cc99-5424-ba37-98a6d514edea | note | Verification Activity: By - PE
b2270c11-7133-4110-aa5b-e85de5d17dac | checkpoint | 4.35.10 - Sign Fixings
df60b97f-c6cb-5846-a052-c25cea4411d3 | note | Acceptance / Conformance Criteria - All signs shall be installed using approved sign support channel bracket fittings that do not penetrate the front face of the sign. No bolts, rivets or other fixings shall penetrate the front face of the sign.
8526ed66-4bd2-5306-b7d9-ce92add9125a | note | Standard / Specification - PS 23.2.23
69ae3068-6100-5535-8644-e333d78cc84d | note | Verifying Document - Datasheet
4d692492-96c4-5b10-a4ab-6afcd4951561 | note | Frequency - Prior to use
630d4006-7778-5cd9-9386-4168b49ae8b7 | note | Verification Activity: Activity - R
3c28ddb7-8f7d-5522-b843-74d948dfdc5c | note | Verification Activity: By - PE
e923276e-9230-4b71-8bd4-ef46625a33d6 | section | 4.36 - Long-life Road Markings Materials
1994c8b9-16b7-470c-8875-d49dac54214b | checkpoint | 4.36.01 - Applicator Approval
c9a09173-e714-5d53-ae26-705f1f82d1b4 | note | Acceptance / Conformance Criteria - The applicator(s) used for the contract works must be certified to NZTA/NZRF T/12.
50eee7d4-7d0d-53bc-b961-25287bbb2fb6 | note | Standard / Specification - PS 23.5.2
97c7abc7-2a56-53e2-b9ea-a4c8aa776df1 | note | Verifying Document - Engineers Approval
94069554-e592-5610-85e7-96d9636888fc | note | Frequency - Prior to Installation
ad6965ea-d6b7-5eeb-b095-d94679d2e870 | note | Verification Activity: Activity - HP
1cf0e5c4-b559-593a-a982-5b4b0587da59 | note | Verification Activity: By - ENG
7dfae7ae-e081-44d1-86ed-0c73f957c2a3 | signoff | AUTHORITY HOLDPOINT
cf9798ea-674f-4d1f-adec-1efe28780738 | checkpoint | 4.36.02 - Approval of Road Marking Materials
90c71df3-0053-5831-965e-f386f818dd6a | note | Acceptance / Conformance Criteria - Only products approved that meet M07 specifications are to be used. The Contractor must submit to the Engineer details of each of the products that will be used in the contract works.
30f90144-9831-53b5-869c-036d2ad9ca50 | note | ○ The Contractor shall nominate the brand, type (white, yellow, and structured if different) and proposed application methods for materials to be used.
1c72126e-8c9e-55e5-8fc4-01eac0c7e160 | note | Standard / Specification - M07 2022
e1a32239-0771-5720-b84b-8c1c1fb5d562 | note | Verifying Document - Data Sheet
580d82d2-4284-54f5-9658-d1461d3b4311 | note | Frequency - Prior to Installation
73a90bf7-effe-5447-aded-803553e55bef | note | Verification Activity: Activity - HP
e1bf021f-624f-5c54-8520-375bf1688d5e | note | Verification Activity: By - ENG
c899b88f-c04d-4814-b34c-31a9a619e390 | signoff | AUTHORITY HOLDPOINT
d753b7a9-137e-4767-ab33-97c037f3eab2 | checkpoint | 4.36.03 - Installation Limitations
41e93d93-0123-5574-8e72-19ce1f0576cc | note | Acceptance / Conformance Criteria - The contractor must provide the engineer with the supplier's specifications or installation instructions for the proposed long-life road marking system including permanent CAP
15471767-b0e7-550a-aed7-57651dc1c1fc | note | Standard / Specification - PS 23.5.4
16d4bee3-7d80-500e-86f8-104a8dfbc7cf | note | Verifying Document - Data Sheet
f3c27e90-f7f9-5eff-b04d-80d4b80340a7 | note | Frequency - Prior to Installation
ec17d0bb-f5ca-55ce-8d59-6ea4f3d9679b | note | Verification Activity: Activity - HP
aeb9f46f-b08c-5737-b357-8924f46df1b7 | note | Verification Activity: By - ENG
fa699495-d534-4f6d-b033-90e7649fdcc8 | signoff | AUTHORITY HOLDPOINT
092dc8f4-1a90-4a7c-bf2d-a8be70d6a3c7 | checkpoint | 4.36.04 - Glass beads
72ce5756-9092-547e-82b6-e2f526840bdc | note | Acceptance / Conformance Criteria - Provide evidence beads meet M07 cl. 6.8. Report As/NZS 2009 appendix N Heavy metals. Provide evidence beads meet proprietry CAP product requirements.
53ea8bad-bb00-5671-915c-b07e64fd0770 | note | Standard / Specification - PS 23.5.5, PS 23.3.1
7c0d7a9c-8bcf-5e57-b51a-bf76ce6ea17e | note | Verifying Document - Data Sheet
1a8f9c7d-00f2-5dab-84f1-e0c7e24424cd | note | Frequency - Prior to Installation
e4eaca26-40ef-5579-84e9-251022c4260e | note | Verification Activity: Activity - HP
861b1c04-dbe1-5ca4-87a7-849c6f259c60 | note | Verification Activity: By - ENG
8af333a2-d022-4f64-8c0e-eb412b3b95b6 | signoff | AUTHORITY HOLDPOINT
1e814dd8-7e44-42a7-a6d2-cfcfab5bf5e4 | checkpoint | 4.36.05 - Raised Pavement Markers
a7005ab3-0f9f-5a50-b77d-d7f0a27d1ffe | note | Acceptance / Conformance Criteria - All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers. Specifically, Contractor shall provide evidence prior to application that raised markers meet M/12 type approval
ade8d0b9-3322-5943-a401-19eefd2b0403 | note | Standard / Specification - PS 23.5.6, PS 23.3.1
8c0bdc73-3cc1-583d-952b-6c3adb207cc2 | note | Verifying Document - Datasheets
8dd6529a-8416-5ad5-8dba-718a69e917f1 | note | Frequency - Prior to Installation
4a2a308e-01f2-55bc-b920-9b661cfd0131 | note | Verification Activity: Activity - H
55a6ebff-2fba-5050-b65b-591790d499c4 | note | Verification Activity: By - PE
2230a6ca-3fbe-4de5-86b7-fd28a1b98398 | checkpoint | 4.36.06 - Raised Pavement Markers (adhesive)
fbba5766-5622-5e0a-b787-cfec18fad898 | note | Acceptance / Conformance Criteria - All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers. Specifically, Contractor shall provide evidence prior to application that the adhesive to be used is an approved type
7aadab37-69ad-5594-af42-84ab1129dd12 | note | Standard / Specification - PS 23.5.6, PS 23.3.1
cc383b7c-eeb3-578e-bfcf-31672cd4b454 | note | Verifying Document - Datasheets
e2436eba-0357-5d33-bed9-220d084fe0a1 | note | Frequency - Prior to Installation
df069ea1-d490-5978-aba7-44a6e54a8b70 | note | Verification Activity: Activity - H
576bbfa3-3907-5288-9fc7-5945258a955a | note | Verification Activity: By - PE
a647cc12-887d-4907-a5b9-7fa638c5f988 | checkpoint | 4.36.07 - Application Crew
91686622-ada4-5f76-9ecf-c2853c9533f2 | note | Acceptance / Conformance Criteria - The Contractor is to notify the Engineer of any proposed changes to the crew. The Contractor shall provide a CV outlining their qualifications, skills and experience related to installation of long-life road marking systems. No installation shall commence without the written approval of the Engineer accepting the suitability of the nominated crew or any changes proposed.
7e4b4df7-2d94-574b-b392-aad3c9bfe1d5 | note | Standard / Specification - PS 23.5.7
405e5fc3-63a3-527e-ac93-38e495b90a75 | note | Verifying Document - Engineers Approval
87de5c07-8f4f-553e-a099-5f240f78fc16 | note | Frequency - Prior to Installation
f09b8d5a-a4e9-53d4-8db2-ddc17ea3805a | note | Verification Activity: Activity - HP
a862d3cd-47b3-5e53-a405-b3a270bdc1fe | note | Verification Activity: By - ENG
aba3fcfe-1be3-4ecc-b716-d8ac74a8f4a0 | signoff | AUTHORITY HOLDPOINT
15dd754d-9d8e-4c0b-8270-c5b00fb98dfb | checkpoint | Edge Marker Posts:
35107114-65a7-5543-88c3-1a859a98d30d | note | Acceptance / Conformance Criteria - Edge Marker posts shall be non-wood and shall comply with NZTA M14. Non-wood posts shall have current NZTA M14 type approval.
5f4c70f7-eaf7-59f8-9ada-ed9e49c0f454 | note | Standard / Specification - PS 23.3.1
e2658730-9d84-5d69-98c6-d4820e0fe3f8 | note | Verifying Document - Datasheets
4d624222-2999-533e-a17b-dda4b8231d40 | note | Frequency - Prior to Installation
1abb8835-35f9-5c33-9968-a3a5a2b1bbd5 | note | Verification Activity: Activity - R
ca4a01e9-8b71-5c1c-904d-10ce09ec8e77 | note | Verification Activity: By - SE
6b7bf30e-f4c6-4bcf-82d5-289d6502736c | section | 16.01 - Signs
653e7a55-b559-43ae-b782-e16274806590 | checkpoint | 16.01.01 - Relocated Signs
12cd984d-4d37-51a5-a80a-2378ca8aa5b7 | note | Acceptance / Conformance Criteria - Relocated signs must be inspected by the Engineer for suitability, installed vertically, and securely attached to posts with appropriate brackets.
1004b4c9-c000-508c-a034-b41398bc3fbc | note | Standard / Specification - PS 23.2.3
ac4325e0-2053-562a-a436-280aefd45c3b | note | Verifying Document - Site Records
34b54db3-3d82-53cd-a89b-4f11a3f03c1b | note | Frequency - Each Sign
671f876e-b576-57ae-9f3a-e9ee2ba59ff4 | note | Verification Activity: Activity - H
edec6920-fbf6-53c5-87d4-f22d728d74d8 | note | Verification Activity: By - PE
2f747007-c59a-4589-b714-3cbd5a722335 | section | 16.02 - Pavement Markings
538d3b5d-31b3-46d2-afc7-1435efab51d8 | checkpoint | 16.02.01 - Surplus Chip Removal
aa342d4e-d0d7-540e-9b28-4b757a39398f | note | Acceptance / Conformance Criteria - Accumulations of surplus chip and other coarse material shall be removed prior to road marking.
150e5eb9-8914-5612-a326-7bac3b2e2198 | note | Standard / Specification - PS 23.3.2
6816a677-8c1d-56f3-a1bd-df036d22336d | note | Verifying Document - Site Records
c9f4508b-40ee-5f66-a5fe-a44dbfb6604f | note | Frequency - Prior to Marking
02c40ff6-1910-575a-aaf1-bb60b84cf626 | note | Verification Activity: Activity - V
28e292be-0ef7-5a0d-acb2-6820d16cf24a | note | Verification Activity: By - SE
920c7fb4-fe98-45ae-a519-15dfa6e3cc45 | checkpoint | 16.02.04 - Raised Pavement Markers
c1427b7e-9cbe-520a-a153-70859c9d9eaa | note | Acceptance / Conformance Criteria - These shall be located as detailed on the Drawings and installed in accordance with the requirements of TNZ P/14. The applicator shall ensure that the placement surface is dry and free of all foreign material and loose chip, which would hinder the correct installation of the raised pavement markers.
a8540d48-e40b-5e6e-8b4c-2bcf347732b9 | note | Standard / Specification - PS 23.3.2
2f05f253-64e0-516c-aa5f-2c6aeccd6a51 | note | Verifying Document - Site Records
f85785f2-b8d6-592a-b58e-bac6552aa2b5 | note | Frequency - Each Marking
29f9fac0-2c6c-5e7e-b351-44bbc66b08e4 | note | Verification Activity: Activity - V
ae7f61a2-e184-57f8-9461-274f01790915 | note | Verification Activity: By - SE
7ecfa909-f98a-4b5a-9ea6-2d504865e1ea | checkpoint | 16.02.05 - Edge Marker Posts:
1e9c3c1a-e0aa-5a29-a86a-d9096ff4b3a3 | note | Acceptance / Conformance Criteria - Edge marker posts shall be installed in accordance with the requirements of NZTA M14. Setting out shall be in accordance with the latest amendment of the Manual of Traffic Signs and Markings and the Drawings.
fc03a65a-0bce-535d-9f44-cdaa15c96504 | note | Standard / Specification - PS 23.3.2
910d9704-cf3c-5d71-bf51-05bcb0bfd05b | note | Verifying Document - Site Records
2414cecb-aedf-5aa1-8414-06fbd65a4639 | note | Frequency - Each Marking
5c98ec8d-e2ae-5162-b681-bc4dadacf653 | note | Verification Activity: Activity - V
2d70d75c-3dd5-56ea-a4e2-c1d2358d96e2 | note | Verification Activity: By - SE
4f1dd5d4-aae1-4ee4-aabb-596d84ab5bc5 | checkpoint | 16.02.06 - Coloured Surfacing
62f9d2e0-f428-5a0e-bf40-d86b4c7bcb99 | note | Acceptance / Conformance Criteria - Coloured surfacing must meet NZTA P33 requirements and come with a minimum five-year warranty. The contractor must provide proof to the Engineer that the material complies with NZTA P33 before preparing and marking the surfacing.
c49a29e9-ec43-5a53-91f9-32dce6d81072 | note | Standard / Specification - PS 23.3.2, PS 23.4
ae025a17-1c11-50a9-a6b6-3ee3fc417526 | note | Verifying Document - Site Records
1b1ccf8f-ef1c-5095-ba4b-cdef6ee40ace | note | Frequency - Each Application
a7c597f5-fbb0-5401-8117-8014cef45fec | note | Verification Activity: Activity - HP
d87bcf5a-94ce-5424-8213-8d09b9f01069 | note | Verification Activity: By - ENG
f10212db-e78c-4a26-8578-59406616ee75 | signoff | AUTHORITY HOLDPOINT
f3e344cf-17f2-4f9b-87a5-b8117214b176 | section | 16.03 - Long-life Road Markings
87742164-98ea-4866-aa8a-21996d50ff69 | checkpoint | 16.03.01 - Mark out the Contract Works with Engineer
3de9de13-48b6-5705-a8f2-0e19de270a2f | note | Acceptance / Conformance Criteria - The Contractor is required to mark out the contract works with the Engineer in accordance with the NZTA Traffic Control Devices Manual Part 5 before any installation commences. The application shall be in accordance with the Land Transport Rule: Traffic Control Devices 2004. The Contractor must give the Engineer 5 Working Day notice of the proposed date the Contractor intents to mark out the extent of the contract works on site.
c6ec5fdd-f7bb-5461-bc17-5031cb749b7b | note | Standard / Specification - PS 23.5.9
d3355f92-2d2e-55e8-9b31-ab46f8d690fd | note | Verifying Document - Notice
6286cc15-6bcd-5274-9fbc-73fc94bb5178 | note | Frequency - 5 Working Day notice prior to mark out
b356c05a-dc4b-5a74-81c9-92cb95bbd000 | note | Verification Activity: Activity - HP
0de56a0b-46c6-59ed-bdf8-8bd02a58d42c | note | Verification Activity: By - ENG
555dfe4a-2e2b-45dc-a342-2df567866e9b | signoff | AUTHORITY HOLDPOINT
efa97e77-9753-4ffe-8d0d-3d680e36cb50 | checkpoint | 16.03.02 - Initial Paint Setout Inspection
07b882eb-849e-536e-b913-eb275d88dfd7 | note | Acceptance / Conformance Criteria - Verify the setout of the initial paint following the completion of the Asphalt Concrete (AC) construction.
1390d6f2-c4df-5fe1-828c-0dfcacc98f23 | note | Standard / Specification - PS 23.5.19
892cf820-3e70-580b-836b-178203e95773 | note | Verifying Document - Markout Records
3d25d883-0e69-5e88-8215-1e43cc708dd7 | note | Frequency - Upon completion of AC laying.
344eb4e8-2d2a-5038-8dc5-9e29dc6e397c | note | Verification Activity: Activity - HP
993692ff-6860-50b4-b137-d1b57d2cf917 | note | Verification Activity: By - ENG
ca4c78c4-fd82-4546-8500-62098fd1e79b | signoff | AUTHORITY HOLDPOINT
6240bd38-f8c9-4572-beae-ae971ef33d47 | checkpoint | 16.03.03 - ATP Setout Inspection
7dba110d-07a6-5c49-bb87-9954bcd488bd | note | Acceptance / Conformance Criteria - Verify the setout of the Audio Tactile Profiled (ATP)
7db3bf57-c661-5c3b-a978-7f70fc283d6c | note | Standard / Specification - PS 23.5.8
da0faf1d-250c-5999-9830-9f5e84e64b87 | note | Verifying Document - Markout Records
d883cd9d-7be1-5f5e-9701-5685728aa0b1 | note | Frequency - Prior to Installation
15597508-e2f8-52f7-aadd-cc0056a08d59 | note | Verification Activity: Activity - HP
293e7722-0c82-586b-a664-5711e608d624 | note | Verification Activity: By - ENG
df5d930f-0bc5-47c0-8d6a-2cc1e44dc2a2 | signoff | AUTHORITY HOLDPOINT
8e8ed9e0-aa5d-4e95-a94b-bda9c1658f50 | checkpoint | 16.03.04 - Applicator, Marking System, Marking Format and Applicator Crew Trial
5d73aa24-26d3-5eb2-96bd-21ad008ff436 | note | Acceptance / Conformance Criteria - The contractor shall demonstrate the application of each marking system format in the presence of the Engineer.The contractor must provide the Engineer with a minimum of 5 working days' notice prior to the trial date.Installation of the marking systems shall only commence if the Engineer is satisfied with the trial.
933f338d-e098-510d-8bc2-b8b527c06b75 | note | Standard / Specification - PS 23.5.11
e3da8271-cac0-5d91-8423-3c04225a41c6 | note | Verifying Document - Engineers Approval
1fe8451a-19d3-5232-805f-e11e737c8370 | note | Frequency - Prior to Installation
7f3e45d5-bb61-56a2-b8e0-42f62d045a1f | note | Verification Activity: Activity - HP
45dece5e-2134-59bf-9400-2394adba2a81 | note | Verification Activity: By - ENG
14f88cbe-76e5-4bd3-b0f5-ad3d122cdf10 | signoff | AUTHORITY HOLDPOINT
e2926d3a-2207-47c9-8503-12137db1cadf | checkpoint | 16.03.05 - Inspection Post Installation
6e208045-fd38-5b8f-b36d-dc98b60d86d7 | note | Acceptance / Conformance Criteria - Formal visual drive over inspections. The visual inspection shall include an initial night inspection followed by a day inspection shall be carried out by the Engineer and Contractor.The visual inspection shall include the following - Colour, Night and Day Time Visibility, Alignment, Coverage (structured only) and Damage.First Inspection following installation of all contract works.
0c02a39b-5dd0-5951-96f1-3bd8eacdb90c | note | Standard / Specification - PS 23.5.16
7e3b8634-e20b-55a3-96be-0cadffb49c72 | note | Verifying Document - Report
7903ed55-acb4-554b-8604-60201cba1c30 | note | Frequency - Three inspections are required: first, 2-4 weeks post-installation; second, six months later; third, before issuing the Final Completion Certificate. The Engineer may waive monitoring if satisfied with the first results.
6a89d826-1f20-5084-9edd-ed9e088ca88e | note | Verification Activity: Activity - V
8a1cbd8d-0b85-5d9e-b24e-23d7357f6cb5 | note | Verification Activity: By - PE
918a13b2-e46b-4aba-90b1-80b3c0f81e9a | checkpoint | 16.03.06 - Monitoring Post Installation
f78af516-5bfb-5594-97a9-71903e6ea8a8 | note | Acceptance / Conformance Criteria - Three monitoring sets are required: First monitoring following installation of all contract works.
e2bcddaa-607b-571c-9b89-e97e27ac97a5 | note | The Contractor shall report on the performance of long-life road markings based on the following criteria:
a59d137f-d45d-5c57-94da-ac635c70f457 | note | ○ Colour: Inspected using AS 2700 standards. Discolouration should not exceed 4/5 per ISO 105-A03 and refers only to the material’s natural colour, not external build-up. The Engineer will investigate if necessary. Road markings should retain their daytime colour at night.
33da83e3-30d5-55b6-8fe6-f1145c8947c5 | note | Retroreflectivity:
019f71b3-1e86-504b-b4ff-fc704d544208 | note | ○ Dry (R): Minimum of 150 mcd/m²/lux for the warranted period.
711dda8b-3988-5145-9be9-94fc58a86275 | note | ○ Wet (RW): Minimum of 80 mcd/m²/lux for the warranted period.
189203e2-5295-5691-a2b4-20ce2a6ec632 | note | ○ Measured per IS EN 1436 or ASTM E1710. Mobile device measurements must use 30-metre geometry. Concerns identified by mobile retroreflectometer should be validated with a hand-held device per BS EN 1436 or ASTM E1710.
99d4bdae-0a7c-5608-b012-e962b92ea173 | note | Standard / Specification - PS 23.5.17
f9a6547c-7df0-53eb-b991-8e70bbe68845 | note | Verifying Document - Report
d5dd4c8c-9f94-5c9a-911e-2e3b2f2beb61 | note | Frequency - First, 2-4 weeks post-installation; second, six months later; third, before issuing the Final Completion Certificate. The Engineer may waive monitoring if satisfied with the first results
559c475a-9451-5d11-82f2-ecae89d34e99 | note | Verification Activity: Activity - HP
0c4c91de-0d24-5293-ba19-b477f29c1bc4 | note | Verification Activity: By - ENG
fac855e8-157e-4c13-ad39-d141b39bc85f | signoff | AUTHORITY HOLDPOINT
11a0be38-5f6d-46d8-a8d5-1a03e275c622 | section | 16.04 - Safety Barriers
50fc98e7-e898-4ac1-bf2f-58226248f9bd | checkpoint | 16.04.01 - Ground profile w-beam
0ef2058b-4464-5f59-a940-ea8589113114 | note | Acceptance / Conformance Criteria - The finished ground profile from the edge of the pavement to the guardrail and for at least 600mm behind the guardrail shall be a maximum crossfall of + or -1 in 10.
ecd838ca-dd67-5f42-839a-e55fb4e66770 | note | Standard / Specification - PS 23.6, M23
84c516e4-9fa8-5048-9882-a3e0ca93921d | note | Verifying Document - Site Records
9110a960-f87f-53f4-b002-a28eee015947 | note | Frequency - Prior to post installation
a2080061-f205-5369-85d7-f37f678eacd9 | note | Verification Activity: Activity - V
43e9ba8c-c7fb-5f03-ba3e-ea67201a2f85 | note | Verification Activity: By - SE
d9f15ff9-adee-4329-807e-afb72af429a1 | checkpoint | 16.04.02 - Installation Notice
5c39c9e6-c140-59f7-8e39-691201716ee4 | note | Acceptance / Conformance Criteria - The Engineer shall be notified and given opportunity to inspect the set-out for the guardrail at least 24 hours prior to construction.
61aa69fe-1d03-5e45-9253-fcc1258337ef | note | Standard / Specification - PS 23.6, M23
3f8528bc-09a4-5aeb-8334-11176b009ee3 | note | Verifying Document - Notice
e9b63f7d-f1ef-54ba-b1ce-5faf566004b2 | note | Frequency - Prior to Guardrail Construction
783b12b9-934b-5c50-86e0-fc39b28f2858 | note | Verification Activity: Activity - HP
26d2616c-cb3d-5ff7-bcc4-fbcc33094c30 | note | Verification Activity: By - ENG
55bf7243-ed05-43fc-a303-46aa73d7d037 | signoff | AUTHORITY HOLDPOINT
8f6f948b-5976-419e-a39c-4ac04f4bb5c5 | checkpoint | 16.04.03 - Guardrail Alignment Visual Inspection
39d7782e-8317-5f93-afe5-e6875a75f712 | note | Acceptance / Conformance Criteria - The horizontal alignment of the barrier shall not deviate more than ± 10 mm from the specified positions and levels. When erected but before posts are permanently fixed the completed guardrail alignment shall be visually acceptable.
cbba9bf9-bb7f-5d28-aa11-b6c916df6bc8 | note | Standard / Specification - PS 23.6, M23
9568d326-3ba4-5e4a-b16c-a0e26179e1bb | note | Verifying Document - Site Records
df1382c5-a65d-5021-be5c-ec828a732c4c | note | Frequency - When erected but before posts are permanently fixed
f9d466f1-f196-5243-b8d0-1d9ca016cb87 | note | Verification Activity: Activity - V
25c5e22c-4575-5899-8870-2c8499258f2c | note | Verification Activity: By - SE
eef9c9c3-3c64-447c-8ad5-48f6892699a7 | checkpoint | 16.04.04 - Safety Barrier Installation Checksheets
e935d460-c7d6-5d5e-a9ef-f19cc1209209 | note | Acceptance / Conformance Criteria - The Contractor shall submit a completed and signed installation check sheet to the Engineer for acceptance
479f8854-2b46-56f6-bf9b-ddc2b53fb977 | note | Standard / Specification - PS 23.6, M23
35e5d209-9385-54f5-b7dd-0b86f05fac44 | note | Verifying Document - Ingal Mashflex and Ezy-Guard 4 checklists and w-beam terminal checklist
53b32a3b-c489-54c9-a2aa-b102c6a5123d | note | Frequency - Upon completion of the Guardrail Construction
e5830958-67f1-556b-b72f-12d9676952ad | note | Verification Activity: Activity - HP
5981512b-34ca-524d-8b91-43cc49f93b07 | note | Verification Activity: By - ENG
4ee5e89b-0d5e-4cec-9d8f-3ed2fc6fb430 | signoff | AUTHORITY HOLDPOINT
dc58233c-66f6-44b5-883d-e5622c1fe2f6 | section | 16.05 - Wire Rope Specific Requirements
0e916a83-309f-4074-9d79-e6a7ed6d4e1d | checkpoint | 16.05.01 - Pull Test
36338261-e373-5ac6-9ad2-0b50f5390fed | note | Acceptance / Conformance Criteria - Per the manufacturer static pull test requirements
52674797-fecb-5600-a32e-fe4c4d91f680 | note | Standard / Specification - NZTA M23
9b68fa3c-845b-5b36-b783-7a349474ca46 | note | Verifying Document - Test record
d10b8c6f-56ce-5204-81b5-c521ca44a337 | note | Frequency - A sample of not less than 3% (or one post in every 100 m, whichever percentage is greater) of each installed length of WRSB shall be tested in accordance with the System Owner’s
10d46a19-0fce-5cfd-88f6-c3b365b72041 | note | Verification Activity: Activity - HP
41610fec-0025-5c58-b30e-8d1c54f489a7 | note | Verification Activity: By - ENG
076f15f0-5263-4ba3-999e-086adf43265e | signoff | AUTHORITY HOLDPOINT
b1b36bc0-a750-4b96-a02e-fee0c433f842 | checkpoint | 16.05.02 - Foundation inspection for depth and width
875d383c-14e1-5cab-901d-18bf55a15a73 | note | Acceptance / Conformance Criteria - Per the manufacturer’s requirements (table 1 assuming mashflex)
70cb1d6e-26f2-53e2-8611-883f939408bd | note | Standard / Specification - NZTA M23
0bd02214-2b5d-5a25-9548-ee42546e7dd4 | note | Verifying Document - foundation logs/site records
43d27a30-d035-548c-b5a5-d5b8e927532d | note | Frequency - Each post
ba13e4a3-399f-5742-8984-7a73a05a28e1 | note | Verification Activity: Activity - S
75185ff5-1b67-57c5-b7e6-b65326879864 | note | Verification Activity: By - SE
0f3767e9-71af-45fb-8607-70c91bb53c9d | checkpoint | 16.05.03 - End terminal Anchorage
b0ba87fa-af26-50a6-8ebb-59b363c6901a | note | Acceptance / Conformance Criteria - Per the manufacturer's requirements
88c20c36-42a2-54ad-bb1f-77e2fdde4beb | note | (Assuming Mashflex)
1a12fdd6-5a43-5f4d-95b3-834f2154cc1d | note | ○ RECTANGULAR (TYPE 1) ANCHOR BLOCK
79aee150-2cd5-5ed6-b42c-5cc7d399129b | note | ○ RECTANGULAR (TYPE 3) ANCHOR BLOCK
7077d9e1-64e1-5631-be9f-8c23c71070a1 | note | Standard / Specification - NZTA M23
a3e0ccb4-4e5f-5bc4-b3db-4e1f93d58333 | note | Verifying Document - Subgrade test record and As-built of anchor
03cc114d-4b73-5c05-8f9e-de1d076c2553 | note | Frequency - Each anchor
cea662c5-ea73-56c2-8619-59b6083d5b60 | note | Verification Activity: Activity - HP
ec7a5e98-654b-5977-a964-9e45c40f25c6 | note | Verification Activity: By - ENG
ca49d771-79fd-453e-8f59-cdfc6fb6d1d7 | signoff | AUTHORITY HOLDPOINT
7bf4a364-8fca-44cf-bf8f-1ae85dbb69a5 | checkpoint | 16.05.04 - Concrete for anchor
449fc4ee-fb1f-502d-ad67-fb2eb38d8bb4 | note | Acceptance / Conformance Criteria - Must be 30 MPA
779282d8-3de1-52c4-9bb7-8ee537911880 | note | Verifying Document - Concrete mix design and 28-day cores
a3d8a5bc-ab91-5790-9df3-e487d617e35c | note | Frequency - Prior to pouring each anchor
061ca8b7-a818-5a13-bcc8-a34e2db8f8f1 | note | Verification Activity: Activity - HP
9704319f-7ae5-5d16-a9cf-780ee0f6dad5 | note | Verification Activity: By - ENG
1c7d3e07-e7ab-4e71-82c5-c4d2a8527673 | signoff | AUTHORITY HOLDPOINT
027491fe-f7c9-4a23-bee6-e04b01eebcf7 | section | 16.06 - W-Beam Barriers
0af432a4-10ba-400f-8745-4057d114c58b | checkpoint | 16.06.01 - Terminal
c79162ce-5298-5207-b277-6b5f514e03b3 | note | Acceptance / Conformance Criteria - Terminals should be installed in accordance with the proprietor’s drawings and specifications.
face6ff3-c378-5bad-a13e-38df4080e809 | note | Standard / Specification - NZTA M23 and manufacturers manual
a7fe2646-2024-5d7a-a44d-32359ce3bdda | note | Verifying Document - Site records
a57d3d12-271c-54ac-bb9f-b6cf842751df | note | Frequency - Each post
06aa0b1b-6c41-5ea9-b8da-4bddcea02cfe | note | Verification Activity: Activity - S
05e61a5f-18d1-5286-815c-67a521a1db79 | note | Verification Activity: By - SE
66bac369-acc7-4f77-8f2c-d25dd02d1d42 | checkpoint | 16.06.02 - Posts on Base Plates
e91e3041-c2a5-5ead-befb-3ee924983877 | note | Acceptance / Conformance Criteria - Constructed as per Ingal Civil Products drawings for the installation of posts on base plates
2078f6c9-df03-51e9-9b57-c5a427a89ff1 | note | Verifying Document - Site records
8454d459-1542-58e4-bddd-796c45ab9ceb | note | Frequency - Each post
d919285a-2950-5990-9741-e4982eb45f7e | note | Verification Activity: Activity - S
b19f92b0-aaa4-5d04-87a0-cf93ff17f6df | note | Verification Activity: By - SE
ec7d360a-b366-4e6a-820a-a3829773a6be | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
37d3d79e-9b0b-5f77-9db8-c213ce70dcea | textbox | Contractor's Rep Name:
d04e9991-539c-5468-a489-2fb07e37f94f | textbox | Engineer's Rep. Name:
e5215c09-034e-5edc-9a47-7b8b92374fc0 | date | Date:
3c61ad79-4096-4427-b1c4-05e20f5d0322 | signoff | Add Signature
e85e9ecc-3421-57a0-bf7b-f45069e6b84c | checklist | ITP - Traffic Services ITP - 105 - Rev B | itp | ITP - Traffic Services ITP - 105 - Rev B
cbb694b5-9a79-5eff-82e8-792fdfcecb63 | section | 16.01 Signs
0e4e7528-b117-573c-bedf-a3265d509aa1 | checkpoint | Redundant Signs
fc652128-0b9b-5889-9f84-c44a7466ca8d | note | Acceptance / Conformance Criteria - All redundant sign equipment shall be offered to the New Zealand Transport Agency to be uplifted for possible future use. All redundant equipment not required by New Zealand Transport Agency, shall be uplifted, removed completely off site, and disposed of in an appropriate manner.
7d07ea0e-24d3-52ea-a3ee-469c31dfa8ce | note | Standard / Specification - PS 23.2.2
1639787e-f88a-562e-94fe-2f1f28688bc9 | note | Verifying Document - Site Records
148b159e-c20d-54ee-8449-7fd712ebf23b | note | Frequency - Where Required
572ef37a-c91d-54e2-bb2b-f9596f112ead | note | Verification Activity: Activity - R
24517924-8f84-5a1d-8e15-394d41e81b7a | note | Verification Activity: By - SE
d95fbd5b-ce62-57ff-a566-dd0d774b22db | checkpoint | Relocated Signs
e446e723-3b92-552d-a602-3b78cc90a82c | note | Acceptance / Conformance Criteria - All relocated signs shall be Firmly installed in a vertical position and securely attached to posts where appropriate. Fixed to posts with appropriate fixing brackets. Signs shall not be fixed to posts by bolting through the sign unless specifically approved by the Engineer.
94bbbc65-7c4b-5c47-9fac-4a9d74f8fdb8 | note | Standard / Specification - PS 23.2.3
25b647c1-1c54-5c81-b265-d6c4d5710bc5 | note | Verifying Document - Site Records
afb46a6d-0e7d-5e4f-8a5d-d66a13119c9c | note | Frequency - Each Sign
0a7cc22e-e010-57dc-8e46-cc3d3515f8c2 | note | Verification Activity: Activity - R
16b1af2c-b10e-571c-9abe-e4603b2c7658 | note | Verification Activity: By - SE
63e60a80-2389-587b-8d02-bcee3658aea1 | checkpoint | Posts and poles
a0ff9fa1-3b5d-57f2-bf74-10aea886e486 | note | Acceptance / Conformance Criteria - The Contractor shall maintain construction records for each sign that clearly shows that all post, poles and foundation details comply with the requirements of this Specification. The design of foundations should, where required, consider the very close proximity of services and not subject these services to any dead or live loadings from the sign support structures.
e293e5b4-bdd3-5a71-adfc-4c7faf8e6169 | note | Standard / Specification - PS 23.2.17 PS 23.2.18 PS 23.2.24
0bdb7a0b-9899-5a69-8953-a9ee74118990 | note | Verifying Document - Checksheet
03a97a80-bb7c-5851-b6db-a111a1e485c1 | note | Frequency - Each Sign
828a02c7-fa0e-5162-850a-0d43cc77ba41 | note | Verification Activity: Activity - I
0a5fbbde-b7a5-54b5-9c1c-4646cfdba6e5 | note | Verification Activity: By - SE
d7ccad97-0972-5c41-9395-f8b1f3223072 | checkpoint | Ground Mounted Signs
433691a6-d99a-5ea7-b6c9-d980c1edab59 | note | Acceptance / Conformance Criteria - All ground mounted signs shall be orientated such that they are turned about five degrees away from the driver’s line of sight or the normal to-the-road centreline as detailed in Clause 1.10 ‘Orientation’ of the Waka Kotahi NZ Transport Agency Manual of Pavement Markings and Signs Part 1.
cf12d1ca-e75a-5493-a5d9-f4bb8f05255f | note | Standard / Specification - PS 23.2.27
56606c29-2f1e-57ee-85e1-778c3a924f06 | note | Verifying Document - Site Records
b2ecc68d-77be-508f-81f5-8ec27963cf17 | note | Frequency - Each Ground Mounted Sign
4c92a8fa-e501-5c9e-94fa-af4ed67d2c5c | note | Verification Activity: Activity - V
490fafcb-8774-56bd-a190-109873203a23 | note | Verification Activity: By - SE
ea2b689c-b2a4-5570-aa94-6d1d1ab86c7c | section | 16.02 Pavement Markings
37d73ff5-7875-592e-bb65-845271c4deab | checkpoint | Surplus Chip Removal
f3d75540-33a1-557c-abc0-84cb0221aa60 | note | Acceptance / Conformance Criteria - Accumulations of surplus chip and other coarse material shall be removed prior to road marking.
4b900777-f199-5f8c-a1a9-0fef82285885 | note | Standard / Specification - PS 23.3.2
e697fffc-8b2c-51f5-878d-595c029ae8d2 | note | Verifying Document - Site Records
97fd5d51-2e06-51f1-bafb-98573ccdfff9 | note | Frequency - Prior to Marking
f0952784-cf2f-5b0d-b658-a5b83ac7ca7a | note | Verification Activity: Activity - V
e73c5472-f2ea-5da5-a6bc-5b6ab72a2580 | note | Verification Activity: By - SE
7cc3473e-9ccd-5e6c-bf8d-16fc32a74903 | checkpoint | High Performance Marking
57a1fbc9-1891-5ff8-a20e-866e6b6759f5 | note | Acceptance / Conformance Criteria - All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified.
6aca3ef2-fb65-505d-971e-9559e6c3b8c2 | note | Standard / Specification - PS 23.3.1
60f27952-3784-5a74-ba11-0db600b5c626 | note | Verifying Document - Site Records
a71becad-6961-53a3-a5c9-4360153c052e | note | Frequency - Each Marking
92ada486-d843-5e60-ac1e-1d3e6ce2b944 | note | Verification Activity: Activity - V
c3302b85-2e6c-5e24-bfaa-1a9827ac2423 | note | Verification Activity: By - SE
a631979e-2c25-5df5-bcfb-e8fb3bc69b5b | checkpoint | Roadmarking Removal
f53357af-e335-5829-90b8-e4c6127587b1 | note | Acceptance / Conformance Criteria - All road markings that are to be permanently removed must be either by water blasting or milling off in line with the NZRF line removal guide. The removal of all redundant pavement marking shall be such that The shape of the marking cannot be distinguished, The final surface texture is like the surrounding pavement; and No evidence of the paint remains.
5f961253-c6c1-5857-b36f-63e00b29b075 | note | Standard / Specification - PS 23.3.2
3aba31d3-f6c8-5e8a-bb2b-e6104a8689ff | note | Verifying Document - Site Records
9042e646-695f-5034-8e3a-161d6e2c68f0 | note | Frequency - Each Removed marking
89d07754-36d2-5820-8ca8-26027fb0dcbc | note | Verification Activity: Activity - V
0ca0ceb1-5666-5cfe-88e4-39dfe828a076 | note | Verification Activity: By - SE
4f67c6ff-9945-532a-87fc-d6a73512f2ec | checkpoint | Raised Pavement Markers
a4dfb383-b16d-5883-a240-b09a33717caa | note | Acceptance / Conformance Criteria - These shall be located as detailed on the Drawings and installed in accordance with the requirements of TNZ P/14. The applicator shall ensure that the placement surface is dry and free of all foreign material and loose chip, which would hinder the correct installation of the raised pavement markers.
7d9ce684-58f3-5bce-8ca4-889f9dea71a3 | note | Standard / Specification - PS 23.3.2
c55645d3-3cb9-56c3-b3c3-836531e7ae1b | note | Verifying Document - Site Records
67404876-f53e-5ab3-914d-ad2783139553 | note | Frequency - Each Marking
4359ebed-c8a0-5623-9fba-9f0887e41775 | note | Verification Activity: Activity - V
2a44a8cc-4498-583e-b8f9-d35a0b033a6d | note | Verification Activity: By - SE
b8086ecc-f696-5e17-95b8-844cc78efc6a | checkpoint | Edge Marker Posts:
2edb267b-dfb7-5e5f-acf0-d7532c142a02 | note | Acceptance / Conformance Criteria - Edge marker posts shall be installed in accordance with the requirements of NZTA M14. Setting out shall be in accordance with the latest amendment of the Manual of Traffic Signs and Markings and the Drawings.
aaff5d05-11e3-5ad9-ab72-7c1672b76a6b | note | Standard / Specification - PS 23.3.2
db5ea000-6319-5ab7-a8ec-35f68e7c87f7 | note | Verifying Document - Site Records
75eaf30b-75ff-5253-b367-23140a2c49b1 | note | Frequency - Each Marking
a7b1cd52-5a24-57b5-b872-cc37c268e5ea | note | Verification Activity: Activity - V
f1864724-2e91-5352-aa4f-ec1fab52a61f | note | Verification Activity: By - SE
e220e36c-c5b4-56e1-99a1-aa71ea3dcc81 | checkpoint | Coloured Surfacing
cc9bba5c-7425-54fd-aef5-d3aa9a42b4f3 | note | Acceptance / Conformance Criteria - Coloured surfacing shall be laid in accordance with the requirements of NZTA P33.
233c1f17-38d3-55f8-ad54-f3068921fcc5 | note | Standard / Specification - PS 23.3.2, PS 23.4
e8ec9b0a-9101-56ee-ac04-1f340ffbb1ad | note | Verifying Document - Site Records
8eb7a64b-c4d9-5fbb-bf54-c8c762275ea3 | note | Frequency - Each Application
825d26d0-57b6-5836-9764-0b1bd37db22c | note | Verification Activity: Activity - V
379dc95d-2f24-5c63-8232-293318aedcdb | note | Verification Activity: By - SE
5a9b8dd9-0399-50f6-9500-2df0acaf5af9 | section | 16.03 Long-life Road Markings
35cc9dea-af9f-518b-9a20-708d74708ef1 | checkpoint | Mark out the Contract Works with Engineer
0c33102b-efdb-5d37-9a0e-10a3274de6d4 | note | Acceptance / Conformance Criteria - The Contractor is required to mark out the contract works with the Engineer in accordance with the NZTA Traffic Control Devices Manual Part 5 before any installation commences. The application shall be in accordance with the Land Transport Rule: Traffic Control Devices 2004. The Contractor must give the Engineer 5 Working Day notice of the proposed date the Contractor intents to mark out the extent of the contract works on site.
d2c59fa7-fa0a-5a9c-9c40-7f6c7541cf46 | note | Standard / Specification - PS 23.5.9
7721a508-a4b1-5ed1-bd6e-bc6cef1fa3cc | note | Verifying Document - Markout Records
32bd25dd-729f-5821-832a-c48560fbefde | note | Frequency - 5 Working Day notice prior to mark out
1c94914f-3c33-59e8-939f-3c0f9741396e | note | Verification Activity: Activity - HP
1fb540b4-8e94-5161-9d50-050f2162b95b | note | Verification Activity: By - ENG
ada6a83f-dae7-5844-b51a-a84e3e8b7844 | signoff | AUTHORITY HOLDPOINT
515d37f4-4ec9-507b-8176-afec39742d6b | checkpoint | Applicator, Marking System, Marking Format and Applicator Crew Trial
6700fb3c-cd42-5882-b30e-cfad2bac4b6d | note | Acceptance / Conformance Criteria - The trial shall be completed using the applicator(s), marking system(s), marking format and crew approved for the contract works. The Contractor shall give the Engineer 5 Working Day notice of the date for the trial(s). Installation shall commence only if the Engineer is satisfied with the trial result(s). Verbal acceptance will be given to the Contractor immediately after the trial with written confirmation to follow.
d8c30e13-298e-578d-a704-33819d9f0665 | note | Standard / Specification - PS 23.5.11
a6be0360-e986-52ef-9bde-50a05719ca4e | note | Verifying Document - Trail Results
4c3f5044-9639-5c89-b428-e1213e557283 | note | Frequency - Prior to Installation
40e0bd42-1e38-5817-940e-4ecbadaa2fba | note | Verification Activity: Activity - HP
fe86147b-36e7-5849-9824-86b689753cf9 | note | Verification Activity: By - ENG
cced6d0d-ca6b-557b-9ff4-09d74853cf42 | signoff | AUTHORITY HOLDPOINT
84221197-005e-50f0-9e01-324fdbcb4a38 | checkpoint | Inspection and Measuring During Installation
ab37c16d-293c-56a7-a8d9-27d0d154d1f5 | note | Acceptance / Conformance Criteria - The Contractor shall inspect the long-life road marking against dimensional and installation tolerances as installation progresses. The Contractor shall on a daily frequency complete a Daily Quality Assurance Form (Thermoplastic and CAP respectively). The form records the material data, environmental conditions, etc.
52bdea2e-e9e8-5b90-9e37-7bb76a71b15c | note | Standard / Specification - PS 23.5.13, PS 23.5.15
c3483788-333b-5a2f-8b41-14f9df41ae49 | note | Verifying Document - Daily Quality Assurance Form
77a8bb25-4cbf-55a6-a3be-7c1c7a41773c | note | Frequency - During installation
a84353cb-2add-5e23-8278-2111961551f5 | note | Verification Activity: Activity - V
fcb24cc4-d125-51ec-9be3-448214c80bf6 | note | Verification Activity: By - SE
593543f2-b853-579e-922b-41949d6ffb5c | checkpoint | Inspection Post Installation
a7ecc87c-3c3b-5ce2-8fa3-66bd611f8a0c | note | Acceptance / Conformance Criteria - Formal visual drive over inspections. The visual inspection shall include An initial night inspection followed by a day inspection shall be carried out by the Engineer and Contractor of the first 25 to 50km per type of roadmarking installed (approximately 5 to 7 days of installation). The inspection shall be carried out 2 to 4 weeks post installation to allow for trafficking and a rainfall event. Subsequent visual inspections by the Engineer and the Contractor shall be jointly carried out of a sample of the contract works.
36818422-5312-5b30-8915-f6eebbefdda5 | note | Standard / Specification - PS 23.5.16
bd776027-565b-5ce7-90f0-d84f558a7af9 | note | Verifying Document - Report
5d19d78f-d9bc-5336-b3e2-bdef61de023d | note | Frequency - Minimum of 20% of the total contract works will be inspected per type of roadmarking
c206c266-7a30-51c4-a696-7e0dc3b56666 | note | Verification Activity: Activity - V
0befd2f0-b085-5032-8a76-d7c6bd3d4b1c | note | Verification Activity: By - SE
b2fb75c1-603e-5892-be9a-c01064ccabea | checkpoint | Monitoring Post Installation
fd49bb47-eb67-53a0-a380-1c2f8d225a02 | note | Acceptance / Conformance Criteria - The Engineer and the Contractor shall agree on representative sites for ongoing monitoring. Monitoring sites shall be 2 per 100km of edge-line per roadmarking type. Three sets of monitoring shall be carried out First monitoring following installation of all contract works. The monitoring shall be carried out 2 to 4 weeks post installation to allow for trafficking and a rainfall event. Second monitoring approximately six months after the first monitoring. The Engineer may waive the monitoring if they are satisfied with the performance of the markings based on the first monitoring. Third monitoring prior the issue of Final Completion Certificate.
888bcbda-554f-5c90-9d65-9a4435c51368 | note | Standard / Specification - PS 23.5.17
7d22f5c1-b411-5c51-8d1b-5be9ed8ba22e | note | Verifying Document - Report
8c91126d-0d0b-5bc3-8c3f-e909c4f32a91 | note | Frequency - 2 per 100km of edge-line per roadmarking type
e9e8ba65-e11b-5ba4-ba95-20940b332d90 | note | Verification Activity: Activity - HP
905666d8-19a1-5771-9b8c-4bc948bd3879 | note | Verification Activity: By - ENG
1331ca8b-8a6e-545b-81ed-6a3977b122c1 | signoff | AUTHORITY HOLDPOINT
a8523497-008f-5d14-abaa-0d6ae1ea132d | section | 16.04 Safety Barriers
fb660e6b-cff0-5921-901c-34d6f0da2710 | checkpoint | Ground profile
c4efcc04-1317-5b89-ab39-592f5b4570f8 | note | Acceptance / Conformance Criteria - The finished ground profile from the edge of the pavement to the guardrail and for at least 600mm behind the guardrail shall be a maximum crossfall of + or -1 in 10.
beb3a0cb-74bc-5201-8574-baf9e9789042 | note | Standard / Specification - PS 23.6 M23
b4553607-8238-57c5-b251-452edb5f206f | note | Verifying Document - Site Records
c9bc83db-0123-5893-949c-9f36cc9c06a2 | note | Frequency - Prior to post installation
9efd250c-3a55-55e1-a0f5-af5ec201ed39 | note | Verification Activity: Activity - V
627fb330-10c0-5d6d-8c84-64ede17e9b25 | note | Verification Activity: By - SE
8884d2a2-559c-52f4-925b-e3a5f67ae036 | checkpoint | Installation Notice
d0a861cc-4875-51e9-80ce-2ecd28f4046c | note | Acceptance / Conformance Criteria - The Engineer shall be notified and given opportunity to inspect the set-out for the guardrail at least 24 hours prior to construction.
50dda0c6-7bb6-573a-81c0-f0fd17ebe5fc | note | Standard / Specification - PS 23.6 M23
114a4f12-7e1e-5da2-96f6-8a06f060ae11 | note | Verifying Document - Notice
a5781f25-9d10-501b-9117-566a282932df | note | Frequency - Prior to Guardrail Construction
ac9cf37e-5226-5d82-8111-cb3dba07093e | note | Verification Activity: Activity - HP
8344221b-dd7b-5772-b788-0525b09b6d48 | note | Verification Activity: By - ENG
8f3a56f4-54f1-5e2a-93a6-b8538ebb393a | signoff | AUTHORITY HOLDPOINT
c575770a-0da0-51f4-8fe7-39613551fc90 | checkpoint | Guardrail Alignment Visual Inspection
b70906a5-a409-5635-9c76-e199b3937ab6 | note | Acceptance / Conformance Criteria - The horizontal alignment of the barrier shall not deviate more than ± 10 mm from the specified positions and levels. When erected but before posts are permanently fixed the completed guardrail alignment shall be visually acceptable.
3e81e72b-2fda-5b2f-9a58-6dcc91d9537a | note | Standard / Specification - PS 23.6 M23
2fb7498d-0483-5820-a77f-a3e7738857c8 | note | Verifying Document - Site Records
76ec074e-21b9-5c53-9562-f5f2af9af603 | note | Frequency - When erected but before posts are permanently fixed
4f46e91a-7745-5f65-816e-252be54ec5de | note | Verification Activity: Activity - V
d865b97f-f06f-5677-99de-6bc3fd5a2591 | note | Verification Activity: By - SE
5891dd1d-d957-538d-9837-de207c510e13 | checkpoint | Guard Rail and End Post Installation Checksheets
956af5c2-5da1-58cc-bd36-7f9a09ef7900 | note | Acceptance / Conformance Criteria - The Contractor shall submit a completed and signed installation check sheet for each terminal and guardrail section installed to the Engineer for acceptance
73dc39c6-7918-52f6-ad87-c9031f2e54dd | note | Standard / Specification - PS 23.6 M23
72c6c1eb-69a0-5619-ae79-90dc372069ff | note | Verifying Document - Checksheets
a565cda2-3064-5c84-98ea-5c437494e4cc | note | Frequency - Upon completion of the Guardrail Construction
ad949362-5162-58c3-8b99-16afd9af5e7c | note | Verification Activity: Activity - HP
4aee2243-32a7-50bf-b528-4a1c164faa15 | note | Verification Activity: By - ENG
bf4cc9ec-2e9c-5ead-92f4-16850b08e11b | signoff | AUTHORITY HOLDPOINT
9a210f72-c819-596c-bd99-c7ddad210861 | checkpoint | Galvanising Repair
ed6b1db2-6d13-5b2d-9217-0ecf9bb9ca64 | note | Acceptance / Conformance Criteria - After assembly, any areas of the galvanised coating that have been damaged or show signs of deterioration shall be wire brushed and washed to thoroughly clean down to fresh zinc or parent metal. They shall then be spot painted with two brush coats of un-thinned approved zinc rich paint the first coat being applied to a dry surface immediately after cleaning.
af2eb423-0bd7-5394-b0a2-1ddebc64b9ed | note | Standard / Specification - PS 23.6 M23
43367e46-e477-5720-9e0c-0d9f53aaf0a1 | note | Verifying Document - Site Records
84fcd489-7141-55ad-904d-be7079124680 | note | Frequency - Where Required
b56e0445-95a4-5231-acec-46d30e7f8202 | note | Verification Activity: Activity - S
ca0103dc-ef04-5882-bfb4-76372d2b521c | note | Verification Activity: By - SE
3b6e694e-ea22-5cf7-9c8c-f50551b48a0a | section | 16.05 Safe Lane Delineators
1893069f-b24e-5962-ab5b-4023fa145f92 | checkpoint | Safe Lane Delineator Installation
078f1647-87b1-5bda-8a9c-8e1b7d605de7 | note | Acceptance / Conformance Criteria - The safe lane delineators are to be installed in accordance with the manufacturer’s specification unless otherwise directed in the Contract Drawings.
b722e735-37db-5f93-a68b-edcf668644e5 | note | Standard / Specification - PS 23.7
d1630399-f55d-5291-a6aa-515441c20118 | note | Verifying Document - Site Records
f084265d-3f5b-5860-8d5d-48706d2497d6 | note | Frequency - Post Installation
3407f6d5-5570-5976-b047-f0a5efbc17ff | note | Verification Activity: Activity - S
7c7bb3e3-c9ec-53af-850e-9dc6af8ee371 | note | Verification Activity: By - SE
a4bb45e6-00c3-5ec9-83ca-06454e70db00 | checkpoint | Chemset Safe Lane Delineator
6978f879-b6e4-5ddd-b6fc-1ebe23e6c604 | note | Acceptance / Conformance Criteria - Where detailed in the Contract Drawings the Contractor shall excavate a 300mm x 300mm diameter hole and ensure all loose debris is removed from the hole. The hole shall be back filled with 20MPa concrete and the safe lane delineator is to be chemset in place. The concrete shall be level with the existing surfacing around the hole and water shall drain away from the delineator.
b24168a3-7a61-5419-a411-7c4277668a10 | note | Standard / Specification - PS 23.7
c18d7f2c-f9a3-5752-bedb-01b14ce7e257 | note | Verifying Document - Site Records
ae674a60-f90b-5421-b042-13c78184eedc | note | Frequency - Each Post
3dd80a83-900f-5e2f-b056-368f195cbe2d | note | Verification Activity: Activity - S
39ae7e2b-04bf-5322-9965-2928d5fd654f | note | Verification Activity: By - SE
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
| textbox | Contractor's Rep Name:
| textbox | Engineer's Rep. Name:
| date | Date:
| signoff | Add Signature