## ITP Cover Page
Stormwater Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 007 - Rev 2
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 007
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | Draft
ITP Description: |  |  | STORMWATER |  |  |  |  | Revision: | 1000 |  | 2
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-STW
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification:
Quality Specified:
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-05-15 |  | Cordelia Girdler-Brown and Chris Benson | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | ITP for Approval | 2024-10-10 |  | Cordelia Girdler-Brown and Chris Benson |  | Changes to Backfill testing requirement for both Stormwater structure and pipes. |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
2 | ITP for Approval | 2025-05-27 |  | Cordelia Girdler-Brown and Chris Benson |  | Changes to Backfill testing requirement: Section: 5.1: 5.1.1, 5.1.3, 5.1.4, 5.1.6. 6.2: 6.2.1, 6.2.3, 6.2.4, 6.2.6. 6.3: 6.3.1, 6.3.3, 6.3.4, 6.3.6. 6.4: 6.4.1, 6.4.3, 6.4.4, 6.4.5, 6.4.6, 6.4.8. 6.5: 6.5.1, 6.5.3, 6.5.4, 6.5.6. 6.6: 6.6.1, 6.6.3 |  |  |  | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | CHRIS BENSON | [5 empty] | Downer PM |  | CHRIS BENSON
Downer QM |  | CORDELIA GIRDLER-BROWN |  |  |  |  | 2025-05-27 | Downer QM |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Stormwater Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 007 - Rev 2
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.1 | GENERAL
3.1.1 | Extent of Line Setout | Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Stormwater drawings. Identify any clashes before construction. | Engineers Approval | Design Drawings | ITP Sign Off | Prior to Construction & Every Revision of IFC Drawings/Data. | M | PE
3.1.2 | Existing Stormwater system | Confirmation of existing stormwater network. | Survey Informations | Appendix V | Survey data | Prior to Construction Review existing service location drawing supplied by WSP. | HP | ENG
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.1 | MATERIAL TESTING
4.1.1 | Material grading: Materials (GAP20/AP20, GAP65/AP65/LRAP65 and Drainage aggregate) | Bedding/Side Zone/ Overlay Zone/Embedment Zone/Pavement subsoil drainage aggregate and undercut material compliance. | Stockpile size 1500 to 4000m3. PS- Table 21.2 for GAP/AP20 PS- Table 20.3 for Overlay and Embedment Zone Material NZTA F/6 for Drainage Aggregate- Grading section 2.2 | PS-21.7.2 | Lab Test Report NZS 4407.3.8.1 | 4 Test 1 Test for each additional 1000m3 | HP | ENG |  |  | The grading limits on the Stevensons quarry materials provided are acceptable to use (LRAP65 and GAP20) |  | Table 21.9 has been considered (we cant find table 20.10)
4.1.2 | Weathering index: Materials (GAP20/AP20, GAP65/AP65/LRAP65 and Drainage aggregate) | Bedding/Side Zone/ Overlay Zone/Embedment Zone/Pavement subsoil drainage aggregate and undercut material compliance. | Engineers Approval AA to CA | PS-21.7.2 | Lab Test Report NZS 4407.3.11 | 2 test per source | HP | ENG |  |  | The grading limits on the Stevensons quarry materials provided are acceptable to use (LRAP65 and GAP20) |  | Table 21.9 has been considered (we cant find table 20.10)
4.1.3 | Crushing Resistance: Materials (GAP20/AP20, GAP65/AP65/LRAP65 and Drainage aggregate) | Bedding/Side Zone/ Overlay Zone/Embedment Zone/Pavement subsoil drainage aggregate and undercut material compliance. | Engineers Approval >100kN | PS-21.7.2 | Lab Test Report NZS 4407.3.10 | 2 test per source | HP | ENG |  |  | The grading limits on the Stevensons quarry materials provided are acceptable to use (LRAP65 and GAP20) |  | Table 21.9 has been considered (we cant find table 20.10)
4.1.4 | Geotextile/Geogrid | Minimum Strength Class C & Filter Class 1 or TNZ F/7geotextile is to be used in Trench Backfill of Drainage pipe in Wet conditions. | Engineers Site Representative to inspect trench. | PS-16.5.7 | Certification | 1 time | HP | ENG
4.2 | RIPRACK ROCK TESTING
4.2.1 | Riprap test Criteria | Weathering Index of Coarse Aggregate. | Engineers Approval AA to CA | PS-21.7.4 | Lab Test Report NZS4407.3.11 | 1 per 1000m3 | HP | ENG
4.2.2 | Riprap test Criteria | Crushing Resistance of Course Aggregate. | Engineers Approval > 150kN | PS-21.7.4 | Lab Test Report NZS4407.3.10 | 1 per 1000m3 | HP | ENG
4.2.3 | Riprap test Criteria | Solid Density of Aggregate. | Engineers Approval ≥ 2.65 tonnes per m3 | PS-21.7.4 | Lab Test Report NZS4407.3.7.1 | 1 per 1000m3 | HP | ENG
4.2.4 | Riprap test Criteria | Grading of the material. | D=50 150mm Riprap Grading Aperture Size- 230mm Aperture Size- 150mm Aperture Size- 95mm | PS-21.7.4 PS-21.5.14 Table 21.3 | Lab Test Report NZS4407.3.8.2 | Percentage passing- 85 Percentage passing- 50 Percentage passing- 15 | HP | ENG
4.2.5 | Riprap test Criteria | Point Load Strength. | Engineers Approval >1.5 Mpa | PS-21.7.4 | Lab Test Report ASTM D5731 | 1 per 1000m3 | HP | ENG
4.2.6 | Riprap test Criteria | UCS Rock | Engineers Approval >30 Mpa | PS-21.7.4 | Lab Test Report AS4133.4.2.1 | 1 per 1000m3 | HP | ENG
4.3 | MATERIAL DELIVERY
4.3.1 | Pipe and fittings. (uPVC SN16, PVC, PP, PE and Concrete pipe). | Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition. | Site Engineer Approval | PS- 21.5.1 PS- 21.5.2 PS- 21.5.3 | Delivery Dockets | Each Delivery to site | H | SE
4.3.2 | Stormwater- Structure (SWMH, SDMH, GMH, CP, DCP, CPMH, MP, HW) | Confirm diameter, class & jointing type as shown on the drawings, and that the Structure are correct and in good condition. | Site Engineer Approval | PS- 21.5.4 NZS 3109:1997 | Delivery Dockets | Each Delivery to site | H | SE
4.3.3 | Granular Material (GAP20/AP20, GAP65/AP65/LRAP65/Riprap and Drainage aggregate) | Confirm Specification and material in good condition. | Site Engineer Approval | PS-21.7.2 | Delivery Dockets | Each Delivery to site | H | SE
4.3.4 | Geotextile/Geogrid | Minimum Strength Class C, Filtration Class 1. | Site Engineer Approval | PS-21.7.3 | Delivery Dockets | Each Delivery to site | H | SE
SECTION 5 – CONSTRUCTION ACTIVITY
5.1 | STORMWATER MANHOLE CONSTRUCTION
5.1.1 | Foundation Compliance | On Granular or Cohesive Material | Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa | PS- 21.7.2 Appendix V | Scala/Shear test result | 1 Test/Manhole | W | SE
5.1.2 | Undercut approval | On Subgrade | Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material. | Table 1 Sheet STW 0405. PS- 21.6.11 AS/NZS 2566.2/2002 | Lab Test Report | If Undercut required | H | SE
5.1.3 | Undercut Backfill Compliance (GAP65/AP65/LRAP65) | On Granular Material | Clegg Reading >10 CIV for non-trafficable areas Clegg Reading >25 CIV for trafficable areas | PS- 16.5.12 Table 21.12 | Lab Test Report | 1 Test per Undercut | H | SE
5.1.4 | Bedding Compaction Testing (GAP65/AP65/LRAP65) | On Granular Material | Clegg Reading >10 CIV for non-trafficable areas Clegg Reading >25 CIV for trafficable areas | PS- 16.5.12 Table 21.12 | Lab Test Report | 1 Test/Manhole | H | SE
5.1.5 | Survey | Inspection of Structure | Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 30mm. | PS- 21.7.6 | Survey Data | Continous | H | SV
5.1.6 | Backfill Compaction Testing | On Granular or Cohesive Material | GAP20 Backfill Compacted in 200mm layers around pipe. Clegg-12 CIV AP65 Backfill Compacted in 200mm layers. Testing to be completed on maximum 200mm lifts of backfill Clegg- 28 CIV (or) Cohesive Material in 200mm layers. Shear vane- 50Kpa | PS- 21.6.12 Appendix V | Lab Test Report | GAP20- 4 test per lift AP65- 6 test per lift Cohesive- 4 test per lift | H | SE
5.1.7 | Pre-Backfill Inspection | Inspection of Structure | Inspection of Structure prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the Structure. | PS- 21.6.11 | Manhole/Catchpit Record | Continous | I | SE
6.2 | STORMWATER CATCHPIT CONSTRUCTION
6.2.1 | Foundation Compliance | On Granular or Cohesive Material | Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa | PS- 21.7.2 Appendix V | Scala/Shear test result | 1 Test/Manhole | W | SE
6.2.2 | Undercut approval | On Subgrade | Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material. | Table 1 Sheet STW 0405. PS- 21.6.11 AS/NZS 2566.2/2002 | Lab Test Report | If Undercut required | H | SE
6.2.3 | Undercut Backfill Compliance (GAP65/AP65/LRAP65) | On Granular Material | Clegg Reading >10 for non-trafficable areas Clegg Reading >25 for trafficable areas | PS- 16.5.12 Table 21.12 | Lab Test Report | 1 Test per Undercut | H | SE
6.2.4 | Bedding Compaction Testing (GAP65/AP65/LRAP65) | On Granular Material | Clegg Reading >10 for non-trafficable areas Clegg Reading >25 for trafficable areas | PS- 16.5.12 Table 21.12 | Lab Test Report | 1 Test/Manhole | H | SE
6.2.5 | Survey | Inspection of Structure | Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 30mm. | PS- 21.7.6 | Survey Data | Continous | H | SV
6.2.6 | Backfill Compaction Testing | On Granular or Cohesive Material | GAP20 Backfill Compacted in 200mm layers around pipe. Clegg-12 CIV AP65 Backfill Compacted in 200mm layers. Testing to be completed on maximum 200mm lifts of backfill Clegg- 28 CIV (or) Cohesive Material in 200mm layers. Shear vane- 50Kpa | PS- 21.6.12 Appendix V | Lab Test Report | GAP20- 4 test per lift AP65- 4 test per lift Cohesive- 4 test per lift | H | SE
6.2.7 | Pre-Backfill Inspection | Inspection of Structure | Inspection of Structure prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the Structure. | PS- 21.6.11 | Manhole/Catchpit Record | Continous | I | SE
6.3 | STORMWATER FLEXIBLE PIPELINE CONSTRUCTION
6.3.1 | Foundation Compliance | On Granular or Cohesive Material | Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa | PS- 21.7.2 Appendix V | Scala/Shear test result | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. | W | SE
6.3.2 | Undercut approval | On Subgrade | Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material. | Table 1 Sheet STW 0405. PS- 21.6.11 AS/NZS 2566.2/2002 | Lab Test Report | If Undercut required | H | SE
6.3.3 | Undercut Backfill Compliance (GAP65/AP65/LRAP65) | On Granular Material | Clegg Reading >10 CIV for non-trafficable areas Clegg Reading >25 CIV for trafficable areas | PS- 16.5.12 | Lab Test Report | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. | H | SE
6.3.4 | Bedding and Embedment Zone Compaction Testing (Polypropylene(civil boss)/Polyethylene Pipe). | On Granular Material | Bedding Zone: 100mm(for DN300 & DN375) 150mm (for pipes greater than DN375) Embedment Zone: Pipe Dia ≤450 - 150mm GAP20/AP20 - Overlay Pipe Dia 450< D ≤900 - 150mm GAP20/AP20 - Overlay Pipe Dia 900< D ≤4000 - 150mm GAP20/AP20 - Overlay Minimum Compaction- Trafficable and Non-Trafficable Clegg Reading >12% CIV | PS- Table 21.7 PS- Table 21.12 AS/NZS 2566.2/2002 | Lab Test Report | One test per 10m evenly spaced intervals along pipeline with aminimum of 1 test between each pit/manhole. | H | SE
6.3.5 | Survey | Surveyor to Setout | Vertical design Setout: Pipes ≤ 1% grade: +/- 10mm variance Pipes > 1% grade: +/- 20mm variance Horizontal design Setout: +/-30mm variance | PS- 21.7.6 Table 21.15 | Survey Data | Every 100m or at Chambers (whichever distance is the lesser) | H | SV
6.3.6 | Backfill Compaction Testing | On Granular or Cohesive Material | AP65 Backfill Compacted in 200mm layers. Testing to be completed on maximum 200mm lifts of backfill Clegg- 28 CIV (or) Cohesive Material in 200mm layers. Shear vane- 50Kpa | PS- 21.6.12 Appendix V | Lab Test Report | One test per 10m evenly spaced intervals along pipeline with aminimum of 1 test between each pit/manhole. | H | SE
6.3.7 | Pipe Inspection | Inspection of Drainage line | Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness | PS- 21.7.6 | Drainage line record | Continious 1 per Line | I | SE
6.4 | STORMATER STEEL REINFORCED CONCRETE PIPELINE CONSTRUCTION
6.4.1 | Foundation Compliance | On Granular or Cohesive Material | Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa | PS- 21.7.2 Appendix V | Scala/Shear test result | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. | W | SE
6.4.2 | Undercut approval | On Subgrade | Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material. | Table 1 Sheet STW 0405. PS- 21.6.11 AS/NZS 2566.2/2002 | Lab Test Report | If Undercut required | H | SE
6.4.3 | Undercut Backfill Compliance (GAP65/AP65/LRAP65) | On Granular Material | Clegg Reading >10 CIV for non-trafficable areas Clegg Reading >25 CIV for trafficable areas | PS- 16.5.12 | Lab Test Report | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. | H | SE
6.4.4 | Bedding Compaction Testing | On Granular Material | Bedding Zone: 100mm(for DN300 & DN375) 150mm (for pipes greater than DN375) Minimum Compaction- Trafficable and Non-Trafficable Clegg Reading >12% CIV | PS- Table 21.6 PS- Table 21.12 AS/NZS 2566.2/2002 | Lab Test Report | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. | H | SE
6.4.5 | Haunch Zone Compaction Testing | On Granular Material | HS2- 100mm if D≤1500 (or) 150mm if D≥1500 Minimum Compaction- Trafficable and Non-Trafficable Clegg Reading >12% CIV | PS- Table 21.6 PS- Table 21.12 AS/NZS 2566.2/2002 | Lab Test Report | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. | H | SE
6.4.6 | Side Zone Compaction Testing | On Granular Material | HS2- 100mm if D≤1500 (or) 150mm if D≥1500 Minimum Compaction- Trafficable and Non-Trafficable Clegg Reading >12% CIV | PS- Table 21.6 PS- Table 21.12 AS/NZS 2566.2/2002 | Lab Test Report | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. | H | SE
6.4.7 | Survey | Surveyor to Setout | Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness | PS- 21.7.6 Table 21.15 | Survey Data | Every 100m or at Chambers (whichever distance is the lesser) | H | SV
6.4.8 | Overlay Zone Compaction Testing | On Granular Material | Minimum Compaction- Trafficable and Non-Trafficable Clegg Reading >12% CIV | PS- Table 21.6 PS- Table 21.12 AS/NZS 2566.2/2002 | Lab Test Report | One test per 10m evenly spaced intervals along pipeline with aminimum of 1 test between each pit/manhole. | H | SE
6.4.9 | Backfill Compaction Testing | On Granular or Cohesive Material | AP65 Backfill Compacted in 200mm layers. Testing to be completed on maximum 200mm lifts of backfill Clegg- 28 CIV (or) Cohesive Material in 200mm layers. Shear vane- 50Kpa | PS- 21.6.12 Appendix V | Lab Test Report | One test per 10m evenly spaced intervals along pipeline with aminimum of 1 test between each pit/manhole. | H | SE
6.4.10 | Pipe Inspection | Inspection of Drainage line | Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness | PS- 21.7.6 | Drainage line record | Continious 1 per Line | I | SE
6.5 | HEADWALL AND WINGWALL INSTALLATION
6.5.1 | Headwall and Wingwall Foundation Compliance | On Granular or Cohesive Material | Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa | PS- 21.7.2 Appendix V | Scala/Shear test result | 1 Test per Structure | HP | ENG
6.5.2 | Undercut approval | On Subgrade | Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material. | Table 1 Sheet STW 0405. PS- 21.6.11 AS/NZS 2566.2/2002 | Lab Test Report | If Undercut required | H | SE
6.5.3 | Undercut Backfill Compliance (GAP65/AP65/LRAP65) | On Granular Material | Clegg Reading >10 for non-trafficable areas Clegg Reading >25 for trafficable areas | PS- 16.5.12 | Lab Test Report | 1 Test per Undercut | H | SE
6.5.4 | Bedding Compaction Testing (GAP65/AP65/LRAP65) | On Granular Material | Clegg Reading >10 for non-trafficable areas Clegg Reading >25 for trafficable areas | PS- 16.5.12 | Lab Test Report | 1 Test per Structure | H | SE
6.5.5 | Survey | Inspection of Structure | Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 30mm. | PS- 21.7.6 | Survey Data | Continous | H | SV
6.5.6 | Backfill Compaction Testing | On Granular or Cohesive Material | GAP20 Backfill Compacted in 200mm layers around pipe. Clegg-12 CIV AP65 Backfill Compacted in 200mm layers. Testing to be completed on maximum 200mm lifts of backfill Clegg- 28 CIV (or) Cohesive Material in 200mm layers. Shear vane- 50Kpa | PS- 21.6.12 Appendix V | Lab Test Report | GAP20- 2 test per lift AP65- 2 test per lift Cohesive- 2 test per lift | H | SE
6.5.7 | Pre-Backfill Inspection | Inspection of Structure | Inspection of Structure prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the Structure. | PS- 21.6.11 | Manhole/Catchpit Record | Continous | I | SE
6.6 | RIPRAP INSTALLATION
6.6.1 | Riprap Foundation Compliance | On Granular or Cohesive Material | Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa | PS- 21.7.2 Appendix V | Scala/Shear test result | One test per 20m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. | W | SE
6.6.2 | Undercut approval | On Subgrade | Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material. | Table 1 Sheet STW 0405. PS- 21.6.11 AS/NZS 2566.2/2002 | Lab Test Report | If Undercut required | H | SE
6.6.3 | Undercut Backfill Compliance (GAP65/AP65/LRAP65) | On Granular Material | Clegg Reading >10 CIV for non-trafficable areas Clegg Reading >25 CIV for trafficable areas | PS- 16.5.12 | Lab Test Report | One test per 20m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. | H | SE
6.7 | CCTV
6.7.1 | CCTV Inspection | CCTV stormwater pipes at completion of trench backfill but prior to final surfacing (pavements, etc.) | Every stormwater pipeline 225mm diameter or greater. | PS- 21.7.6 PS- 21.7.8 | CCTV Report | 1 per line | S | PE
SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7.1 | AS-BUILTS
7.1.1 | Survey As-Builts | Quality Check on New Works based on the tolerances in RITS | Meets spec and thickness requirements as per drawings | PS-21.7.7 | Red pen markup only | Post works completion of a lot | H | SE