## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-007 ITP Stormwater | itp |  |  |  |  | DN1210-007 ITP Stormwater Rev 2
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.1.1 - Extent of Line Setout
label | Detail - Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Stormwater drawings.
label | ○ Identify any clashes before construction.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Design Drawings
label | Verifying Document - ITP Sign Off
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction & Every Revision of IFC Drawings/Data.
label | Verification Activity: Activity - M
label | Verification Activity: By - PE
checkpoint | 3.1.2 - Existing Stormwater system
label | Detail - Confirmation of existing stormwater network.
label | Acceptance / Conformance Criteria - Survey Informations
label | Standard / Specification - Appendix V
label | Verifying Document - Survey data
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction, Review existing service location drawing supplied by WSP.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.1.1 - Material grading: Materials (GAP20/AP20, GAP65/AP65/LRAP65 and Drainage aggregate)
label | Detail - Bedding/Side Zone/ Overlay Zone/Embedment Zone/Pavement subsoil drainage aggregate and undercut material compliance.
label | Acceptance / Conformance Criteria - Stockpile size 1500 to 4000m3.
label | ○ PS- Table 21.2 for GAP/AP20
label | ○ PS- Table 20.3 for Overlay and Embedment Zone Material
label | ○ NZTA F/6 for Drainage Aggregate- Grading section 2.2
label | Standard / Specification - PS-21.7.2
label | Verifying Document - Lab Test Report NZS 4407.3.8.1
label | Testing Quantity Required (based from schedule qtys) - 4 Test, 1 Test for each additional 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - Weathering index: Materials (GAP20/AP20, GAP65/AP65/LRAP65 and Drainage aggregate)
label | Detail - Bedding/Side Zone/ Overlay Zone/Embedment Zone/Pavement subsoil drainage aggregate and undercut material compliance.
label | Acceptance / Conformance Criteria - Engineers Approval AA to CA
label | Standard / Specification - PS-21.7.2
label | Verifying Document - Lab Test Report NZS 4407.3.11
label | Testing Quantity Required (based from schedule qtys) - 2 test per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.3 - Crushing Resistance: Materials (GAP20/AP20, GAP65/AP65/LRAP65 and Drainage aggregate)
label | Detail - Bedding/Side Zone/ Overlay Zone/Embedment Zone/Pavement subsoil drainage aggregate and undercut material compliance.
label | Acceptance / Conformance Criteria - Engineers Approval >100kN
label | Standard / Specification - PS-21.7.2
label | Verifying Document - Lab Test Report NZS 4407.3.10
label | Testing Quantity Required (based from schedule qtys) - 2 test per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.4 - Geotextile/Geogrid
label | Detail - Minimum Strength Class C & Filter Class 1 or TNZ F/7geotextile is to be used in Trench Backfill of Drainage pipe in Wet conditions.
label | Acceptance / Conformance Criteria - Engineers Site Representative to inspect trench.
label | Standard / Specification - PS-16.5.7
label | Verifying Document - Certification
label | Testing Quantity Required (based from schedule qtys) - 1 time
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.1 - Riprap test Criteria
label | Detail - Weathering Index of Coarse Aggregate.
label | Acceptance / Conformance Criteria - Engineers Approval AA to CA
label | Standard / Specification - PS-21.7.4
label | Verifying Document - Lab Test Report NZS4407.3.11
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.2 - Riprap test Criteria
label | Detail - Crushing Resistance of Course Aggregate.
label | Acceptance / Conformance Criteria - Engineers Approval > 150kN
label | Standard / Specification - PS-21.7.4
label | Verifying Document - Lab Test Report NZS4407.3.10
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.3 - Riprap test Criteria
label | Detail - Solid Density of Aggregate.
label | Acceptance / Conformance Criteria - Engineers Approval ≥ 2.65 tonnes per m3
label | Standard / Specification - PS-21.7.4
label | Verifying Document - Lab Test Report NZS4407.3.7.1
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Riprap test Criteria
label | Detail - Grading of the material.
label | Acceptance / Conformance Criteria - D=50 150mm Riprap Grading
label | ○ Aperture Size - 230mm
label | ○ Aperture Size - 150mm
label | ○ Aperture Size - 95mm
label | Standard / Specification - PS-21.7.4, PS-21.5.14 Table 21.3
label | Verifying Document - Lab Test Report NZS4407.3.8.2
label | Testing Quantity Required (based from schedule qtys) - Percentage passing - 85
label | ○ Percentage passing - 50
label | ○ Percentage passing - 15
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.5 - Riprap test Criteria
label | Detail - Point Load Strength.
label | Acceptance / Conformance Criteria - Engineers Approval >1.5 Mpa
label | Standard / Specification - PS-21.7.4
label | Verifying Document - Lab Test Report ASTM D5731
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.6 - Riprap test Criteria
label | Detail - UCS Rock
label | Acceptance / Conformance Criteria - Engineers Approval >30 Mpa
label | Standard / Specification - PS-21.7.4
label | Verifying Document - Lab Test Report AS4133.4.2.1
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3.1 - Pipe and fittings (uPVC SN16, PVC, PP, PE and Concrete pipe).
label | Detail - Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Acceptance / Conformance Criteria - Site Engineer Approval
label | Standard / Specification - PS- 21.5.1
label | ○ PS- 21.5.2
label | ○ PS- 21.5.3
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.3.2 - Stormwater - Structure (SWMH, SDMH, GMH, CP, DCP, CPMH, MP, HW)
label | Detail - Confirm diameter, class & jointing type as shown on the drawings, and that the Structure are correct and in good condition.
label | Acceptance / Conformance Criteria - Site Engineer Approval
label | Standard / Specification - PS- 21.5.4, NZS 3109:1997
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.3.3 - Granular Material (GAP20/AP20, GAP65/AP65/LRAP65/Riprap and Drainage aggregate)
label | Detail - Confirm Specification and material in good condition.
label | Acceptance / Conformance Criteria - Site Engineer Approval
label | Standard / Specification - PS-21.7.2
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.3.4 - Geotextile/Geogrid
label | Detail - Minimum Strength Class C, Filtration Class 1.
label | Acceptance / Conformance Criteria - Site Engineer Approval
label | Standard / Specification - PS-21.7.3
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.1.1 - Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength 70kPa
label | Standard / Specification - PS- 21.7.2 Appendix V
label | Verifying Document - Scala/Shear test result
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 5.1.2 - Undercut approval
label | Detail - On Subgrade
label | Acceptance / Conformance Criteria - Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material.
label | Standard / Specification - Table 1 Sheet STW 0405. PS- 21.6.11, AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.1.3 - Undercut Backfill Compliance (GAP65/AP65/LRAP65)
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Clegg Reading >10 CIV for non-trafficable areas
label | ○ Clegg Reading >25 CIV for trafficable areas
label | Standard / Specification - PS- 16.5.12 Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per Undercut
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.1.4 - Bedding Compaction Testing (GAP65/AP65/LRAP65)
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Clegg Reading >10 CIV for non-trafficable areas
label | ○ Clegg Reading >25 CIV for trafficable areas
label | Standard / Specification - PS- 16.5.12 Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.1.5 - Survey
label | Detail - Inspection of Structure
label | Acceptance / Conformance Criteria - Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 30mm.
label | Standard / Specification - PS- 21.7.6
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - Continous
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 5.1.6 - Backfill Compaction Testing
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - GAP20 Backfill Compacted in 200mm layers around pipe.
label | ○ Clegg - 12 CIV
label | ○ AP65 Backfill Compacted in 200mm layers.
label | ○ Testing to be completed on maximum 200mm lifts of backfill
label | ○ Clegg - 28 CIV
label | (or)
label | ○ Cohesive Material in 200mm layers.
label | ○ Shear vane - 50Kpa
label | Standard / Specification - PS- 21.6.12 Appendix V
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - GAP20- 4 test per lift
label | ○ AP65 - 6 test per lift
label | ○ Cohesive - 4 test per lift
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.1.7 - Pre-Backfill Inspection
label | Detail - Inspection of Structure
label | Acceptance / Conformance Criteria - Inspection of Structure prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the Structure.
label | Standard / Specification - PS- 21.6.11
label | Verifying Document - Manhole/Catchpit Record
label | Testing Quantity Required (based from schedule qtys) - Continous
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.2.1 - Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength 70kPa
label | Standard / Specification - PS- 21.7.2 Appendix V
label | Verifying Document - Scala/Shear test result
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 6.2.2 - Undercut approval
label | Detail - On Subgrade
label | Acceptance / Conformance Criteria - Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material.
label | Standard / Specification - Table 1 Sheet STW 0405. PS- 21.6.11, AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.2.3 - Undercut Backfill Compliance (GAP65/AP65/LRAP65)
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Clegg Reading >10 for non-trafficable areas
label | ○ Clegg Reading >25 for trafficable areas
label | Standard / Specification - PS- 16.5.12 Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per Undercut
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.2.4 - Bedding Compaction Testing (GAP65/AP65/LRAP65)
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Clegg Reading >10 for non-trafficable areas
label | ○ Clegg Reading >25 for trafficable areas
label | Standard / Specification - PS- 16.5.12 Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.2.5 - Survey
label | Detail - Inspection of Structure
label | Acceptance / Conformance Criteria - Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 30mm.
label | Standard / Specification - PS- 21.7.6
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - Continous
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 6.2.6 - Backfill Compaction Testing
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - GAP20 Backfill Compacted in 200mm layers around pipe.
label | ○ Clegg - 12 CIV
label | ○ AP65 Backfill Compacted in 200mm layers.
label | ○ Testing to be completed on maximum 200mm lifts of backfill
label | ○ Clegg - 28 CIV
label | (or)
label | ○ Cohesive Material in 200mm layers.
label | ○ Shear vane - 50Kpa
label | Standard / Specification - PS- 21.6.12 Appendix V
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - GAP20- 4 test per lift
label | ○ AP65 - 4 test per lift
label | ○ Cohesive - 4 test per lift
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.2.7 - Pre-Backfill Inspection
label | Detail - Inspection of Structure
label | Acceptance / Conformance Criteria - Inspection of Structure prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the Structure.
label | Standard / Specification - PS- 21.6.11
label | Verifying Document - Manhole/Catchpit Record
label | Testing Quantity Required (based from schedule qtys) - Continous
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.3.1 - Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength 70kPa
label | Standard / Specification - PS- 21.7.2 Appendix V
label | Verifying Document - Scala/Shear test result
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 6.3.2 - Undercut approval
label | Detail - On Subgrade
label | Acceptance / Conformance Criteria - Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material.
label | Standard / Specification - Table 1 Sheet STW 0405. PS- 21.6.11, AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.3.3 - Undercut Backfill Compliance (GAP65/AP65/LRAP65)
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Clegg Reading >10 CIV for non-trafficable areas
label | ○ Clegg Reading >25 CIV for trafficable areas
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.3.4 - Bedding and Embedment Zone Compaction Testing (Polypropylene(civil boss)/Polyethylene Pipe).
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Bedding Zone: 100mm(for DN300 & DN375) 150mm (for pipes greater than DN375)
label | ○ Embedment Zone:
label | — Pipe Dia ≤450 - 150mm GAP20/AP20 - Overlay
label | — Pipe Dia 450< D ≤900 - 150mm GAP20/AP20 - Overlay
label | — Pipe Dia 900< D ≤4000 - 150mm GAP20/AP20 - Overlay
label | ○ Minimum Compaction - Trafficable and Non-Trafficable Clegg Reading >12% CIV
label | Standard / Specification - PS- Table 21.7, PS- Table 21.12, AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipeline with aminimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.3.5 - Survey
label | Detail - Surveyor to Setout
label | Acceptance / Conformance Criteria - Vertical design Setout:
label | — Pipes ≤ 1% grade: +/- 10mm variance
label | — Pipes > 1% grade: +/- 20mm variance
label | ○ Horizontal design Setout: +/-30mm variance
label | Standard / Specification - PS- 21.7.6 Table 21.15
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - Every 100m or at Chambers (whichever distance is the lesser)
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 6.3.6 - Backfill Compaction Testing
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - AP65 Backfill Compacted in 200mm layers.
label | ○ Testing to be completed on maximum 200mm lifts of backfill
label | ○ Clegg- 28 CIV
label | (or)
label | ○ Cohesive Material in 200mm layers.
label | ○ Shear vane - 50Kpa
label | Standard / Specification - PS- 21.6.12 Appendix V
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipeline with aminimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.3.7 - Pipe Inspection
label | Detail - Inspection of Drainage line
label | Acceptance / Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | Standard / Specification - PS- 21.7.6
label | Verifying Document - Drainage line record
label | Testing Quantity Required (based from schedule qtys) - Continuous 1 per Line
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.4.1 - Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength 70kPa
label | Standard / Specification - PS- 21.7.2 Appendix V
label | Verifying Document - Scala/Shear test result
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 6.4.2 - Undercut approval
label | Detail - On Subgrade
label | Acceptance / Conformance Criteria - Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material.
label | Standard / Specification - Table 1 Sheet STW 0405. PS- 21.6.11, AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.4.3 - Undercut Backfill Compliance (GAP65/AP65/LRAP65)
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Clegg Reading >10 CIV for non-trafficable areas
label | ○ Clegg Reading >25 CIV for trafficable areas
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.4.4 - Bedding Compaction Testing
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Bedding Zone: 100mm(for DN300 & DN375) 150mm (for pipes greater than DN375)
label | ○ Minimum Compaction - Trafficable and Non-Trafficable Clegg Reading >12% CIV
label | Standard / Specification - PS- Table 21.6, PS- Table 21.12, AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.4.5 - Haunch Zone Compaction Testing
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - HS2- 100mm if D≤1500 (or) 150mm if D≥1500
label | ○ Minimum Compaction - Trafficable and Non-Trafficable Clegg Reading >12% CIV
label | Standard / Specification - PS- Table 21.6, PS- Table 21.12, AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.4.6 - Side Zone Compaction Testing
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - HS2- 100mm if D≤1500 (or) 150mm if D≥1500
label | ○ Minimum Compaction- Trafficable and Non-Trafficable Clegg Reading >12% CIV
label | Standard / Specification - PS- Table 21.6, PS- Table 21.12, AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.4.7 - Survey
label | Detail - Surveyor to Setout
label | Acceptance / Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | Standard / Specification - PS- 21.7.6 Table 21.15
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - Every 100m or at Chambers (whichever distance is the lesser)
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 6.4.8 - Overlay Zone Compaction Testing
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Minimum Compaction- Trafficable and Non-Trafficable Clegg Reading >12% CIV
label | Standard / Specification - PS- Table 21.6, PS- Table 21.12, AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipeline with aminimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.4.9 - Backfill Compaction Testing
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - AP65 Backfill Compacted in 200mm layers.
label | ○ Testing to be completed on maximum 200mm lifts of backfill
label | ○ Clegg - 28 CIV
label | (or)
label | ○ Cohesive Material in 200mm layers.
label | ○ Shear vane - 50Kpa
label | Standard / Specification - PS- 21.6.12 Appendix V
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipeline with aminimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.4.10 - Pipe Inspection
label | Detail - Inspection of Drainage line
label | Acceptance / Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | Standard / Specification - PS- 21.7.6
label | Verifying Document - Drainage line record
label | Testing Quantity Required (based from schedule qtys) - Continuous 1 per Line
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.5.1 - Headwall and Wingwall Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength 70kPa
label | Standard / Specification - PS- 21.7.2 Appendix V
label | Verifying Document - Scala/Shear test result
label | Testing Quantity Required (based from schedule qtys) - 1 Test per Structure
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.5.2 - Undercut approval
label | Detail - On Subgrade
label | Acceptance / Conformance Criteria - Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material.
label | Standard / Specification - Table 1 Sheet STW 0405. PS- 21.6.11, AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.5.3 - Undercut Backfill Compliance (GAP65/AP65/LRAP65)
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Clegg Reading >10 for non-trafficable areas
label | ○ Clegg Reading >25 for trafficable areas
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per Undercut
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.5.4 - Bedding Compaction Testing (GAP65/AP65/LRAP65)
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Clegg Reading >10 for non-trafficable areas
label | ○ Clegg Reading >25 for trafficable areas
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per Structure
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.5.5 - Survey
label | Detail - Inspection of Structure
label | Acceptance / Conformance Criteria - Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 30mm.
label | Standard / Specification - PS- 21.7.6
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - Continous
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 6.5.6 - Backfill Compaction Testing
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - GAP20 Backfill Compacted in 200mm layers around pipe.
label | ○ Clegg - 12 CIV
label | ○ AP65 Backfill Compacted in 200mm layers.
label | ○ Testing to be completed on maximum 200mm lifts of backfill
label | ○ Clegg - 28 CIV
label | (or)
label | ○ Cohesive Material in 200mm layers.
label | ○ Shear vane - 50Kpa
label | Standard / Specification - PS- 21.6.12 Appendix V
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - GAP20- 2 test per lift
label | ○ AP65 - 2 test per lift
label | ○ Cohesive - 2 test per lift
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.5.7 - Pre-Backfill Inspection
label | Detail - Inspection of Structure
label | Acceptance / Conformance Criteria - Inspection of Structure prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the Structure.
label | Standard / Specification - PS- 21.6.11
label | Verifying Document - Manhole/Catchpit Record
label | Testing Quantity Required (based from schedule qtys) - Continous
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.6.1 - Riprap Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength 70kPa
label | Standard / Specification - PS- 21.7.2 Appendix V
label | Verifying Document - Scala/Shear test result
label | Testing Quantity Required (based from schedule qtys) - One test per 20m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 6.6.2 - Undercut approval
label | Detail - On Subgrade
label | Acceptance / Conformance Criteria - Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material.
label | Standard / Specification - Table 1 Sheet STW 0405. PS- 21.6.11, AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.6.3 - Undercut Backfill Compliance (GAP65/AP65/LRAP65)
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Clegg Reading >10 CIV for non-trafficable areas
label | ○ Clegg Reading >25 CIV for trafficable areas
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 20m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.7.1 - CCTV Inspection
label | Detail - CCTV stormwater pipes at completion of trench backfill but prior to final surfacing (pavements, etc.)
label | Acceptance / Conformance Criteria - Every stormwater pipeline 225mm diameter or greater.
label | Standard / Specification - PS- 21.7.6, PS- 21.7.8
label | Verifying Document - CCTV Report
label | Testing Quantity Required (based from schedule qtys) - 1 per line
label | Verification Activity: Activity - S
label | Verification Activity: By - PE
section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 7.1.1 - Survey As-Builts
label | Detail - Quality Check on New Works based on the tolerances in RITS
label | Acceptance / Conformance Criteria - Meets spec and thickness requirements as per drawings
label | Standard / Specification - PS-21.7.7
label | Verifying Document - Red pen markup only
label | Testing Quantity Required (based from schedule qtys) - Post works completion of a lot
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature