## Project Checklist Templates
Type | Name | Values | Prompting Name
checklist | Waterproofing - Balcony Areas |  | Waterproofing - Balcony Areas
section | Prior to Works
checkpoint | Substrate - Review to ensure any voids or protrusions are filled and removed and ensure surface is prepared to take membrane (lightly sanded to promote adhesion)
note | Also ensure substrate is clean and free of any water, dust and debris.
checkpoint | Verify with Plumber that their drainage works are completed prior to membrane commencement.
note | Attach Subcontractor ITP where relevant.
checkpoint | Concrete Cracks - Review substrate for any cracking. Up to 2mm cracks fill with Polyurethane sealant. Above 2mm to be chased, cleaned and primed, then sealant applied.
checkpoint | Falls - Review concrete substrate to ensure min. 1:100 falls achieved and falling to floor wastes.
checkpoint | Floor Wastes - Review puddle flange to ensure it is recessed and flush with floor substrate. The PVC flange should be lightly sanded to promote membrane adhersion.
note | Also check internal of floor wastes to ensure free from debris prior to waterproofing.
checkpoint | Overflow Points - Review overflow points are installed correctly per plans (min. x2 per balcony) and pipework is proud of slab surface by min. 30mm.
note | Check overflow points are connected below to curtain wall façade and not blocked.
checkpoint | Substrate Moisture Content - Verify that waterproofing contractor has tested moisture content of concrete substrate and is happy to proceed with works (ie; below 5%).
textbox | Record moisture meter reading.
signoff | Subcontractor to sign-off on substrate.
checkpoint | Waterproofing Materials - Confirm approved waterproofing materials are being used for the works.
note | Waterproofing Primer: Sikalastic PU Primer. Waterproofing Membrane: Sikalastic 488
checkpoint | Record product batch/serial numbers for tracking of any future defects.
textbox | Batch/Serial Numbers:
checkpoint | HOLD POINT INSPECTION - Organise membrane consultants, regulated designer (FJC), membrane suppliers or PCA to inspect substrate to ensure prepared in accordance with design & specifications.
note | Attach record of inspection where applicable.
section | During Works
checkpoint | Ambient Conditions - Membrane Works
textbox | Record the ambient temperature information during membrane installation:
textbox | Record the Commencement date/time of the application:
textbox | Record the Finish date/time of the application:
checkpoint | Sealant/Bond Breakers - Confirm applied to all wall/floor and wall/wall junctions as well as around any services penetrations and wall fixings (ie; screw fixings, etc…). Surfaces should be primed prior to application of sealant/bond breakers.
note | Waterproofing Sealant: Nitroseal PU250 or PU400 (Check to ensure gaps not more than 20mm wide/deep for sealant application. Min. fillet of sealant should be 5mm). Bond Breaker: Nitroband Tape (ensure surface primed prior to install and overlapping at joints 150mm each side).
note | Check to ensure gaps not more than 20mm wide/deep for sealant application. Min. fillet of sealant should be 5mm. Record photos of the installation.
checkpoint | HOLD POINT INSPECTION - Organise membrane consultants, regulated designer (FJC), membrane suppliers or PCA to inspect priming and sealant/bond breakers to ensure they are installed in accordance with design & specifications.
note | Attach record of inspection where applicable.
checkpoint | Floor Membrane - Confirm 1x coat of primer (Fosroc Nitroproof 510 - 6hr curing time prior to membrane application) & 2x coats of membrane (Fosroc Nitroproof 750 - requires 16hrs curing time between coats, final coat 36hrs curing time prior to Water Test).
note | Attach progress photos of completed membrane works. Ensure no membrane on top of exposed elements (ie; curtain wall, etc…). Ensure balcony access is barricaded with signage to prevent damage from other trades.
checkpoint | Membrane Skirting Upturn - ensure membrane applied 150mm up wall from structural floor level per standards.
checkpoint | Wall Membrane - confirm membrane applied to wall substrate where taps installed (under finishes) and around curtain wall to slab junctions.
note | Attach progress photos of completed membrane works.
section | After Works
checkpoint | Flood Testing: Block floor waste points & overflows and fill balcony to internal hob height and leave for 24hrs.
note | Verify that final coat of membrane has had appropriate curing time (refer curring time notes in ITP above) prior to Flood testing.
note | Mark water level at start of flood testing to verify for any leaks/drops in water level. Attach before and after photos with time/date stamps.
checkpoint | HOLD POINT - verification of Flood Testing Results - Any leaks Found?
textbox | Note: if any leaks identified (if so re-membrane and test)?
signoff | Contractor to sign-off on flood testing results once passed.
checkpoint | Attach subcontractor ITP
section | Sign-off
checkpoint | Subcontractor Signoff
signoff | Subcontractor Sign-off
checkpoint | SDC Signoff
signoff | SDC Sign-off