## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
0b201768-9013-5d87-a4fd-5a69e04455ae | checklist | Framing/Sheeting |  | Framing/Sheeting
1530de07-be34-5ea4-9be0-034b905e4913 | section | Survey/Wall Framing
23e408dd-5135-5585-8838-3938629743f7 | checkpoint | Confirm set-out of walls in correct locations & cross check with surveyors grids.
bf593cf7-e545-5d09-9b0b-ec0e6373d66f | textbox | Confirm wall set-out plan/revision used for set-out
a16d87db-338a-538f-a086-c2dff04f4e24 | checkpoint | Confirm that 1m benchmark has been reviewed and agreed. Ensure it is marked on most relevant permanent structure.
172e069e-c65b-54dc-b5a7-1c15435da685 | note | Attach photo of 1m benchmark for reference.
9d89ff1b-c508-5ac3-bd00-4946b21dcaac | checkpoint | Review wall types are installed correctly per architectural wall type details.
b3289e54-f7f4-5040-ae16-579651fe5a19 | checkpoint | Review wet area framing to ensure square and plumb to take tiling.
2475c618-869c-5955-91b7-ed342460614d | checkpoint | Strengthening Requirements - Confirm all noggins, trimming blocks and struts have been appropriately installed to support the following items (Min. 12mm structural plywood). Ensure to cross check relevant drawings:
2c5a047b-960f-5c5f-aa3a-0cb88c8cc8cb | note | Appliances (Wall mounted dryers, etc…)
c1b1f60c-6dc9-5f9a-8745-995ef2938d45 | note | Bathroom Accessories (Robe hooks, towel rails, shower shelves, toilet roll holders, adaptable handrails, etc…)
925b3429-826e-5c1e-b9d5-42f3bd35a048 | note | Bathroom Furniture (Mirror Cabinets, Vanity Basins, shower roses, etc…)
3d0db52b-01eb-5cce-8cbf-3a3679aa89de | note | Services (pendant lighting, display screens, TV areas, etc…)
adce8afe-bf59-540f-a059-012355501f0e | checkpoint | Adaptable Apartments - Check blocking installed to cater for post adaptation layouts
1f6ff53a-205c-5f4d-9e46-ea4d22ee9c5f | checkpoint | Confirm that all framing is square at corners (check top, middle & bottom of frame junctions)
08416204-8429-568e-afd7-c9fa6e7deb30 | checkpoint | Confirm studs not bridging or touching hydraulic pipes, mechanical units, columns in intertenancy walls or lift shaft walls to ensure vibration is not transferred through walls
f50e86d9-dd83-5f11-aa50-b871c9ce3f96 | checkpoint | Deflection Requirements - Ensure gap is present (10-15mm) at top of stud inside head track
7dc97a50-13d3-5d72-a8a4-3e023ea7fc7a | checkpoint | Joinery Openings - check gaps between framing to joinery + wall finishes will fit (5mm tolerance)
a9f86b22-e357-52ed-8b42-f7e8c3cec071 | checkpoint | Stud Spacing - Spot check studwork is spaced at 600mm maximum per Architectural Specification. Check additional studwork reinforcement at openings (ie; double studwork).
39866e90-f81a-57a8-a328-13140080c264 | note | Staggered Studs (if required) - to be installed at 300mm centres alternating per architectural specification
800c99ae-fb54-518e-8b80-7904c5f20f9d | checkpoint | Movement Joints - check walls are discontinued where they pass over building movement joints.
0fb9cac1-74f6-5835-97fe-e2f3275bfea0 | checkpoint | Services Risers - Ensure stud and trackwork is kept a minimum of 20mm away from vertical services within risers per acoustic specification
7b5c79f8-64ee-516a-84e0-855baefc7c2d | checkpoint | Engineered Designs - Spot check any engineered framing designs and attached engineers review and sign-off on system.
62a0e57d-2239-53a4-ac18-f77d094f5587 | section | Wall Sheeting
120a946f-ec6f-599e-bb9b-b8960ce99ed1 | checkpoint | Confirm acoustic/thermal insulation installed to achieve design ratings
9214adb6-d2ff-5660-8c6b-148031b3d64c | note | Cross check product ratings against architectural insulation plans
89c41d83-a979-5103-9f52-baa51290c96e | checkpoint | Confirm there is a minimum of 45mm cavity (or 20mm where double sheeted with recessed skirting shown both sides of wall) between the residential intertenancy wall studwork per Acoustic Details/Wall type Plans
4dd07011-91a4-5458-83e3-bb6a7828e05b | checkpoint | Confirm door frames are installed vertical and plumb and at correct height.
6dd1553e-b07f-5f38-8ad6-7ad960f7ad18 | note | Check metal door frames in wet areas are outside of membrane zone (ie; notched accordingly).
fdf1f2cb-3f25-5dac-8ad1-e2d57b621fdf | checkpoint | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting walls
cf6a3ad0-9bac-535e-bb27-643a2e2def4c | signoff | Review & Sign-off by Acoustic Consultant
3406cd78-db00-5dcb-bfaa-92bc3b90dba2 | checkpoint | Check plasterboard sheets installed with 10-15mm gap at top and bottom to allow for deflection and fire sealant.
f70875dd-ec8f-5405-a8b4-37e1f96d5b9a | checkpoint | Control Joints - Ensure controls joints installed in wall runs larger than 12m in length.
ac438481-ab6e-51d7-9fcb-8324a93b993c | checkpoint | Check correct plasterboard linings installed (type and thickness) per architectural wall types
3ffd3315-cf0c-5aa2-a990-9022ef15a0b5 | checkpoint | Ensure sheets are staggered on multiple sheet layer walls. Stagger all sheet joints by minimum 200mm per architectural specification.
1fcf115e-b487-5f8b-8f9d-3eb3e9c1ee8a | checkpoint | Confirm plasterboard lining installed to wet areas are sealed up to concrete soffit on both sides of wall where adjacent to habitable rooms.
9736503d-c21f-51e6-96ba-c5b04f89b1fc | checkpoint | Confirm all services penetrations through wet area walls adjacent to habitable rooms are sealed and caulked for acoustic performance.
2e46ccf7-7f4f-5172-a94e-48007bf168d3 | note | Check that mechanical flex ducts are not passing through walls - to be rigid ductwork or sleave installed over.
1eaaba03-6b1a-5154-a302-05cc6d20387e | checkpoint | Check intertenancy walls extend to façade panels, leave 10-15mm gap and caulked with fire sealant.
| checkpoint | Check that Durasteel Fire Board and Rockwool insulation is installed around perimeter at soffit at façade bracket locations as per agreed fire engineering detail (ie; 500mm long board with 2x fixings and 120mm of rockwool either side of the bracket).
ee010fbd-1046-56c5-b493-1d37862a0f5a | section | Sheeting Ceilings
1f688c69-de7d-5db6-9592-47ca2fce1731 | checkpoint | Confirm ceiling insulation complete where applicable
94e08ce9-c2d6-58ed-a243-14d3407f27c2 | checkpoint | Confirm provisions made in ceiling framing for access panels and air grilles were required by architectural RCP
7fdffaac-406b-5801-bef2-6361fc7b31f7 | note | Spot check access panels installed to allow access to fire dampers and mechanical fans
036d84fe-11bd-5ad9-ab55-b8fa4ef58f5a | checkpoint | Confirm ceiling framing bulkheads are square and level
4e88e007-6712-548b-af61-90634071bf08 | checkpoint | Confirm furring channels do not clash with other services (eg; downlights, access panels, mechanical exhaust, sprinkler heads, etc…).
6d815a4b-f7ea-50d6-8d30-a42333b3b1fe | checkpoint | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting
82729cd5-dd85-5ad5-8e66-822a52f5bab6 | signoff | Review & Sign-off by Acoustic Consultant
e217164f-af7e-5616-bd19-3343bb541cc7 | checkpoint | HOLD POINT - Confirm BCA consultant inspection of services penetrations through fire rated walls prior to sheeting ceilings
894062ba-2286-5c42-97a3-5edb7e8965e2 | signoff | Review & Sign-off by BCA consultant
f2dee40a-a9fb-576d-a20a-9675ba9b5e42 | checkpoint | Confirm Plasterboard fixings are at correct intervals
47cc8396-5364-55eb-8c95-5ebafa007f1a | note | For painted surfaces, screw fixing onto sheeted frames should be max 400mm spacing. Refer to Manufacturer’s Installation guide
53c9c7bc-564d-5ce9-8daa-a26dc6b32637 | checkpoint | Confirm Villaboard/FC (wet area) fixings are of the correct intervals
be026fdc-1154-5e26-8d0d-16328c8b72b7 | note | For 9mm Villaboard/FC: Tiled wall screw fixings must be max 150mm spacing. Stud centres to be 400mm. Refer to Manufacturer’s Installation guide
49327a45-bf8d-5b9f-bcb8-d2eef0571ecf | checkpoint | Control Joints - Ensure ceiling bays are not larger than 12m without a joint or wall break.
1f79f360-0ac1-56e2-8b33-690dce63e2a6 | checkpoint | Attach Subcontractor ITP for the Works
c76b51ab-6264-5b4b-ab7d-fd597107fe72 | checkpoint | HOLD POINT - OK to proceed to painting
b4d64f56-0ea4-5b50-a1c8-90071a066939 | note | All defects completed?
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off