## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-0007– Fill Earthworks Type B |  |  |  |  | Yes | ITP-0007– Fill Earthworks Type B | 78c391e1-eb71-454e-9197-1f032f8c0fb0
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Define Work Lot
label | 6a64a428-2aa1-57fb-a585-00b3e75a0455 |  | note | Ref docs - 173.02 204.03 (h) Table 204.142 Quality Management Plan Lot Diagram
label | f4194164-39f2-5163-8c0f-7dfb8cbee6bb |  | note | Acceptance criteria - Survey boundaries clearly define the Earthworks Type B Construction works. Lot diagram to be provided clearly marking up extents of lot area. Work Lot open on TeamBinder.
label | b9a60f5d-c060-50a4-afd0-325578052c8b |  | note | Lot size with no more than one day’s production or a maximum of 10000m² for Type B Material. In case of Random level assessments of the surface measurements, the lot size shall be a maximum of 4000m².
button | cd17f1f8-06ea-5654-9e33-6eaebab83c90 |  | button | Has all of the above been completed and approved? | Yes, No
label | aae6eb37-0c1b-54c9-b621-f15b343314d7 |  | note | Freq - Prior to start of works
label | 0d0c1fa5-d343-50af-ac8d-ba442867c816 |  | note | Key - R S
label | af7818b0-73dc-5290-abae-878daa308e9e |  | note | Resp - SE
checkpoint-group |  |  | section | 2.0 Set Out
checkpoint-status |  |  | checkpoint | 2.1 - Set Out Survey Completed
label | ff48f63d-fb5c-5634-ab6b-b91de563617c |  | note | Ref docs - VR Clause 204.03 (a) IFC Drawings
label | bd2ffcaf-3591-5158-a291-4a550b22a92a |  | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per IFC drawings.
button | 239f6e45-c18a-5d47-b300-956737023480 |  | button | Has all of the above been completed and approved? | Yes, No
label | 6c8c9cf2-b41f-5101-b142-deb5e3006fbf |  | note | Freq - Each Lot
label | 258df0c5-cb77-5d08-ae72-b738344990bc |  | note | Key - R
label | 08910880-ed9c-5e25-b302-f25a33225e97 |  | note | Resp - SE
checkpoint-group |  |  | section | 3.0 Placement of Type B Material
checkpoint-status |  |  | checkpoint | 3.1 - Underlying Layer Conformance
label | 3699e946-ea07-5afd-ae96-3cc528fe9169 |  | note | Ref docs - VR Clause 204.10(b) Construction Document
label | a15e209a-40ce-5ee4-a7d0-f1de3cb63399 |  | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent.
button | 19f6a3e5-02b7-5d31-87d9-8a7a52489d99 |  | button | Approval to proceed granted? | Yes, No
label | edf88a63-be7c-5378-8540-7616730cef61 |  | note | Freq - Each Lot
label | 98f07a4b-023a-5ea2-ac05-659c8c51c641 |  | note | Key - H W
label | 3dc2c10a-318c-522b-8838-3c767ddc603a |  | note | Resp - SE
label | 2c9b5ad8-b3c0-5fde-9132-aee44e2cfc05 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Placing Geotextiles (if applicable)
label | bacdb45f-5be2-57ea-a2d5-856cb397b902 |  | note | Ref docs - VR Clause 210.05 Table PS3020.071 IFC Drawing
label | d447922e-5ab1-58c2-97cb-cba3d7a7b69f |  | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval of the Superintendent. Geotextile shall be placed to the limits as shown on drawings or specified. The geotextile shall be placed without punctures or tears and, if these occur, they shall be rectified or the entire roll of geotextile replaced prior to covering. Any rolls with imperfections shall not be used. All joints shall be overlapped or sewn in accordance with the Geotextile Record. Geotextiles shall be covered by filling within 48 hours of placement.
button | d37d3dd0-f639-532b-80dd-d4dd6f2e739c |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 88c15eda-bc82-577c-9f0b-9e6694fb796f |  | note | Freq - Each Lot
label | 2f7d8ee1-a96b-5219-a43b-b1b86684217d |  | note | Key - H W
label | abcc499f-3545-5660-86f3-efeab34ebce4 |  | note | Resp - SE
label | e503fdb1-886c-5eb6-9cd7-1da6da86212d |  | note | SI Key - H
checkpoint-status |  |  | checkpoint | 3.3 - Placing Subsurface Drainage
label | 30c30e33-e703-50a5-876a-c0da870c3274 |  | note | Ref docs - 1630-P200-SYM-TPW-RPT-0001 Appendix B – Table 5
label | d6181277-f431-5c9a-bee6-0f166e21a944 |  | note | Acceptance criteria - Subsurface drainage mat to be prepared in accordance with drawings. Superintendent to review and approve prior to placement of any fill on top of subsurface drainage mat.
button | e39bed4f-9d19-56f2-b909-8973661c793f |  | button | Approval to proceed granted? | Yes, No
label | 4e13bf65-da00-50ef-9c99-e97f1b2ef58e |  | note | Freq - Each Lot
label | ae4979e1-931d-54dc-a0aa-6ef7601e334e |  | note | Key - H
label | c96fbda1-ce71-5aea-b4cb-dffa1484bd06 |  | note | Resp - SE
label | 5ebb2857-9a7e-5270-98cc-3cdc89988620 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Placing of Fill
label | bbcf2b5a-9c14-5e02-8873-8e3f10d0d42c |  | note | Ref docs - VR Clause 204.10(d)
label | d73a39a0-c060-5ee8-b124-b6001ef174eb |  | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 200 mm. Where Type B material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 200 mm thick layer, the loose thickness of each layer may equal 125% of the typical maximum particle dimension of the rock up to a maximum layer thickness of 500 mm. Any rock with a maximum particle dimension greater than 80% of the loose thickness of the layer shall be removed. The material shall be placed and compacted such that voids are completely filled with fine material. Type B material containing rock with a particle dimension greater than 150 mm after compaction shall not be placed within 400 mm of the top of Type B and/or Type C material zones. Material shall be compacted at minimum moisture ratio of 80% Material shall also achieve
button | 15714b5e-ab7b-51c9-9d34-90c464d661ee |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | c5e3de5f-8561-576b-b7f7-8b0995497ded |  | note | Freq - Once Each Lot
label | d2730be5-900a-5679-a319-f3ca14ce1009 |  | note | Key - W
label | 83185d72-f13b-54fa-8c0a-ab38f9f2f7ab |  | note | Resp - SE
label | 59b14ed3-488b-5284-926f-b115bd94eea3 |  | note | Remarks/ record (eg. test frequency reports, certificates, checklist etc)
button | 0f33730a-5098-5259-a254-d6a28f1adb9e |  | button | Verification Records: Layer Thickness at least every three layers | Yes, No
button | 581ace1a-4829-501c-9e96-c146f186b943 |  | button | Material Compliance Certificates & Material Approval Register | Yes, No
button | fba1548b-cad3-5f28-bbe3-f3e0a8fe21d2 |  | button | VicRoads registration of recycled material blend (if applicable) | Yes, No
checkpoint-status |  |  | checkpoint | 3.5 - Keyed Fill Layers
label | 1759e5b9-0efe-51d3-a433-6529b174ade5 |  | note | Ref docs - VR Clause 204.10(c) 204.10(d) Construction Document
label | 526b9418-df6b-5993-8ce8-6fbf64910c99 |  | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other. Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
button | ca94546b-60de-52dd-a01f-edc2b1766c0b |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 2933ee0b-79e9-52fd-b3df-b0f7df738493 |  | note | Freq - Once Each Lot
label | 35407e58-ebf7-5321-a59a-0c37b384bb98 |  | note | Key - W
label | b466d427-6b77-544b-8e52-ab3fd64c3307 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.6 - Test Roll of Type B fill layer
label | fc78e6d5-84c2-5c90-ab85-5f0f75a0829c |  | note | Ref docs - VR Clause 204.12 173.03 Construction Document (Test roll Procedure in specification 173.03) 1630-P200-SYM-GEO-DPK-0001 Table 43
label | 27274407-cc24-52e9-acca-b376caa6b794 |  | note | Acceptance criteria - Test Roll in accordance with Section 173. Surface shall withstand test rolling without visible deformation or springing. Test roll to be completed using at least a fully loaded water cart with 8 tonne axle load or 20 tonne gross vehicle mass. Where unstable areas exceed 20% of the area being considered by proof roll the whole area should be ripped and recompacted. The Contractor shall provide for the Superintendent to be present during all test rolling.
button | 4c355b49-7cb3-5a6d-b008-4c775f3ee538 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 3b878e4a-2553-55a1-9b74-b8767f3ad4fc |  | note | Freq - Each Lot
label | e0656e59-80cf-5f44-af10-d528c97650e3 |  | note | Key - H
label | ee996129-5968-5ac5-a1b6-bb638ab79328 |  | note | Resp - SE
label | 00b4a4a1-75b2-5816-82f6-49655354a311 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Monitoring of Settlement
label | 951f4855-73d2-5f8a-8f46-57dd9b2287ef |  | note | Ref docs - 1630-P200-SYM-GEO-DPK-0001 5.4.2.2.10 Table 33
label | e91c1548-48c0-5be0-8d7d-74292b51b86a |  | note | Acceptance criteria - ITEM 3.7 ON HOLD (seeking clarification on intervals) Delete? The rate of filing lifts and effect on settlement, lateral displacement and excess pore water pressure to be monitored. The ratio of change in maximum lateral movement to change in maximum settlement should be calculate at the competition of each lift. If the ratio exceeds 0.6, Superintendent is to be notified. Superintendent to review and approve monitoring data at each subsequent lift. A minimum of two readings are to be taken immediately post installation and immediately prior to the commencement of embankment construction from the settlement plates, extensometers, survey prisms on culverts, inclinometers, and standpipes. During the construction phase measurements are to be taken when the fill height reaches 1.0m and then every 0.5m of fill after. During the hold period measurements are to be taken twice weekly and monthly until practical completion is reached. Vibrating Wire Piezometers readings are to be taken for at least one week prior to commencement of construction. Continuous readings are to be taken during the construction stages with data sent to the logger on 6 hourly intervals. Survey prisms installed on bridge abutments are to have baseline readings taken immediately post installation. Following that readings are to be taken weekly for two months, two weekly for the following six months and monthly following that until practical completion is reached. The contractor is required to use the monitoring data to check the predicted settlement against the actual settlement during the delivery activities. Where at any time the predicted settlement is 30% outside of the corresponding predicted theoretical settlements for that nominated stage of delivery activities the contractor must provide revised construction procedures to the superintendent for review in accordance with the review procedures
button | 437a5022-eb04-5e45-a5c2-17282ffb6030 |  | button | Approval to proceed granted? | Yes, No
label | a27a3a99-6dd4-5c5c-ad08-1c3a5e04c2d0 |  | note | Freq - Each Lot
label | af76d2b2-73dc-5b87-b22c-bdabdf9a3403 |  | note | Key - R
label | 9189245a-fe82-5296-b64f-5428ea6fb81b |  | note | Resp - SE
label | 2be3f24a-ec50-5953-9449-10f95c952e6f |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.0 Geotechnical Analysis
checkpoint-status |  |  | checkpoint | 4.1 - CBR/Swell – Initial Testing
label | 3c0c7dd0-9129-5b8e-bb44-847e335bdc33 |  | note | Ref docs - VR Clause 204.04(c) PS3020.05 (c)(v)
label | 6b22508c-7d4f-51de-9d46-71ade5222b1a |  | note | Acceptance criteria - First lot tested to determine assigned CBR and Swell: CBR ≥ 2.5% Swell < 2.5% If swell exceeds 2.5%, material shall be classified as expansive. Raise RFI and request approval from Superintendent to use material.
label | 326bc01b-58a7-5503-9d1a-e9b3bb029d20 |  | note | Freq - Each Lot
label | abfbf415-99df-5b8b-bf76-416d49898a7d |  | note | Key - R
label | 780122e5-3d49-5536-ae09-4542e2618b5b |  | note | Resp - SE
label | 4777e0fb-807b-5f94-b738-9a2ca106b832 |  | note | Remarks/ record (eg. test frequency reports, certificates, checklist etc)
button | bd3a9b11-2ecf-58c8-93f6-5e4104014a64 |  | button | NATA Test Report: CBR and Swell | Yes, No
checkpoint-status |  |  | checkpoint | 4.2 - Compaction Testing / Moisture Testing
label | e2431ac2-1bc1-569b-a294-bcdc69e30f6d |  | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d)
label | b08369a8-7003-5560-a4a4-95fd84e40558 |  | note | Acceptance criteria - Type B material placed within 400 mm of top of Type B material: 99% (Scale A) Type B Material placed more than 400 mm below top of Type B Material: 97% (Scale A) Type B material placed within 400 mm of top of Type B material: 98% (Scale B) Type B Material placed more than 400 mm below top of Type B Material: 95% (Scale B) All areas of the job will be considered as scale A. Type B material is to be tested as per table 201.142. And should meet the moisture content requirements as per VR204. >70% for any material within 150mm of subgrade. >80% for all material below cut floor level.
button | 429ca267-ca79-5c27-b9e1-5f78e2a45930 |  | button | Have the results been achieved? | Yes, No
label | debfcc54-9cab-5d76-bc2b-dfba7786f797 |  | note | Freq - Each Lot
label | 51d2b35f-7420-5153-b9ed-5b6321ac89a4 |  | note | Key - R
label | 2b578989-fab3-54e0-9b6c-95ee3cabd89d |  | note | Resp - SE
label | 74994c9e-670a-5e7e-bef1-66d907d8b5d7 |  | note | Remarks/ record (eg. test frequency reports, certificates, checklist etc)
button | e598ea3d-82cb-5dfb-9158-f1ba103d0823 |  | button | NATA Test Report: Compaction | Yes, No
checkpoint-status |  |  | checkpoint | 4.3 - Material Requirements
label | 752d198e-b230-535a-9063-ac7582bf7523 |  | note | Ref docs - VR Clause Table 204.041
label | 0e763c27-a2aa-5809-93c9-c5a27f0c42e0 |  | note | Acceptance criteria - Maximum Particle Distribution (MPD) ≤ 150 mm within 400 mm of Top of Type B. or MPD ≤ 40mm at depths greater than 400 mm below the top of Type B material.
button | 9ce9e668-54a6-5844-a4b3-6cd361f46edc |  | button | Have the results been achieved? | Yes, No
label | 55374bda-3058-5574-9318-eaa8267d7cd2 |  | note | Freq - Each Lot
label | 829b5ffa-0ec4-57ee-b81e-6adbd55ba981 |  | note | Key - R
label | bb0a93c5-b9ce-5759-82a1-6f919cdb337b |  | note | Resp - SE
label | b1ed5ac6-669d-5e23-bdd2-b8b317bca8de |  | note | Acceptance criteria - Type A Material shall comply with the requirements of table 204.041 and be free of topsoil, or perishable matter. Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
checkpoint-status |  |  | checkpoint | 4.4 - LL and PI Testing
label | ba4a5ddb-85dd-5920-bec3-760c3403778b |  | note | Ref docs - VR Clause Table 204.141 Table 204.142 173.04(d)
label | 3c4970f6-92c5-5f6d-bb22-226c421e6bc0 |  | note | Acceptance criteria - LL and comparison of PI against LL, (identification of silt) is required for Type B Material. Initial testing is 1 Test per 2 lots.
button | 5109e29f-0870-522f-87d6-84033dc5e104 |  | button | Have the results been achieved? | Yes, No
label | 283c2088-1b2a-53c7-8ee8-ae16d845089d |  | note | Freq - Each Lot
label | 9591ed9d-889c-5a9d-aa24-f8271f27c106 |  | note | Key - R
label | dd943c4d-a961-5f11-bd8b-26bf20d0ef64 |  | note | Resp - SE
label | cb50dc63-d98e-5877-af6e-44ceb707805e |  | note | Remarks/ record (eg. test frequency reports, certificates, checklist etc)
button | ade3e392-f57e-543a-a71b-04de28fb2610 |  | button | NATA Test Report: LL, PI | Yes, No
checkpoint-status |  |  | checkpoint | 4.5 - Reduced Frequency Post compaction testing of initial lots.
label | 7ed6db20-513b-5748-9819-02ac1eb20d50 |  | note | Ref docs - VR Clause 204.14 – Table 204.141 PS3020.07 (f)
label | ff5edad3-ae5a-557a-86e3-13a850d0d0cc |  | note | Acceptance criteria - Test initial lot for CBR/Swell. Test initial 3 lots for compaction. Once material and work have achieved the specified requirements in the first test. And; Established a compaction procedure to the satisfaction of the Superintendent’s. Symal can reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142 If Reduced frequency has been granted, the testing can be conducted at the following frequency. 1 test per every 8 lots for CBR/Swell 1 every 2 lots OR every 3rd lot if placed >400 mm below top of type B for Compaction Testing. 1 test per 4 lots of LL and comparison of PI against LL.
button | 025ee5f0-6e19-565b-8cdf-1e05b39dc571 |  | button | Has the criteria been achieved? | Yes, No
label | 4b37193d-ebe9-5fad-a480-ad88d1f9eaa9 |  | note | Freq - Each Lot
label | 35e0e037-08e3-5906-a8da-40130281be44 |  | note | Key - R
label | 620ccfe5-39b6-5c13-a129-59dd5413e4a8 |  | note | Resp - SE
label | b7273acf-bd6d-56d9-a770-4bc0fe82644a |  | note | SI Key - R
checkpoint-status |  |  | checkpoint | 4.6 - Embankment Settlement Monitoring – New Embankment Settlement
label | 4d40905e-3ffe-5c40-a565-ff4750b4f9a9 |  | note | Ref docs - MRPV – PRU WP1 – Bulk Earthworks Package Stage 1 – Advice Memorandum – Table 5
label | 86e5c8a2-5671-55e3-bc5e-88ff2de0a414 |  | note | Acceptance criteria - Submit settlement monitoring data to the superintendent for review at the following nominated stages: · End of hold-period · End of each subsequent 3-month period prior to pavement placement · Prior to placement of pavement If total settlement lies outside 30% of predicted settlement, Superintendent must review and consult with geotechnical designer.
label | 6e4d84c2-cabb-562d-adbc-af05644992bc |  | note | Freq - Each Lot
label | f43e5d28-6518-5821-813e-6760e994e78a |  | note | Key - R
label | 179cc2af-4c47-59a4-8bfe-dde1b25c7403 |  | note | Resp - SE
label | 97926869-4d40-5ac9-af16-7227644ee0cb |  | note | SI Key - H
label | 2285e3a6-d17f-565d-b008-368121004b71 |  | note | Remarks/ record (eg. test frequency reports, certificates, checklist etc)
button | 673c2ff5-f89c-5077-8609-c3cdbde3150d |  | button | Settlement Monitoring Data | Yes, No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.7 - Embankment Settlement Monitoring – Existing Bridge Movement
label | 56f80a5a-06f4-55fc-a6f8-4ad634ecbb6e |  | note | Ref docs - MRPV – PRU WP1 – Bulk Earthworks Package Stage 1 – Advice Memorandum – Table 5
label | 2941470c-3df6-54ed-a048-e8fe7d76e855 |  | note | Acceptance criteria - Submit settlement monitoring data to the superintendent for review at the following nominated stages: · End of hold-period · End of each subsequent 3-month period prior to pavement placement · Prior to placement of pavement If total settlement at the existing bridge abutment location exceeds 21mm at any time, Superintendent must review and consult with geotechnical designer.
label | 3e8e40a5-1177-5b8e-9a67-9dabe50f8e92 |  | note | Freq - Each Lot
label | 58bb19d5-8621-56f9-a3f9-28a5c04444c2 |  | note | Key - R
label | 1098ebe5-25fb-5380-815d-2892843a58af |  | note | Resp - SE
label | 92c48136-df32-5b8a-b6f2-4e681c7eedb2 |  | note | SI Key - H
label | 3bd4b5ee-eda9-573a-9160-af919505655a |  | note | Remarks/ record (eg. test frequency reports, certificates, checklist etc)
button | 8f7e7df9-feb4-582a-be97-df4e3442a28c |  | button | Settlement Monitoring Data | Yes, No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5.0 Completion
checkpoint-status |  |  | checkpoint | 5.1 - Conformity with IFC Drawings and Construction Tolerances
label | 97a5a6f5-ba8b-51d0-b552-00004d60e278 |  | note | Ref docs - VR Clause 204.03 Table 204.031
label | 83eda371-0c92-552b-94e8-d7cc50badf21 |  | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings with the following requirements. Scale A: 80 measurements per lot Mean +5 / -15 mm Max Std Dev. 12 mm
button | 97754a68-bc90-5f43-9190-a65516dc7426 |  | button | Does the final product conform to the above criterial? | Yes, No
label | 4bbe36e7-cc18-5652-9d79-9ba9ba66acb0 |  | note | Freq - Each Lot
label | f5214e3c-509e-5963-b9b1-79ce28f82aca |  | note | Key - R
label | 35901560-e3aa-5e17-9e44-304ced6aa67e |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 5.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
label | 5e444fcf-45c5-5381-98d9-eab9e538ce51 |  | note | Ref docs - VR Clause 204.15
label | c48a291e-8731-53ba-9ab6-0ba4c884ab5f |  | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water. Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
button | 3393a6c2-6297-5690-ba33-4dc987275b51 |  | button | Does the final product conform to the above criterial? | Yes, No
label | 143754ba-f233-5857-bb34-ebc8d24054c2 |  | note | Freq - Each Lot
label | b160920b-2d5d-52b2-94d2-aa1a0c098023 |  | note | Key - R
label | d9ab7336-757b-5592-bb82-ef9e67285af1 |  | note | Resp - SE
checkpoint-group |  |  | section | 6.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 6.1 - Test Reports
label | 1aa98182-e01f-53bb-b6de-5db44f045449 |  | note | Ref docs - DoT Specs
label | 15f28b23-e08a-52bd-9ac2-d3a71b3982b9 |  | note | Acceptance criteria - All Test reports received and reviewed
label | 1fef3a7f-547b-5453-b98b-003dc6247e21 |  | note | Freq - Each Lot
label | 3c0e361e-054e-5f7b-b7d8-a0119fd4bae4 |  | note | Key - R
label | 0881f7bc-0c52-547c-a3d7-45d529b76c41 |  | note | Resp - PE
label | 384c260b-ab86-5685-b9b3-2550499ec852 |  | note | Remarks/ record (eg. test frequency reports, certificates, checklist etc)
label | 36677cdd-dd57-5447-adff-9d3d67aacb30 |  | note | NATA Endorsed Test Reports
checkpoint-status |  |  | checkpoint | 6.2 - Product Non-Conformance
label | 024649f1-0601-5edb-a286-07ef5b14e899 |  | note | Ref docs - QMP
label | 53a4ceba-ba4d-510c-8e9c-e22b7234bdf5 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | cfe2163f-101d-539b-aad7-d4ee7f2b16be |  | note | Freq - Each Lot
label | 07569ad6-faec-530a-a688-03efbd17002a |  | note | Key - R
label | e8ef3be2-9458-5c91-b9e4-364872a17f7d |  | note | Resp - PE
label | 8f6a4e06-de28-57cd-b950-11089872655d |  | note | Remarks/ record (eg. test frequency reports, certificates, checklist etc)
label | ac965cc6-b750-56b9-86e7-e4f55c73f713 |  | note | NCR reports
checkpoint-status |  |  | checkpoint | Work complete
text | a11e7299-b308-5739-bb62-2d808a296b7d |  | textbox | Name:
text | 90e11a0f-fd91-5522-bda1-df5f613913f3 |  | textbox | Position:
text | aa88b1e4-fbe9-5dd1-a68b-30c390b86c7a |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot conforms
text | d62dc8a4-f8eb-5b0f-82e1-35b7a8d9e8c6 |  | textbox | Name:
text | 33c6cdf5-d62e-5fd8-b2c5-baaf4995e1f9 |  | textbox | Position:
text | 74dd2e27-a62d-5ed5-9369-5e98d1700a26 |  | textbox | Date lot closed:
text | 885637c9-d289-5701-8389-421488cf9712 |  | textbox | NCR/s no. raised:
text | b2bcdf64-8e13-5402-8b78-243a73970101 |  | textbox | Date NCR closed for this lot:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-0001– Site Clearing and Grubbing |  |  |  |  | Yes | ITP-0001– Site Clearing and Grubbing | 7c5fabf2-603c-4979-8154-450311ed9b1c
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Define Lot
label | c69f8f8b-7a9d-552a-83ce-9b276bae2cfa |  | note | Ref docs - 1200.15 (b) (i) (B)
label | 39b65139-4525-54d5-a303-c735f2ad323d |  | note | Acceptance criteria - Clearly mark out lot and extents. All No-Go Zones must be protected by temporary fencing and signage visible. All fencing of No-Go Zones must be: a. erected a minimum of 1 metre beyond the boundary of the habitat to be protected, at the Tree Protection Zone or as directed by the Superintendent; b. at minimum, constructed of star picket and paraweb with two wire supports. The star pickets must be 1.3m in height, installed to a height of 1m above ground level and the paraweb must be installed to ensure a minimum 30cm gap is available between the bottom of the fence and existing ground to allow for fauna movement; c. communicated by signage installed on the temporary fencing at intervals no less than 10 metres apart stating ‘Environmental No-Go Zone – no unauthorised access’; d. installed prior to commencement of works in the immediate area, in accordance with the relevant approved SEP; and e. retained in place for the duration of construction activities.
button | b0bf4a40-398a-5970-8a5e-7ed0d50110a3 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 2119f181-aeea-5731-98ff-244d35cebd61 |  | note | Freq - Prior to start of works
label | ddaea79f-a36b-5a3f-a779-278361ffecb2 |  | note | Key - R
label | eab492aa-c823-5d4a-808f-f74441b9a925 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.2 - Works required inside a No-Go Zone
label | 59c0cff6-7c93-5825-8232-a17ea80a5e4d |  | note | Ref docs - 1200.15 (b) (i) (B)
label | c698d8be-5f96-5840-83ad-c30ca24c16cf |  | note | Acceptance criteria - No works are to occur inside any No-Go Zones, except for where the following process is followed: Before commencement, where works have potential to impact flora and fauna protected by a No Go Zone, the Superintendent has been provided a report to the requirements of 1200.15 (b) (i) (B) for approval 5 days before the proposed Delivery Activities and it has been approved by the Superintendent.
button | b0740bb3-48d9-5c8b-a8c1-abfd241d2387 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 39047928-ebb5-5052-bb3e-c0d28771c91f |  | note | Freq - Prior to start of works
label | 13b9e37a-9fcd-5185-985d-f03d30c23d3f |  | note | Key - H
label | c7a7413f-3bc0-5122-abc4-6338c0e72665 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.3 - MRPV Vegetation Removal Permit
label | c9403924-d27c-5440-ac10-b2384e3610a8 |  | note | Ref docs - Vegetation Removal Permit / PS3020.07 (a) (ii)
label | ce19c04c-a8bd-52e1-92df-203010c6019b |  | note | Acceptance criteria - Sign off by the Project and MRPV Environmental Representatives. This is to be reviewed by the Superintendent prior to removal and provided to Environmental team
button | 4612ad96-44d7-5de5-9c15-29355d4aabe2 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 3ae7d7d6-c892-5dca-84b7-0f26d94c582d |  | note | Freq - Prior to start of works
label | 4f11648c-a9e7-5cfb-a940-9a78e2cc10be |  | note | Key - H
label | 23bbaf7b-0943-5232-a21c-77132de92144 |  | note | Resp - SE
label | f6f62785-9edf-5803-8c6d-d1f654a8794c |  | note | Holdpoint - H
checkpoint-status |  |  | checkpoint | 1.4 - Design Documents Required
label | 8fbd7c89-18d6-5186-8d2c-4f500a2746b8 |  | note | Ref docs - 1170.11
label | 9f6498d2-ccdc-52f8-9a45-cd7f2d147be2 |  | note | Acceptance criteria - For site clearing and grubbing, the documents needed are: (1) marked up drawings that relate to the design Documents and clearly define the scope of the Enabling Works; (2) any relevant Construction Specification for the Enabling Works. (3) a drawing showing environmental approval boundaries, activity areas and no-go zones. (4) evidence that any required design related Approvals have been obtained; and (5) a list of all required Approvals.
button | 5207c20e-dec0-5315-8b9e-b9903430d899 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 19e943e3-67b7-5996-8192-249aff4c7350 |  | note | Freq - Prior to start of works
label | 94217fd0-a0e9-580c-ac24-ef39d2b9ff08 |  | note | Key - R
label | 947a1812-b196-5134-88b5-760046f86b80 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.5 - Site Environmental Protection Plan
label | 90483aba-b641-5fb3-95ea-2cf89bb9625e |  | note | Acceptance criteria - Site Environmental Protection Plans and Site Erosion Control Plans have been reviewed and approved for works.
button | 8d37b707-ea60-576b-8078-0f3752382608 |  | button | Has all of the above been completed? | Yes, No, N/A
label | fa6771b0-84fb-58ab-84f5-e03fab6d98c4 |  | note | Freq - Prior to start of works
label | e71ecd94-19a3-5102-a226-171abef30c7f |  | note | Key - R
label | 315c863e-035d-57a3-a55a-08a21e910fb6 |  | note | Resp - ENV REP
checkpoint-group |  |  | section | 2.0 Pre-Clearing activities
checkpoint-status |  |  | checkpoint | 2.1 - Pre-Clearing Identification
label | a16a19bc-79fa-55fd-9bf8-e1b89cd4fa7a |  | note | Ref docs - 1200.15 (b)(i)(C)
label | 3845e31b-b367-5b3a-bbdb-2c5ba01041a7 |  | note | Acceptance criteria - Not more than 7 days prior clearing, an ecologist has certified that all habitat trees are clearly identified and marked with flagging tape or survey, consistent with the Design Documents and permits and approvals. Any salvageable timber suitable for reuse to be identified and marked for stockpiling, for it to be reused after clearing.
button | 8223b96f-6405-56f9-8a42-08d1f41f1405 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 39e73601-df7a-5109-ac9a-72c0105524aa |  | note | Freq - <7 days prior to proposed clearing
label | 962e1cd4-db61-5238-b496-c42153da986b |  | note | Key - H
label | 8fa8b964-a32c-5f20-a525-56c8537df7e5 |  | note | Resp - SE
checkpoint-group |  |  | section | 2.0 Pre-Clearing activities
checkpoint-status |  |  | checkpoint | 2.2 - On-site inspection
label | 720d65b9-3736-5996-a13a-e857499c1832 |  | note | Ref docs - 1200.15 (b)(i)(C) (4)
label | 97ae3a21-98e8-55e0-8eb2-8603469a8a72 |  | note | Acceptance criteria - Prior to removal of vegetation, site inspection to be arranged with the Superintendent and other authorities to confirm the requirements of Sections 1200.15(b)(i)(C)(1) and 1200.15(b)(i)(C)(2) have been achieved. All Approvals are in place and the ecologist is always on site, ready to perform further inspections in accordance with Sections 1200.15(b)(i)(C)(3) and 200.15(b)(i)(C)(5).
button | 691fd303-b92f-54f4-bb47-882b17a3e256 |  | button | Has all of the above been completed? | Yes, No, N/A
label | a284c9a4-ccd7-567e-90b2-9e721d1e5e05 |  | note | Freq - Prior to clearing
label | 9de50117-64d1-597e-ad6f-b989a5fb31f6 |  | note | Key - H
label | ffa1d3cc-a127-5a1f-af91-5d3cf025913b |  | note | Resp - SE
label | 171217c6-73b6-5f78-8be8-bf3d3264ffd5 |  | note | Holdpoint - H
checkpoint-group |  |  | section | 3.0 Onsite Clearing and Grubbing
checkpoint-status |  |  | checkpoint | 3.1 - Clearing
label | bfb65c74-7f2f-58e2-b318-43d5ceb44315 |  | note | Ref docs - VR201.04 1200.15 (b)(i)(C) (5)
label | 9f4ee2e0-ec8a-5a45-bf5a-5db3ebc492ab |  | note | Acceptance criteria - Only non-habitat trees can be removed during the first stage of clearing. Habitat trees can then be removed after approvals have been received and a minimum of 24 hours after the removal of non-habitat trees. Prior to commencing of clearing each day, the ecologist appointed should inspect the area for signs of wildlife.
button | 6221fcda-be70-5c99-aed4-0316054040b2 |  | button | Has all of the above been completed? | Yes, No, N/A
label | b5cf3fdf-78ea-5efd-b645-d93c25fb7ae9 |  | note | Freq - Each lot
label | c158b07c-c2ae-5f81-b043-b448f4979c48 |  | note | Key - H
label | b9385558-9f3d-545a-92c8-908e1b6f2700 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.2 - Grubbing
label | a1bea147-2d00-54c3-952e-c88afa6c0064 |  | note | Ref docs - VR201.05
label | ed1ff7ea-0951-5c2f-96d4-22571d07f4e3 |  | note | Acceptance criteria - In areas where excavation will be undertaken, all vegetation shall be grubbed as per the requirements of VR 201.05 and early works – subgrade improvement design package Holes resulting from grubbing shall be backfilled with similar material and compacted to same degree as surrounding material.
label | a739072b-6b9d-5864-9ad5-36cc4d5fc709 |  | note | Freq - Each Lot
label | 83d981f4-774c-5af5-8a04-6aaadd7a39d8 |  | note | Key - R
label | f6d6197e-3ff2-55a4-a889-392275ae0213 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.3 - Clearing at Culvert Sites
label | ed007adf-fc60-5535-a641-d1e8bf58566c |  | note | Ref docs - VR201.06
label | a28860fc-8a91-57d9-a096-9d20624cc7b2 |  | note | Acceptance criteria - Any trees or stumps with 10m of any portion of a proposed culvert having a waterway area greater than 6m^2 shall be cleared and grubbed in accordance with the requirements of VR201.
button | e7494f2d-e114-5915-b3ad-56980e3b0d8c |  | button | Has all of the above been completed? | Yes, No, N/A
label | e652f01d-95dc-5f2b-9f3d-6c41a81d3497 |  | note | Freq - Each lot
label | 91298a74-947d-57ce-92b5-ab336d9bc864 |  | note | Key - R
label | 05667efa-870c-50d6-9830-70808eb696b9 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.4 - Flora and fauna handling and removal
label | 204284d6-278a-5e38-a141-42287fce7317 |  | note | Ref docs - 1200.15 (b)(i)(F)
label | 129cc37e-302d-5feb-9153-7d8701cc30ac |  | note | Acceptance criteria - The Superintendent must be notified if any significant flora and fauna is found, and an ecologist must identify and provide advice on what to do with the found flora or fauna. The Superintendent must notify Environmental representative of any flora and fauna found.
button | b67ae319-f997-5fd1-ab7c-4878c5790702 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 326ce175-1a9f-57bb-acae-c410fca9416c |  | note | Freq - Each lot
label | 0de92732-1133-541b-b602-8d55ad2defc7 |  | note | Key - I
label | 4f0630b9-b770-52f6-9f7a-e7b26aa59c6f |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.5 - Identified habitat
label | 5751edb6-4c1c-5e6d-b1bf-c264661ff890 |  | note | Ref docs - VR201.10 1200.15
label | 7896b512-f227-5a87-9f13-02cb1d95b25f |  | note | Acceptance criteria - Trees with hollows can only be removed during initial clearing, if hollow is occupied, the section is to be left and cut after clearance from the ecologist and a minimum of 24 hours after removal of non-habitat trees in the area.
button | 176ffc63-b6de-5cdb-b0c4-250a734b2a0c |  | button | Has all of the above been completed? | Yes, No, N/A
label | 7ab16d21-5157-5d32-93a8-edec17417921 |  | note | Freq - Each lot
label | e4723225-a813-5bf1-8def-a20915f1f1c3 |  | note | Key - I
label | 7b476fbb-f89f-539f-bc1a-34be0fa7b4c9 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.6 - Reuse of Material
label | e40cb280-2a0f-5766-98be-66bf11d4968e |  | note | Ref docs - 1200.15 (b)(i)(G)
label | 5a46d7a3-056d-5ae8-a44b-b2b493842a95 |  | note | Acceptance criteria - Seek and adopt where practical reuse opportunities for vegetation felled during the vegetation clearing operations. Reuse may include: a. retention of sections of a branch/trunk with hollows; b. habitat logs on the ground in revegetation sites; c. placement as in-stream habitat with the appropriate approval of the relevant Catchment Management Authority; or d. timber for furniture construction e. Mulch provided to Council, local schools, or to landscaping facilities Update tree removal/retention register
button | 8049f506-cbbb-5f8a-bacb-b5211b5fc267 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 5764b5b7-1078-5521-8445-cb204b059f7c |  | note | Freq - Each lot
label | 36ac1c18-2891-5e63-94d4-2cc60141978f |  | note | Key - R
label | 747af2b5-7349-5561-adb0-e9192b91d1cb |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.7 - Disposal of Material
label | 1fbd1e5b-430e-5384-8427-be3374648617 |  | note | Ref docs - VR201.07 VR177.I2 PS3020.07 (a)
label | 15d8c455-e946-5602-86c6-805d69f1bd05 |  | note | Acceptance criteria - No removal of noxious weeds from the site. Identify and undertake treatment of declared noxious weeds prior to the commencement of any ground disturbing activities. The disposal of these materials shall be in accordance with the CEMP and its sub plans
button | 7c0fff9e-7c84-5cba-a9d0-9db7594b28eb |  | button | Has all of the above been completed? | Yes, No, N/A
label | 269d8a60-3d8a-547d-92f4-a05c9d066c17 |  | note | Freq - Each lot
label | 17d55846-f5e6-50bd-94b6-0846ef765e11 |  | note | Key - R
label | 34b5c490-bc0c-509c-9ca8-78a201fcef80 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.8 - Salvage of Vegetation
label | 9f040940-669b-5e10-b768-a607973371e5 |  | note | Ref docs - VR201.11
label | 9fa9094b-10a5-51fb-83ab-de9a37d8bea5 |  | note | Acceptance criteria - Salvaging any plants as well as collecting cuttings and available seed from areas of native vegetation on site to be completed where applicable
button | 6ecc0353-c67e-599c-9b32-d3cfc4dd6de4 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 9e2d0a59-aaf4-5210-813c-825a281a1be9 |  | note | Freq - Each Lot
label | c0f79726-b106-5d7c-a60c-b2d523e1648d |  | note | Key - R
label | 27be45b8-6e09-5fe6-a3d2-60205709c50c |  | note | Resp - SE
checkpoint-group |  |  | section | 4.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 4.1 - Product Non-Conformance
label | 2c3f3048-79bb-5e65-9a82-6e31a593d931 |  | note | Ref docs - CQMP
label | d5f3b7e6-4b05-591c-8eef-b07d82ce1da9 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 18b3925e-9377-5dbc-ac05-9405db9295ab |  | note | Freq - Each lot
label | 180f804d-ec1a-57d8-bdd1-0970abbddf41 |  | note | Key - R
label | 1d0359e3-ff12-5d17-9045-6de5086225a2 |  | note | Resp - SE
label | 0496cb18-1aaf-53b2-a86f-b1355504273f |  | note | Remarks/ record (eg. test frequency reports, certificates, checklist etc)
text | 858c0e77-dca3-5df8-b3a0-9752d1c082b0 |  | textbox | NCR No:
button | 49c31617-ca24-5c77-82bf-b3ffb9ff5513 |  | button | NCR reports | Yes
checkpoint-status |  |  | checkpoint | 4.2 - Quality Representative to check the above criteria and records to confirm
label | fa867243-87b3-5c05-867d-5d9dfb2118de |  | note | Ref docs - CQMP Lot Records
label | 04732ff2-9997-5b33-bc1d-266a9afe0eb8 |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | dd43550b-a5ca-563b-932f-a03d56c513aa |  | note | Freq - Each lot
label | 511e454e-909e-5aad-a785-64a2a43fb634 |  | note | Key - R
label | c616d87d-4097-5b39-a7df-9932cff6f21b |  | note | Resp - SE
label | 5182848d-0ac0-5a83-ad4d-a99ca9cf88d9 |  | note | Remarks/ record (eg. test frequency reports, certificates, checklist etc)
button | 70dfde8c-4618-5573-b4a1-42a84c48059a |  | button | Completed Checklist (if applicable) and reports and other compliance records attached | Yes
checkpoint-status |  |  | checkpoint | Work complete
text | 27bd1ed1-5fa6-5c8e-b34d-72b820fd7ca2 |  | textbox | Name:
text | ea276f6d-0ee0-5aa7-81b3-06e8e204102a |  | textbox | Position:
text | 82fe8b2f-f993-5d0c-bd17-fa64a73778df |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot conforms
text | a583d19c-8e69-5f67-a375-d61f1f83c5f1 |  | textbox | Name:
text | bc587a59-577a-5e6f-a777-a95932674957 |  | textbox | Position:
text | b4ff73ad-a840-506a-86a0-454122375333 |  | textbox | Date lot closed:
text | 1ec36898-18ca-5779-9d03-51a35a60ca51 |  | textbox | NCR/s no. raised:
text | 37c27e3e-b317-5a0a-809d-1c944d715921 |  | textbox | Date NCR closed for this lot:
holdpoint |  |  | signoff | Sign ITP