## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist - Rev.3 | itp |  |  |  | Yes | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist - Rev.3
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - Issued drawings / Site copy drawings
label | Acceptance Criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
checkpoint | 1.2 - Lot Traceability
label | Ref docs - Spec. 0161 Quality [Cl 7.2]
label | Acceptance Criteria - Prepare a lot map for traceability of the work area
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Lot map
checkpoint | 1.3 - Survey set-out
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 2.2]
label | Acceptance Criteria - Has the work area been set out as per the drawings?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
checkpoint | 1.4 - Establishment of stockpile sites
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.1]
label | Acceptance Criteria - Approval to use any stockpile sites not shown on drawings.
label | Notice: 3 working days before stockpiling
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Excavation material classification
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.7]
label | Acceptance Criteria - Ensure that excavated material is separated as follows:
bool | Topsoil
bool | Embankment Material
bool | Unsuitable Material
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
checkpoint | 1.6 - Fill Material Conformance
label | Ref docs - Spec. 1112 Earthworks (Roadways)
label | Acceptance Criteria - Fill Material to be free of roots, clay, topsoil, steel and organic material. Use primarily Site-won cuttings and supplement with imported material if necessary.
label | CBR to be > 3%
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Material Test Reports
checkpoint | 1.7 - Water management
label | Ref docs - Spec. 1102 Control of erosion and sedimentation [Cl 3.7]
label | Acceptance Criteria - Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
checkpoint-no-status | Is the area in cut / fill / both?
label | If in cut proceed to step 2.0 and strike out section 3.0.
label | If in fill please strike out section 2.0 and proceed to section 3.0
label | If in both proceed to step 2.0 as well as section 3.0
section | 2.0 Bulk earthworks – cut
checkpoint | 2.1 - Subgrade preparation
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.1, 4.3]
label | Acceptance Criteria - Has the cut surface been trimmed to an even surface free from lose material and within tolerance of +/- 50mm from design floor level?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
checkpoint | 2.2 - Unsuitable material removal
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.3, 4.6]
label | Acceptance Criteria - Any Unsuitable material to be removed as directed by the superintendent
label | Notice: Progressive
label | WITNESS POINT
button | Acceptance | Yes,No,N/A
label | Key - W
label | UGL Key - W
checkpoint | 2.3 - Unsuitable material floor inspection
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.3, 4.6]
label | Acceptance Criteria - Floor of excavation to be inspected to determine sufficient depth of unsuitable material has been removed
label | Notice: Prior to Backfilling
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - CBR Testing
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.3]
label | Acceptance Criteria - Prior to ripping, test the CBR of the material in the cut floor to ensure it is > 3%
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Test reports
checkpoint | 2.5 - Ripping Cut Floor (Not required if foundation is in stabilised remediation pad)
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.3]
label | Acceptance Criteria - Has the floor of cuttings been adequately ripped to a min. depth of 200mm?
label | ○ The max. dimension for any particles in the ripped or loosened zone not to exceed 150mm.
label | ○ Ripped material to be presented for inspection.
label | Notice: Before recompacting commences
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Re-Compaction
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.3, 4.13]
label | Acceptance Criteria - Re-compact the ripped floor to achieving a relative compaction of 97%
label | ○ If unsuitable replacement has occurred, compact the replacement layers to 92% and the design cutting floor to 97%
label | Notice: Prior to placing subsequent layers
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Test reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Proof Roll – Subgrade (Not required if foundation is in stabilised remediation pad)
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.13, 7.1]
label | Acceptance Criteria - Does the layer withstand proof rolling without visible deformation or springing?
label | Notice: 2 working days before next activity
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Bulk earthworks - fill
checkpoint | 3.1 - Foundation Preparation (Not required if foundation is in stabilised remediation pad)
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.7]
label | Acceptance Criteria - Grade and level the area, adjust the moisture content and compact the top 200mm to 97% relative compaction
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Test reports
checkpoint | 3.2 - Foundation Inspection & Unsuitable Removal
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.6, 4.7]
label | Acceptance Criteria - Embankment foundation to be inspected by the superintendent. Any Unsuitable material to be removed as directed.
label | Notice: 1 working day before next activity
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Unsuitable Material Floor Inspection
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.6, 4.7]
label | Acceptance Criteria - Floor of excavation to be inspected to determine sufficient depth of unsuitable material has been removed
label | Notice: Prior to Backfilling
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Proof Roll – Subgrade (Not required if foundation is in stabilised remediation pad)
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.13, 7.1]
label | Acceptance Criteria - Does the layer withstand proof rolling without visible deformation or springing?
label | Notice: 2 working days before next activity
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Fill Placement
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.8, 4.10]
label | Acceptance Criteria - Has fill been placed in maximum 200mm compacted layer thickness?
label | (Approval required to increase compacted later thickness to 300mm)
label | Note: Maximum fill layer thickness adjacent to structures 150mm)
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Delivery dockets (if imported)
checkpoint | 3.6 - Moisture Content
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.13, 7.1]
label | Acceptance Criteria - Is the moisture content within the range of 60% to 90% of optimum moisture content for all fill layers
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Test reports
checkpoint | 3.7 - Compaction (General)
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.13, 7.1], Spec. 0161 Quality (Construction) [Cl 7.2]
label | Acceptance Criteria - Compact any material used for unsuitable replacement, general fill (>1.5m deep), verges and medians to a relative compaction > 92%
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Test reports
checkpoint | 3.8 - Compaction (Selected Material Zone)
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.13, 7.1], Spec. 0161 Quality (Construction) [Cl 7.2]
label | Acceptance Criteria - Compact any material used for shallow embankments, Select Fill or behind kerbs to a relative compaction > 97%
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Test reports
checkpoint | 3.9 - Compaction (Fill adjacent to structures)
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.10, 4.13]
label | Acceptance Criteria - Compact all material adjacent to structures to achieve a relative compaction of 92% (up to 1.5m from top of pavement) or 97% (within 1.5m of top of pavement)?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Test reports
checkpoint | 3.10 - Material Conformance (Fill adjacent to structures)
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.10, 4.13]
label | Acceptance Criteria - Backfill material granular and not exceeding 50mm particle size
label | ○ Plasticity index in between 2 & 12
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Test reports
checkpoint | 3.11 - Proof Roll / Select Material Zone Inspection
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.13]
label | Acceptance Criteria - After trimming & compaction, present the top layer of SMZ for inspection.
label | ○ Does the layer withstand proof rolling without visible deformation or springing?
label | Notice: 2 working days before next activity
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Bulk earthworks - other
checkpoint | 4.1 - Batters
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.4]
label | Acceptance Criteria - Provide batter slopes as shown on the drawings. Clean the cut faces of any loose or unstable batters as the excavation proceeds
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
checkpoint | 4.2 - Cut to Fill Transitions
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.5]
label | Acceptance Criteria - Excavate a terrace as per the figure in Cl 4.5 for the width of the SMZ to a depth of 900mm below the cutting floor
label | Notice: 1 working days before excavating terrace
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - W
label | UGL Key - W
section | 5.0 Conformance check
checkpoint | 5.1 - Width and alignment
label | Ref docs - Drawings
label | Acceptance Criteria - Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
checkpoint | 5.2 - Level Conformance – Top of Embankments
label | Ref docs - Spec. 1112 Earthworks (Roadways) [Cl 4.8, 5], Drawings
label | Acceptance Criteria - Trimmed top of embankment to be within the range -40mm to +10mm from design levels
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - As built report