## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist - Rev.7 | itp |  |  |  | Yes | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist - Rev.7
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - Issued drawings / Site copy drawings
label | Acceptance Criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 1.2 - Lot Traceability
label | Ref docs - Spec. 0161 Quality [Cl 7.3]
label | Acceptance Criteria - Prepare a lot map for traceability of the work area
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot map
checkpoint | 1.3 - Precast Pit Approval
label | Ref docs - Spec. 1354 Stormwater Drainage Structures [Cl 2.2]
label | Acceptance Criteria - Submit Drawings and Installation Procedures for Precast Pits to the Superintendent for Review prior to delivery of the first pit to site
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Precast Supply
label | Ref docs - Spec. 1354 Stormwater Drainage Structures [Cl 2.2]
label | Acceptance Criteria - Does the supplied pit, slab, culvert or headwall meet all requirements of the specification and the drawings
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material conformance certificates
checkpoint | 1.5 - Underlying Lot Conformance
label | Ref docs - Underlying Lot ITP
label | Acceptance Criteria - Underlying services and/or assets have been installed prior to commencing works over and/or above.
label | ○ Refer underlying lot ITP(s)
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 1.6 - Set out
label | Ref docs - Spec. 1351 Stormwater Drainage [Cl 2.2]
label | Acceptance Criteria - Setout pits to the location and levels on the drawings. This shall be presented for inspection by the superintendent.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
section | 2.0 Construction
checkpoint | 2.1 - Unsuitable Material
label | Ref docs - Spec. 1351 Stormwater Drainage [Cl 2.3]
label | Acceptance Criteria - Any Unsuitable Material to be removed to the depth as directed by the Superintendent
label | Notice: Prior to Placing Bedding
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Compaction - Foundation
label | Ref docs - Spec. 1351 Stormwater Drainage [Cl 2.5]
label | Acceptance Criteria - Foundation (including any unsuitable replacement) to be compacted to a relative compaction of 95% to a depth of 150mm below foundation level
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 2.3 - Compaction - Bedding
label | Ref docs - Spec. 1353 Stormwater Box Culverts [Cl 3.4], Spec. 1351 Stormwater Drainage [Cl 2.5]
label | Acceptance Criteria - Precast Structures to be installed on bed of Select Fill with a minimum thickness of 150mm
label | ○ Bedding layer to be compacted to a relative compaction of 95%
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 2.4 - Pit Buoyancy Slabs
label | Ref docs - Design Drawings
label | Acceptance Criteria - Pit Buoyancy Slabs to be installed and bolted to precast pits as per the design drawings.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.5 - Pit Installation
label | Ref docs - Spec. 1354 Stormwater Drainage Structures [Cl 3.1, 3.3]
label | Acceptance Criteria - Pits to be installed as per drawings and manufacturers specifications utilising certified lifting points.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.6 - Access Covers & Grates
label | Ref docs - Spec. 1354 Stormwater Drainage Structures [Cl 3.3]
label | Acceptance Criteria - Access covers, grates and frames to be installed as per AS 3996
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.7 - Step Irons
label | Ref docs - Spec. 1354 Stormwater Drainage Structures [Cl 3.3]
label | Acceptance Criteria - Pits deeper than 600 to be fitted with galvanised plastic-coated step irons as per AS1657
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.8 - Pit & Pipe Connections
label | Ref docs - Spec. 1354 Stormwater Drainage Structures [Cl 3.3]
label | Acceptance Criteria - Inlet and outlet pipes to be connected into precast pit walls as per design drawings & manufacturer specifications
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.9 - Pit Jointing
label | Ref docs - Spec. 1354 Stormwater Drainage Structures [Cl 3.5]
label | Acceptance Criteria - Internal joints between precast pits and riser units to be waterproofed as per Symal RFI-037 & manufacturer recommendations.
label | ○ External Joints between pits and abutting concrete pavement, kerb or structures to be a 10mm isolation joint.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.10 - Backfill
label | Ref docs - Spec. 1354 Stormwater Drainage Structures [Cl 3.7], Spec. 1112 Earthworks [Cl 4.10]
label | Acceptance Criteria - Precast Structures to be backfilled & compacted in 150mm thick layers.
label | ○ Backfill to be Select fill for material within 1.5m of pavement surface and General Fill below 1.5m deep.
label | ○ Select backfill material to be a granular material with a maximum particle size of 50mm and a PI between 2 & 12
label | HOLD POINT Prior to Backfill
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - W
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material Test Report
checkpoint | 2.11 - Compaction - Backfill
label | Ref docs - Spec. 1112 Earthworks [Cl 4.13
label | Acceptance Criteria - Minimum relative compaction requirements for backfill against pits to be:
label | – 92% for general fill
label | – 97% for select fill
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 2.12 - Moisture Content
label | Ref docs - Spec. 1351 Stormwater Drainage [Cl 2.5]
label | Acceptance Criteria - Moisture Content for Backfill material to be within 60% to 95% OMC unless otherwise approved by Superintendent
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
section | 3.0 Conformance Check
checkpoint | 3.1 - Survey Report
label | Ref docs - Spec. 0161 Quality [Cl 3.13], RFI-026
label | Acceptance Criteria - An as-built survey of the drainage system been completed to ensure all structures are within construction tolerances.
label | Plan: +/- 200mm
label | Level: +/- 20mm
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - W
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Survey report
checkpoint | 3.2 - Acceptance and closure of non-conforming items
label | Ref docs - Spec. 0161 Quality [Cl 3.8]
label | Acceptance Criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT