## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist - Rev.6 | itp |  |  |  | Yes | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist - Rev.6
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - Issued drawings / Site copy drawings
label | Acceptance Criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 1.2 - Lot Traceability
label | Ref docs - Spec. 0161 Quality [Cl 7.3]
label | Acceptance Criteria - Prepare a lot map for traceability of the work area.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot map
checkpoint | 1.3 - Drainage Pipe Material
label | Ref docs - Drawings
label | Acceptance Criteria - Has the correct class & type of drainage structure been supplied and free of defects?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material conformance certificate
checkpoint | 1.4 - Embedment material
label | Ref docs - Spec. 1352 Pipe Drainage [Cl 5.1]
label | Acceptance Criteria - Material has plasticity index less than 6.
label | – – – – – – – – – – – – – – – –
label | Table 5.1 Embedment material grading
label | – – – – – – – – – – – – – – – –
label | Sieve size (mm) ¦¦ Weight passing (%)
label | – – – – – – – – – – – – – – – –
label | 19.0 ¦¦ 100
label | 2.36 ¦¦ 50-100
label | 0.6 ¦¦ 20-90
label | 0.3 ¦¦ 10-60
label | 0.15 ¦¦ 0-25
label | 0.075 ¦¦ 0-10
label | (Table taken from AS/NZS 2566.2, Table 5.5)
label | – – – – – – – – – – – – – – – –
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Delivery dockets
bool | Test reports
checkpoint | 1.5 - Underlying Lot Conformance
label | Ref docs - Underlying Lot ITP
label | Acceptance Criteria - Underlying services and/or assets have been installed prior to commencing works over and/or above.
label | ○ Refer underlying lot ITP(s)
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 1.6 - Temp. drainage during construction
label | Ref docs - Spec. 1351 Stormwater Drainage [Cl 2.1]
label | Acceptance Criteria - Adequate provision for runoff flows at drainage works under construction implemented and in good repair.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 1.7 - Set out
label | Ref docs - Spec. 1351 Stormwater Drainage [Cl 2.2], Drawings
label | Acceptance Criteria - Setout Culvert inlet/outlet and drainage structure positions to the location and levels on the drawings. This shall be presented for inspection by the superintendent.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
section | 2.0 Excavation and Pipe Laying
checkpoint | 2.1 - Excavation
label | Ref docs - Spec. 1352 Pipe Drainage [Cl 5.1, 5.2]
label | Acceptance Criteria - DICL and Plastic Pipe:
label | – – – – – – – – – – – – – – – –
label | Table 5.2 Trench and embedment dimensions
label | – – – – – – – – – – – – – – – –
label | Extreme external ¦¦ Minimum dimensions (mm)
label | Dia (De)mm ¦¦ x : s : o : y
label | – – – – – – – – – – – – – – – –
label | ≥ 75 ≤ 150 ¦¦ 75 : 100 : 100 : Pipe dia.
label | > 150 ≤ 300 ¦¦ 100 : 150 : 150 : Pipe dia.
label | > 300 ≤ 450 ¦¦ 100 : 150 : 150 : Pipe dia.
label | > 450 ≤ 900 ¦¦ 150 : 300 : 150 : Pipe dia.
label | > 900 ≤ 1500 ¦¦ 150 : 350 : 200 : Pipe dia.
label | – – – – – – – – – – – – – – – –
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.2 - Unsuitable Material
label | Ref docs - Spec. 1351 Stormwater Drainage [Cl 2.3]
label | Acceptance Criteria - Any Unsuitable Material to be removed to the depth as directed by the Superintendent
label | Notice: Prior to Placing Bedding
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Compaction – Foundation
label | Ref docs - Spec. 1351 Stormwater Drainage [Cl 2.5]
label | Acceptance Criteria - Trench foundation (including any unsuitable replacement) to be compacted to a relative compaction of 95% to a depth of 150mm below foundation level
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 2.4 - Compaction – Embedment material
label | Ref docs - Spec. 1352 Pipe Drainage [Cl 5.1, 5.4]
label | Acceptance Criteria - DICL and Plastic Pipe:
label | Bedding:
label | ○ Required relative compaction in the bedding zone shall be 95% (AS 1289.5.4.1 Standard Compaction)
label | ○ Layers not to exceed 150mm compacted thickness.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 2.5 - Pipe Laying
label | Ref docs - Drawings, Manufacturer Specifications
label | Acceptance Criteria - Have correct pipes (size and type) been laid and jointing installed as per manufacturer specifications
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - W
label | SHL Key - W
checkpoint | 2.6 - Pipe joints
label | Ref docs - Manufacturer Specifications
label | Acceptance Criteria - Pipe joints installed as per drawings and manufacturers specifications
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
section | 3.0 Filling and Compaction
checkpoint | 3.1 - Compaction – Embedment material
label | Ref docs - Spec. 1352 Pipe Drainage [Cl 5.1, 5.4]
label | Acceptance Criteria - DICL and Plastic Pipe:
label | Side and Overlay:
label | Required relative compaction in the side and overlay zone shall be 70% for trafficable areas and 60% for non-trafficable areas (AS 1289.5.4.1 Standard Compaction)
label | – – – – – – – – – – – – – – – –
label | Table 5.3 Minimum relative compaction
label | – – – – – – – – – – – – – – – –
label | Embedment material ¦¦ Test method ¦¦ Compaction - Traffic loading :: No traffic loading
label | – – – – – – – – – – – – – – – –
label | Cohesionless ¦¦ Density index (AS 1289) ¦¦ 70% :: 60%
label | – – – – – – – – – – – – – – – –
label | Layers not to exceed 150mm compacted thickness.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 3.2 - Compaction – General Fill
label | Ref docs - Spec. 1352 Pipe Drainage [Cl 5.4]
label | Acceptance Criteria - For sections of the trench above the overlay zone; backfill with general fill if in verges, medians or greater than 1.5m from top of pavement.
label | ○ Minimum relative compaction to be 92%
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 3.3 - Compaction – Select Fill
label | Ref docs - Spec. 1352 Pipe Drainage [Cl 5.4]
label | Acceptance Criteria - For sections of the trench above the overlay zone and within 1.5m of top of pavement; backfill with Select fill.
label | ○ Minimum relative compaction to be 97%
label | ○ Layers not to exceed 150mm compacted thickness.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 3.4 - Moisture Content
label | Ref docs - Spec. 1352 Pipe Drainage [Cl 5.4]
label | Acceptance Criteria - Moisture Content for Backfill material to be within 60% to 95% OMC unless otherwise approved by Superintendent
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
section | 4.0 Conformance check
checkpoint | 4.1 - Survey Report
label | Ref docs - Spec. 0161 Quality [Cl 3.13], RFI-026
label | Acceptance Criteria - An as-built survey of the drainage system been completed to ensure all structures are within construction tolerances.
label | Plan: +/- 200mm
label | Level: +/- 20mm
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - W
label | SHL Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Survey Report
checkpoint | 4.2 - Acceptance and closure of non-conforming items
label | Ref docs - Spec. 0161 Quality [Cl 3.8]
label | Acceptance Criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT