## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0375-ITP-006 Kerb and Channel & Checklist- Rev.5 | itp |  |  |  | Yes | INF-HSEQ CC0375-ITP-006 Kerb and Channel & Checklist- Rev.5
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine lot size
label | Ref docs - Spec. 0161 Quality [Cl 7.3]
label | Acceptance Criteria - Lots to be broken up accordingly and outlined on a lot map
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot map
checkpoint | 1.2 - Concrete Mix Design
label | Ref docs - Spec. 1121 Open Drains [Cl 3.1]
label | Acceptance Criteria - Submission of Mix Design and compliance certificates for concrete constituents
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material conformance certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Joint Fillers & Sealants
label | Ref docs - Spec. 1121 Open Drains [Cl 3.2]
label | Acceptance Criteria - Submission of Compliance Certificate for joint fillers and sealants
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material conformance certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Kerb & Gutter Methodology
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
label | Acceptance Criteria - Construct kerb and channel in fixed forms, by extrusion or by slip forming to AS2876.
label | ○ Submit details of method proposed including type of extrusion or slipform, concrete properties, equipment and finish.
label | HOLD POINT
label | Notice: 14 working days prior to commencement on site
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Underlying Lot Conformance
label | Ref docs - Underlying Lot ITP
label | Acceptance Criteria - Underlying services and/or assets have been installed prior to commencing works over and/or above.
label | ○ Refer underlying lot ITP(s)
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 1.6 - Survey set out
label | Ref docs - Drawings
label | Acceptance Criteria - Set out the alignment and level of the kerb
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
section | 2.0 Kerb and channel placement
checkpoint | 2.1 - Foundation
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
label | Acceptance Criteria - Shape and compact foundation material to the requirements of the respective pavement course
label | HOLD POINT
label | Notice: 1 working day before forming
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Trial section
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
label | Acceptance Criteria - Construct trial section to demonstrate the Contractors capability of forming equipment.
label | HOLD POINT
label | Notice: To be completed on 1st section of kerb,
label | 3 days prior to commencing next section
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Concrete supply and placement
label | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.8, 4.9, 4.10, 4.11] Drawings
label | Acceptance Criteria - Check docket to ensure strength and slump is as per design requirements
label | ○ Ensure the temperature of freshly mixed concrete is maintained in between 5°C and 35°C. Ensure elapsed time between batching and discharge of the mix complies with the below table.
label | – – – – – – – – – – – – – – – –
label | Concrete temperature at time of discharge (C) ¦¦ Maximum elapsed time (hours)
label | – – – – – – – – – – – – – – – –
label | 10 - 24 ¦¦ 2.00
label | 24 - 27 ¦¦ 1.50
label | 27 - 30 ¦¦ 1.00
label | 30 - 32 ¦¦ 0.75
label | – – – – – – – – – – – – – – – –
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Delivery dockets
checkpoint | 2.4 - Concrete sampling
label | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.2]
label | Acceptance Criteria - The nominal rate of sampling shall be taken as:
label | (a) Compressive strength: See table below
label | – – – – – – – – – – – – – – – –
label | Number of batches for each type and grade of concrete per day ¦¦ Minimum number of samples
label | – – – – – – – – – – – – – – – –
label | 1 ¦¦ 1
label | 2-5 ¦¦ 2
label | 6-10 ¦¦ 3
label | 11-20 ¦¦ 4
label | each additional 10 ¦¦ 1 additional
label | – – – – – – – – – – – – – – – –
label | (b) Slump: One per batch of concrete
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Concrete pour record
checkpoint | 2.5 - Concrete testing
label | Ref docs - Drawings
label | Acceptance Criteria - Average compressive strength at 28 days meets minimum design requirements
label | Slump within tolerances specified in AS 1379
label | – – – – – – – – – – – – – – – –
label | Table 5.1 Permissible Tolerance on Slump
label | – – – – – – – – – – – – – – – –
label | Specified slump, mm ¦¦ Tolerance, mm
label | – – – – – – – – – – – – – – – –
label | <60 ¦¦ ±10
label | ≥60 ≤80 ¦¦ ±15
label | >80 ≤110 ¦¦ ±20
label | >110 ≤150 ¦¦ ±30
label | >150 ¦¦ ±40
label | – – – – – – – – – – – – – – – –
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 2.6 - Finish
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
label | Acceptance Criteria - Finish true to line: The top and face of the finished kerb and channel.
label | Top surface: Uniform width, free from humps, sags and other irregularities.
label | Type: Steel float finish or as otherwise shown on drawings.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.7 - Joints - Contraction
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
label | Acceptance Criteria - Contraction joints to conform to the following:
label | – Width: 5mm min.
label | – Depth: 20mm
label | – Intervals: every 3m for a min of 50% cross sectional area
label | – Tooling: 20mm depth / 5mm width
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.8 - Joints – Expansion
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
label | Acceptance Criteria - Expansion joints to conform to the following:
label | – Width: 15mm
label | – Depth: Full depth of kerb/channel
label | – Intervals: Max interval 15m
label | ○ To be provided where channel/gutter abuts against pits, retaining walls, overbridges and both sides of kerb laybacks unless otherwise shown on drawings.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.9 - Backfill
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.4]
label | Acceptance Criteria - Timing: Backfill behind kerb no earlier than 3 days after concreting.
label | Material: Granular material, free of organic material, clay and rock in excess of 50mm or approval material
label | Layers: Compact in layers not greater than150mm
label | WITNESS POINT
label | ○ 1 Working days before backfilling behind kerb
label | ○ 3 Working days before to backfilling gutter pavement
button | Acceptance | Yes,No,N/A
label | Key - W
label | UGL Key - W
label | SHL Key - W
checkpoint | 2.10 - Backfill Compaction
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.4]
label | Acceptance Criteria - Compaction: As per pavement design drawings or otherwise 95% relative compaction in conformance with AS 1289.5.4.1
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 2.11 - Gully Pit Tie Ins
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.4]
label | Acceptance Criteria - Adjust gully pits or precast units to suit the new kerb and gutter profile without reducing hydraulic capacity of the pit.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
section | 3.0 Conformance Check
checkpoint | 3.1 - Survey Report
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.0]
label | Acceptance Criteria - Survey report verifying kerb and gutter has been constructed within tolerance:
label | ○ Finish levels of channel/gutter surface: within ± 10mm of design level
label | ○ Surface deviation of kerb face and channel surface: ±5 mm from edge of a 3m straight edge, except at laybacks, grade changes or curves, or at gully pits requiring channel/gutter depression.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Survey report
checkpoint | 3.2 - Acceptance and closure of non-conforming items
label | Ref docs - Spec. 0161 Quality [Cl 3.8]
label | Acceptance Criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT